## ProPlanSch
SINDH SMALL INDUSTRIES CORPORATION
REVISED PROCUMENT PLAN IN RESPECT OF DEVELOPMENT CAPITAL
Sr. No. | ADP No. | Name of Scheme | Estimated Cost | Allocated Funds (2016-17) | Funds to be allocated for the year 2017-18 | Cost of on-going works (expdt already incurred) | Funds earmarked for ongoing works | Cost of new works (Component) | Funds earmarked for new works (c-e) | Nature of Procurement | Method of Procurement | Anticipated/ Actual date of advertisement | Anticipated/ Actual date of start | Anticipated/ actual date of completion
1. | 807 | Establishment of un-developed area of Small Industrial Estate, Nawabshah | 59.74 | 59.74
i) |  | Construction of Road | 27.242 |  |  | 0 | 27.242 | 0 | 0 | Open Competitive Bidding | National Competitive Bidding "Single Stage - One Evelope Procedure) | 5th March 2016 | 21st Oct 2016 | 30th June 2017
ii) |  | Providing/ Laying Water Supply Line | 5.7797 |  |  | 0 | 5.7797 | 0 | 0 | do | do | do | do | 31st May 2017
iii) |  | Construction of underground Drainage | 13.437 |  |  | 0 | 0 | 13.437 | 0 | do | do | 20th January 2017 | 5th March 2017 | 4th May 2017
iv) |  | Providing & Laying A.C. Pressure Pipe | 6.043 |  |  | 0 | 6.043 | 0 | 0 | do | do | 5th March 2016 | 21st Oct 2016 | 30th June 2017
v) |  | Providing & Fixing HT/LT Line | 5.4074 |  |  | 0 | 0 | 5.4074 | 0 | do | do | 20th January 2017 | 5th March 2017 | 4th May 2017
2. | 808 | Establishment of un-developed area of Small Industrial Estate, Thatta | 45.32 | 45.32
i) |  | Construction of Road | 13.8217 |  |  | 0 | 13.8217 | 0 | 0 | Open Competitive Bidding | National Competitive Bidding "Single Stage - One Evelope Procedure) | 5th March 2016 | 21st Oct 2016 | 30th June 2017
ii) |  | Construction of underground Drainage | 4.5712 |  |  | 0 | 4.5712 | 0 | 0 | Open Competitive Bidding | National Competitive Bidding "Single Stage - One Evelope Procedure) | 20th January 2017 | 5th March 2017 | 4th May 2017
iii) |  | Providing/ Laying Water Supply Line | 9.5749 |  |  | 0 | 9.5749 | 0 | 0 | do | do | 5th March 2016 | 21st Oct 2016 | 30th June 2017
iv) |  | Providing & Fixing HT/LT Line | 5.2857 |  |  | 0 | 0 | 5.2857 | 0 | do | do | 20th January 2017 | 5th March 2017 | 4th May 2017
v) |  | Reconditioning of Road | 5.0662 |  |  | 0 | 0 | 5.0662 | 0 | do | do | do | do | do
vi) |  | Rep of Drainage Line and Construction of pump house | 4.3241 |  |  | 0 | 0 | 4.3241 | 0 | do | do | do | do | do
3. | 809 | Establishment of un-developed area of Small Industrial Estate, Sanghar | 26.45 | 12.67 | 13.78
i) |  | Construction of Road | 6.1847 |  |  | 0 | 6.1847 | 0 | 0 | Open Competitive Bidding | National Competitive Bidding "Single Stage - One Evelope Procedure) | 5th March 2016 | 21st Oct 2016 | 30th June 2017
ii) |  | Providing/ Laying Water Supply Line | 1.323 |  |  | 0 | 1.323 | 0 | 0 | do | do | do | do | do
iii) |  | Construction of underground Drainage | 9.0703 |  |  | 0 | 0 | 9.0703 | 0 | do | do | 20th January 2017 | 5th March 2017 | 4th May 2017
iv) |  | Providing & Fixing HT/LT Line | 4.0468 |  |  | 0 | 0 | 4.0468 | 0 | do | do | do | do | do
4. | 810 | Establishment of un-developed area of Small Industrial Estate, Rohri | 45 | 11.25 | 33.75
i) |  | Construction of Road | 22.1415 |  |  | 0 | 0 | 22.1415 | 0 | Open Competitive Bidding | National Competitive Bidding "Single Stage - One Evelope Procedure) | 20th January 2017 | 5th March 2017 | 4th February 2018
ii) |  | Providing/ Laying Rising Main, Rep of S.Chamber / S.Well and Const. of pump house | 2.4571 |  |  | 0 | 0 | 2.4571 | 0 | do | do | do | do | do
iii) |  | Construction of underground Drainage | 13.7061 |  |  | 0 | 0 | 13.7061 | 0 | do | do | do | do | do
iv) |  | Providing & Fixing HT/LT Line | 5.2838 |  |  | 0 | 0 | 5.2838 | 0 | do | do | do | do | do

## Sheet2
REQUIREMENTS OF SPPRA FOR HOISTING NIT IN OFFICIAL WEBSITE
► | Procurement Plan (duly signed) | Hard/Soft Copies |  | Revised Prepared
► | Notice Inviting Tenders | do |  | Already published
► | Notification Constitution of P.C. | Hard Copy |  | Available
► | Notification Constitution of C.R.C. | do |  | Available
► | Bidding Documents | Hard/Soft Copies |  | Prepared
► | Cheque Rs. 2000.00 Hoisting Ch. |  | -