## SCH-C
SCHEDULE-B PART-C (P.W)
DETAILED WORKING ESTIMATE FOR CONSTRUCTION OF PROTECTION WALL ON
CONSTRUCTION OF ROAD FROM MITHI NABISAR ROAD TO BHANANI BHEEL MILE 0/0-0/5 (1.00 KMS)
S.N | ITEM OF WORK | QTY |  | RATE |  | UNIT |  |  | AMOUNT
1 | EXCAVATION.
Excavation in foundation of buildings bridges and other Structures i/c degbelling dressing refilling around structure with excavated eaeth watering and ramming lead upto 5.0 ft in ordinary soil.(S.I.No: 18 b/P.No: 5 ).
|  | 600 | Cft. | @ Rs: | 2722.5 |  | %0 Cft |  | Rs. | 1633.5
(Twenty Seven Hundred Twenty two Rupees And Fifty Paisa)
2 | C.C. 1:6:12.
Cement concrete brick or stone ballast 1½” to 2" gauge Ratio ( 1:6:12 ) (S.I.No: 4 / P.No: 17).
|  | 100 | Cft. | @ Rs: | 8122.95 |  | % Cft |  | Rs. | 8122.95
(Eighty One Hundred Twenty two Rupees And Ninty Five Paisa)
3 | ERRECTION & REMOVAL.
Errection and removal of centering for R.C.C or plain cement concrete works Partial wood Vertical.(S.I.No: 18 b(ii) / P.No: 21).
|  | 500 | Cft. | @ Rs: | 3127.41 |  | % Cft |  | Rs. | 15637.05
(Thirty One Hundred Twenty Seven Rupees And Forty One Paisa)
4 | C.C. PLAIN RATIO 1:3:6.
Cement concrete plain including placing compacting, finishing and curing ,complete( including screening and washing of stone aggregate without shuttering) Ratio 1:3:6 (S.I.No: 5 / P.No: 18).
|  | 281 | Cft. | @ Rs: | 12595 |  | % Cft |  | Rs. | 35391.95
(Tweleve Thousand Five Hundred Ninty Five Rupees)
[6 empty] | Total |  | Rs. |  | 60785.45

## SCH-B
SCHEDULE-B PART-B (5’ CULVERT)
DETAILED WORKING ESTIMATE FOR CONSTRUCTION OF 5’ SPAN R.C.C. SLAB CULVERTS ON
CONSTRUCTION OF ROAD FROM MITHI NABISAR ROAD TO BHANANI BHEEL MILE 0/0-0/5 (1.00 KMS)
S.N: | ITEM OF WORK |  |  | QTY |  |  |  |  | RATE |  |  | UNIT |  |  |  |  | AMOUNT
1 | EXCAVATION.
Excavation in foundation of buildings bridges and other Structures i/c degbelling dressing refilling around structure with excavated eaeth watering and ramming lead upto 5.0 ft in ordinary soil.(S.I.No: 18 b /P.No: 5 ).
|  |  |  | 3044 |  |  | Cft. |  | @ Rs: |  | 2722.5 |  |  | %0 Cft |  |  | Rs. |  | 8287.29
(Twenty Seven Hundred Twenty Two Rupees And Fifty Paisa)
2 | C.C. 1:4:8.
Cement concrete brick or stone ballast 1 1/2" to 2" gauge Ratio ( 1:4:8 ) (S.I.No: 4 b / P.No: 17).
|  |  |  | 433 |  |  | Cft. |  | @ Rs: |  | 9416.28 |  |  | % Cft |  |  | Rs. |  | 40772.4924
(Ninty Four Hundred Sixteen Rupees And Eighty Two Paisa)
3 | PUCCA BRICK WORK.
Pucca brick work in foundation and plinth in cement sand mortor ratio (1:6) . (S.I.No: 4(i) e / P.No: 25).
|  |  |  | 977 |  |  | Cft. |  | @ Rs: |  | 11948.36 |  |  | % Cft |  |  | Rs. |  | 116735.4772
(Eleven Thousand Nine Hundred Forty Eight Rupees And Thirty Six Paisa)
4 | C.C. PLAIN RATIO 1:2:4.
Cement concrete plain including placing compacting, finishing and curing ,complete ( including screening and washing of stone aggregate without shuttering) Ratio 1:2:4 (S.I.No: 5 / P.No: 18).
|  |  |  | 113 |  |  | Cft. |  | @ Rs: |  | 14429.25 |  |  | % Cft |  |  | Rs. |  | 16305.0525
(Forteen Thousand Four Hundred Twenty Nine Rupees And Twenty Five Paisa)
5 | FABRICATION.
Fabrication of mild steel reinforcement for cement concrete i/c cutting bending, Laying in position making joints and fastenings including cost of Binding wire (also i/c removal of rust from bars.)(S.I.No: 7ii(a)/P.No:20). .
|  | Qty. | 971.98 |  | = | 8.67 | Cwt | @ Rs: |  | 4820.2 |  |  | P.Cwt |  |  | Rs. |  | 41791.134
112
(Forty Eight Hundred Twenty Rupees And Twenty Paisa)
6 | R.C.C. WORK.
R.C.C. work i/c all labour and materials except the cost of steel Reinforcement and its labour for bending and binding, which will be paid separately. This rate also i/c all kinds of forms moulds: lifting shuttering curing rendering and finishing the exposed surface(i/c screening and washing of shingle) R.C. work in roof slab, beams, columns rafts, lintels and other structural members laid in situ or precast laid in position completed in all respects. Ratio (1:2:4).(S.I.No: 6a-I/P.No:19).
[6 empty] | 284 | Cft. |  | @ Rs: |  | 337 |  |  | Per Cft. |  |  | Rs. |  | 95708
Three Hundred Thirty Seven Rupees
7 | CEMENT PLASTER.
Cement plaster (1:4) upto 20’ height ½ ” thick.(S.I.No: 11 b/P.No:58). .
|  |  |  | 430 |  |  | Sft |  | @ Rs: |  | 2283.93 |  |  | %Sft |  |  | Rs. |  | 9820.899
(Twenty Two Hundred Eighty Three Rupees And Ninty Three Paisa)
[12 empty] | Total |  |  | Rs. |  |  |  | 329420.3451

## SCH A
SCHEDULE-B
PART-A
NAME OF WORK: |  | CONSTRUCTION OF ROAD FROM MITHI NABISAR ROAD TO BHANANI BHEEL MILE 0/0-0/5 (1.00 KMS)
S.No: | ITEM OF WORK |  | QTY |  |  | RATE |  | UNIT |  | AMOUNT
1 | JUNGLE CLEARANCE
Jungle clearance and removing Within 100 ft (Thin jungle).
|  |  | 169950 | Sft | @ Rs: |  | 69.58 | %0 Sft |  | Rs. | 11825.121
(Sixty Nine Rupees And Fifity Eight Paisa)
2 | (CUTTING)
Earth work excavation in ashes soil or silt clearance including all lead and lifts.
|  |  | 269201 | Cft | @ Rs: |  | 1663.75 | %0 Cft |  | Rs. | 447883.1638
(Sixteen Hundred Sixty Three Rupees And Seventy Five Paisa)
3 | (FILLING).
Earth work excavation in ashes, sand soft soil or silt clearance i/e all lift and leads dressing and leveling of earth work to design section etc complete i/c earth work compaction by sheep foot roller with optimum moisture content upto 85% density as per modified AASHO specification.
|  |  | 135960 | Cft | @ Rs: |  | 3206.13 | %0 Cft |  | Rs. | 435905.4348
(Thirty Two Hundred Six Rupees And Thirteen Paisa)
4 | EARTH WORK.
Earth work for road embankment by bulldozers i/c ploughing mixing clod breaking dressing and compacting with optimum moisture content in all types soil except rock (if earth work is done by other than departmental agency) as per modified AASHO specification.
A. | 95% Density |  | 47586 | Cft | @ Rs: |  | 11977.82 | %0 Cft |  | Rs. | 569976.5425
(Eleven Thousand Nine Hundred Seventy Seven Rupees And Eighty Two Paisa)
B. | 85% Density |  | 98035.6575 | Cft | @ Rs: |  | 9448.05 | %0 Cft |  | Rs. | 926245.7938
(Ninty Four Hundred Forty Eight Rupees And Five Paisa)
5 | SUB-BASE COURSE.
Preparing sub-base course by s/s/ metal 1 1/2 “2” gauge of approved quarry in required thickness of 6” in 2 layers of 3” each to proper camber and grade i/c hand paking filling voids with 10cft pit sand watering and compacting the same so as to achieve 98-100 density as per modified AASHO specifications Rate i/c all cost of materials labour T&P carriage to site for work.
|  |  | 20394 | Cft | @ Rs: |  | 11173.4183 | % Cft |  | Rs. | 2278706.9281
(ElevenThousand One Hundred Seventy Three Rupees And Fourty Two Paisa)
6 | BRICKS ON END EDGING.
Laying bricks on end edging i/c supplying of 9:x42”x3” 1st class burnt bricks excavation on for laying edging with small side paroled to the road i/c all cost of materials T&P and carriage to site of work.
|  |  | 6798 | Rft | @ Rs: |  | 2927.936 | % Rft | Rs. |  | 199041.0893
(Twenty Nine Hundred Twenty Seven Rupees And Ninty Four Paisa)
7 | BASE COURSE.
Preparing base course by s/s stone metal form approved quarry of approved quality properly graded to maximum size of 1 ½”- 2” gauge in required thickness to proper cambers and grade i/c 15cft screening and non plastic quarry fines filling depressions with stone metal after initial rolling i/c watering and compacting the same so as to achieve 100% density as per modified specifications this r/c providing and using the templates camber plates screen form as directed Rate i/cs all cost of material T&P and carriage to site of work.
|  |  | 10197 | Cft | @ Rs: |  | 12810.0448 | % Cft |  | Rs. | 1306240.2683
(Twleve Thousand Eight Hundred Ten Rupees And Four Paisa)
8 | 1st COAT
P. surface dressing 1st Coat on new or existing surface with 30 Lbs bitumen and 4 Cft of Bajree of Required siae incleading cleaning the road surface roling etc complete (Rate includes all cost of matrials T & P and cariage up site of work
|  |  | 40788 | Sft | @ Rs: |  | 1743.9144 | % Sft |  | Rs. | 711307.8226
(Seventeen Hundred Fourty Three Rupees And Ninty One Paisa)
9 | 1-1/2” THICK CARPET (WITH PAVER MACHINE).
Providing 1-1/2” thick ( Consolidate ) premix Carpet in Proper Camber and Grade i/c Supply of 15 Cft Crush Bajri and 5 cft hill Sand of approved quarry and Gauge with 93 LBS of Bitumen 80 to 100 Penetration i/c Mixing in Mechanical mixture in Required protection i/c heating the material cleaning the road surface(Hill sand 3Cft: for mixing and 2.0Cft: for dusting) Rate i/c all cost of materials T&P and carriage up to site of work.
|  |  | 40788 | Sft | @ Rs: |  | 7478.3964 | % Sft |  | Rs. | 3050288.308
| (Seventy Four Hundred Seventy Eight Rupees And Fourty Paisa) | [6 empty] | Total | Rs. |  | 9937420.4721