## Measurement
Measurement Sheet
CONSTRUCTION OF BRICK PAVEMENT / JUMO MALLAH
|  |  | Brick Pavement |  |  | 1960 | Rft
S.No | Description | No | L | B | D | Qty | T-Qty
1 | Excavation in foundation of building bridges and other structures i/c bailing, dressing, filling around the structure with excavated earth, watering, ramming Lead up to one chain & lift up to 5.0' (CSI No:18 P4) | 2 | 1720 | 1.25 | 0.5 | 2150 | 2150
2 | Cement Concrete brick or stone Ballast 1 1/2" to 2" guage ratio 1:4:8 (GSI No.4 P17) | 2 | 1720 | 1.25 | 0.25 | 1075 | 1075
3 | Pucca Brick work in foundation and plinth in cement sand mortar 1:6 (CSI No:4 P24) | 1 | 1720 | 0.75 | 1.5 | 1935 | 1935
4 | Cement plaster 1:4 upto 20' height 1/2" thick (CSI No:11 P-57) | 2 | 1720 |  | 2 | 6880 | 6880
1 | Barrow pit excavation undressed lead up to 100' in Ordinary Soil (GSI No 3 P 1) | 1 | 1720 | 10 | 2 | 34400 | 34400
2 | Extra for every 50 ft additional lead or part there of (GSI No 8 P3) Qty same as Item No 8
| Average Lead =2600 ft - 100 ft = 2500 ft No of Lead = 2500 / 50 = 50 leads 50 Leads @ Rs. 30.40 per lead = Rs. 1520/= |  |  |  |  | 34400 | 34400
3 | Laying earth in 6" thick layers levelling, dressing and watering for compaction etc complete (GSI No 13b P4) Qty Same as Item No 8 |  |  |  |  | 34400 | 34400
4 | Ramming earth work (All types of Soil) (GSI No 13d P 4) Qty same as Item No 8 |  |  |  |  | 34400 | 34400
5 | Supplying and filling sand under floor and plugging in wells (GSI No 29 P 31) | 1 | 1720 | 10 | 0.25 | 4300 | 4300
6 | Dry brick on edge paving sand grouted i/c preparation of bed by watering ramming and bringing the same to proper cambre by 1/2" thick mud plaster (GSI No 5 P 46) | 1 | 1720 | 10 |  | 17200 | 17200

## Faceshet
FACE SHEET
Sponsoring Agency: | TOWN COMMITTEE TANDO GHULAM HYDER |  |  | S
Fund Head | Octroi and Zila Tax Share 2016-2017
Minor Head | CONSTRUCTION OF BRICK PAVEMENT / JUMO MALLAH
TOWN COMMITTEE TANDO GHULAM HYDER
Estimated Cost Rs.
This Detailed Working Estimate is prepared in the office of th ENGINEER TOWN COMMITTEE TANDO GHULAM HYDER for the probable expenditure that will be incurred on construction of BriCK PAVEMENT AT SIDIQUE JAT
General Description
On great demand of residents of SIDIQUE JAT and concsidering their great difficulties the work of Brick Pavement on the main streets of their Village is proposed.
Specifications | The Work will be carried out as per PWD/ PHE Specifications
Time | The period required to complete the work is 10 months
Rate | The rates are based on General Schedule of Rates
| ASSISTANT EXECUTIVE ENGINEER |  | TOWN OFFICER
| TOWN COMMITTEE |  | TOWN COMMITTEE
| TANDO GHULAM HYDER |  | TANDO GHULAM HYDER
CHAIRMAN
TOWN COMMITTEE
TANDO GHULAM HYDER

## Estimate
ABSTRACT
CONSTRUCTION OF BRICK PAVEMENT / JUMO MALLAH
0
S.No | Description | Qty | Unit | Rate | Amount
1 | Excavation in foundation of building bridges and other structures i/c bailing, dressing, filling around the structure with excavated earth, watering, ramming Lead up to one chain & lift up to 5.0' (CSI No:18 P4) | 2150 | P%o Cft | 2117.5 | 4553
2 | Cement Concrete brick or stone Ballast 1 1/2" to 2" guage ratio 1:4:8 (GSI No.4 P17) | 1075 | P% Cft | 5039 | 54169
3 | Pucca Brick work in foundation and plinth in cement sand mortar 1:6 (CSI No:4 P24) | 1935 | P% Cft | 354 | 6850
4 | Cement plaster 1:4 upto 20' height 1/2" thick (CSI No:11 P-57) | 6880 | P% Sft | 572.77 | 39407
1 | Barrow pit excavation undressed lead up to 100' in Ordinary Soil (GSI No 3 P 1) | 34400 | P%o Cft | 2117 | 72825
2 | Extra for every 50 ft additional lead or part there of (GSI No 8 P3) Qty same as Item No 8 | 34400 | P%o Cft | 5039 | 173342
3 | Laying earth in 6" thick layers levelling, dressing and watering for compaction etc complete (GSI No 13b P4) Qty Same as Item No 8 | 34400 | P%o Cft | 354 | 12178
4 | Ramming earth work (All types of Soil) (GSI No 13d P 4) Qty same as Item No 8 | 34400 | P%o Cft | 1141.25 | 39259
5 | Supplying and filling sand under floor and plugging in wells (GSI No 29 P 31) | 4300 | P% Cft | 203.54 | 8752
6 | Dry brick on edge paving sand grouted i/c preparation of bed by watering ramming and bringing the same to proper cambre by 1/2" thick mud plaster (GSI No 5 P 46) | 17200 | P% Sft | 3823.57 | 657654
7 | Carriage of Material
i | Bajri from Shadi Shaheed Lead 98 Miles | 0 | P %Cft | 0 | 0
ii | Hill Sand from Sui Lead 153 Miles | 1312 | P %Cft | 0 | 0
iii | Cement from Rohri Lead 80 Miles | 0 | P %Cft | 0 | 0
iv | Pucca Bricks from Nearest Kiln, Lead 24 Miles | 94600 | P %0 No | 1086.44 | 102777
v | Pit Sand from nearest Source Lead 3 Miles | 5418 | P %Cft | 579.41 | 31392
Grand Total Rs. |  |  |  |  | 1203158
Grand Total Say Rs. |  |  |  |  | 1200000
| ASSISTANT EXECUTIVE ENGINEER | TOWN OFFICER
| TOWN COMMITTEE | TOWN COMMITTEE
| TANDO GHULAM HYDER | TANDO GHULAM HYDER

## Material stat
Material Statement
CONSTRUCTION OF BRICK PAVEMENT / JUMO MALLAH
0
S.No | Item of Work | Length of Drain | Quantity |  | Stone Ballast | Bajri in CFT | Hill Sand in CFT | Cement in Bags | Steel in Cwt | Bricks in Nos | Pit Sand
1 | CC Bick or Stone 1:4:8 |  | 1075 | Cft |  | 967.5 | 483.75 | 96.75
2 | Pucca Brick Work 1:6 |  | 1935 | Cft |  |  | 580.5 | 77.4 |  | 26122.5
3 | Cement Plaster 1:4, 1/2" thick |  | 6880 | Sft |  |  | 247.68 | 50.22
1 | Brick on Edge |  | 17200 | Sft | [5 empty] | 94600 | 1118
2 | Pit Sand |  | 4300 | Cft | [6 empty] | 4300
Total |  |  |  |  | 0 | 0 | 1311.93 | 0 | 0 | 94600 | 5418
Say |  |  |  |  | 0 | 0 | 1312 | 0 | 0 | 94600 | 5418
|  |  | ASSISTANT EXECUTIVE ENGINEER |  |  |  | TOWN OFFICER
|  |  | TOWN COMMITTEE |  |  |  | TOWN COMMITTEE
|  |  | TANDO GHULAM HYDER |  |  |  | TANDO GHULAM HYDER

## Statement
STATEMENT OF BRICK PAVEMENT
CONSTRUCTION OF BRICK PAVEMENT / JUMO MALLAH
0
S. No. | Location |  | Brick Pavement
| Street Name | Marking | Length | Average Width
1 | 2 | 3 | 4 | 5
1
Total |  |  | 0
| ASSISTANT EXECUTIVE ENGINEER |  | TOWN OFFICER
| TOWN COMMITTEE |  | TOWN COMMITTEE
| TANDO GHULAM HYDER |  | TANDO GHULAM HYDER

## Cartage Ana
RATE ANALYSIS FOR CARTAGE OF MATERIAL
CONSTRUCTION OF BRICK PAVEMENT / JUMO MALLAH
0
Carriage of 100 cft / 5 Tons of all materials like stoneaggregate , spawl, coat, lime, Surkhi, etc B.G. Rail fastening points and crossing bridges girders pipe sheets rails MS Bars etc or 1000 No of Bricks 10" x 5" x 3" or 1000 No of tiles 12" x 6" x 2" or 150 cft f timber or 100 maunds of fuel wood by trucks or any other means owned by the contractor (Schedule of carriage Item No: 1 P5)
S. No | Description | Mileage |  | Rate | Unit | Total | G. Total
A | Stone Ballast 100 cft from Bulhari to site of Work, Lead | 0 | Miles
| For 1st | 6 | Miles | 0 | P Mile | 0
| For remaining | 0 | Miles | 0 | P Mile | 0 | 0
B | Bajri 100 cft from bulhari to site of Work, Lead | 0 | Miles
| For 1st | 0 | Miles | 0 | P Mile | 0
| For remaining | 0 | Miles | 0 | P Mile | 0 | 0
C | Hill Sand 100 cft from Bulhari to site of Work, Lead | 0 | Miles
| For 1st | 0 | Miles | 0 | P Mile | 0
| For remaining | 0 | Miles | 0 | P Mile | 0 | 0
D | Cement Bags from hyderabad to site of Work, Lead | 0 | Miles
| For 1st | 0 | Miles | 0 | P Mile | 0
| For remaining | 0 | Miles | 0 | P Mile | 0 | 0
E | Steel in Cwt fromhyderabad to site of Work, Lead | 0 | Miles
| For 1st | 0 | Miles | 0 | P Mile | 0
| For remaining | 0 | Miles | 0 | P Mile | 0 | 0
F | Bricks 1000 No from nearest Kiln to site of Work, Lead | 24 | Miles
| For 1st | 6 | Miles | 617.54 | P Mile | 617.54
| For remaining | 18 | Miles | 26.05 | P Mile | 468.9 | 1086.44
G | Pit Sand 100 cft from Source to site of Work, Lead | 3 | Miles | 579.41 | P Mile | 579.41 | 579.41

## Schedule B
Schedule B
CONSTRUCTION OF BRICK PAVEMENT / JUMO MALLAH
0
S.No | Description | Qty | Unit | Rate | Amount
1 | Excavation in foundation of building bridges and other structures i/c bailing, dressing, filling around the structure with excavated earth, watering, ramming Lead up to one chain & lift up to 5.0' (CSI No:18 P4) | 2150 | P%o Cft | 2117.5 | 4553
2 | Cement Concrete brick or stone Ballast 1 1/2" to 2" guage ratio 1:4:8 (GSI No.4 P17) | 1075 | P% Cft | 5039 | 54169
3 | Pucca Brick work in foundation and plinth in cement sand mortar 1:6 (CSI No:4 P24) | 1935 | P% Cft | 354 | 6850
4 | Cement plaster 1:4 upto 20' height 1/2" thick (CSI No:11 P-57) | 6880 | P% Sft | 572.77 | 39407
1 | Barrow pit excavation undressed lead up to 100' in Ordinary Soil (GSI No 3 P 1) | 34400 | P%o Cft | 2117 | 72825
2 | Extra for every 50 ft additional lead or part there of (GSI No 8 P3) Qty same as Item No 8 | 34400 | P%o Cft | 5039 | 173342
3 | Laying earth in 6" thick layers levelling, dressing and watering for compaction etc complete (GSI No 13b P4) Qty Same as Item No 8 | 34400 | P%o Cft | 354 | 12178
4 | Ramming earth work (All types of Soil) (GSI No 13d P 4) Qty same as Item No 8 | 34400 | P%o Cft | 1141.25 | 39259
5 | Supplying and filling sand under floor and plugging in wells (GSI No 29 P 31) | 4300 | P% Cft | 203.54 | 8752
6 | Dry brick on edge paving sand grouted i/c preparation of bed by watering ramming and bringing the same to proper cambre by 1/2" thick mud plaster (GSI No 5 P 46) | 17200 | P% Sft | 3823.57 | 657654
Total Rs. |  |  |  |  | 1068989
Conditions
1 | The Work Shall have to be executed according to the PWD/PHE Specifications.
2 | No premium on non schedule Items shall be paid to the contractor.
3 | Any error & omision and description of Item of work will be governed with relvent Schedule of Rates
4 | The Contractor shall have to bring the material to be used in the work from the quaries as mentioned in the estimate.
| Contractor | ASSISTANT EXECUTIVE
ENGINEER
TOWN COMMITTEE
TANDO GHULAM HYDER

## bidding face sheet
OFFICE OF THE CHAIRMAN TOWN COMMITTEE TANDO GHULAM HDYER DISTRICT TANDO MUHAMAMD KHAN
SUBJECT: |  | CONSTRUCTION OF BRICK PAVEMENT / JUMO MALLAH
ESTIMATE COST RS. |  |  | 1200000
TOWN COMMITTEE TANDO GHULAM HYDER
FROM :
ASISTANTANT EXCUTIVE ENIGINEER
TOWN COMMITTEE TANDO GHULAM HYDER

## bidding data
BIDDING DATA
(This section should be filled by the Engineer /Procuring Agency before issuance of the Biddings Doucments
a) | Name & Address of Procuring Agency |  | Town Committee Tando Ghulam Hyder
under (O.Z.T. Share 2016-2017)
Breif Description of Work: |  | CONSTRUCTION OF BRICK PAVEMENT / JUMO MALLAH
b) | Estimate cost |  | Rs: | 1400000 | 1500000
c) | amount of bid security |  | 2 % Rs | 28000
d) | Period Bid Validity |  | 2-1/2 Months
e) | amount of Bid Security |  | 10% (Rs. 2% at the time of
submission of bid & deductible from
from the runnig bill.
f) | Percentage if any to be deducted from bill. |  | 8% Rs:
g) | Dead line of submission of bid along with time |  | 20 / 02/ 2017 upto 12.00 noon
h) | Venue, Date & time of Bid opening |  | Office of the Chairman Town
committee Tando Ghulam
Hyder 21-02-2017 at 1.00 PM
i) | Time for completion from witten order commence: |  | 10 Months
j) | Stamp duty: |  | 0.35% or notified by the govt of
Sindh Will be paid successful
a stamp duty

## Tender Form
OFFICE OF THE CHAIRMAN TOWN COMMITTEE TANDO GHULAM HDYER DISTRICT TANDO MUHAMAMD KHAN
CDR. NO.
M/S
DATED: | / /2017
SUBJECT: | CONSTRUCTION OF BRICK PAVEMENT / JUMO MALLAH
GENERAL ABSTRACT
1 | COST OF SHEDULE ITEMS |  | RS:
| ADD/…………..% ABOVE/BELOW |  | RS:
| COST OF NON SHEDULE ITEMS |  | RS:
|  | TOTAL | RS:
CONTRACTOR
ASSISTANT EXECUTIVE ENIGNEER
TOWN COMMITTEE
TANDO GHULAM HYDER