## SHEET 1
LOCAL GOVERNMENT GOVERNMENT OF SINDH
Name Of Work:- Construction OF CULVERT/SAMALL BIRDGE @GHULAM MUHAMMAD UMARI
Taluka : | TANDO GHULAM HYDER
OZT:2016-2017
COST RS. |  | 800000
TOWN COMMITTEE TANDO GHULAM HYDER

## Facesheet
FACE SHEET
Sponsoring Agency: | TOWN COMMITTEE TANDO GHULAM HYDER
Fund Head | 2016-2017
Minor Head | Name Of Work:- Construction OF CULVERT/SAMALL BIRDGE @GHULAM MUHAMMAD UMARI
Estimated Cost Rs. | 800000
This Detailed Working Estimate is prepared in the office of Assistant executive Engineer Town Committee Tando Ghulam Hyder for the probable expenditure that will be incurred on the work mentioned under Minor Head.
General Description
Specifications | The Work will be carried out as per PWD/ PHE Specifications
Time | The period required to complete the work is 10 months
Rate | The rates are based on General Schedule of Rates
| Assistant Executive Engineer |  | TOWN OFFICER
| TOWN COMMITTEE |  | TOWN COMMITTEE
| TANDO GHULAM HYDER |  | TANDO GHULAM HYDER
CHAIRMAN
TOWN COMMITTEE
TANDO GHULAM HYDER

## estimate
Town Committee Tando Ghulam Hyder
Name Of Work:- Construction OF CULVERT/SAMALL BIRDGE @GHULAM MUHAMMAD UMARI
S# | Description |  |  |  |  | No | L | B | H/D | Qty |  | Amount
1 | Barrow Pit excavation underssed lead
up to 100ft (a) in ordinary soil (GSI No: 3 P/1)
[6 empty] | 0 | 400 | 7 | 1 | 0
[9 empty] | Total | 0 | Cft
[5 empty] | 0 | Cft | @ | Rs: | 847 | P % 0Cft |  | 0
2 | Earth work compaction (soft,ordnary or hard
Soil) (b) laying earth in 6" layer levelling dressing
and watering for compaction etc complete
(GSI No: 13 (b) P/4)
[6 empty] | Same Qty Item No: 1 |  |  |  | 0 | Cft
[5 empty] | 0 | Cft | @ | Rs: | 167 | P % 0 Cft |  | 0
3 | Cement concrete brick or Stone ballast 1 1/2" to
2" gauge.1:4:8.(G.S.I.No:4 (b) P/16)
[6 empty] | 0 | 400 | 7 | 0.5 | 0
[9 empty] | Total | 0 | Cft
[5 empty] | 0 | Cft | @ | Rs: | 847 | P % 0Cft |  | 0
1 | Excavation in foundation of building bridge and
other structure I/c degbelling dressing,Refilling
around structure with excavated earth watering
and ramming lead upto 5 feet(b) in rdinarysoil.
[6 empty] | 2 | 24 | 3.5 | 3 | 504
[6 empty] | 4 | 10 | 3.5 | 3 | 420
924
[5 empty] | 924 | Cft | @ | Rs: | 3176.25 | P % 0 Cft | RS | 2935
2 | Cement concrete brick or Stone ballast 1 1/2" to
2" gauge.1:4:8.(G.S.I.No:4 (b) P/16)
| Bed |  |  |  |  | 2 | 24 | 3.5 | 1 | 168
| Bed |  |  |  |  | 1 | 24 | 18 | 1 | 432
600
[5 empty] | 600 | Cft | @ | Rs: | 9416.28 | P % Cft | RS | 56498
3 | Pucca brick work in foundation and plinth in
(i) cement sand mortor (GSI.NO.5 P/25)
|  | 1st step |  |  |  | 2 | 24 | 3 | 2 | 288
|  | 2nd step |  |  |  | 2 | 24 | 2.5 | 1.5 | 180
|  | 3rd step |  |  |  | 2 | 24 | 2 | 1 | 71.68
|  | 4th step |  |  |  | 2 | 24 | 1.5 | 3 | 216
|  | 4th step w/w |  |  |  | 4 | 10 | 1.5 | 4 | 240
995.68
[5 empty] | 995.68 | Cft | @ | Rs: | 11948.36 | P % Cft | RS | 118967
4 | Cement concrete plain I/c placing compacting,
finishing and curing (I/c acreening washing of
stone aggregate without shuttering (1:2:4)
(G.S.I.No: 5 (f) P/17)
|  | w/w topping |  |  |  | 4 | 10 | 1.5 | 0.25 | 15
|  | bed |  |  |  | 1 | 24 | 18 | 0.25 | 108
123
[5 empty] | 123 | Cft | @ | Rs: | 14429.25 | P % Cft | RS | 17748
5 | Cement plaster (1:4) upto 20 ft: height 1/2" thick
| (GSI.No.11 /58) |  |  | 4th step |  | 4 | 10 |  | 4 | 16
|  |  |  | 4th step | w/w | 8 | 10 |  | 3 | 24
40
[5 empty] | 40 | Cft | @ | Rs: | 2283.93 | P.% Sft | RS | 914
4 | Cement concrete plain I/c placing compacting,
finishing and curing (I/c acreening washing of
stone aggregate without shuttering (1:3:6)
(G.S.I.No: 5 (h) P/17)
[6 empty] | 0 | #REF! | 1.5 | 0.75 | #REF!
[9 empty] | Total | #REF! | Cft
[5 empty] | #REF! | Cft | @ | Rs: | 5001.7 | P % Cft |  | #REF!
5 | Erection &Removal of centering for R.C.C or plain
cement concrete work of deodar wood
(Second class ). (G.S.I.No: 18 P/20).
[5 empty] | 2 | 0 | #REF! |  | 1.5 | #REF!
[9 empty] | Total | #REF! | Cft
[5 empty] | #REF! | Cft | @ | Rs: | 1405.75 | P % Cft |  | #REF!
5 | Applying floating coat of cement 1/32" thick
(G.S.I No: 14 P/59)
|  | Type-II Drain |  |  | 1 | 0 | #REF! |  | 2.5 | #REF!
[9 empty] | Total | #REF! | Sft
[5 empty] | #REF! | Sft | @ | Rs: | 361.08 | P % Sft |  | #REF!
6 | Cement Plaster (1:4) upto 20'Height 1/2" thick
(G.S.I No: 11 P/58)
[6 empty] | Same Qty Item No: 5 |  |  |  | #REF! | Sft
[5 empty] | #REF! | Sft | @ | Rs: | 572.77 | P % Sft |  | #REF!
7 | Construction of standard open type drain
counette block cement concrete
(1:2:4) costn situ the design profiles include
cost of moulds as per drawing include applying
floatingcement 1/32"thick exposed smooth
surface curing etc complete.(PHSI.No-1 P-44)
|  | Type-II Drain |  |  |  | 0 | #REF! |  |  | #REF! | Rft
[5 empty] | #REF! | Rft | @ | Rs: | 72.2 | P Rft |  | #REF!
7 | R.C.C work I/c all labour & material except the
of steel reinforcement & its labour of bending
wich will be paid separately. This rate also I/c all
kind of forms mould lifting shuttering curing
rendering and washing of shinmgle (a) R.C work
in roof slab beams columnsrafts lintel & other
structure members laid in situ or prcast laid in
position complete in all respect Ratio 1:2:4
90 Lbs cement 2 Cft sand 4Cft shingle 1/8" to 1/4"
gauge.(G.S.I.No:6 P/17)
[6 empty] | 0 | 15 | 3 | 0.75 | 0
[9 empty] | Total | 0 | Cft
[5 empty] | 0 | Cft | @ | Rs: | 114 | P Cft |  | 0
8 | Fabrication of mild steel reinforcement for C.C I/c cutting bending laying position making &
Jointing I/c cost of bending laying in position
making fastening I/c cost of binding wire also I/c
removl of rust from bars.(G.S.I.No: 7 (ii) P/19).
[7 empty] | 0 | x | 4.5 | 0 | Cwt
112
[5 empty] | 0 | Cwt | @ | Rs: | 2651.55 | P Cwt |  | 0
6 | Barrow Pit excavation underssed lead
up to 100ft (a) in ordinary soil (GSI No: 3 P/1)
[6 empty] | 0 | 300 | 2 | 1.5 | 0
[9 empty] | Total | 0 | Cft
[5 empty] | 0 | Cft | @ | Rs: | 847 | P % 0Cft |  | 0
7 | Earth work compaction (soft,ordnary or hard
Soil) (b) laying earth in 6" layer levelling dressing
and watering for compaction etc complete
(GSI No: 13 (b) P/4)
[6 empty] | Same Qty Item No: 6 |  |  |  | 0 | Cft
[5 empty] | 0 | Cft | @ | Rs: | 167 | P % 0 Cft |  | 0
6 | R.C.C work I/c all labour & material except the
of steel reinforcement & its labour of bending
wich will be paid separately. This rate also I/c all
kind of forms mould lifting shuttering curing
rendering and washing of shinmgle (a) R.C work
in roof slab beams columnsrafts lintel & other
structure members laid in situ or prcast laid in
position complete in all respect Ratio 1:2:4
90 Lbs cement 2 Cft sand 4Cft shingle 1/8" to 1/4"
gauge.(G.S.I.No:6 P/17)
| beams |  |  |  |  | 4 | 18 | 1.75 | 2 | 252 | Cft
| slab |  |  |  |  | 1 | 22 | 18 | 1 | 396 | Cft
| p/w |  |  |  |  | 2 | 24 | 1 | 3 | 144 | Cft
792
[5 empty] | 792 | Cft | @ | Rs: | 337 | P Cft | RS | 266904
7 | Fabrication of mild steel reinforcement for C.C I/c cutting bending laying position making &
Jointing I/c cost of bending laying in position
making fastening I/c cost of binding wire also I/c
removl of rust from bars.(G.S.I.No: 7 (ii) P/19).
[7 empty] | 792 | 4.5 | 31.8214 | Cwt
112
[5 empty] | 31.8214 | Cwt | @ | Rs: | 4820.2 | P Cwt | RS | 153386
8 | Barrow Pit excavation underssed lead
up to 100ft (a) in ordinary soil (GSI No: 3 P/1)
[6 empty] | 1 | 60 | 16 | 4 | 3840
[5 empty] | 3840 | Cft | @ | Rs: | 2117.5 | P % 0Cft | RS | 8131
9 | Extra for every 50ft addititional lead or part of
| (GSI No: 8 P3) |  |  |  |  | Same Qty Item No: 8 |  |  |  | 3840 | Cft
[5 empty] | 3840 | Cft | @ | Rs: | 5039 | P % 0Cft | RS | 19350
10 | Earth work compaction (soft,ordnary or hard
Soil) (b) laying earth in 6" layer levelling dressing
and watering for compaction etc complete
(GSI No: 13 (b) P/4)
[6 empty] | Same Qty Item No: 8 |  |  |  | 3840 | Cft
[5 empty] | 3840 | Cft | @ | Rs: | 354 | P % 0 Cft |  | 1359
11 | Remaining earth worth (all types of soil)
| (GSI No: 13 P/4) |  |  |  |  | Same Qty Item No: 8 |  |  |  | 3840
[5 empty] | 3840 | Cft | @ | Rs: | 453.75 | P % 0Cft | RS | 1742
| Cartage of Material | [8 empty] | Total | Rs | 647934
Cartage of Material
a | Bajri from Khanote to site of work lead |  |  |  |  | 77 | Miles
[5 empty] | 118.08 | Cft | @ | Rs: | 3083.72 | P % Cft | RS | 3641
b | Hill Sand from Bholari to site of work |  |  |  |  | 57 | Miles
[5 empty] | 657.88 | Cft | @ | Rs: | 2432.56 | P % Cft | RS | 16003
c | Cement from Lucky Factory to site of work |  |  |  |  | 86 | Miles
[5 empty] | 185.7434 | Bag | @ | Rs: | 32.13 | P.Bag | RS | 5968
f | Steel from Hyderbad |  |  |  |  | 25 | Miles
[5 empty] | 31.8214 | Cwt | @ | Rs: | 4 | P Cwt |  | 127.2857
d. | bricks from local |  |  |  |  | 43 | Miles
[5 empty] | 13441.68 | Nos |  | Rs: | 669.54 | P.%0 Noa | RS | 9000
e | Barrow pit |  |  |  | 3 | Miles
[5 empty] | 3840 |  | @ | Rs: | 579.41 | P.%Cft | RS | 22249
a | steel |  |  |  |  | 47 | Miles
[5 empty] | 31.8214 | cwt | @ | Rs: | 19.67 | cwt | RS | 625.9275
| Cartage of Matriales | [8 empty] | RS |  | 56988.2857
| Total Schdule Amount | [8 empty] | RS |  | 647934
| Add: | 10% |  |  | 704922.2857 |  |  |  |  | RS |  | 70492
775414.2857
[10 empty] | Say | Rs | 800000
| Assistant Executive Engineer | [6 empty] | TOWN OFFICER
| Town Committee Tando Ghulam Hyder | [6 empty] | Town Committee Tando Ghulam Hyder
MATERIAL STATEMENT
MATERIAL STATEMENT
S# | ITEM |  | Qty | Stone |  | Bajri |  | Hill Sand | Cement | Briks. |  | Steel
1 | C.C1:4:8 Plain |  | 123 | - |  | 118.08 |  | 59.04 | 11.808 | - |  | -
2 | Pucca brick work 1:6 |  | 995.68 | - |  | - |  | 248.92 | 34.2514 | 13441.68 |  | -
3 | R.C.C.1:2:4 |  | 0 | - |  | 0 |  | 0 | 0 | - |  | 0
5 | Cement Plaster 1:4 |  | #REF! | - |  | - |  | #REF! | #REF!
4 | Cement Plaster 1:4 |  | 40 |  |  |  |  | 1.44 | 0.292
| RCC 1:2:4 |  | 792 |  |  |  |  | 348.48 | 139.392 |  |  | 31.8214
| TOTAL |  |  | 0 |  | 118.08 |  | 657.88 | 185.7434 | 13441.68 |  | 31.8214
| SAY |  |  | 0 |  | 118.08 |  | 657.88 | 185.7434 | 13441.68 |  | 31.8214
Assistant Executive Engineer
Town Committee Tando Ghulam Hyder

## shedule b
Town Committee Tando Ghulam Hyder
NAME OF WORK:- Construction @ Village Muharam Leghari
S# | Description |  |  | Qty |  |  | Rate | Unit |  | Amount
1 | Barrow Pit excavation underssed lead
up to 100ft (a) in ordinary soil (GSI No: 3 P/1)
|  |  |  | 0 | 400 | 7 | 1 | 0
[7 empty] | Total | 0 | Cft
|  |  | 0 | Cft | @ | Rs: | 847 | P % 0Cft |  | 0
2 | Earth work compaction (soft,ordnary or hard
Soil) (b) laying earth in 6" layer levelling dressing
and watering for compaction etc complete
(GSI No: 13 (b) P/4)
|  |  |  | Same Qty Item No: 1 |  |  |  | 0 | Cft
|  |  | 0 | Cft | @ | Rs: | 167 | P % 0 Cft |  | 0
3 | Cement concrete brick or Stone ballast 1 1/2" to
2" gauge.1:4:8.(G.S.I.No:4 (b) P/16)
|  |  |  | 0 | 400 | 7 | 0.5 | 0
[7 empty] | Total | 0 | Cft
|  |  | 0 | Cft | @ | Rs: | 847 | P % 0Cft |  | 0
1 | Excavation in foundation of building bridge and
other structure I/c degbelling dressing,Refilling
around structure with excavated earth watering
and ramming lead upto 5 feet(b) in rdinarysoil.
|  |  | 924 | Cft | @ | Rs: | 3176.25 | P % 0 Cft | RS | 2935
2 | Cement concrete brick or Stone ballast 1 1/2" to
2" gauge.1:4:8.(G.S.I.No:4 (b) P/16)
|  |  | 600 | Cft | @ | Rs: | 9416.28 | P % Cft | RS | 56498
3 | Pucca brick work in foundation and plinth in
(i) cement sand mortor (GSI.NO.5 P/25)
|  |  | 995.68 | Cft | @ | Rs: | 11948.36 | P % Cft | RS | 118967
4 | Cement concrete plain I/c placing compacting,
finishing and curing (I/c acreening washing of
stone aggregate without shuttering (1:2:4)
(G.S.I.No: 5 (f) P/17)
|  |  | 123 | Cft | @ | Rs: | 14429.25 | P % Cft | RS | 17748
5 | Cement plaster (1:4) upto 20 ft: height 1/2" thick
|  |  | 40 | Cft | @ | Rs: | 2283.93 | P.% Sft | RS | 914
4 | Cement concrete plain I/c placing compacting,
finishing and curing (I/c acreening washing of
stone aggregate without shuttering (1:3:6)
(G.S.I.No: 5 (h) P/17)
|  |  |  | 0 | #REF! | 1.5 | 0.75 | #REF!
[7 empty] | Total | #REF! | Cft
|  |  | #REF! | Cft | @ | Rs: | 5001.7 | P % Cft |  | #REF!
5 | Erection &Removal of centering for R.C.C or plain
cement concrete work of deodar wood
(Second class ). (G.S.I.No: 18 P/20).
|  |  | 2 | 0 | #REF! |  | 1.5 | #REF!
[7 empty] | Total | #REF! | Cft
|  |  | #REF! | Cft | @ | Rs: | 1405.75 | P % Cft |  | #REF!
5 | Applying floating coat of cement 1/32" thick
(G.S.I No: 14 P/59)
|  | Type-II Drain | 1 | 0 | #REF! |  | 2.5 | #REF!
[7 empty] | Total | #REF! | Sft
|  |  | #REF! | Sft | @ | Rs: | 361.08 | P % Sft |  | #REF!
6 | Cement Plaster (1:4) upto 20'Height 1/2" thick
(G.S.I No: 11 P/58)
|  |  |  | Same Qty Item No: 5 |  |  |  | #REF! | Sft
|  |  | #REF! | Sft | @ | Rs: | 572.77 | P % Sft |  | #REF!
7 | Construction of standard open type drain
counette block cement concrete
(1:2:4) costn situ the design profiles include
cost of moulds as per drawing include applying
floatingcement 1/32"thick exposed smooth
surface curing etc complete.(PHSI.No-1 P-44)
|  | Type-II Drain |  | 0 | #REF! |  |  | #REF! | Rft
|  |  | #REF! | Rft | @ | Rs: | 72.2 | P Rft |  | #REF!
7 | R.C.C work I/c all labour & material except the
of steel reinforcement & its labour of bending
wich will be paid separately. This rate also I/c all
kind of forms mould lifting shuttering curing
rendering and washing of shinmgle (a) R.C work
in roof slab beams columnsrafts lintel & other
structure members laid in situ or prcast laid in
position complete in all respect Ratio 1:2:4
90 Lbs cement 2 Cft sand 4Cft shingle 1/8" to 1/4"
gauge.(G.S.I.No:6 P/17)
|  |  |  | 0 | 15 | 3 | 0.75 | 0
[7 empty] | Total | 0 | Cft
|  |  | 0 | Cft | @ | Rs: | 114 | P Cft |  | 0
8 | Fabrication of mild steel reinforcement for C.C I/c cutting bending laying position making &
Jointing I/c cost of bending laying in position
making fastening I/c cost of binding wire also I/c
removl of rust from bars.(G.S.I.No: 7 (ii) P/19).
[5 empty] | 0 | x | 4.5 | 0 | Cwt
112
|  |  | 0 | Cwt | @ | Rs: | 2651.55 | P Cwt |  | 0
6 | Barrow Pit excavation underssed lead
up to 100ft (a) in ordinary soil (GSI No: 3 P/1)
|  |  |  | 0 | 300 | 2 | 1.5 | 0
[7 empty] | Total | 0 | Cft
|  |  | 0 | Cft | @ | Rs: | 847 | P % 0Cft |  | 0
7 | Earth work compaction (soft,ordnary or hard
Soil) (b) laying earth in 6" layer levelling dressing
and watering for compaction etc complete
(GSI No: 13 (b) P/4)
|  |  |  | Same Qty Item No: 6 |  |  |  | 0 | Cft
|  |  | 0 | Cft | @ | Rs: | 167 | P % 0 Cft |  | 0
6 | R.C.C work I/c all labour & material except the
of steel reinforcement & its labour of bending
wich will be paid separately. This rate also I/c all
kind of forms mould lifting shuttering curing
rendering and washing of shinmgle (a) R.C work
in roof slab beams columnsrafts lintel & other
structure members laid in situ or prcast laid in
position complete in all respect Ratio 1:2:4
90 Lbs cement 2 Cft sand 4Cft shingle 1/8" to 1/4"
gauge.(G.S.I.No:6 P/17)
|  |  | 792 | Cft | @ | Rs: | 337 | P Cft | RS | 266904
7 | Fabrication of mild steel reinforcement for C.C I/c cutting bending laying position making &
Jointing I/c cost of bending laying in position
making fastening I/c cost of binding wire also I/c
removl of rust from bars.(G.S.I.No: 7 (ii) P/19).
|  |  | 31.8214 | Cwt | @ | Rs: | 4820.2 | P Cwt | RS | 153386
8 | Barrow Pit excavation underssed lead
up to 100ft (a) in ordinary soil (GSI No: 3 P/1)
|  |  | 3840 | Cft | @ | Rs: | 2117.5 | P % 0Cft | RS | 8131
9 | Extra for every 50ft addititional lead or part of
|  |  | 3840 | Cft | @ | Rs: | 5039 | P % 0Cft | RS | 19350
10 | Earth work compaction (soft,ordnary or hard
Soil) (b) laying earth in 6" layer levelling dressing
and watering for compaction etc complete
(GSI No: 13 (b) P/4)
|  |  | 3840 | Cft | @ | Rs: | 354 | P % 0 Cft |  | 1359
11 | Remaining earth worth (all types of soil)
|  |  | 3840 | Cft | @ | Rs: | 453.75 | P % 0Cft | RS | 1742
[8 empty] | Total | Rs | 647934
Cartage of Material
| Assistant Executive Engineer |  |  |  |  | Assistant Executive Engineer
| Town Committee Tando Ghulam Hyder |  |  |  |  | Town Committee Tando Ghulam Hyder

## bidding face sheet
OFFICE OF THE CHAIRMAN TOWN COMMITTEE TANDO GHULAM HDYER DISTRICT TANDO MUHAMAMD KHAN
SUBJECT: |  | Name Of Work:- Construction OF CULVERT/SAMALL BIRDGE @GHULAM MUHAMMAD UMARI
ESTIMATE COST RS. |  |  | 800000
TOWN COMMITTEE TANDO GHULAM HYDER
FROM :
ASSISTANT EXECUTIVE ENIGNEER
TOWN COMMITTEE TANDO GHULAM HYDER

## bidding data
BIDDING DATA
(This section should be filled by the Engineer /Procuring Agency before issuance of the Biddings Doucments
a) | Name & Address of Procuring Agency |  | Town Committee Tando Ghulam Hyder
under (O.Z.T. Share 2016-2017)
Breif Description of Work: |  | Name Of Work:- Construction OF CULVERT/SAMALL BIRDGE @GHULAM MUHAMMAD UMARI
b) | Estimate cost |  | Rs: | 1400000 | 800000
c) | amount of bid security |  | 2 % Rs | 28000
d) | Period Bid Validity |  | 2-1/2 Months
e) | amount of Bid Security |  | 10% (Rs. 2% at the time of
submission of bid & deductible from
from the runnig bill.
f) | Percentage if any to be deducted from bill. |  | 8% Rs:
g) | Dead line of submission of bid along with time |  | 20 / 02 /2017 upto 12.00 noon
h) | Venue, Date & time of Bid opening |  | Office of the Chairman Town
committee Tando Ghulam
Hyder 21 / 02 /2017 at 1.00 PM
i) | Time for completion from witten order commence: |  | 10 Months
j) | Stamp duty: |  | 0.35% or notified by the govt of
Sindh Will be paid successful
a stamp duty

## Tender Form
OFFICE OF THE CHAIRMAN TOWN COMMITTEE TANDO GHULAM HDYER DISTRICT TANDO MUHAMAMD KHAN
CDR. NO.
M/S
DATED: | / /2017
SUBJECT: | Name Of Work:- Construction OF CULVERT/SAMALL BIRDGE @GHULAM MUHAMMAD UMARI
GENERAL ABSTRACT
1 | COST OF SHEDULE ITEMS |  | RS:
| ADD/…………..% ABOVE/BELOW |  | RS:
| COST OF NON SHEDULE ITEMS |  | RS:
|  | TOTAL | RS:
CONTRACTOR
ASSISTANT EXECUTIVE ENIGNEER
TOWN COMMITTEE
TANDO GHULAM HYDER