## Sheet1
LOCAL GOVERNMENT GOVERNMENT OF SINDH
CONSTRUCTION OF C.C BLOCK & SURFACE DRAINS @ VILLAGE GUL HASSAN NOTKANI
| Taluka : | TANDO GHULAM HYDER
O.Z.T SHARE 2016-2017
ESTIMATED COST |  | RS | 800000
TOWN COMMITTEE TANDO GHULAM HYDER

## Facesheet
FACE SHEET
Sponsoring Agency: | TOWN COMMITTEE TANDO GHULAM HYDER
Fund Head | 2016-2017
Minor Head | CONSTRUCTION OF C.C BLOCK & SURFACE DRAINS @ VILLAGE GUL HASSAN NOTKANI
Estimated Cost Rs. | 800000
This Detailed Working Estimate is prepared in the office of Assistant Engineer TOWN COMMITTEE TANDO GHULAM HYDER for the probable expenditure that will be incurred on the work mentioned under Minor Head.
General Description
The existing drains have given up thier life and require complete reconstruction as these have become dangerous for streets, nearby buildings and pedstrians. Also new drains in leftover / newly flourished streets along with provision of CC Blocks are proposed to be constructed. Consequently this estimate is prepared
Specifications | The Work will be carried out as per PWD/ PHE Specifications
Time | The period required to complete the work is 10 months
Rate | The rates are based on General Schedule of Rates
| Assistant Executive Engineer |  | TOWN OFFICER
| TOWN COMMITTEE |  | TOWN COMMITTEE
| TANDO GHULAM HYDER |  | TANDO GHULAM HYDER
CHAIRMAN
Town committee
TANDO GHULAM HYDER

## Measurement
Measurement Sheet
Construction of CC Drains & CC Block @ Village GUL HASSAN NOTKANI
| Type I | 550 |  | Type II |  | 520
S.No | Description | Nos | L | B | D | Qty | T-Qty
1 | Excavation in foundation of building bridges and other structures i/c bailing, dressing, filling around the structure with excavated earth, watering, ramming Lead up to one chain & lift up to 5.0' (CSI No:18 P4) | [5 empty] | 2977
| Type-I Drains | 1 | 550 | 2.42 | 0.83 | 1104.73
| Type-II Drains | 1 | 520 | 3 | 1.2 | 1872
2 | CC plain i/c placing compacting finishing & curing complete i/c screening and washing of stone aggregate w/o shuttering (CSI NO:5 P-16)
| Ratio 1:4:8 | [5 empty] | 848
| Type-I Drains | 1 | 550 | 2.42 | 0.25 | 332.75
| Type-II Drains | 1 | 520 | 3 | 0.33 | 514.8
| Ratio 1:2:4 | [5 empty] | 59
| CC Slabs on Type-I Drains | 11 | 6 | 2.42 | 0.37 | 59.0964
3 | Construction of standard open drain cunette block of CC 1:2:4 in situ to the design profile i/c cost of mould as per drawing i/c applying floating coat of cement 1/32" thick to the exposed face finished smooth curing etc complete as per detailed drawing (PHSI. No. D P-58)
| Type-I Drains @ 0.35 cft per Rft | 1 | 550 |  |  | 550 | 550
| Type-II Drains @ 0.74 cft per Rft | 1 | 520 |  |  | 520 | 520
4 | Pucca Brick work in foundation and plinth in cement sand mortar 1:6 (CSI No:4 P24) | [5 empty] | 1399
| Type-I Drain | 2 | 550 | 0.75 | 0.75 | 618.75
| Type-II Drain | 2 | 520 | 0.75 | 1 | 780
5 | Cement plaster 1:4 up to 20' height 1/2" thick (CSI No:11 P-57) | [5 empty] | 2010
| Type-I Drains | 2 | 550 |  | 0.92 | 1012
| Type-II Drains | 2 | 520 |  | 0.96 | 998.4
6 | RCC work in roof slabs beams columns rafts lintels and other structural members laid in situ are pre-cast laid in position etc complete in all respects ratio 1:2:4(CSI.No:6 P-17) | [5 empty] | 112
| Type-I Drains | 5 | 8 | 2.5 | 0.37 | 37
| Type-II Drains | 5 | 10 | 3 | 0.5 | 75
7 | Fabrication of mild steel reinforcement for cement concrete i/c cutting bending laying in position making joints and fastening i/c cost of binding wire also includes removal of rust from bars (CSI NO.7 P-17) | 112 | 4.5 |  | 112 | 4.5 | 4.5
8 | Barrow pit excavation undressed lead up to 100' in Ordinary Soil (GSI No 3 P 1) | 1 | 200 | 8 | 0.5 | 800 | 800
9 | Extra for every 50 ft additional lead or part there of (GSI No 8 P2) Qty same as Item No 8
| Average Lead =2600 ft - 100 ft = 2500 ft No of Lead = 2500 / 50 = 50 leads 50 Leads @ Rs. 178/ per lead = Rs. 5039/= |  |  |  |  | 800 | 800
10 | Laying earth in 6" thick layers leveling, dressing and watering for compaction etc complete (GSI No 13b P3) Qty Same as Item No 8 |  |  |  |  | 800 | 800
11 | Ramming earth work (All types of Soil) (GSI No 13d P 3) Qty same as Item No 8 |  |  |  |  | 800 | 800
12 | Supplying and filling sand under floor and plugging in wells (GSI No 29 P 26) | [5 empty] | 400
| For CC Blocks | 1 | 200 | 8 | 0.25 | 400
13 | Cement Concrete brick or stone Ballast 1 1/2" to 2" guage ratio 1:4:8 (GSI No.4 P17) | 1 | 200 | 8 | 0.37 | 592 | 592
14 | Providing and laying 3" thick CC topping cement concrete 1:2:4 including surface finishing and dividing into pannels (GSI No 16 P 42) | 1 | 200 | 8 | 0 | 1600 | 1600

## Estimate
ABSTRACT
Construction of CC Drains & CC Block @ Village GUL HASSAN NOTKANI
S.No | Description | Qty | Unit | Rate | Amount
1 | Excavation in foundation of building bridges and other structures i/c bailing, dressing, filling around the structure with excavated earth, watering, ramming Lead up to one chain & lift up to 5.0' (CSI No:18 P4) | 2977 | P %0Cft | 3176.25 | 9456
2 | CC plain i/c placing compacting finishing & curing complete i/c screening and washing of stone aggregate w/o shuttering (CSI NO:5 P-16) | 848 | 1:4:8 P %Cft | 11288.75 | 95729
|  | 59 | 1:2:4 P %Cft | 14429.25 | 8513
3 | Construction of standard open drain cunette block of CC 1:2:4 in situ to the design profile i/c cost of mould as per drawing i/c applying floating coat of cement 1/32" thick to the exposed face finished smooth curing etc complete as per detailed drawing (PHSI. No. D P-58) | 550 | Type-I P Rft | 94 | 51700
|  | 520 | Type-II P Rft | 174 | 90480
4 | Pucca Brick work in foundation and plinth in cement sand mortar 1:6 (CSI No:4 P24) | 1399 | P %Cft | 11948.36 | 167158
5 | Cement plaster 1:4 up to 20' height 1/2" thick (CSI No:11 P-57) | 2010 | P %Cft | 2283.93 | 45907
6 | RCC work in roof slabs beams columns rafts lintels and other structural members laid in situ are pre-cast laid in position etc complete in all respects ratio 1:2:4(CSI.No:6 P-17) | 112 | P.Cft | 337 | 37744
7 | Fabrication of mild steel reinforcement for cement concrete i/c cutting bending laying in position making joints and fastening i/c cost of binding wire also includes removal of rust from bars (CSI NO.7 P-17) | 4.5 | Cwt | 4820.2 | 21691
8 | Barrow pit excavation undressed lead up to 100' in Ordinary Soil (GSI No 3 P 1) | 800 | P%o Cft | 2117.5 | 1694
9 | Extra for every 50 ft additional lead or part there of (GSI No 8 P2) Qty same as Item No 8 | 800 | P%o Cft | 5039 | 4031
10 | Laying earth in 6" thick layers leveling, dressing and watering for compaction etc complete (GSI No 13b P3) Qty Same as Item No 8 | 800 | P%o Cft | 354 | 283
11 | Ramming earth work (All types of Soil) (GSI No 13d P 3) Qty same as Item No 8 | 800 | P%o Cft | 453.75 | 363
12 | Supplying and filling sand under floor and plugging in wells (GSI No 29 P 26) | 400 | P% Cft | 1141.25 | 4565
13 | Cement Concrete brick or stone Ballast 1 1/2" to 2" guage ratio 1:4:8 (GSI No.4 P17) | 592 | P %Cft | 9416.28 | 55744
14 | Providing and laying 3" thick CC topping cement concrete 1:2:4 including surface finishing and dividing into pannels (GSI No 16 P 42) | 1600 | P %Sft | 4411.82 | 70589
15 | Carriage of Material
15.1 | Stone from SHAH NIHAL Lead 37 Miles | 568 | P %Cft | 1781.32 | 10118
15.2 | Bajri from Shadi KHANOTE Lead 77 Miles | 1824 | P %Cft | 3083.72 | 56247
15.3 | Hill Sand from BULLAHRI Lead 57 Miles | 1628 | P %Cft | 2432.52 | 39601
15.4 | Cement from ZEEL PAK Lead 43 Miles | 405 | P Bag | 32.13 | 13013
15.5 | Pucca Bricks from Nearest Kiln, Lead 6 Miles | 18887 | P %o No | 669.64 | 12647
15.6 | Steel from HYDERABAD Lead 47 Miles | 4.5 | P Cwt | 19.6772 | 89
15.7 | Pit Sand from nearest Source Lead 1 Mile | 400 | P %Cft | 579.41 | 2318
Grand Total Rs. |  |  |  |  | 799680
|  | say |  | RS. | 800000
| Assistant Executive Engineer | TOWN OFFICER
| TOWN COMMITTEE | TOWN COMMITTEE
| TANDO GHULAM HYDER | TANDO GHULAM HYDER

## Material stat
Material Statement
Construction of CC Drains & CC Block @ Village GUL HASSAN NOTKANI
S.No | Item of Work | Length of Drain | Quantity |  | Stone Ballast | Bajri in CFT | Hill Sand in CFT | Cement in Bags | Steel in Cwt | Bricks in Nos | Pit Sand
1 | CC 1:4:8 |  | 848 | Cft |  | 814.08 | 407.04 | 81.41
2 | Pucca Brick Work 1:6 |  | 1399 | Cft |  |  | 359.54 | 48.13 |  | 18886.5
3 | Cunnette Block CC 1:2:4 Type I | 550 | 190 | Cft |  | 167.2 | 83.6 | 32.3
4 | Cunnette Block CC 1:2:4 TypeII | 520 | 387 | Cft |  | 340.56 | 170.28 | 65.79
5 | CC 1:2:4 for slabs over Type I Drain |  | 59 | Cft |  | 51.92 | 25.96 | 10.03
6 | Cement Plaster 1:4, 1/2" thick |  | 2010 | Sft |  |  | 72.36 | 20.1
7 | RCC 1:2:4 |  | 112 | Cft |  | 98.56 | 49.28 | 19.71 | 4.5
8 | CC Brick or stone ballast 1:4:8 |  | 592 | Cft | 568.32 |  | 284.16 | 56.83
9 | CC Topping 1:2:4 3" Thick |  | 1600 | Sft |  | 352 | 176 | 70.4
10 | Pit Sand |  | 400 | Cft | [6 empty] | 400
Total |  |  |  |  | 568.32 | 1824.32 | 1628.22 | 404.7 | 4.5 | 18886.5 | 400
Say |  |  |  |  | 568 | 1824 | 1628 | 405 | 4.5 | 18887 | 400
Assistant Executive Engineer
TOWN COMMITTEE
TANDO GHULAM HYDER

## Cartage Ana
RATE ANALYSIS FOR CARTAGE OF MATERIAL
Construction of CC Drains & CC Block @ Village GUL HASSAN NOTKANI
Carriage of 100 cft / 5 Tons of all materials like stoneaggregate , spawl, coat, lime, Surkhi, etc B.G. Rail fastening points and crossing bridges girders pipe sheets rails MS Bars etc or 1000 No of Bricks 10" x 5" x 3" or 1000 No of tiles 12" x 6" x 2" or 150 cft f timber or 100 maunds of fuel wood by trucks or any other means owned by the contractor (Schedule of carriage Item No: 1 P5)
S. No | Description | Rate | Unit | Total | G. Total
A | Stone Ballast 100 cft from SHAH NIHAL to site of Work, Lead | 37 | Miles
| For 1st 6 miles | 771.96 |  | 771.96
| For remaining Miles 31 Miles | 32.56 | Per Mile | 1009.36 | 1781.32
B | Bajri 100 cft from KHANOTE to site of Work, Lead | 77 | Miles
| For 1st 6 miles | 771.96 |  | 771.96
| For remaining Miles 71 Miles | 32.56 | Per Mile | 2311.76 | 3083.72
C | Hill Sand 100 cft from BULHARI to site of Work, Lead | 57 | Miles
| For 1st 6 miles | 771.96 |  | 771.96
| For remaining Miles 51 Miles | 32.56 | Per Mile | 1660.56 | 2432.52
D | Cement Bags from ZEEL PAK to site of Work, Lead | 43 | Miles
| For 1st 2 miles | 7.53 |  | 7.53
| For remaining Miles 41 Miles | 0.6 | Per Mile | 24.6 | 32.13
E | Steel in Cwt from HYDERBAD to site of Work, Lead | 47 | Miles
| For 1st 2 miles | 502.52 |  | 502.52
|  | 32.56 | Per Mile | 1465.2 | 19.6772
F | Bricks 1000 No from nearest Kiln to site of Work, Lead | 8 | Miles
| For 1st 6 miles | 617.54 | Per Mile | 617.54
| For remaining Miles 2 Miles | 26.05 | Per Mile | 52.1 | 669.64
G | Pit Sand 100 cft from Source to site of Work, Lead | 3 | Mile
| For 1st 3 miles | 579.41 |  | 579.41 | 579.41

## Statment
STATEMENT OF CC DRAINS & CC BLOCK
Construction of CC Drains & CC Block @ Village GUL HASSAN NOTKANI
| S. No. | Marking | Type I | Type II | CC Blocks
[5 empty] | Length | Av: Width
| 1 | 2 | 3 | 4 | 5 | 6
1
2
3
4
5
| Total |  | 0 | 0 | 0
Assistant Executive Engineer
TOWN COMMITTEE
TANDO GHULAM HYDER

## Schedule B
Schedule B
Construction of CC Drains & CC Block @ Village GUL HASSAN NOTKANI
S.No | Description | Qty | Unit | Rate | Amount
1 | Excavation in foundation of building bridges and other structures i/c bailing, dressing, filling around the structure with excavated earth, watering, ramming Lead up to one chain & lift up to 5.0' (CSI No:18 P4) | 2977 | P %0Cft | 3176.25 | 9456
2 | CC plain i/c placing compacting finishing & curing complete i/c screening and washing of stone aggregate w/o shuttering (CSI NO:5 P-16) | 848 | 1:4:8 P %Cft | 11288.75 | 95729
|  | 59 | 1:2:4 P %Cft | 14429.25 | 8513
3 | Construction of standard open drain cunette block of CC 1:2:4 in situ to the design profile i/c cost of mould as per drawing i/c applying floating coat of cement 1/32" thick to the exposed face finished smooth curing etc complete as per detailed drawing (PHSI. No. D P-58) | 550 | Type-I P Rft | 94 | 51700
|  | 520 | Type-II P Rft | 174 | 90480
4 | Pucca Brick work in foundation and plinth in cement sand mortar 1:6 (CSI No:4 P24) | 1399 | P %Cft | 11948.36 | 167158
5 | Cement plaster 1:4 up to 20' height 1/2" thick (CSI No:11 P-57) | 2010 | P %Cft | 2283.93 | 45907
6 | RCC work in roof slabs beams columns rafts lintels and other structural members laid in situ are pre-cast laid in position etc complete in all respects ratio 1:2:4(CSI.No:6 P-17) | 112 | P.Cft | 337 | 37744
7 | Fabrication of mild steel reinforcement for cement concrete i/c cutting bending laying in position making joints and fastening i/c cost of binding wire also includes removal of rust from bars (CSI NO.7 P-17) | 4.5 | Cwt | 4820.2 | 21691
8 | Barrow pit excavation undressed lead up to 100' in Ordinary Soil (GSI No 3 P 1) | 800 | P%o Cft | 2117.5 | 1694
9 | Extra for every 50 ft additional lead or part there of (GSI No 8 P2) Qty same as Item No 8 | 800 | P%o Cft | 5039 | 4031
10 | Laying earth in 6" thick layers leveling, dressing and watering for compaction etc complete (GSI No 13b P3) Qty Same as Item No 8 | 800 | P%o Cft | 354 | 283
11 | Ramming earth work (All types of Soil) (GSI No 13d P 3) Qty same as Item No 8 | 800 | P%o Cft | 453.75 | 363
12 | Supplying and filling sand under floor and plugging in wells (GSI No 29 P 26) | 400 | P% Cft | 1141.25 | 4565
13 | Cement Concrete brick or stone Ballast 1 1/2" to 2" guage ratio 1:4:8 (GSI No.4 P17) | 592 | P %Cft | 9416.28 | 55744
14 | Providing and laying 3" thick CC topping cement concrete 1:2:4 including surface finishing and dividing into pannels (GSI No 16 P 42) | 1600 | P %Sft | 4411.82 | 70589
Total Rs. |  |  |  |  | 665647
Conditions
1 | The Work Shall have to be executed according to the PWD/PHE Specifications.
2 | No premium on non schedule Items shall be paid to the contractor.
3 | Any error & omision and description of Item of work will be governed with relvent Schedule of Rates
4 | The Contractor shall have to bring the material to be used in the work from the quaries as mentioned in the estimate.
Contractor
Engineer
TOWN COMMITTEE
TANDO GHULAM HYDER

## abstract
#VALUE! | Pumping Machinary | 2823929
#VALUE! | Surface Drains | 799680
| Total | 3623609