## Faceshet
FACE SHEET
Sponsoring Agency: | TOWN COMMITTEE TANDO GHULAM HYDER
Fund Head | 2016-2017
Minor Head | EARTH FILLING OF KATCHA ROAD SHAFI MUHAMMAD NOTKANI TO M.HASSAN NOTKANI
Estimated Cost Rs. | 800000
This Detailed Working Estimate is prepared in the office of Assistant executive Engineer Town Committee Tando Ghulam Hyder for the probable expenditure that will be incurred on the work mentioned under Minor Head.
General Description
Specifications | The Work will be carried out as per PWD/ PHE Specifications
Time | The period required to complete the work is 10 months
Rate | The rates are based on General Schedule of Rates
Assistant Executive Engineer |  | TOWN OFFICER
TOWN COMMITTEE |  | TOWN COMMITTEE
TANDO GHULAM HYDER |  | TANDO GHULAM HYDER
CHAIRMAN
TOWN COMMITTEE
TANDO GHULAM HYDER

## Measurement
Measurement Sheet
EARTH FILLING OF KATCHA ROAD SHAFI MUHAMMAD NOTKANI TO M.HASSAN NOTKANI
S.No | Description | Nos | L | B | D | Qty
1 | Barrow pit excavation undressed lead up to 100' in Ordinary Soil (GSI No 3 P 1) | 1 | 3950 | 10 | 3 | 118500
2 | Extra for every 50 ft additional lead or part there of (GSI No 8 P3) Qty same as Item No 1 |  |  |  |  | 118500
| Average Lead =2600 ft - 100 ft = 2500 ft No of Lead = 2500 / 50 = 50 leads 50 Leads @ Rs. 30.40 per lead = Rs. 1520/= |  |  |  | 0 | 118500
3 | Laying earth in 6" thick layers levelling, dressing and watering for compaction etc complete (GSI No 13b P4) Qty Same as Item No 1 |  |  |  |  | 118500
4 | Ramming earth work (All types of Soil) (GSI No 13d P 4) Qty same as Item No 1 |  |  |  |  | 118500

## Estimate
ABSTRACT
EARTH FILLING OF KATCHA ROAD SHAFI MUHAMMAD NOTKANI TO M.HASSAN NOTKANI
S.No | Description | Qty | Unit | Rate | Amount
1 | Barrow pit excavation undressed lead up to 100' in Ordinary Soil (GSI No 3 P 1) | 118500 | P %0Cft | 2117.5 | 250924
2 | Extra for every 50 ft additional lead or part there of (GSI No 8 P3) Qty same as Item No 1 | 118500 | P %0Cft | 5039 | 597122
Average Lead =2600 ft - 100 ft = 2500 ft No of Lead = 2500 / 50 = 50 leads 50 Leads @ Rs. 30.40 per lead = Rs. 1520/=
3 | Laying earth in 6" thick layers levelling, dressing and watering for compaction etc complete (GSI No 13b P4) Qty Same as Item No 1 | 118500 | P %0Cft | 354 | 41949
4 | Ramming earth work (All types of Soil) (GSI No 13d P 4) Qty same as Item No 1 | 118500 | P %0Cft | 453.75 | 53769
| Total |  |  |  | 943764
| 15below |  |  |  | 141564.6
| Grand Total |  |  |  | 802199.4
Total Rs. |  |  |  |  | 802199.4
Say Rs. |  |  |  |  | 800000
| ASSISTANT EXCUTIVE ENGINEER | TOWN OFFICER
| TOWN COMMITTEE | TOWN COMMITTEE
| TANDO GHULAM HYDER | TANDO GHULAM HYDER

## Schedule B
Schedule B
EARTH FILLING OF KATCHA ROAD SHAFI MUHAMMAD NOTKANI TO M.HASSAN NOTKANI
S.No | Description | Qty | Unit | Rate | Amount
1 | Barrow pit excavation undressed lead up to 100' in Ordinary Soil (GSI No 3 P 1) | 118500 | P %0Cft | 2117.5 | 250924
2 | Extra for every 50 ft additional lead or part there of (GSI No 8 P3) Qty same as Item No 1 | 118500 | P %0Cft | 5039 | 597122
Average Lead =2600 ft - 100 ft = 2500 ft No of Lead = 2500 / 50 = 50 leads 50 Leads @ Rs. 30.40 per lead = Rs. 1520/=
3 | Laying earth in 6" thick layers levelling, dressing and watering for compaction etc complete (GSI No 13b P4) Qty Same as Item No 1 | 118500 | P %0Cft | 354 | 41949
4 | Ramming earth work (All types of Soil) (GSI No 13d P 4) Qty same as Item No 1 | 118500 | P %0Cft | 453.75 | 53769
Total Rs. |  |  |  |  | 943764
1
2
3 | Any error & omission and description of Item of work will be governed with relevant Schedule of Rates
4 | The Contractor shall have to bring the material to be used in the work from the quarries as mentioned in the estimate.
Contractor
ASSISTANT EXCUTIVE ENGINEER
TOWN COMMITTEE
TANDO GHULAM HYDER

## Sheet1
FIRST AND FINAL BILL
Name of Agency |  |  | Mashuqe Ali Khoso
Name of Work |  |  | EARTH FILLING OF KATCHA ROAD SHAFI MUHAMMAD NOTKANI TO M.HASSAN NOTKANI
Head of account |  |  | SC 21021-021(PHS KA 4534 Works Rural A 12 Total Civil and works A12502 Works Rural-2 A13101 (Repair and Miantenance Charges)
Authorty |  |  | Work order issued by E.E PHE Division Kashmore @ Kandhkot vide his no AB/TC/ Dated
1 | Barrow pit excavation undressed lead up to 100' in Ordinary Soil (GSI No 3 P 1)
|  | Qty | 118500 | P %0Cft | 2117.5 | 250924
2 | Extra for every 50 ft additional lead or part there of (GSI No 8 P3) Qty same as Item No 1
|  | Qty | 118500 | P %0Cft | 5039 | 597122
3 | Laying earth in 6" thick layers levelling, dressing and watering for compaction etc complete (GSI No 13b P4) Qty Same as Item No 1
|  | Qty | 118500 | P %0Cft | 354 | 41949
4 | Ramming earth work (All types of Soil) (GSI No 13d P 4) Qty same as Item No 1
|  | Qty | 118500 | P %0Cft | 453.75 | 53769
|  |  | Total Rs |  |  | 943764
CERTIFICATE
1. Certify that this bill has not been paid before in any shape .
2. Certify that nothing is out standing against the contractor.
3. Certify that work has been done as per PWD and PHE specification
4. Certify that measurement has been recorded by Mr. Kailash AEN vide MB No Page No date
(Kailash Amar lal Hablani)
Assistant Engineer
Public Health Engg: Sub Division
Kashmore @ Kandh Kot