## Sheet1
LOCAL GOVERNMENT GOVERNMENT OF SINDH
Construction of C.C Block @ VILLAGE ISMAIL MALLAH
Taluka : | TANDO GHULAM HYDER
OZT:2016-2017
COST RS. |  | 1200000
TOWN COMMITTEE TANDO GHULAM HYDER

## Facesheet
FACE SHEET
Sponsoring Agency: | TOWN COMMITTEE TANDO GHULAM HYDER
Fund Head | 2016-2017
Minor Head | Construction of C.C Block @ VILLAGE ISMAIL MALLAH
Estimated Cost Rs. | 1200000
This Detailed Working Estimate is prepared in the office of Assistant executive Engineer Town Committee Tando Ghulam Hyder for the probable expenditure that will be incurred on the work mentioned under Minor Head.
General Description
Specifications | The Work will be carried out as per PWD/ PHE Specifications
Time | The period required to complete the work is 10 months
Rate | The rates are based on General Schedule of Rates
| Assistant Executive Engineer |  | TOWN OFFICER
| TOWN COMMITTEE |  | TOWN COMMITTEE
| TANDO GHULAM HYDER |  | TANDO GHULAM HYDER
CHAIRMAN
TOWN COMMITTEE
TANDO GHULAM HYDER

## Measurement
Measurement Sheet
Construction of C.C Block @ VILLAGE ISMAIL MALLAH
S.No | Description | Nos | L | B | D | Qty | T-Qty
1 | Barrow pit excavation undressed lead up to 100' in Ordinary Soil (GSI No 3 P 1) | 1 | 1000 | 10 | 1.75 | 17500 | 17500
2 | Extra for every 50 ft additional lead or part there of (GSI No 8 P2) Qty same as Item No 8
| Average Lead =2600 ft - 100 ft = 2500 ft No of Lead = 2500 / 50 = 50 leads 50 Leads @ Rs. 178/ per lead = Rs. 5039/= |  |  |  |  | 17500 | 17500
3 | Laying earth in 6" thick layers leveling, dressing and watering for compaction etc complete (GSI No 13b P3) Qty Same as Item No 8 |  |  |  |  | 17500 | 17500
4 | Ramming earth work (All types of Soil) (GSI No 13d P 3) Qty same as Item No 8 |  |  |  |  | 17500 | 17500
5 | Supplying and filling sand under floor and plugging in wells (GSI No 29 P 26) | [5 empty] | 2500
| For CC Blocks | 1 | 1000 | 10 | 0.25 | 2500
6 | Cement Concrete brick or stone Ballast 1 1/2" to 2" guage ratio 1:4:8 (GSI No.4 P17) | 1 | 1000 | 10 | 0.37 | 3700 | 3700
7 | Providing and laying 3" thick CC topping cement concrete 1:2:4 including surface finishing and dividing into pannels (GSI No 16 P 42) | 1 | 1000 | 10 | 0 | 10000 | 10000

## Estimate
ABSTRACT
Construction of C.C Block @ VILLAGE ISMAIL MALLAH
S.No | Description | Qty | Unit | Rate | Amount
1 | Barrow pit excavation undressed lead up to 100' in Ordinary Soil (GSI No 3 P 1) | 17500 | P%o Cft | 2117.5 | 37056
2 | Extra for every 50 ft additional lead or part there of (GSI No 8 P2) Qty same as Item No 8 | 17500 | P%o Cft | 5039 | 88183
3 | Laying earth in 6" thick layers leveling, dressing and watering for compaction etc complete (GSI No 13b P3) Qty Same as Item No 8 | 17500 | P%o Cft | 354 | 6195
4 | Ramming earth work (All types of Soil) (GSI No 13d P 3) Qty same as Item No 8 | 17500 | P%o Cft | 453.75 | 7941
5 | Supplying and filling sand under floor and plugging in wells (GSI No 29 P 26) | 2500 | P% Cft | 1141.25 | 28531
6 | Cement Concrete brick or stone Ballast 1 1/2" to 2" guage ratio 1:4:8 (GSI No.4 P17) | 3700 | P %Cft | 9416.28 | 348402
7 | Providing and laying 3" thick CC topping cement concrete 1:2:4 including surface finishing and dividing into pannels (GSI No 16 P 42) | 10000 | P %Sft | 4411.82 | 441182
8 | Carriage of Material
8.1 | Stone from SHAH NIHAL Lead 37 Miles | 3552 | P %Cft | 1781.32 | 63272
8.2 | Bajri from Shadi KHANOTE Lead 77 Miles | 2200 | P %Cft | 3083.72 | 67842
8.3 | Hill Sand from BULLAHRI Lead 57 Miles | 2876 | P %Cft | 2432.52 | 69959
8.4 | Cement from ZEEL PAK Lead 43 Miles | 795 | P Bag | 32.13 | 25543
8.5 | Pucca Bricks from Nearest Kiln, Lead 6 Miles | 0 | P %o No | 669.64 | 0
8.6 | Steel from HYDERABAD Lead 47 Miles | 0 | P Cwt | 19.6772 | 0
8.7 | Pit Sand from nearest Source Lead 1 Mile | 2500 | P %Cft | 579.41 | 14485
Grand Total Rs. |  |  |  |  | 1198591
|  | SAY |  | RS | 1200000
| Assistant Executive Engineer | TOWN OFFICER
| TOWN COMMITTEE | TOWN COMMITTEE
| TANDO GHULAM HYDER | TANDO GHULAM HYDER
CHAIRMAN
TOWN COMMITTEE
TANDO GHULAM HYDER

## Material stat
Material Statement
Construction of C.C Block @ VILLAGE ISMAIL MALLAH
S.No | Item of Work | Length of Drain | Quantity |  | Stone Ballast | Bajri in CFT | Hill Sand in CFT | Cement in Bags | Steel in Cwt | Bricks in Nos | Pit Sand
1 | CC Brick or stone ballast 1:4:8 |  | 3700 | Cft | 3552 |  | 1776 | 355.2
2 | CC Topping 1:2:4 3" Thick |  | 10000 | Sft |  | 2200 | 1100 | 440
3 | Pit Sand |  | 2500 | Cft | [6 empty] | 2500
Total |  |  |  |  | 3552 | 2200 | 2876 | 795.2 | 0 | 0 | 2500
Say |  |  |  |  | 3552 | 2200 | 2876 | 795 | 0 | 0 | 2500
Assistant Executive Engineer
TOWN COMMITTEE
TANDO GHULAM HYDER

## Cartage Ana
RATE ANALYSIS FOR CARTAGE OF MATERIAL
Construction of C.C Block @ VILLAGE ISMAIL MALLAH
Carriage of 100 cft / 5 Tons of all materials like stoneaggregate , spawl, coat, lime, Surkhi, etc B.G. Rail fastening points and crossing bridges girders pipe sheets rails MS Bars etc or 1000 No of Bricks 10" x 5" x 3" or 1000 No of tiles 12" x 6" x 2" or 150 cft f timber or 100 maunds of fuel wood by trucks or any other means owned by the contractor (Schedule of carriage Item No: 1 P5)
S. No | Description | Rate | Unit | Total | G. Total
A | Stone Ballast 100 cft from SHAH NIHAL to site of Work, Lead | 37 | Miles
| For 1st 6 miles | 771.96 |  | 771.96
| For remaining Miles 31 Miles | 32.56 | Per Mile | 1009.36 | 1781.32
B | Bajri 100 cft from KHANOTE to site of Work, Lead | 77 | Miles
| For 1st 6 miles | 771.96 |  | 771.96
| For remaining Miles 71 Miles | 32.56 | Per Mile | 2311.76 | 3083.72
C | Hill Sand 100 cft from BULHARI to site of Work, Lead | 57 | Miles
| For 1st 6 miles | 771.96 |  | 771.96
| For remaining Miles 51 Miles | 32.56 | Per Mile | 1660.56 | 2432.52
D | Cement Bags from ZEEL PAK to site of Work, Lead | 43 | Miles
| For 1st 2 miles | 7.53 |  | 7.53
| For remaining Miles 41 Miles | 0.6 | Per Mile | 24.6 | 32.13
E | Steel in Cwt from HYDERBAD to site of Work, Lead | 47 | Miles
| For 1st 2 miles | 502.52 |  | 502.52
|  | 32.56 | Per Mile | 1465.2 | 19.6772
F | Bricks 1000 No from nearest Kiln to site of Work, Lead | 8 | Miles
| For 1st 6 miles | 617.54 | Per Mile | 617.54
| For remaining Miles 2 Miles | 26.05 | Per Mile | 52.1 | 669.64
G | Pit Sand 100 cft from Source to site of Work, Lead | 3 | Mile
| For 1st 3 miles | 579.41 |  | 579.41 | 579.41

## Statment
STATEMENT OF CC DRAINS & CC BLOCK
Construction of C.C Block @ VILLAGE ISMAIL MALLAH
| S. No. | Marking | Type I | Type II | CC Blocks
[5 empty] | Length | Av: Width
| 1 | 2 | 3 | 4 | 5 | 6
1
2
3
4
5
| Total |  | 0 | 0 | 0
Assistant Executive Engineer
TOWN COMMITTEE
TANDO GHULAM HYDER

## Schedule B
Schedule B
Construction of C.C Block @ VILLAGE ISMAIL MALLAH
S.No | Description | Qty | Unit | Rate | Amount
#VALUE! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF! | #REF!
#VALUE! | #REF! | #REF! | #REF! | #REF! | #REF!
#VALUE! | #REF! | #REF! | #REF! | #REF! | #REF!
#VALUE! | #REF! | #REF! | #REF! | #REF! | #REF!
#VALUE! | #REF! | #REF! | #REF! | #REF! | #REF!
1 | Barrow pit excavation undressed lead up to 100' in Ordinary Soil (GSI No 3 P 1) | 17500 | P%o Cft | 2117.5 | 37056
2 | Extra for every 50 ft additional lead or part there of (GSI No 8 P2) Qty same as Item No 8 | 17500 | P%o Cft | 5039 | 88183
3 | Laying earth in 6" thick layers leveling, dressing and watering for compaction etc complete (GSI No 13b P3) Qty Same as Item No 8 | 17500 | P%o Cft | 354 | 6195
4 | Ramming earth work (All types of Soil) (GSI No 13d P 3) Qty same as Item No 8 | 17500 | P%o Cft | 453.75 | 7941
5 | Supplying and filling sand under floor and plugging in wells (GSI No 29 P 26) | 2500 | P% Cft | 1141.25 | 28531
6 | Cement Concrete brick or stone Ballast 1 1/2" to 2" guage ratio 1:4:8 (GSI No.4 P17) | 3700 | P %Cft | 9416.28 | 348402
7 | Providing and laying 3" thick CC topping cement concrete 1:2:4 including surface finishing and dividing into pannels (GSI No 16 P 42) | 10000 | P %Sft | 4411.82 | 441182
Total Rs. |  |  |  |  | 957490
Conditions
1 | The Work Shall have to be executed according to the PWD/PHE Specifications.
2 | No premium on non schedule Items shall be paid to the contractor.
3 | Any error & omision and description of Item of work will be governed with relvent Schedule of Rates
4 | The Contractor shall have to bring the material to be used in the work from the quaries as mentioned in the estimate.
Contractor
ASISTANT EXECUTIVE ENGINEER
TOWN COMMITTEE
TANDO GHULAM HYDER

## bidding face sheet
OFFICE OF THE CHAIRMAN TOWN COMMITTEE TANDO GHULAM HDYER DISTRICT TANDO MUHAMAMD KHAN
SUBJECT: |  | Construction of C.C Block @ VILLAGE ISMAIL MALLAH
ESTIMATE COST RS. |  |  | 1200000
TOWN COMMITTEE TANDO GHULAM HYDER
FROM :
ASISTANTANT EXCUTIVE ENIGINEER
TOWN COMMITTEE TANDO GHULAM HYDER

## bidding data
BIDDING DATA
(This section should be filled by the Engineer /Procuring Agency before issuance of the Biddings Doucments
a) | Name & Address of Procuring Agency |  | Town Committee Tando Ghulam Hyder
under (O.Z.T. Share 2016-2017)
Breif Description of Work: |  | Construction of C.C Block @ VILLAGE ISMAIL MALLAH
b) | Estimate cost |  | Rs: | 1200000 | 1200000
c) | amount of bid security |  | 2 % Rs | 24000
d) | Period Bid Validity |  | 2-1/2 Months
e) | amount of Bid Security |  | 10% (Rs. 2% at the time of
submission of bid & deductible from
from the runnig bill.
f) | Percentage if any to be deducted from bill. |  | 8% Rs:
g) | Dead line of submission of bid along with time |  | 20-08-2016 upto 12.00 noon
h) | Venue, Date & time of Bid opening |  | Office of the Chairman Town
committee Tando Ghulam
Hyder 21-02-2017 at 1.00 PM
i) | Time for completion from witten order commence: |  | 10 Months
j) | Stamp duty: |  | 0.35% or notified by the govt of
Sindh Will be paid successful
a stamp duty

## Tender Form
OFFICE OF THE CHAIRMAN TOWN COMMITTEE TANDO GHULAM HDYER DISTRICT TANDO MUHAMAMD KHAN
CDR. NO.
M/S
DATED: | / /2017
SUBJECT: | Construction of C.C Block @ VILLAGE ISMAIL MALLAH
GENERAL ABSTRACT
1 | COST OF SHEDULE ITEMS |  | RS:
| ADD/…………..% ABOVE/BELOW |  | RS:
| COST OF NON SHEDULE ITEMS |  | RS:
|  | TOTAL | RS:
CONTRACTOR
ASSISTANT EXECUTIVE ENIGNEER
TOWN COMMITTEE
TANDO GHULAM HYDER