## Drains
BILL OF QUANTITIES
(A) Description and rate of Items based on Composite Schedule of Rates.
Name of Work |  | CONSTRUCTION OF SURFACE DRAINS TYPE-I & II I/C C.C TOPPING AT ZONE-A & B FOR RURAL RDRAINAGE SCHEME VILLAGE GAHAND TALUKA KAZI AHMED DISTRICT SHAHEED BENAZIR ABAD
PART-A |  | SURFACE DRAINS TYPE-I & II
Item No. | Description of item to be executed at site |  |  | Unit | Quantity | Rate | Amount in Rupees
1 | Excavation in foundation of building bridges and other structures I/c dag belling dressing refilling around the structures with excavated Earth watering ramming lead up to one chain and lift up to 5’ (GSI No. 18 P-04) |  |  | P: %0 Cft: | 16430 | 3176.25 | 52185.7875
2 | Cement concrete plain i/c placing compacting finishing and curing complete i/c screening and washing of stone aggregate without shuttering Ratio 1:4:8 (GSI No. 5 (i) P-16) |  |  | P: % Cft: | 3545 | 11288.75 | 400186.1875
3 | Pacca brick work in foundation and plinth in cement, sand, mortar (1:6) (GSI No 5 (e) P-21) |  |  | P: % Cft: | 9375 | 11948.36 | 1120158.75
4 | Construction of Standard open drains bundle block of cement concret (1:2:4) in situ to the design profile i/c cost of module as per drawing i/c applying floating cost of cement 1/2" thick to the exposed face finished smooth curing etc complete as per detailed drawing (PHSI No. 1 (ii) P-58)
|  |  | Type-I | P: Rft: | 4000 | 94 | 376000
|  |  | Type-II | P: Rft: | 1500 | 174 | 261000
5 | Cement Plaster (1:4) 1/2” thick up to 12’ height (GSI No.11 (b) P-52) |  |  | P: % Sft: | 5490 | 2283.93 | 125387.757
6 | R.C.C work in roof slab beams columns rafts lintels and other structural members laid in situ or prrecast laid in position complete in all respect. (i) Ratio 1:2:4 Lbs cement2 Cft, sand 4 cft shingle1/8” to ¼” gauge (GSI No. 6 P-49) |  |  | P: Cft: | 3545 | 337 | 1194665
7 | Fabrication of mild steel reinforcement for C.C i/c cutting, bending, laying in position making joints and fastening i/c cost of binding wire (also i/c removal of rust from bars) (Using Tor Bars) (GSI No. 8 (b) P-17) |  |  | P: Cwt: | 126.6 | 5001.7 | 633215.22
[6 empty] | TOTAL | 4162798.702
|  | CONTRACTOR | EXECUTIVE ENGINEER PUBLIC HEALTH ENGG: DIVISION SHAHEED BENAZIR ABAD

## C.C Top..
BILL OF QUANTITIES
(A) Description and rate of Items based on Composite Schedule of Rates.
PART-B |  | C.C TOPPING
Item No. | Description of item to be executed at site |  |  |  |  | Unit | Quantity | Rate | Amount in Rupees
1 | Barrow pit excavation undressed lead upto 100 ft: (ordinary soil) (CSI No. 3 P-1) |  |  |  |  | P: %0 Cft: | 50710 | 2117.5 | 107378.425
2 | Earth work compaction (Soft, ordinary and hard soil) (b) Laying earth in 6" layers levelling and dressing etc completed (CSI No. 13 (b) P-3) |  |  |  |  | P: %0 Cft: | 67140 | 263 | 17657.82
3 | Cement concrete brick or stone ballast 1 1/2" to 2" gauge Ratio 1:4:8 (GSI No. 5 P-15) |  |  |  |  | P: % Cft: | 14770.8 | 9416.28 | 1390859.8862
4 | Cement concrete plain i/c placing compacting finishing and curing complete i/c screening and washing of stone aggregate without shuttering Ratio 1:2:4 (CSI No. 5 P-16) |  |  |  |  | P: % Cft: | 11190 | 14429.25 | 1614633.075
5 | Earth from outside (Lead 1 Mile) |  |  |  |  | P: %0 Cft: | 50710 | 407 | 206389.7
6 | Erection and removal of centering for RCC or plain C.C Work of Partal Wood 1st class(vertical) (GSI No. 18 (b) P-19) |  |  |  |  | P: % Sft: | 2797.5 | 3127.41 | 87489.2948
[8 empty] | TOTAL | 3424408.201
| PART-A |  | Rs. | 4162799
| PART-B |  | Rs. | 3424408
| TOTAL (a) |  | Rs. | 7587207
--------- | % above/ below on the rates of CSR. |  |  |  | Amount to be added/ deducted on the basis of
[5 empty] | of premium quoted |  | Total (b) | __________________
Total (A) = a + b in words & figures
|  |  |  | CONTRACTOR |  | EXECUTIVE ENGINEER PUBLIC HEALTH ENGG: DIVISION SHAHEED BENAZIR ABAD