|  |
| --- |
|  |

|  |
| --- |
|  |

***Guidelines Regulations for Procurement of Works. (Annexure A-I)***

***(Annexure A-I)***

***PROCUREMENT PLAN (Development / Capital) for the Year 2016-17***

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ***S No*** | ***Name of Scheme & Estimated Cost*** | ***Allocated Funds*** | ***Cost of ongoing works (Expenditure already incurred)*** | ***Funds earmarked for ongoing works*** | ***Cost of New Works (components)*** | ***Funds for Works (c-e)*** | ***Nature of Procurement*** | ***Method of Procurement*** | ***Anticipated /Actual Date of Advertisement*** | ***Anticipated /Actual Date of Start*** | ***Anticipated /Actual Date of Completion.*** |
|  | ***B*** | ***c*** | ***d*** | ***e*** | ***f*** | ***g*** | ***h*** | ***i*** | ***j*** | ***k*** | ***l*** |
| *01* | *Re-Constt: of road Buchen road to Railway Over Head Bridge along Sakrand Railway mile 0/0-0/7 (1.40 km).* | *41.373* | *=* | *=* | *=* | *20.6855* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *12 Months* |
| *02* | *Constt: of Road from Taj Colony Near Railway Track road to Connect Sugar Mill Road mile 0/0-0/5 (1.0 km).* | *10.639* | *=* | *=* | *=* | *5.3195* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *12 Months* |
| *03* | *Constt: of road from Mohbat Colony road to Street Waqas Shahani House mile 0/0-0/1+440 (0.30 km).* | *3.919* | *=* | *=* | *=* | *1.9595* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *12 Months* |
| *04* | *Constt: of road from Noor Mustafa Masjid Street to Ramzan Arain House mile 0/0-0/1+440 (0.30 km).* | *3.272* | *=* | *=* | *=* | *1.636* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *12 Months* |
| *05* | *Reconstruction of road from Nawabshah Sanghar and @ 60th Mile Naka to Gajrahwah road via Afazal Shah Town road mile 0/0-0/6 (1.20 km) (Wide 14).* | *7.635* | *=* | *=* | *=* | *3.8175* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *12 Months* |
| *06* | *Constt: of road from Desert Area road @ Mile 11/3 to New Village Manzoor Ahmed Arain mile 0/0-0/5 (1.00 km).* | *10.608* | *=* | *=* | *=* | *5.304* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *12 Months* |
| *07* | *Reconstruction of road from Old Jam Sahib Road to Dhobi Ghat to Connect A-I Town Kekepota Colony I/C 2 Nos Street road mile 0/0-0/6 (1.20 km).* | *9.319* | *=* | *=* | *=* | *46595* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *12 Months* |
| *08* | *Constt: of road from Noohja Dahri to village Ali Akber Otho, Bachal Otho & Village Lutuf Otho road mile 0/0-0/3+310 (0.69 K.M) Taluka Kazi Ahmed District Shaheed Benazir Abad.* | *7.500* | *=* | *=* | *=* | *7.500* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *12 Months* |
| *09* | *Constt: of road from Ghulam Muhammad Arain High School Near Village Chanda Singh to Village Waryam Dahesirai Road mile 0/0-0/3+265 (0.69 K.M) Taluka Kazi Ahmed Distirct Shaheed Benazir Abad.* | *7.500* | *=* | *=* | *=* | *7.500* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *12 Months* |
| *10* | *Recondg: / Repair of road from Old National Highway to village Khar road mile 0/0-0/3 (0.60 K.M) Taluka Kazi Ahmed District Shaheed Benazir Abad.* | *4.000* | *=* | *=* | *=* | *4.000* | *National Competitive Bidding* | *=* | *February 2017* | *March* | *12 Months* |
| *11* | *M/R of VIP Road from Sakrand road upto Varr road mile 0/0-0/5 I/C 1 No Street Sarfaraz Shah Colony 400 ft.* | *5.400* | *=* | *=* | *=* | *5.400* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *12* | *M/R Nawabshah Kazi Ahmed road Sheen Park / Zia Ul Hassan Lanjar Streets 2 Nos. I/C Passport Office to Connect Grid Station Road Via Aftab Ahmed Memon House and Shakeel House Street Mile 0/0-0/1+330. (In Reaches).* | *2.500* | *=* | *=* | *=* | *2.500* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *13* | *M/R to Bhangwar Colony Faiz Petrol Pump road Nawabshah Varr Road Via Airport Colony 0/0-1/2 (In Reaches) I/C Street of Changazi House Near I.S.I Office 160 ft.* | *3.000* | *=* | *=* | *=* | *3.000* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *14* | *M/R of road from Old Jam Sahib Road to Street Imtiaz Ahmed Wagan road mile 0/0-0/1+440.* | *0.500* | *=* | *=* | *=* | *0.500* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *15* | *Repair of Bridge Sim Nala Near Village Kalhori Deh 15 Nusrat UC Soomar Khan Jamali.* | *2.000* | *=* | *=* | *=* | *2.000* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *16* | *Repair of Culverts Various Roads of Taluka Daur.* | *5.400* | *=* | *=* | *=* | *5.400* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *17* | *M/r Bye Pass road to Ghariabad Via Moro Chowk Gorchani House & Infront Bunglow Via RHC (In Reaches).* | *2.500* | *=* | *=* | *=* | *2.500* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *18* | *M/R road from Nawabshah 60th Mile road @ Mile 7/0 to village Syed Noor Ahmed Shah Mile 0/0-1/2 (In Reaches).* | *1.600* | *=* | *=* | *=* | *1.600* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *19* | *M/R road from Nawabshah Jam Sahib road to Village New Gul Baig Mari mile 0/0-0/5 (In Reaches) I/C C.C Topping Jam Sahib Gupchani road to Village Mirza Najaf Baig mile 0/0-0/1+330 (In Reaches).* | *4.500* | *=* | *=* | *=* | *4.500* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *20* | *M/R road from Nawabshah Kazi Ahmed road to village Channesar Zardari Ehsan Zardari, & Mashooque Zardari mile 0/0-0/5+330 (In Reaches).* | *2.000* | *=* | *=* | *=* | *2.000* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *21* | *M/R road from Nawabshah 60th Mile road to Village Saeed Khan Mari mile 0/0-0/3 (In Reaches).* | *2.000* | *=* | *=* | *=* | *2.000* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *22* | *M/R road from 60th Mile Desert Area road to village Dost Ali Rind mile 0/0-1/4 (In Reaches).* | *2.000* | *=* | *=* | *=* | *2.000* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *23* | *M/R road from Shahzado Dahri to Khudadad Brohi Via Pervaizabad mile 0/0-5/0 (In Reaches).* | *0.700* | *=* | *=* | *=* | *0.700* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *24* | *M/R road from Shahzado Dahri to Dargah Aeto Shah road mile 0/0-0/6 (In Reaches).* | *1.800* | *=* | *=* | *=* | *1.800* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *25* | *M/R Chaper Khoso to Fazal Keerio & Village Usman Jamali road mile 0/0-1/0 (In Reaches).* | *1.800* | *=* | *=* | *=* | *1.800* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *26* | *M/R Pir Shah Ji Mori to Commando Center mile 0/0-3/0 (In Reaches).* | *1.000* | *=* | *=* | *=* | *1.000* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *27* | *M/R Mashakh Nasri road to Village Golo Dahri mile 0/0-1/0 (In Reaches).* | *4.500* | *=* | *=* | *=* | *4.500* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *28* | *M/R High School Mehar Ali Jamali to Jamia Masjid 2000 ft.* | *2.000* | *=* | *=* | *=* | *2.000* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *29* | *Repair of Various Culverts Taluka Nawabshah & Sakrand.* | *2.500* | *=* | *=* | *=* | *2.500* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *30* | *M/R Old National Highway to Khar road mile 0/0-2/4 (In Reaches).* | *2.500* | *=* | *=* | *=* | *2.500* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *31* | *M/R Kazi Ahmed Sawai Manjhoto road mile 2/0-2/5 (In Portion).* | *0.900* | *=* | *=* | *=* | *0.900* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *32* | *M/R Shahpur Jahania to Haji Umer Sethar mile 0/3-2/1 (In Portion) (I/C 2 Nos 10 ft Bridge).* | *3.000* | *=* | *=* | *=* | *3.000* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *33* | *M/R Nawabshah Kazi Ahmed Road along Raini Shakh Canal Shakh to village Chuttal Shah mile (In Reaches) Taluka Sakrand.* | *4.000* | *=* | *=* | *=* | *4.000* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *34* | *M/R to Various Streets in Nawabshah City.* | *3.000* | *=* | *=* | *=* | *3.000* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *35* | *M/R Link road to National Highway to Khair Muhammad Leghari Via Mir Khan Leghari mile 0/0-0/5 (In Reaches).* | *2.000* | *=* | *=* | *=* | *2.000* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *36* | *M/R Allah Rakhio Jamali to village Jamal Din Jamali Deh Halawalhar mile 0/0-0/3 (In Reaches).* | *1.300* | *=* | *=* | *=* | *1.300* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *37* | *M/R Nawabshah - Sarhari road to Hashim Keerio mile 0/0-0/5.* | *2.000* | *=* | *=* | *=* | *2.000* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *38* | *M/R of Nawabshah-Kazi Ahmed road to village Misri Chandio mile 0/0-0/5 upto village Hussain Unnar (In Reaches).* | *0.500* | *=* | *=* | *=* | *0.500* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |
| *39* | *Old National Highway Khar to Budo Dahri road (3 Rft Culvert)* | *1.000* | *=* | *=* | *=* | *1.000* | *National Competitive Bidding* | *=* | *February 2017* | *March 2017* | *06 Months* |

***EXECUTIVE ENGINEER***

***HIGHWAY DIVISION***

***SHAHEED BENAZIR ABAD***