## ROUGH WORK
1 | Excavation
(A) | CR L/w | 1x3x40.00x2.50x3.00 | 900
| CR s/w | 1x3x12.25x2.50x3.00 | 276
| Ver: sw | 1x2x4.25x2.50x50x3.00 | 64
(B) | CW | 1x1x260.00x2.00x2.00 | 1040
| M. G. Col: | 1x2x2.50x2.00 | 25
| Lav: L/w | 1x2x11.50x2.00 | 92
| Lav: S/w | 1x3x2.75x2.00x2.00 | 33
| M.B. Steps | 1x1x10.00x6.00x1.00 | 60
| Lav: steps | 1x1x6.00x4.00x1.00 | 24
| Path Gate to V | 1x2x30.00x1.00 | 60
| M.Gate Ramp | 1x2x5.00x1.00x1.00 | 10
| M. Gate Ramp | 1x1x11.00x1.00 | 11
| Septic Tank | 1x1x8.00x6.00x5.00 | 240
| Motor Room | 1x1x(5.75+3.75)x2.00x2.00 | 38
2 | c.c.
| C/R Lw | 1x3x40.00x2.50x0.75 | 225
| C/R S/w | 1x3x12.25x2.50x0.75 | 69
| Ver: s/w | 1x2x4.25x2.50x0.75 | 16
| C/Wall | 1x1x260.00x2.00x0.50 | 260
| M. Gate Col: | 1x2x2.50x2.50x0.50 | 6
| G. Lav: Path | 1x2x30.00x1.00x0.33 | 20
| Lav: L/w | 1x2x11.60x2.00x0.50 | 23
| Lav: S/w | 1x3x2.75x2.00x0.50 | 8
| M.G. Steps | 1x1x10.00x6.00x0.50 | 30
| Lav: Steps | 1x1x6.00x4.00x0.50 | 12
| Path Gate to V | 1x2x30.00x1.00x0.50 | 30
| M. Gate Ramp | 1x2x5.00x1.00x0.50 | 5
| M. Gate Ramp | 1x1x11.00x1.00x0.50 | 6
| S. Tank | 1x1x8.00x6.00x0.50 | 24
| CR U/Bed. | 1x2x17.63x13.63x0.42 | 202
| Ver: | 1x1x39.75x5.63x0.42 | 94
| Lav: | 1x2x3.63x3.63x0.42 | 11
| M.R | 1x1x3.63x3.63x0.42 | 6
| Path | 1x1x30.00x8.50x0.42 | 107
| Gate Ramp | 1x1x10.00x4.25x0.42 | 18
3 | Pacca found:
| CR Lw | 1x3x39.37x1.87x0.87 | 166
| Ver: Lw | 1x3x12.87x1.87x0.75 | 54
| Ver: Sw | 1x2x4.87x1.87x0.75 | 14
| Lav: Lw | 1x2x11.00x1.50x0.50 | 17
| Lav: Sw | 1x3x3.25x1.50x0.50 | 7
| MR Lw | 1x1x5.25x0.50 | 4
| MR Sw | 1x1x3.25x1.50x0.50 | 2
| M.B. Steps | 1x9.50x(6.00+4.00+3.00+1.00)x0.50 | 76
| Lav: steps | 1x6.00(4.0+3.0+2.0+1.0)x0.50 | 30
| path Toe wall | 1x2x30.00x0.75x1.50 | 68
| path Toe wall | 1x2x5.00x0.75x1.50+0.50/2 | 8
| path Toe wall | 1x1x11.00x0.75x0.50 | 4
Second Steps
| C/R Lw | 1x3x39.00x1.50x1.50x0.75 | 132
| CR Sw | 1x3x13.25x1.50x0.75 | 45
| Ver: Sw | 1x2x5.25x1.50x0.75 | 12
| Lav: Lw | 1x2x10.63x1.13x2.00 | 48
| Lav: sw | 1x3x3.63x1.13x2.00 | 25
| MR Lw | 1x1x4.87x1.13x2.00 | 11
| MR Sw | 1x1x3.63x1.13x2.00 | 2
| CW | 1x1x260x1.13x0.50 | 147
Third Steps
| C/R Lw | 1x3x38.63x1.13x2.00 | 262
| C/R Sw | 1x3x13.63x1.13x2.00 | 92
| Ver: Sw | 1x2x5.63x1.13x2.00 | 25
| S.Tank Lw | 1x2x8.00x0.75x5.50 | 66
| S.Tank Sw | 1x2x4.50x0.75x5.50 | 37
| C/Wall | 1x1x260.00x0.75x1.50 | 193
PLINTH BEAMS
| CR Lw | 1x3x38.63x1.13x0.75 | 98
| CR Sw | 1x3x13.63x1.13x0.75 | 35
| Ver: Sw | 1x2x5.63x1.13x0.75 | 10
| Lav: Lw | 1x2x10.63x1.13x0.50 | 12
| Lav: Sw | 1x3x3.63x1.13x0.50 | 6
| Plinth B. Cw | 1x1x260.00x0.75x0.50 | 98
| Lintel Door | 1x2x6.00x0.75x0.75 | 7
| CR Wind: | 1x6x5.00x0.75x0.75 | 17
| Lintel F/s | 1x1x38.25x0.75x1.00 | 29
| Lintel side. | 1x2x7.50x1.00 | 11
| Lintel Lav: Fs | 1x1x10.25x0.75x0.75 | 6
| M.G. Col: foot: | 1x2x2x2.00x2.50 | 20
| M.G. Col: foot: | 1x2x1.50x1.50x7.00 | 32
| CR T. Beam | 1x2x15.50x0.75x1.50 | 35
| CR Base plate | 2x2x2.50x0.75x0.50 | 4
| CR+Ver: Slab | 1x1x41.37x0.42 | 441
| Lav: Slab | 1x1x12.25x7.50x0.37 | 34
| M.R. Slab | 1x1x5.50x5.50x0.33 | 10
| S. Tank Slab | 1x1x8.00x6.00x0.50 | 24
8 | River pit
| C/R U/bed | 1x2x17.63x13.63x0.50 | 240
| Ver: U/bed | 1x1x36.75x5.63x0.50 | 103
| Path U/bed. | 1x1x30.00x8.50x0.75 | 191
9 | Pacca G.F
| CR Lw | 1x3x38.25x0.75x11.00 | 947
| CR Sw | 1x3x14.00x0.75x11.00 | 346
| Ver: Sw | 1x2x6.00x0.75x11.00 | 99
| Lav: L/w | 1x2x10.25x0.75x8.00 | 123
| Lav: sw | 1x3x4.00x0.75x8.00 | 72
| Motor Room Lw | 1x2x5.50x0.75x4.00 | 33
| M. Room Sw | 1x2x4.00x0.75x4.00 | 24
Deduction
| CR Door | 1x2x4.00x0.75x7.25 | 44
| Lav: Door | 1x2x2.50x0.75x7.25 | 27
| CR Window | 1x6x3.00x0.75x4.00 | 54
| Lintel Door | 1x2x6.00x0.75x0.75 | 7
| Lintel Window | 1x6x5.0x0.75x0.75 | 17
| Lintels | 1x1x38.25x0.75x1.00 | 29
| Lintels | 2x1x7.50x0.75x1.00 | 11
| Ver: Opening | 1x4x5.00x0.75x5.00 | 75
| Ver: Opening | 1x2x4.50x0.75x5.00 | 34
| Ver: Opening | 1x7.00x0.75x8.00 | 42
12 | Plaster 1:6.1/2
| CR i/s | 1x2x2x(18.00+14.00)x11.00 | 1408
| Ver: i/s | 1x1x2x(36.75+6.00)x11.00 | 941
| Ver: f/s | 1x1x38.25x11.00 | 421
| Ver: side. | 1x2x7.50x11.00 | 165
| M.B. Plinth | 1x2x(38.63+25.63)x2.00 | 257
| C/Wall i/s | 1x260.00x4.37 | 1136
| CW Pillars | 1x40x2x0.37x4.37 | 129
| CW Plinth | 1x2x260.00x1.75 | 910
| Lav: i/s | 1x2x2x(4.00+4.00)x8.00 | 256
| Lav: i/s | 1x1x10.25x8.00 | 82
| Lav: Plinth | 2x(10.63+5.60)x1.50 | 49
| M. Room Lw | 1x2x(4.00+4.00)x4.00 | 64
| M. Room Sw | 1x2x(5.50+5.50)x4.00 | 88
14 | Plaster 1:4 3/4
| Path | 1x2x30.00x1.50 | 90
| M.B. P/s Patta | 1x(38.25+14.75+14.75)x0.50 | 34
| S. Tank i/s | 1x2x(6.50+4.50)x5.00 | 110
| S. Tank o/s | 1x2x(8.00+6.00)x1.50 | 42
| CW Patta | 1x1x260.00x0.50 | 130
| CR Corner | 1x6x0.50x11.00 | 33
| CR W. Patta | 1x4x15.00x0.50 | 30
15 | Cement pointing
| CR b/s | 1x1x37.25x10.50 | 391
| CR side. | 1x2x14.25x10.50 | 299
| Lab: b/s | 1x1x10.25x8.00 | 82
| Lav: side. | 1x2x5.50x8.00 | 88
| C/Wall b/s | 1x1x260.00x3.50 | 910
DEDUCTION
| CR Window | 1x4x4.00x4.00 | 72
| Lav: Ventilator | 1x2x2.00x1.50 | 6
16 | F.C. wood
| CR Door | 1x2x3.75x6.75 | 51
| Lav: door | 1x2x2.25x6.75 | 30
| CR Window | 1x6x2x1.33x3.75 | 60
20 | Topping
(A) | 3" Thick
| CR | 1x2x18.00x14.00 | 504
| Ver: | 1x1x37.13x6.00 | 223
| D.W | 1x2x4.00x0.75 | 6
| Ver: Opening | 1x4x4.50x0.37 | 7
| M. G. Ramp | 1x1x11.00x5.00 | 55
(B) | 2" Thick
| C O/Roof | 1x1x41.37x25.37 | 1050
| Lav: O/Roof | 1x1x12.25x7.50 | 92
21 | Extra Labour
| CW Patta | 1x1x260.00 | 260
| CR Corner Pt | 1x6x11.00 | 66
| CR Window Pt | 1x4x12.00 | 48
| M.B. Patta | 1x(38.25+14.75+14.75) | 68
24 | Hala Tile
| Ver: F/s | 1x38.25x1.00 | 38
| Pillars | 1x10.00x11.50 | 115
| Gate Pillars | 1x2x1.00x7.00 | 14
| V W Sides. | 1x2x7.50x1.00 | 15
27 | W. Washing
| CR | 1x2x18.00x14.00 | 504
| CR Beams | 1x2x2x14.00x1.50 | 84
| CR Chajja | 1x2x(42.37+23.37)x1.50 | 197
| Ver: Ceiling | 1x1x37.13x6.00 | 223
| Lav: Ceiling | 1x2x4.00x4.00 | 32
| Lav: Chajja | 1x2x(12.25+5.50)x1.00 | 36
28 | Painting
| CR Door | 1x2x2x4.00x7.00 | 112
| CR Window | 1x6x2x3.00x4.00 | 144
| Lav: Door | 1x2x2x2.50x7.00 | 70
| Lav: Ventilator | 1x2x2x2.00x1.50 | 12

## SCHEDULE B (A.D. NIMRIO
NAME OF WORK:- |  | ADP # 72/27 - CONSTRUCTION OF BUILDING FOR EXISTING SHELTERLESS PRIMARY SCHOOL (2 ROOMED) IN TALUKA HYDERABAD AT
S.NO. | DESCRIPTION |  | QUANTITY |  | RATE |  | UNIT | AMOUNT
1 | Excavation in foundation of building, bridges and other structures i/c degbelling, dressing refilling around structure with excavated earth watering and ramming lead upto five feet (b) in ordinary soil (S.I. # 18/P-4)
|  |  | = | 3209 |  | 1306/80 | %0Cft | Rs. | 4194
2 | Cement concrete brick or stone ballast 1 1/2" to 2" guage ratio 1:5:10 (S.I. # 04/P-17).
|  |  | = | 1737 |  | 3213/95 | %Cft | Rs. | 55826
3 | Pacca brick work in foundation and plinth in cement sand and mortor ratio 1:6. (S.I. # 04/P-24).
|  |  | = | 2556 |  | 3865/15 | %Cft | Rs. | 98793
4 | R.C.C work i/c all labour and material except the cost of steel reinforcement and its labour for bending and binding which will be paid seperately. This rate also includes all kinds of forms moulds lifting shuttering curring rendering and finishing the exposed surface (i/c screeening and washing of shingle (a) R.C work in roof slab beams, columns, rafts lintels and other structural members laid in situ or precast in position complete in all respect ratio 1:2:4 (S.I. # 06-a/P-18).
|  |  | = | 1086 |  | 114/- | P.Sft | Rs. | 123804
5 | Fabrication of mild steel reinforcement for cement concrete i/c cutting bending laying in position, making joints and fastenings i/c cost of binding wire (also removal of rust from bars)(S.I.# 7(ii)/P-20).
A | Tor Bars |  | = | 43.63. |  | 2772/55 | P.Cwt | Rs. | 120966
B | Mild Steel |  | = | 7.27. |  | 2651/55 | P.Cwt | Rs. | 19277
6 | Filling watering and ramming earth in floors with surplus earth from foundation lead upto one chain and lift upto five feet. (S.I. # 21/P-4).
|  |  | = | 994 |  | 641/30 | %0Cft | Rs. | 637
7 | Filling watering and ramming earth under floor with new earth (Excavated from outside) lead upto one chain and lift upto five feet. (S.I. #22/P-5).
|  |  | = | 5610 |  | 1488/30 | %0Cft | Rs. | 8349
8 | Pacca brick work in Ground Floor in i/c stricking of joints cement sand mortar 1:6 (S.I. # 05(i)e/P-25).
|  |  | = | 1426 |  | 4246/30 | %Cft | Rs. | 62718
9 | Pacca brick work in other than building i/c stricking of joints upto 20 feet height in cement snd mortar ratio 1:6. (S.I.#07/P-23).
|  |  | = | 530 |  | 4089/- | %Cft | Rs. | 21671
10 | Providing and fixing G.I. frames / chowkhats of a size 7" x 2" or 4 1/2" x 3" for a door using 20 guage G.I. sheet including welded hanges and fixing at site with necessary hold fasts. Filling with cement sand slurry of ratio 1:6 and repairing the jambs. The cost also includes all carriage tools and plants used in making and fixing. (S.I. # 29/P-98).
(A) | Door Frame |  | = | 71 |  | 113/37 | P.Sft | Rs. | 8049
(B ) | Wind: Frame |  | = | 122 |  | 122/17 | P.Sft | Rs. | 14905
11 | Cement plaster 1:6 upto 20' height (b) 1/2" thick. (S.I. # 13(b)/P-58).
|  |  | = | 8155 |  | 531/41 | %Sft | Rs. | 43336
12 | Cement plaster 1:4 upto 20' height (a) 3/8" thick. (S.I. # 11(a)/P-58).
|  |  | = | 8085 |  | 536/14 | %Sft | Rs. | 43159
13 | Cement pointing struck joints on walls (S.I. # 19/P-54).
|  |  | = | 2166 |  | 563/70 | %Sft | Rs. | 12210
14 | Cement plaster 1:4 upto 20' height 3/4" thick. (S.I. # 13/P-54).
|  |  | = | 325 |  | 779/96 | %Sft | Rs. | 2535
15 | First class deodar wood wrought joinery in doors and windows etc: fixed in position i/c chowkhats hold fasts hinges iron tower bolts, chocks cleats handles and cords with hooks etc. Deodar panelled or panelled and glazed or fully glazed (b) 1 3/4" thick.
|  |  | = | 143 |  | 228/38 | P.Sft | Rs. | 32658
16 | Supplying and fixing in position Iron steel grill of 3/4" x 1/4" size flat iron of approved design i/c painting three coats etc. Complete (Wt not to be less than 3 - 7 lbs sq; ft of finishing grill. (S.I. # 26/P-97).
|  |  | = | 59 |  | 115/47 | P.Sft | Rs. | 7275
17 | Making notice board made with cement and sand. (S.I. #
|  |  | = | 64 |  | 28/86 | P.Sft | Rs. | 1847
18 | M/F Steel grated door with 1/16" thick sheeting i/c angle iron frame 2"x2"x3/8" & 3/4" square bars at 4" centre to centre. (S.I. # 28/P-91).
|  |  | = | 40 |  | 385/76 | P.Sft | Rs. | 15430
19 | Providing and laying topping cement concrete (1:2:4) i/c surface finishing and divided into panelles. (S.I. # 6/P-47).
(A) | 3" Thick |  | = | 1355 |  | 1820/23 | %Sft | Rs. | 24664
(B) | 2" Thick |  | = | 549 |  | 1396/67 | %Sft | Rs. | 7668
© | 1.1/2 Thick |  | = | 1325 |  | 1115/18 | %Sft | Rs. | 14776
20 | Extra labour rate for making cement plaster pattas/bend around straight or curved openings and around the edges of roof slab, the width not less than 6" with fine finishing as directed by Engineer Incharge. (S.I. # 35/P-56)
|  |  | = | 650 |  | 11/25. | P.Rft | Rs. | 7313
21 | Laying floor of approved with glazed tile 1/4" thick in white cement 1:2 over 3/4" thick cement mortar 1:2 complete. (S.I.# 24/P-48)
|  |  | = | 32 |  | 10443/85 | %Sft | Rs. | 3342
22 | White glazed tile 1/4" thick dado jointed in white cement and laid over 1:2 cement sand mortar 3/4" thick including finishing. (S.I.# 38/P-49)
|  | Net Qty: 128 ( - ) 16 | = | 112 |  | 10700/69 | %Sft | Rs. | 11985
23 | Providing and laying HALA or pattern tiles glazed 6" x 6" x 1/4" on floor or wall facing in required colour and pattern fo STILE specififcation jointed in white cement and pigment over a base of 1:2 grey cement mortar 3/4" thick including washing and filling of joints with slurry of white cement and pigment in desired shape with finishing cleaning and cost of wax polish etc. complete including cutting tiles to proper profile. (S.I. # 61/P-53).
|  |  | = | 254 |  | 17091/69 | %Sft | Rs. | 43413
24 | Primary coat of chalk under distemper (S.I. # 23/Page No. 55).
|  |  | = | 8050 |  | 58/85 | %Sft | Rs. | 4737
25 | Distempering three coats (S.I. # 24/Page No. 55).
|  |  | = | 8050 |  | 263/51 | %Sft | Rs. | 21213
26 | White washing three coats. (S.I. # 26/P-59).
|  |  | = | 1292 |  | 115/18 | %Sft | Rs. | 1488
27 | Painting new surface, preparing surface and painting of doors and windows any type i/c edges three coats. (S.I.#
|  |  | = | 338 |  | 978/95 | %Sft | Rs. | 3309
28 | Painting new surfaces, preparing surface and painting guard bars, gates of iron bars, gratings, railings i/c standard braces etc and similar open work. (S.I.# 5-d/P-68).
|  |  | = | 80 |  | 584/54 | %Sft | Rs. | 468
29 | Two coat of bitumen laid hot using 34 lbs for %sft over roof and blinded with sand at one Cft per% Sft. (S.I.# 13/P- ).
|  |  | = | 1325 |  | 431/21 | %Sft | Rs. | 5714
[8 empty] | Rs. | 847729
SCHEDULE "B"

## ESTIMATE ADP 72-27 (2)
NAME OF WORK:- |  | (ADP-985/1124) UP-GRADATION OF PRIMARY SCHOOL TO MIDDLE SCHOOL IN SINDH (20-UNITS) (2005-06) PROGRAMME @ GBPS PUBAN SHARIF UC MOOLAN TALUKA HYDERABAD.
S.NO. | DESCRIPTION |  | QUANTITY |  | RATE |  | UNIT | AMOUNT
1 | Excavation in forundation of building, bridges and other structures i/c degbelling, dressing refilling around structure with excavated earth watering and ramming lead upto five feet (b) in ordinary soil (S.I. # 18/P-4)
A. | Main Bldg. | 1x64.50x50.12x4.0 | = | 12931
B. | C/Wall. | 1x400.0x2.0x2.0 | = | 1600
| Gate Piller. | 1x2x2.0x2.02.0 | = | 16
| P.P. | 1x2x(56.50+42.12)x1.0x1.0 | = | 197
| Path. | 1x2x40.0x1.0x1.0 | = | 80
|  |  | = | 14824 | @ | 1306.8 | %0Cft | Rs. | 19372.0032
2 | Cement concrete brick or stone ballast 1 1/2" to 2" guage ratio 1:5:10 (S.I. # 04/P-17).
| M. Bldg. | 1x64.50x50.12x0.75 | = | 2425
| C/Wall | 1x400.0x2.0x0.50 | = | 400
| Piller | 1x2x2.0x2.0x0.50 | = | 4
|  | 1x2x19.63x15.63x0.50 | = | 307
| U/Bed C/R | 1x17.63x13.63x0.50 | = | 120
| Office | 1x9.63x13.63x0.50 | = | 66
| Lav: | 1x8.12x13.63x0.50 | = | 55
| Ver: | 1x38.75x5.63x0.50 |  | 110
| Hall | 1x20.87x13.63x0.50 |  | 142
| Inter | 1x11.63x16.0x0.50 |  | 93
| P.P. | 1x2x(56.50+42.12)x2.25x0.50 |  | 221
| Path. | 1x40.0x12.0x0.50 |  | 240
|  | 1x2x(56.50+42.12)x1.0x0.33 |  | 65
|  | 2x40.0x1.0x0.33 |  | 27
|  |  | = | 4275 | @ | 3213.95 | %Cft | Rs. | 137396.3625
3 | Pacca brick work in foundation and plinth in cement sand and mortor ratio 1:6. (S.I. # 04/P-24).
| Main Bldg. | 1x3x56.50x1.13x3.75 | = | 718
| D/Wall L/W | 1x42.0x1.13x3.75 | = | 178
| S/w | 3X20.87X1.13X3.75 | = | 265
| Gen: Lav: S/W | 1x3x13.63x1.13x3.75 | = | 173
| S/W | 1x8.42x1.13x3.50 | = | 33
| C/R S/W | 1x4x15.63x1.13x3.50 |  | 247
| C/Wall | 1x400x1.50x0.75 | = | 450
| " " | 1x400x1.13x2.0 | = | 904
| P.P. | 1x(100+97.0)x0.75x2.0 | = | 296
| Path. | 1x2x40.0x0.75x2.0 |  | 120
|  |  | = | 3384 | @ | 3865.15 | %Cft | Rs. | 130796.676
4 | R.C.C work i/c all labour and material except the cost of steel reinforrcement and its labour forr bending and binding which will be paid seperately. This rate also includes all kinds of forrms moulds lifting shuttering curring rendering and finishing the exposed surface (i/c screeening and washing of shingle (a) R.C work in roof slab beams, columns, rafts lintels and other structural members laid in situ or precast in position complete in all respect ratio 1:2:4 (S.I. # 06-a/P-18).
| Footing | 1x64.0x50.0x1.50 | = | 4800
| Padestal. | 1x22x1.0x1.75x3.75 | = | 144
| P.beam L/W | 1x3x56.50x1.13x0.75 | = | 144
| S/W | 1x3x20.87x1.13x0.75 | = | 78
| C/R S/W | 1x3x13.63x1.13x0.75 | = | 34
| Gen: Lav: S/W. | 1x8.42x1.13x0.75 | = | 7
| D/Wall | 1x42.0x1.13x0.75 | = | 36
| C/R S/W | 1x4x15.63x1.13x0.75 | = | 53
| C/R Lintel | 1x56.12x0.75x0.75 | = | 32
|  | 1x42.0x0.75x0.75 | = | 24
| S/W | 1x(8.25+21.25)0.75x0.75 | = | 16
| F/S C/R | 1x2x22.25x0.75x0.75 | = | 25
|  | 1x2x6.0x0.75x.75 | = | 7
| Inter | 1x23.0x0.75x0.75 | = | 13
| Tie beam | 2x(56.12+41.75)x0.75x1.50 | = | 220
| " " | 1x42.0x0.75x1.50 | = | 47
| " " | 1x56.12x0.75x1.50 |  | 63
| " " | 1x2x13.63x0.75x1.50 |  | 31
| " " | 1x21.25x0.75x1.50 |  | 24
| C/R S/W | 1x2x16.0x0.75x1.50 | = | 36
| M. Bldg. Col: | 1x2x0.75x1.50x9.75 | = | 241
| Tower Piller | 1x4x0.75x1.50x7.25 | = | 33
| Tie beam | 1x2x(11.0+6.0)x0.75x1.0 | = | 26
| Centre beam | 1x2x14.0x0.75x1.50 | = | 32
| " " | 1x2x16.0x0.75x1.50 | = | 36
| Tower slab. | 1x13.0x10.50x0.33 | = | 45
| M. Bldg. Slab. | 1x59.12x44.75x0.42 | = | 111
| Lending. | 1x6.0x3.0x0.50 | = | 9
| Steps. | 1x2x10x1/2x3.0x1.0x0.50 | = | 15
|  |  | = | 6382
Deduction.
| Tower | 1x11.0x6.0x0.42 |  | 28
|  | 2x12.0x0.75x1.50 |  | 27
| Duck | 1x2x10.0x6.0x1.50 |  | 180
| " " | 1x12.0x5.0x1.50 |  | 90
| " " | 1x10.0x5.0x1.50 |  | 75
| " " | 1x5.0x5.0x1.50 |  | 38
438
|  | Net: Qnty: 6382.0 (-) 438.0 |  | 5944 | @ | 114 | P.Cft | Rs. | 677616
5 | Fabrication of mild steel reinforcement for cement concrete i/c cutting bending laying in position, making joints and fastenings i/c cost of binding wire (also removal of rust from bars)(S.I.# 7(ii)/P-20).
| Tor Bars | Qnty: RCC. 5944.0 x 5.00 / 112 | = | 265.35 | @ | 2772.55 | P.cwt | Rs. | 735696.1425
| Mild Steel | Qnty: RCC. 5944.0x0.50/112 |  | 26.53 | @ | 2651.55 | P.cwt | Rs. | 70345.6215
=
6 | Supplying of clean screened (River or Pit) sand with five chain including removal Top crust of earth or over burden and rovalty to the Government or cost to the Private owner (S.I.No:36/P-7).
| C/R | 1x2x19.63x15.63x2.50 |  | 1534
| Hall | 1x20.87x13.63x2.50 |  | 711
| C/R | 1x17.63x13.63x2.50 |  | 601
| Office | 1x9.63x13.63x2.50 |  | 328
| Lav: | 1x13.63x8.42x2.50 |  | 287
| Ver: | 1x39.87x5.63x2.50 |  | 561
| Inter. | 1x12.0x15.63x2.50 |  | 469
|  |  |  | 4491 | @ | 176.3 | %Cft | Rs. | 7917.633
7 | Pacca brick work in Ground Floor in i/c stricking of joints cement sand mortar 1:6 (S.I. # 05(i)e/P-25).
| C/R | 1x1x14.0x0.75x9.75 | = | 102
| Hall | 1x4x9.87x0.75x9.75 | = | 289
| C/R+Office | 1x3x14.0x0.75x9.75 | = | 307
| " " L/W | 1x4x8.25x0.75x9.75 | = | 241
| Office | 1x2x10.0x0.75 | = | 146
| Lav: | 1x2x8.42x0.75x9.75 | = | 123
| C/R L/W | 1x4x2x9.25x0.75x9.75 | = | 541
| Ver: S/W. | 1x6.0x0.75x9.75 | = | 44
| Tower | 1x2x(11.0+6.0)x0.75x7.25 | = | 184
|  |  | = | 1977
DEDUCTION
| CR Door | 1x4x4.0x0.75x7.25 | = | 87
| CR Door | 1x3x3.0x0.75x7.25 | = | 49
| Window | 1x15x3.0x0.75x4.0 | = | 135
| Vent: | 1x3x2.50x0.75x7.25 | = | 41
|  | 1x3x2.0x0.75x1.50 | = | 7
319
|  | Net Qty: 1977.0 ( - ) 319.0 | = | 1658 | @ | 4246.3 | %Cft | Rs. | 70403.654
8 | Pacca brick work in other than building I/c stricking of joints upto 20' feet height in cement and mortor ratio 1:6 (S.I.No:07/P-23)
| C/Wall | 1x400x0.37x4.0 |  | 592
| Piller | 1x90x0.75x0.37x4.0 |  | 100
|  |  |  | 692 | @ | 4089 | %Cft | Rs. | 28295.88
9 | Cement plaster 1:6 upto 20' height (b) 1/2" thick. (S.I. # 13(b)/P-58).
| C/R | 2x2x(20.0+16.0)x11.25 | = | 1620
| Hall | 1x2x(21.25+14.0)x11.25 | = | 793
| C/R | 1x2x(18.0+14.0)x11.25 | = | 720
| Office | 1x2x(10.0+14.0)x11.25 | = | 540
| Gen: Lav: | 1x2x(14.0+8.42)x11.25 |  | 504
| Mid wall | 1x2x(8.42+9.0+4.0)x11.25 |  | 482
| Ver: | 1x2x(39.87+6.0)x11.25 |  | 1032
| Inter side | 1x(12.0+16.75+16.75)x11.25 |  | 511
| Tower I/S | 1x2x(11.0+6.0)x8.25 |  | 280
| O/S | 1x2x(12.50+7.50)x8.25 |  | 330
| M.Bldg. Plinth | 1x2x(56.50+42.12)x2.75 |  | 542
| C/Wall | 1x400x4.37 |  | 1748
| Piller side | 1x90x2x0.37x4.37 |  | 291
| C/W Plinth | 1x2x400x2.0 |  | 1600
|  |  | = | 10993 | @ | 531.41 | %Sft | Rs. | 58417.9013
10 | Cement plaster 1:4 upto 20' height (b) 3/8"" thick. (S.I. # 13(b)/P-58).
|  | Qty: same as item # 9. | = | 10993
Deduction.
| N. bar | 1x4x8.0x4.0 |  | 128
| Gen: Lav: wall. | 1x2x(8.42+4.0)x2.0 |  | 50
|  | 1x2x2x(4.0+4.0)x2.0 |  | 60
|  | 1x2x(4.75+3.0)x2.0 |  | 31
209
|  | Net: Qnty: 10993.0 (-) 209.0 |  | 10724 | @ | 536.14 | %Sft | Rs. | 57495.6536
11 | Cement plaster 1:4 upto 20' height (b) 3/4"" thick. (S.I. # 13(b)/P-58).
| M. Bldg. | 2x56.12x0.50 | = | 56
| " " | 1x2x42.0x0.50 | = | 42
| Corner | 1x4x2x0.25x11.25 |  | 45
| Window | 1x13x2x4.50x0.50 |  | 59
|  | 1x13x3.0x0.50 |  | 20
|  | 1x400x0.50 |  | 200
|  |  |  | 422 | @ | 779.96 | %Sft | Rs. | 3291.4312
12 | Extra labour rate for making cement plaster pattas/bend around straight or curved openings and around the edges of roof slab, the width not less than 6" with fine finishing as directed by Engineer Incharge. (S.I. # 35/P-56)
|  | Qnty: same item No: (10) 422.0/0.50 |  | 844 | @ | 11.25 | P.Sft | Rs. | 9495
13 | Cement pointing struck joints on walls (S.I. # 19/P-54).
| M. Bldg. I/S | 1x55.12x11.75 | = | 648
| Side | 1x2x41.0x11.75 |  | 963
|  | 1x2x21.75x11.75 |  | 499
| C/Wall. | 1x400x3.50 |  | 1400
3510
Deduction.
| Window | 1x13x4.50x4.50 |  | 263
| Lintel | 1x2x(56.12+42)x0.75 |  | 147
|  |  | = | 410
|  | Net Qnty: 3510.0 (-) 410.0 |  | 3100 | @ | 645.37 | %Sft | Rs. | 20006.47
14 | Providing and fixing G.I. frames / chowkhats of a size 7" x 2" or 4 1/2" x 3" for a door using 20 guage G.I. sheet including welded hanges and fixing at site with necessary hold fasts. Filling with cement sand slurry of ratio 1:6 and repairing the jambs. The cost also includes all carriage tools and plants used in making and fixing. (S.I. # 29/P-98).
A | Doors
| Doors | 1x10x2x7.0 | = | 140
| Doors | 1x4x3.75 | = | 15
|  | 1x3x2.75 |  | 8
|  | 1x3x2.25 |  | 7
|  |  | = | 170 | @ | 113.37 | P.Rft | Rs. | 19272.9
B | Windows
| Window. | 1x15x2x3.0 |  | 90
| Window | 1x15x3x3.67 |  | 165
| Vent: | 1x3x2x2.0 |  | 12
|  | 1x3x2x1.25 |  | 8
|  |  | = | 275 | @ | 122.17 | P.Rft | Rs. | 33596.75
=
15 | Supplying and fixing in position Iron steel grill of 3/4" x 3/4" size flat iron of approved design i/c painting three coats etc. Complete (Wt not to be less than 3 - 7 lbs sq; ft of finishing grill. (S.I. # 26/P-97).
| Ver: opening. | 1x2x3.0x5.0 | = | 30
|  | 1x5.0x8.0 |  | 40
|  | 1x15x2x1.25x3.67 |  | 138
|  | 1x3x1.75x1.25 |  | 7
| Ver: side open. | 1x6.0x5.0 |  | 30
|  |  |  | 245 | @ | 115.47 | P.Sft | Rs. | 28290.15
16 | First class deodar wood wrought joinery in doors and windows etc: fixed in position i/c chowkhats hold fasts hinges iron tower bolts, chocks cleats handles and cords with hooks etc. Deodar panelled or panelled and glazed or fully glazed (b) 1 3/4" thick. (S.I.# 07(b)/P-65).
| Door. | 1x4x3.75x6.83 | = | 102
| Door. | 1x3x2.75x6.83 |  | 56
| Door. | 1x3x2.25x6.83 |  | 46
| Window. | 1x15x2x1.29x3.75 |  | 145
| Vent: | 1x3x1.75x1.25 |  | 7
|  |  | = | 356 | @ | 228.38 | P.Sft | Rs. | 81303.28
17 | Providing and fixing 3/8" thick marble tiles of approved quality and colour shade size 8"x4/6"x3/8" in dado skarting and facing removal / tucking of existing plaster surface etc:. Over 1/2" thick base of cement mortar 1:3 setting mortor base including filling the joints and washing the tiles with white cement slurry, current, finishing cleaning and polishing etc. complete. (ii) forr old works (S.I.# 68(ii)/P-55)
| Hall | 1x21.25x14.0 | = | 298
|  | 1x2x20.0x16.0 |  | 640
|  | 1x18.0x14.0 |  | 252
|  | 1x10.0x14.0 |  | 140
| Ver: | 1x38.75x6.0 |  | 233
| Inter Lobby | 1x12.0x17.0 |  | 204
| Dada | 1x2x(21.25+14.0)x0.50 |  | 350
|  | 1x2x2x(20.0+16.0)x0.50 |  | 640
|  | 1x2x(18.0+14.0)x0.50 |  | 32
|  | 1x2x(10.0+14.0)x0.50 |  | 24
|  | 1x2x(38.75+6.0)x0.50 |  | 45
| Lobby. | 1x2x(12.0+17.0)x0.50 |  | 29
|  |  | = | 2887 | @ | 74.65 | P.Sft | Rs. | 215514.55
18 | Providing and laying tiles glazed 6"x6"x1/4" on floor or wall facing in required colour and pattern of STILE specification jointed in white cement and pigment over a base of 1:2 grey cement mortor 3/4" thick including washing and filling of joints with slurry of white cement and pigment in desired shape with finishing, cleaning and cost of wax polish etc. complete including cutting tiles to proper profile.(S.I.No:60/P-52).
| H.M. Lav: | 1x2x(8.42+5.0)x2.0 |  | 54
| G. Lav: | 1x2x2x(4.0+4.0)x2.0 |  | 64
| Passage. | 1x2x(8.75+3.0)x2.0 |  | 94
| H.M. Lav: | 1x8.42x5.0 |  | 42
| G. Lav: | `1x2x4.0x4.0 |  | 32
| Passage. | 1x8.75x3.0 |  | 26
312
Deduction.
| Door | 1x3x2.50x2.0 |  | 15
| Door | 1x3x.0x4.0 |  | 6
21
|  | Net Qnty: 312.0 (-) 21.0 |  | 291 | @ | 13663.35 | %Cft | Rs. | 39760.3485
19 | Making notice board made with cement and sand (S.I.No: /P- ).
| C/R | 1x4x8.0x4.0 |  | 128 | @ | 28.86 | P.Sft | Rs. | 3694.08
20 | Providing and laying topping cement concrete (1:2:4) i/c surface finishing and divided into panelles. (S.I. # 6/P-47).
1-1/2" Thick.
| C/R+Ver: O/R | 1x59.12x44.75 | = | 2646 | @ | 1115.18 | %Sft | Rs. | 29507.6628
3" Thick.
| M. Bldg. O/S | 1x2x(62.50+42.37)x3.0 |  | 629
| Path. |  |  | 540
|  |  |  | 1169 | @ | 1820 | %Sft | Rs. | 21275.8
21 | Providing and laying HALA or pattern tiles glazed 6" x 6" x 3/4" on floor or wall facing in required colour and pattern for STILE specififcation jointed in white cement and pigment over a base of 1:2 grey cement mortar 3/4" thick including washing and filling of joints with slurry of white cement and pigment in desired shape with finishing cleaning and cost of wax polish etc. complete including cutting tiles to proper profile. (S.I. # 61/P-53).
| Ver: F/S | 1x12.0x3.0 |  | 36
| Side | 1x2x2x(16.0+11.25)x1.0 |  | 109
| Stand | 1x2x4.0x4.0 |  | 32
| Gater Piller. | 1x2x6.0x6.0 |  | 72
|  |  | = | 249 | @ | 17091.67 | %Sft | Rs. | 42558.2583
22 | M/Fixing Steel grated door with 1/16" thick sheeting I/c angle iron frame 2"x2"x3/8" & 3/4" square bars at 4" centre to centre (S.I.No:28/P-91).
| Main Bldg. | 1x10.0x6.0 |  | 60 | @ | 385.76 | P.Sft | Rs. | 23145.6
23 | Two coat of bitumen laid hot using 34 lbs forr %sft over roof and blinded with sand at one Cft per% Sft. (S.I.# 13/P- ).
| O/Roof | 1x59.12x41.75 | = | 2468 | @ | 431.25 | %Sft | Rs. | 10643.25
24 | White washing three coats. (S.I. # 29/Page No. 55).
| Celing | 1x21.25x14.0 | = | 298
| Ceiling | 1x2x20.0x16.0 | = | 640
| C/R | 1x18.0x14.0 | = | 252
| Office | 1x10.0x14.0 | = | 140
| Ver: | 1x38.75x6.0 | = | 233
| Chajja. | 2x(59.12+41.75)x1.75 |  | 353
|  |  |  | 1916 | @ | 115.18 | %Sft | Rs. | 2206.8488
25 | Primary coat of chalk under distempering. (S.I.# 23/P-55).
|  | Qty: same as item # 10. | = | 10724
|  | Qnty: same as item No: 11. |  | 422
|  |  |  | 11146 | @ | 58.85 | %Sft | Rs. | 6559.421
26 | Distempering three coats. (S.I.# 24/P-59).
|  | Qty: same as item #25 | = | 11146 | @ | 263.51 | %Sft | Rs. | 29370.8246
27 | Painting new surface, preparing surface and painting of doors and windows any type i/c edges three coats. (S.I.# 66/P-97).
| C/R Door | 1x4x2x4.0x7.0 |  | 224
| Door | 1x3x2x3.0x7.0 |  | 126
| Door | 1x3x2x2.50x7.0 |  | 105
| Window | 1x15x2x3.0x4.0 | = | 360
| Vent: | 1x3x2x2x1.50 | = | 18
|  |  | = | 833 | @ | 978.95 | %Sft | Rs. | 8154.6535
28 | Painting new surfaces, preparing surface and painting guard bars, gates of iron bars, gratings, railing I/c standard braces etc. and similar open work (S.I.No:5-d/P-68).
| Main Gate. | 1x10.0x2x6.0 |  | 120 | @ | 584.54 | %Sft | Rs. | 701.448
[6 empty] | Total. |  | Rs. | 2621400.8063
| SUB-ENGINEER |  |  |  |  | DEPUTY DISTRICT OFFICER
EDUCATION WORKS (W&S)
TALUKA HYDERABAD
ESTIMATE

## Jaro Babar
NAME OF WORK:- |  | (ADP-152/156) ADDITIONAL OF CLASS ROOMS IN EXISTING PRIMARY SCHOOL IN DISTRICT HYDERABAD (18-UNITS) (2011-12) PROGRAMME UNDER BLOCK ALLOCATION @ GGPS JARO BABAR (1-C/R), TALUKA HYDERABAD (BALANCE WORK).
S.NO. | DESCRIPTION |  |  | RATE |  | UNIT | AMOUNT
PART------A------
1 | Excavation in forundation of building, bridges and other structures i/c degbelling, dressing refilling around structure with excavated earth watering and ramming lead upto five feet (b) in ordinary soil (S.I. # 18/P-4)
|  |  | 26 | @ | 3176.25 | %0Cft | Rs. | 82.5825
2 | Cement concrete brick or stone ballast 1 1/2" to 2" guage ratio 1:4:8 (S.I. # 04/P-17).
|  |  | 200 | @ | 9416.28 | %Cft. | Rs. | 18832.56
3 | Pacca brick work in foundation and plinth in cement sand and mortor ratio 1:6. (S.I. # 04/P-24).
|  |  | 21 | @ | 11948.36 | %Cft | Rs. | 2509.1556
4 | R.C.C work i/c all labour and material except the cost of steel reinforrcement and its labour forr bending and binding which will be paid seperately. This rate also includes all kinds of forrms moulds lifting shuttering curring rendering and finishing the exposed surface (i/c screeening and washing of shingle (a) R.C work in roof slab beams, columns, rafts lintels and other structural members laid in situ or precast in position complete in all respect ratio 1:2:4 (S.I. # 06-a/P-18).
|  |  | 537 | @ | 337 | P.Cft | Rs. | 180969
5 | Pacca brick work in Ground Floor in i/c stricking of joints cement sand mortar 1:6 (S.I. # 05(i)e/P-25).
|  |  | 424 | @ | 12674.36 | %Cft | Rs. | 53739.2864
6 | Cement plaster 1:6 upto 20' height (b) 1/2" thick. (S.I. # 13(b)/P-58).
|  |  | 2091 | @ | 2206.6 | %Sft | Rs. | 46140.006
7 | Cement plaster 1:4 upto 20' height (b) 3/8" thick. (S.I. # 13(b)/P-58).
|  |  | 2059 | @ | 2197.52 | %Sft | Rs. | 45246.9368
8 | Cement concrete plain including placing compacting, finishing and curring, complete (including screening and washing at stone aggregate without shuttering, ratio 1:3:6. (S.I. # 5-h'P-17).
|  |  | 80 | @ | 12595 | %Cft | Rs. | 10076
9 | Cement pointing struck joints on walls (S.I.No:19/P-54).
|  |  | 428 | @ | 1287.44 | %Sft | Rs. | 5510.2432
10 | Providing and fixing G.I. frames / chowkhats of a size 7" x 2" or 4 1/2" x 3" for a door using 20 guage G.I. sheet including welded hanges and fixing at site with necessary hold fasts. Filling with cement sand slurry of ratio 1:6 and repairing the jambs. The cost also includes all carriage tools and plants used in making and fixing. (S.I. # 29/P-98).
(A) | DOOR FRAMES. |  | 19 | @ | 240.5 | P.Rft | Rs. | 4569.5
(B) | WINDOW FRAMES. |  | 71 | @ | 228.9 | P.Rft | Rs. | 16251.9
11 | Making notice board made with cement and sand. (S.I. # 01/P-54).
|  |  | 32 | @ | 58.11 | P.Sft | Rs. | 1859.52
12 | First class deodar wood wrought joinery in doors and windows etc: fixed in position i/c chowkhats hold fasts hinges iron tower bolts, chocks cleats handles and cords with hooks etc. Deodar panelled or panelled and glazed or fully glazed (b) 1 3/4" thick. (S.I.# 07(b)/P-65).
|  |  | 67 | @ | 902.93 | P.Sft | Rs. | 60496.31
13 | Providing and laying topping cement concrete (1:2:4) i/c surface finishing and divided into panelles. (S.I. # 6/P-47).
| 2" Thick. |  | 692 | @ | 3275.52 | %Sft | Rs. | 22666.5984
14 | White washing three coats (S.I.No:29 /P-55 ).
|  |  | 884 | @ | 829.95 | %Sft | Rs. | 7336.758
15 | Primary coat of chalk under distemper (S.I.No:23/P-5).
|  |  | 2059 | @ | 442.75 | %Sft | Rs. | 9116.2225
16 | Distempering three coats (S.I.No:24/P-59).
|  |  | 2059 | @ | 1079.65 | %Sft | Rs. | 22229.9935
17 | Paianting NEW surface painting of Door and Window any type i/c edge (3-coats) (S.I.No:66/P-97).
|  |  | 164 | @ | 2116.41 | %Sft | Rs. | 3470.9124
[5 empty] | TOTAL. |  | Rs. | 511103.4853
PART------B------
1 | Providing and fixing 3/8" thick marble tiles of approved quality and colour shade size 8"x4/6"x3/8" in dado skarting and facing removal / tucking of existing plaster surface etc:. Over 1/2" thick base of cement mortar 1:3 setting mortor base including filling the joints and washing the tiles with white cement slurry, current, finishing cleaning and polishing etc. complete. (ii) forr old works (S.I.# 68(ii)/P-55)
|  |  | 492 | @ | 186.04 | P.Sft | Rs. | 91531.68
2 | Providing and laying HALA or pattern tiles glazed 6" x 6" x 3/4" on floor or wall facing in required colour and pattern for STILE specififcation jointed in white cement and pigment over a base of 1:2 grey cement mortar 3/4" thick including washing and filling of joints with slurry of white cement and pigment in desired shape with finishing cleaning and cost of wax polish etc. complete including cutting tiles to proper profile. (S.I. # 61/P-53).
|  |  | 24 | @ | 47651.56 | %Sft | Rs. | 11436.3744
[5 empty] | TOTAL. |  | Rs. | 102968.0544
PART------C------
1 | Fabrication of mild steel reinforcement for cement concrete i/c cutting bending laying in position, making joints and fastenings i/c cost of binding wire (also removal of rust from bars)(S.I.# 7(ii)/P-20).
| Tor Bars |  | 23.97 | @ | 5001.7 | P.cwt | Rs. | 119890.749
2 | Supplying and fixing in position Iron steel grill of 3/4" x 3/4" size flat iron of approved design i/c painting three coats etc. Complete (Wt not to be less than 3 - 7 lbs sq; ft of finishing grill. (S.I. # 26/P-97).
|  |  | 41 | @ | 180.5 | P.Sft | Rs. | 7400.5
[5 empty] | TOTAL. |  | Rs. | 127291.249
`
SHEDULE-B