## Estimate
SCHEDULE "B"
Name of Work:- Repair / Renovation, Rehabilitation, of Primary / Middle / High Schools in Distt: Shaheed Benazirabad (ADP- 475 , 2016-17 Programme) @ GBPS Chakar Ali Siyal @ Village Gul Hassan Siyal Tal: Daur
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
1 | Dismantling cement concrete reinforced separating reinforcement from concrete cleaning
and straightening the same. (SI, NO: 20 P.10)
659
|  |  | @ | 5445 | %cft | 35882.55
2 | Dismantling brick work in lime or cement mortar. (SI, NO: 13 P.10)
595
|  |  | @ | 1285.63 | %cft | 7649.4985
3 | Dismantling cement concrete plain. Ratio 1:3:6 (SI, NO:19 (b) P.10)
151
|  |  | @ | 1306.8 | %cft | 1973.268 | 1973.268
4 | Removing door with chowkat. (SINO: 33-A, P.NO: 12)
4
|  |  | @ | 142.18 | P.No | 568.72
5 | Removing window and sky light with chowkats. (SI NO: 33-B, NO: 12)
6
|  |  | @ | 102.85 | P.No | 617.1
6 | Removing cement or lime plaster.(SI, NO: 53 P.13)
861
|  |  | @ | 121 | %sft | 1041.81
7 | Excavation in foundation of building bridges and other structures including dagbelling
dressing refilling around structure with excavated earth watering and ramming lead upto
5ft. In ordinary soil. (SI, NO: 18 (b) P. 4)
431
|  |  | @ | 3176.25 | %0cft | 1368.9637 | 1368.9637
8 | Cement concrete brick or stone bllast 1½" to 2" gauge.(SI, NO: 4 (c) P. 15)
| Ratio 1:5:10 |  | 409
|  |  | @ | 8694.95 | %cft | 35562.3455 | 35562.3455
9 | Pacca brick work in foundation and plinth in.1:6. (SI,NO: 4( I )e. P. 21)
839
|  |  | @ | 11948.36 | %cft | 100246.7404 | 100246.7404
10 | Reinforced cement concrete work including all labour and material except the cost of steel
reinforcement and its labour for bending and binding which will be paid separately. This rate
also includes all kinds of forms moulds. Lifting shuttering curing rendering and finishing the
exposed surface (including screening and washing of shingle)
R.C. work in roof slab, beams columns rafts. Lintels and other structural members laid in
situ or precast laid in position completed in all respects. 1:2:4. (SI, NO: 6i P. 17)
753
|  |  | @ | 337 | P.cft | 253761 | 253761
11 | Fabrication of mild steel reinforcement for cement concrete including cutting bending,
laying in position making joints and fastenings including cost of binding wire (also includes
removal of rust from bars.) Using Tor Bars. (SI, NO: 8 (b) P.17)
33.6161
|  |  | @ | 5001.7 | P.cwt | 168137 | 168137
12 | Damp proof course with cement sand and shingle concrete (1:2:4) including 2 coats of
asphltic mixture. (SI, NO: 28 P. 19)
3" thick
339
|  |  | @ | 4982.18 | %cft | 16889.5902 | 16889.5902
Page NO: 02
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
13 | Filling watering and ramming earth under floor with new earth excavated from outside lead
upto one chain and lift upto 5feet. (SI, NO: 22 P.4)
1026
|  |  | @ | 3630 | %0cft | 3724.38 | 3724.38
14 | Pacca brick work in ground floor in Cement sand mortar 1:6. (SI, NO: 5( I )e P. 21)
184
|  |  | @ | 12674.36 | %cft | 23320.8224 | 23320.8224
15 | Pacca brick work in other than building i/ c strcking of joints on walls upto 20 feet
height in:1:6. (SI, NO: 7( I )e P. 22)
1125
|  |  | @ | 12346.65 | %cft | 138899.8125 | 138899.8125
16 | Providing and fixing G.I frames / chowkhats of size 7" x 2" or 4½" x 3" for door using/
window using 20 gauge G.I. sheet i/c welded hinges and fixing at site with necessary hold
fasts filling with cement sand slurry of tation 1:6 and repairing the jambs. The cost also i/c
carriage tools and plants used in making and fixing.(SI, NO: 29 P. 93)
36
|  |  | @ | 228.9 | P.rft | 8240.4 | 8240.4
17 | Providing and fixing G.I frames / chowkhats of size 7" x 2" or 4½" x 3" for Window using/
window using 20 gauge G.I. sheet i/c welded hinges and fixing at site with necessary hold
fasts filling with cement sand slurry of tation 1:6 and repairing the jambs. The cost also i/c
carriage tools and plants used in making and fixing.(SI, NO: 28 P. 93)
142
|  |  | @ | 240.5 | P.rft | 34151 | 34151
18 | Supplying & fixing in position iron / steel grill of ¾" x ¼" size flat iron of approved
designe including painting 3 coats etc. complete wight not tobe less than 3.7 Lbs/sq foot of
finished grill.(SI, NO: 26 P.93)
83
|  |  | @ | 180.5 | P.sft | 14981.5 | 14981.5
19 | Making & fixing steel grated doors with 1/16"thick sheeting including angle iron frame 2"x2"
⅜" and ¾" square bars 4" centre to centre with locking arrangement.(SI, NO: 24 P. 92)
|  |  | 60 |  |  |  | 43603.2
|  |  | @ | 726.72 | P.sft | 43603.2
20 | 1st class deodar wood wrought. Joinery in doors and windows etc. fixed in position including
chowkats hold fasts h inges, iron tower blts. Chocks cleats, handles and cords with hooks,
etc. Deodar panelled or panelled and glazed or fully glazed. 1¾" thick. (SI, NO: 7(b) P.58)
only shuttrs.
171
|  |  | @ | 902.93 | P.sft | 154401.03 | 154401.03
21 | Notice board made with cement.(SI, NO: 1 P. 95)
64
|  |  | @ | 58.11 | Psft | 3719.04 | 3719.04
22 | Laying floor of approved with glazed tile ¼" thick cement 1:2 over ¾" thick cement
mortar 1:2 complete. (SI, NO: 24 P. 43)
40
|  |  | @ | 27678.86 | %sft | 11071.544 | 11071.544
23 | White glazed tile ¼" thick dado jointed in white cment and laid over 1:2 cement sand
mortar ¾" thick including finishing. (SI, NO: 37 P.45)
93
|  |  | @ | 28253.61 | %sft | 26275.8573 | 26275.8573
Page NO: 03
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
24 | Providing and laying 1" thick topping cement concrete (1:2:4) including surface finishing and
dividing into panels. (SI, NO: 16 P. 42)
"A" | 2" thick
1805
|  |  | @ | 3275.5 | %sft | 59122.775 | 59122.775
"B" | 3" thick
696
|  |  | @ | 4411.82 | %sft | 30706.2672 | 30706.2672
25 | Two coats of bitumen laid hot using 34 lbs for %sft over roof and blinded with sand at one
Cft per % Sft. (SI, NO: 13 P.35)
1267
|  |  | @ | 1887.4 | %sft | 23913.358 | 23913.358
26 | Cement pointing struck joints on walls.Ratio 1:2. (SI, NO: 19(a) P. 53)
1350
|  |  | @ | 1287.44 | %sft | 17380.44 | 17380.44
27 | Cement plaster 1:6 upto 20" height.(b) ½" thick. (SI, NO: 13(b) P. 52)
3848
|  |  | @ | 2206.6 | %sft | 84909.968 | 84909.968
28 | Cement plaster 1:4 upto 20" height.(a) ⅜" thick. (SI, NO: 11(a) P. 52)
3848
|  |  | @ | 2197.52 | %sft | 84560.5696 | 84560.5696
29 | Cement plaster 1:4 upto 20" height.(c) ¾" thick. (SI, NO: 11(c) P. 52)
1242
|  |  | @ | 3015.76 | %sft | 37455.7392 | 37455.7392
30 | Extra labour rate for making cement plaster pattas/band around straight or carved opening
& around the edges of roof slabs the width not less than 6" with fine finshing as directed
by Engineer Incharge. (SI, NO: 35 P.55)
300
|  |  | @ | 19.36 | P.rft | 5808 | 5808
31 | P/L floor of Verona Marble tiles of Size 12"x12" and 3/4" fine dressed on the surface without
winding set in white cement laid over 3/4" thick bed of 1:2 grey cement mortor setting the tiles
with grey cement slurry, jointing and washing the tiles with slurry of white cement and pigment
to match the colour of tiles including curring grinding rubbing and chemical polishing etc
complete i/c cutting tiles to proper profile. (R.A)
907
|  |  | @ | 307 | Psft | 278449 | 278449
32 | Whit washing.(SI,NO: 26 P.54)
Three Coats.
1267
|  |  | @ | 829.95 | %sft | 10515.4665 | 10515.4665
33 | Primary coat of chalk under distempering.(SI,NO: 23 P.54)
2665
|  |  | @ | 442.75 | %sft | 11799.2875 | 11799.2875
34 | Colour washing Two Coats..(SI,NO: 25 P.54)
5879
|  |  | @ | 859.9 | %sft | 50553.521 | 50553.521
35 | Distempering Three Coats.. (SI,NO: 24 ( C) P.54)
2665
|  |  | @ | 1079.65 | %sft | 28772.6725 | 28772.6725
Page NO: 04
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
36 | Painting doors and windows any type.three coats. (SI,NO: 5(c/c) P. 70)
"A" | NEW SURFACE
398
|  |  | @ | 2116.41 | %sft | 8423.3118 | 8423.3118
37 | Painting Guard bars, gates iron bars gratings, railings including standard barces (etc) and
similar open work. (SI,NO: 5(d) P. 70)
NEW SURFACE
120
|  |  | @ | 1270.83 | %sft | 1524.996 | 1524.996
38 | Borrowpit excavation undressed lead upto 100ft. (SI, NO: 3 P. 1)
Ordinarry soil.
1560
|  |  | @ | 2117.5 | %0cft | 3303.3
39 | Dressing & Leveling of earth work to designed section etc (b) ordinary or hard soil (SI, NO: 11-b P. 3)
1560
|  |  | @ | 187.55 | %0cft | 292.578
[5 empty] | Total:- | 1823579
Executive Engineer
| Contractor |  |  |  | Education Works Division
Shaheed Benazir Abad
21 | Cement concrete plain including placing compcting, finishing and curing, complete (including
screening and washing of stone aggregate without shuttering.). (SI, NO: 5 P.18)
Ratio 1:3:6
| Lav: Bed | 2x5.0x4.0x0.12 | 5
| C/R Bed | 2x20.0x16.0x0.12 | 77
| Ver: | 1x41.0x6.0x0.12 | 30
112
|  |  | @ | 12595 | %cft | 14106.4 | 14106.4
34 | Painting Guard bars, gates iron bars gratings, railings including standard barces (etc) and
similar open work. (SI,NO: 4(d) P. 69)
NEW SURFACE
| M/Gate | 1x2x8.0x6.0 | 96
96
|  |  | @ | 1270.83 | %sft | 1219.9968 | 1219.9968
[5 empty] | Total:- | 1621930
Mosaic tiles availbe in the market is of poor quaility and not durable heance of Provision of Marble
3/8" thick has been provided keeping in view the estibility of flooring w/o exceeding
of over all aproved cost.
Assistant Engineer
| Sub-Engeenir |  |  |  | Education Works Division
Nawabshah.
"B" | NEW SURFACE
|  | 1x2x3.0x4.0 | 24
24
|  |  | @ | 1270.83 | %sft | 304.9992 | 304.9992
Page NO: 02
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
8 | Providing and fixing ⅜" thick marble tiles of approved quality & colour shade size
8" x 4/6" x 4" in dado skirting & facing removal / tucking of existing plaster surface etc.
over ½" thick of cement mortar 1:3 setting mortar base including filling the joints &
washing the tiles with white cement slurry, current, finishing cleaning and polishing etc.
complete.(SI,NO: 68 P.49)
| C/R Floor | 2x20.0x14.0 | 560
| Ver: | 1x41.17x7.0 | 288
| Step | 1x10.0x5.0 | 50
898
|  |  | @ | 186.04 | P.sft | 167063.92 | 167063.92
9 | Borrowpit excavation undressed lead upto 100ft. (SI, NO: 3 P. 1)
Ordinarry soil.
| C/Wall I/S | 1x83.50x41.50x1.0 | 3465
| " | 1x12.75x30.50x1.0 | 389
3854
|  |  | @ | 2117.5 | %0cft | 8160.845
10 | Laying Earth work compaction in 6" layer leveling & dressing complete. (SI, NO: 13-A P. 3)
|  | Qty same as above item(09) | 3854
|  |  | @ | 187 | %0cft | 720.698
11 | Providing and laying 1" thick topping cement concrete (1:2:4) including surface finishing and
dividing into panels. (SI, NO: 16 P. 42)
"A" | 2" thick
| Over Roof | 1x46.0x27.0 | 1242
| P/P Floor | 1x40.50x3.0 | 122
| " | 1x48.50x4.0 | 194
| " | 1x23.50x2.50 | 59
| " | 1x23.50x3.0 | 71
1688
|  |  | @ | 3275.5 | %sft | 55290.44 | 55290.44
"B" | 3" thick
| Path | 1x41.50x10.0 | 415
| Lav: Path | 1x40.0x6.0 | 240
655
|  |  | @ | 4411.82 | %sft | 28897.421 | 28897.421
Page NO: 03
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
13 | Pacca brick work in other than building i/ c strcking of joints on walls upto 20 feet
height in:1:6. (SI, NO: 7( I )e P. 22)
| C/Wall | 1x280.0x0.37x4.50 | 466
| Piller | 48x0.75x0.37x4.50 | 60
526
|  |  | @ | 12346.65 | %cft | 64943.379 | 64943.379
14 | Pacca brick work in ground floor in Cement sand mortar 1:6. (SI, NO: 5( I )e P. 21)
| OHT | 2x(6.50+4.75)x0.37x3.0 | 25
| M/Room | 2x4.0x0.75x4.0 | 24
49
|  |  | @ | 12674.36 | %cft | 6210.4364 | 6210.4364
15 | Reinforced cement concrete work including all labour and material except the cost of steel
reinforcement and its labour for bending and binding which will be paid separately. This rate
also includes all kinds of forms moulds. Lifting shuttering curing rendering and finishing the
exposed surface (including screening and washing of shingle)
R.C. work in roof slab, beams columns rafts. Lintels and other structural members laid in
situ or precast laid in position completed in all respects. 1:2:4. (SI, NO: 6i P. 17)
| M/Gate Piller | 2x1.50x1.50x7.0 | 32
| S/T Slab | 1x6.0x5.50x0.25 | 8
| OHT Slab | 2x6.50x5.50x0.33 | 24
| M/Room | 1x4.75x4.75x0.25 | 6
70
|  |  | @ | 337 | P.cft | 23590 | 23590
16 | Fabrication of mild steel reinforcement for cement concrete including cutting bending,
laying in position making joints and fastenings including cost of binding wire (also includes
removal of rust from bars.) Using Tor Bars. (SI, NO: 8 (a) P.17)
| Qty: Same Item No: (15) R.C.Cx 70 x5.0/112 |  | 3.125
|  |  | @ | 5001.7 | P.cwt | 15630.3125 | 15630.3125
17 | Making & fixing steel grated doors with 1/16"thick sheeting including angle iron frame 2"x2"
⅜" and ¾" square bars 4" centre to centre with locking arrangement.(SI, NO: 24 P. 97)
| S/ Gate | 1x3.0x4.0 | 12
|  |  | 12 |  |  |  | 8720.64
|  |  | @ | 726.72 | P.sft | 8720.64
18 | Supplying & fixing in position iron / steel grill of ¾" x ¼" size flat iron of approved
designe including painting 3 coats etc. complete wight not tobe less than 3.7 Lbs/sq foot of
finished grill.(SI, NO: 26 P.93)
| M/Room | 1x3.0x4.0 | 12
12
|  |  | @ | 180.5 | P.sft | 2166 | 2166
Page NO: 04
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
20 | Laying floor of approved with glazed tile ¼" thick cement 1:2 over ¾" thick cement
mortar 1:2 complete. (SI, NO: 24 P. 43)
| Lav: Floor | 2x5.0x4.0 | 40
40
|  |  | @ | 27678.86 | %sft | 11071.544 | 11071.544
21 | White glazed tile ¼" thick dado jointed in white cment and laid over 1:2 cement sand
mortar ¾" thick including finishing. (SI, NO: 37 P.45)
| Lav: I/S | 2x2x(5.0+4.0)x3.0 | 108
108
Deduction
| Door | 2x2.50x3.0 | 15
15
|  | Net Qty:- 108 - 15 = | 93
|  |  | @ | 28253.61 | %sft | 26275.8573 | 26275.8573
22 | Notice board made with cement.(SI, NO: 1 P. 95)
| C/R Board | 1x8.0x4.0 | 32
32
|  |  | @ | 58.11 | Psft | 1859.52 | 1859.52
23 | Two coats of bitumen laid hot using 34 lbs for %sft over roof and blinded with sand at one
Cft per % Sft. (SI, NO: 13 P.35)
| Over Roof | 1x46.0x27.0 | 1242
1242
|  |  | @ | 1887.4 | %sft | 23441.508 | 23441.508
24 | Cement plaster 1:6 upto 20" height.(b) ½" thick. (SI, NO: 13(b) P. 52)
"A" | C/Wall o/S | 1x280.0x1.0 | 280
| C/Wall I/S | 1x280.0x5.50 | 1540
| Piller | 48x2x0.37x4.50 | 142
| OHT I/S | 1x2x(5.75+4.75)x3.0 | 63
| " | 1x2x(6.50+5.50)x3.0 | 72
| M/Room | 2x2x4.0x4.0 | 64
2161
|  |  | @ | 2206.6 | %sft | 47684.626 | 47684.626
25 | Cement plaster 1:4 upto 20" height.(a) ⅜" thick. (SI, NO: 11(a) P. 52)
|  | Qty: same as above item No:(24) | 2161
|  |  | @ | 2197.52 | %sft | 47488.4072 | 47488.4072
26 | Cement plaster 1:4 upto 20" height.(c) ¾" thick. (SI, NO: 11(c) P. 52)
"A" | C/Wall Patta | 1x280.0x0.50 | 140
| Path Toe | 2x41.50x1.0 | 83
| S/Tank O/S | 2x(6.0+5.50)x1.50 | 35
| Lav: O/S | 1x2x(12.25+10.25)x2.0 | 90
| C/R O/S | 1x2x(43.0+23.50)x2.0 | 266
614
|  |  | @ | 3015.76 | %sft | 18516.7664 | 18516.7664
27 | Cement pointing struck joints on walls.Ratio 1:2. (SI, NO: 19(a) P. 53)
| C/Wall O/S | 1x280.0x4.0 | 1120
1120
|  |  | @ | 1286.44 | %sft | 14408.128 | 14408.128
28 | Extra labour rate for making cement plaster pattas/band around straight or carved opening
& around the edges of roof slabs the width not less than 6" with fine finshing as directed
by Engineer Incharge. (SI, NO: 35 P.55)
| C/Wall | 1x280.0 | 280
280
|  |  | @ | 19.36 | P.rft | 5420.8 | 5420.8
29 | Whit washing.(SI,NO: 26 P.54)
Two Coats.
| Lav: Ceilling | Qty: Same as Ite NO: (23) | 1242
| Lav: Ceilling | 2x5.0x4.0 | 40
1282
|  |  | @ | 425.84 | %sft | 5459.2688 | 5459.2688
30 | Distempering Two Coats.. (SI,NO: 24 ( C) P.54)
| C/R I/S | 2x2x(20.0+14.0)x10.50 | 1428
| Ver: I/S | 1x2x(41.17+7.0)x10.50 | 1012
2440
Deduction
| Door | 2x4.0x7.0 | 56
| Windows | 6x4.0x4.0 | 96
| N.Board | 2x8.0x4.0 | 64
216
|  | Net Qty:- 2440 - 216 = | 2224
|  |  | @ | 1079.65 | %sft | 24011.416 | 24011.416
Page NO: 06
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
31 | Colour washing Two Coats..(SI,NO: 25 P.54)
| O/S C/R | 1x2x(43.0+23.50)x12.0 | 1596
| C/Wall | 1x1x280.0x5.50 | 1540
| Lav: O/S | 1x2x(12.25x10.25)x8.75 | 394
| OHT O/S | 1x2x(6.50+5.50)x4.50 | 108
3638
|  |  | @ | 859.9 | %sft | 31283.162 | 31283.162
32 | Colour washing of two coats over one coat white washed surface.(SI,NO: 25 P.60)
| C/Wall I/S | 1x280.0x5.50 | 1540
1540
|  |  | @ | 859.9 | %sft | 13242.46 | 13242.46
33 | Painting doors and windows any type.three coats. (SI,NO: 4(c/c) P. 70)
"A" | OLD SURFACE
| Door | 2x2x4.0x7.0 | 112
| Windows | 6x2x4.0x4.0 | 192
| Door | 2x2x2.50x7.0 | 70
374
|  |  | @ | 1160.06 | %sft | 4338.6244 | 4338.6244
33 | Painting Guard bars, gates iron bars gratings, railings including standard barces (etc) and
similar open work. (SI,NO: 4(d) P. 69)
"A" | NEW SURFACE
| M/Gate | 1x2x8.0x6.0 | 96
96
|  |  | @ | 1270.83 | %sft | 1219.9968 | 1219.9968
"B" | NEW SURFACE
|  | 1x2x3.0x4.0 | 24
24
|  |  | @ | 1270.83 | %sft | 304.9992 | 304.9992
[5 empty] | Total:- | 764092
Mosaic tiles availbe in the market is of poor quaility and not durable heance of Provision of Marble
3/8" thick has been provided keeping in view the estibility of flooring w/o exceeding
of over all aproved cost.
Assistant Engineer
| Sub-Engeenir |  |  |  | Education Works Division
Nawabshah.
Page NO: 02
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
9 | Pacca brick work in other than building i/ c strcking of joints on walls upto 20 feet
height in:1:6. (SI, NO: 7( I )e P. 22)
| C/Wall | 1x76.75x0.37x4.0 | 114
| " | 1x74.50x0.37x4.0 | 110
| " | 1x66.50x0.37x4.0 | 98
| " | 1x62.75x0.37x4.0 | 93
| Piller | 40x0.75x0.37x4.0 | 44
| " | 3x0.37x0.37x4.0 | 2
461
Deducation
| Main Gate | 1x11.50x0.37x4.0 | 17
17
|  | Net Qty:- 461 - 17 = | 444
|  |  | @ | 12346.65 | %cft | 54819.126 | 54819.126
10 | Providing and fixing ⅜" thick marble tiles of approved quality & colour shade size
8" x 4/6" x 4" in dado skirting & facing removal / tucking of existing plaster surface etc.
over ½" thick of cement mortar 1:3 setting mortar base including filling the joints &
washing the tiles with white cement slurry, current, finishing cleaning and polishing etc.
complete.(SI,NO: 68 P.49)
| C/R Dado | 2x2x(20.0+16.0)x0.50 | 72
| " | 2x(41.0+6.0)x0.50 | 47
119
Deducation
|  | 2x2x4.0x0.50 | 8
|  | 2x5.50x10.50 | 6
14
|  | Net Qty:- 119 - 14 = | 105
|  |  | @ | 186.04 | P.sft | 19534.2 | 19534.2
13 | Cement plaster 1:6 upto 20" height.(b) ½" thick. (SI, NO: 13(b) P. 52)
"A" | C/Wall | 1x75.25x5.0 | 376
| " | 1x74.50x5.0 | 373
| " | 1x65.75x5.0 | 329
| " | 1x62.75x5.0 | 314
1392
"B" | OHT I/S | 1x2x(5.75+4.75)x3.0 | 63
| " O/S | 1x2x(6.50+5.50)x3.0 | 72
| Piller | 4x(2.25+1.50)x1.50 | 21
| Lav: I/S | 2x2x(5.17+4.0)x4.0 | 147
303
|  | Total: A+B= 1392 + 303 = | 1695
|  |  | @ | 2206.6 | %sft | 37401.87 | 37401.87
14 | Cement plaster 1:4 upto 20" height.(a) ⅜" thick. (SI, NO: 11(a) P. 52)
|  | Qty: same as above item No:(13) | 1695
|  |  | @ | 2197.52 | %sft | 37247.964 | 37247.964
15 | Cement plaster 1:4 upto 20" height.(c) ¾" thick. (SI, NO: 11(c) P. 52)
"A" | C/Wall Patta | 2x76.75x0.50 | 77
| " | 2x66.50x0.50 | 67
| " | 2x76.0x0.50 | 76
| " | 2x63.50x0.50 | 64
| " | 18x3.50x0.50 | 32
316
Page NO: 04
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
"B" | S/T O/S | 1x2x(8.0+4.50)x1.0 | 25
| Lav: Steps | 1x4.0x4.0 | 16
| M/G Step | 2x11.50x4.50 | 104
145
|  | Total:- (A+B) = 316 + 145 = | 461
|  |  | @ | 3015.76 | %sft | 13902.6536 | 13902.6536
17 | Cement pointing struck joints on walls.Ratio 1:2. (SI, NO: 19(a) P. 53)
| C/Wall O/S | 1x76.75x(3.50+4.0) | 345
| " | 1x76.0x(3.50+1.0) | 342
| " | 1x62.50x(3.50+1.0) | 281
| " | 1x63.50x(3.50+1.0) | 286
1254
Deduction
| M/Gate | 15x3.50x0.50 | 32
| " | 1x11.50x(3.50+1.0) | 50
82
|  | Net Qty:- 1254 - 82 = | 1172
|  |  | @ | 1286.44 | %sft | 15077.0768 | 15077.0768
Page NO: 05
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
21 | Providing and laying 1" thick topping cement concrete (1:2:4) including surface finishing and
dividing into panels. (SI, NO: 16 P. 42)
"A" | 2" thick
| Passage Floor | 1x11.50x3.0 | 35
| P/P Floor | 1x139.0x3.0 | 417
452
|  |  | @ | 3275.5 | %sft | 14805.26 | 14805.26
"B" | 3" thick
| Path | 1x65.0x15.0 | 975
975
|  |  | @ | 4411.82 | %sft | 43015.245 | 43015.245
24 | Colour washing of two coats over one coat white washed surface.(SI,NO: 25 P.60)
|  | Qty Same Item No. (13-A) | 1392
1392
|  |  | @ | 859.9 | %sft | 11969.808 | 11969.808
26 | Whit washing.(SI,NO: 26 P.54)
Three Coats.
| Lav: Ceilling | 2x5.0x4.0 | 40
| C/R Ceilling | 2x20.0x16.0 | 640
| Ver: | 1x41.0x7.0 | 287
| Roof Chajja | 2x14.25x1.0 | 29
| " | 2x5.62x1.0 | 11
1007
|  |  | @ | 829.95 | %sft | 8357.5965 | 8357.5965
27 | Colour washing Two Coats..(SI,NO: 25 P.54)
| C/R B/S | 1x42.58x10.0 | 426
| " | 1x2x24.75x10.0 | 495
|  | Qty same Item NO: (15) | 316
|  |  | 1237 |  |  |  |  | 1237
|  |  | @ | 425.84 | %sft | 5267.6408 | 5267.6408 | 5267.6408
Page NO: 06
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
25 | Painting doors and windows any type.three coats. (SI,NO: 4(c/c) P. 70)
"A" | OLD SURFACE
| Door | 2x2x4.0x7.0 | 112
| Windows | 6x2x4.50x4.0 | 216
328
|  |  | @ | 1160.06 | %sft | 3804.9968 | 3804.9968
"B" | NEW SURFACE
| Lav: Door | 2x2x2.50x7.0 | 70
70
|  |  | @ | 2116.4 | %sft | 1481.48 | 1481.48
26 | Painting Guard bars, gates iron bars gratings, railings including standard barces (etc) and
similar open work. (SI,NO: 4(d) P. 69)
NEW SURFACE
| S.Gate | 1x2x8.0x6.0 | 96
96
|  |  | @ | 1270.83 | %sft | 1219.9968 | 1219.9968
[5 empty] | Total:- | 474054
Mosaic tiles availbe in the market is of poor quaility and not durable heance of Provision of Marble
3/8" thick has been provided keeping in view the estibility of flooring w/o exceeding
of over all aproved cost.
Assistant Engineer
| Sub-Engeenir |  |  |  | Education Works Division
Nawabshah.
22 | Providing & laying HALLA or pattern tiles glazed 6"x 6" x1/4" on floor or wall facing in
required floor & pattern of STILE specification jointed in white cement & pigment over a
base of 1:2 grey cement mortar ¾" thick including washing & filling of joins with slaurry
of white cement and pigment in desired shape with finishing claning & cost of wax polish etc.
complete including cutting tiles to proper profile.(SI, NO: 61 P. 48)
| Main Gate Piller | 2x4x0.75x7.0 | 42
42
|  |  | @ | 47651.56 | %sft | 20013.6552 | 20013.6552
23 | Whit washing.(SI,NO: 26 P.54)
Three Coats.
| Lav: Ceilling | 2x5.0x4.0 | 40
| Roof Chajja | 2x14.25x1.0 | 29
| " | 2x5.62x1.0 | 11
80
|  |  | @ | 859.9 | %sft | 687.92 | 687.92
24 | Colour washing Two Coats..(SI,NO: 25 P.54)
| C/R B/S | 1x42.58x10.0 | 426
| " | 1x2x24.75x10.0 | 495
|  | Qty same Item NO: (13) | 2372
|  | Qty same Item NO: (15) | 316
|  | Qty same Item NO: (17) | 1172
|  |  | 4781 |  |  |  |  | 4781
|  |  | @ | 425.84 | %sft | 20359.4104 | 20359.4104 | 20359.4104
25 | Painting Guard bars, gates iron bars gratings, railings including standard barces (etc) and
similar open work. (SI,NO: 4(d) P. 69)
NEW SURFACE
| S.Gate | 1x2x4.0x6.0 | 48
48
|  |  | @ | 1270.83 | %sft | 609.9984 | 609.9984
26 | Painting doors and windows any type.three coats. (SI,NO: 4(c/c) P. 70)
NEW SURFACE
| Lav: Door | 2x2x2.50x7.0 | 70
70
|  |  | @ | 2116.41 | %sft | 1481.487 | 1481.487
27 | Supplying & fixing in position iron / steel grill of ¾" x ¼" size flat iron of approved
designe including painting 3 coats etc. complete wight not tobe less than 3.7 Lbs/sq foot of
finished grill.(SI, NO: 26 P.93)
| M/Room | 1x3.0x4.0 | 12
| " | 2x2.0x1.50 | 6
18
|  |  | @ | 180.5 | P.sft | 3249 | 3249
[5 empty] | Total:- | 595999
Mosaic tiles availbe in the market is of poor quaility and not durable heance of Provision of Marble
3/8" thick has been provided keeping in view the estibility of flooring w/o exceeding
of over all aproved cost.
Assistant Engineer
| Sub-Engeenir |  |  |  | Education Works Division
Nawabshah.
1 | Dismantling cement concrete reinforced separating reinforcement from concrete cleaning
and straightening the same. (SI, NO: 20 P.10)
| C/R Ver: Roof | 1x45.0x27.50x0.42 | 520
| OHT Slab | 1x5.50x5.50x0.33 | 10
| T-Beam | 2x17.50x0.75x1.50 | 39
| Main Gate Piller | 2x1.50x1.50x3.0 | 14
| W=Chajja | 4x5.0x1.50x0.25 | 8
591
|  |  | @ | 5445 | %cft | 32179.95
4 | Removing door with chowkat. (SINO: 33-A, P.NO: 12)
|  | 1x2 | 2
2
|  |  | @ | 142.18 | P.No | 284.36
6 | Cement concrete brick or stone bllast 1½" to 2" gauge.(SI, NO: 4 (c) P. 15)
Ratio 1:5:10
| Path Toe | 2x44.0x0.75x0.33 | 36
| Path Bed | 1x270.0x0.75x0.33 | 123
| C/R Bed | 2x20.0x16.0x0.33 | 211
| Ver: | 1x10.0x0.75x1.0 | 81
451
|  |  | @ | 8694.95 | %cft | 39214.2245 | 39214.2245
Page NO: 02
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
12 | Providing and laying 1" thick topping cement concrete (1:2:4) including surface finishing and
dividing into panels. (SI, NO: 16 P. 42)
"A" | 2" thick
| P/P Floor | 1x140.0x3.0 | 420
| Over Roof | 1x45.50x27.50 | 1251
1671
|  |  | @ | 3275.5 | %sft | 54733.605 | 54733.605
Page NO: 03
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
"B" | 3" thick
| Path Floor | 1x44.0x10.0 | 440
440
|  |  | @ | 4411.82 | %sft | 19412.008 | 19412.008
13 | Two coats of bitumen laid hot using 34 lbs for %sft over roof and blinded with sand at one
Cft per % Sft. (SI, NO: 13 P.35)
| Lav: Over Roof | 1x14.0x7.50 | 105
105
|  |  | @ | 1887.4 | %sft | 1981.77 | 1981.77
14 | 1st class deodar wood wrought. Joinery in doors and windows etc. fixed in position including
chowkats hold fasts h inges, iron tower blts. Chocks cleats, handles and cords with hooks,
etc. Deodar panelled or panelled and glazed or fully glazed. 1¾" thick. (SI, NO: 7(b) P.58)
only shuttrs.
| Door | 2x3.75x6.75 | 51
| Windows | 6x3x1.33x3.75 | 90
141
|  |  | @ | 902.93 | P.sft | 127313.13 | 127313.13
15 | Notice board made with cement.(SI, NO: 1 P. 95)
| C/R Board | 2x8.0x4.0 | 64
64
|  |  | @ | 58.11 | Psft | 3719.04 | 3719.04
16 | Supplying & fixing in position iron / steel grill of ¾" x ¼" size flat iron of approved
designe including painting 3 coats etc. complete wight not tobe less than 3.7 Lbs/sq foot of
finished grill.(SI, NO: 26 P.93)
| Vent: | 2x2.0x1.50 | 6
6
|  |  | @ | 180.5 | P.sft | 1083 | 1083
17 | Laying floor of approved with glazed tile ¼" thick cement 1:2 over ¾" thick cement
mortar 1:2 complete. (SI, NO: 24 P. 43)
| Lav: Floor | 1x5.50x4.0 | 22
| Passage | 1x5.50x3.0 | 17
39
|  |  | @ | 27678.86 | %sft | 10794.7554 | 10794.7554
18 | White glazed tile ¼" thick dado jointed in white cment and laid over 1:2 cement sand
mortar ¾" thick including finishing. (SI, NO: 37 P.45)
| Lav: I/S | 1x2x(5.50+4.0)x3.0 | 57
| " | 2x5.50x3.0 | 33
| " | 1x3.0x3.0 | 9
99
Deduction
| Door | 1x2.0x2.50x3.0 | 15
15
|  | Net Qty:- 99 - 15 = | 84
|  |  | @ | 28253.61 | %sft | 23733.0324 | 23733.0324
Page NO: 04
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
19 | Providing and fixing ⅜" thick marble tiles of approved quality & colour shade size
8" x 4/6" x 4" in dado skirting & facing removal / tucking of existing plaster surface etc.
over ½" thick of cement mortar 1:3 setting mortar base including filling the joints &
washing the tiles with white cement slurry, current, finishing cleaning and polishing etc.
complete.(SI,NO: 68 P.49)
| C/R Floor | 2x20.0x16.0 | 640
| Ver: | 1x41.0x6.0 | 246
886
|  |  | @ | 186.04 | P.sft | 164831.44 | 164831.44
20 | Cement concrete plain including placing compcting, finishing and curing, complete (including
screening and washing of stone aggregate without shuttering.). (SI, NO: 5 P.18)
Ratio 1:3:6
| Qty:- Same Item NO: (19) 886x0.12= |  | 106
106
|  |  | @ | 12595 | %cft | 13350.7 | 13350.7
21 | Cement plaster 1:6 upto 20" height.(b) ½" thick. (SI, NO: 13(b) P. 52)
| C/Wall I/S | 1x270.0x5.50 | 1485
| C/Wall O/S | 1x270.0x1.0 | 270
| OHT I/S | 1x2x(6.25+4.75)x3.0 | 66
| OHT O/S | 1x2x(7.0+5.50)x5.0 | 125
1946
|  |  | @ | 2206.6 | %sft | 42940.436 | 42940.436
22 | Cement plaster 1:4 upto 20" height.(a) ⅜" thick. (SI, NO: 11(a) P. 52)
|  | Qty: same as above item No:(19) | 1946
|  |  | @ | 2197.52 | %sft | 42763.7392 | 42763.7392
23 | Cement plaster 1:4 upto 20" height.(c) ¾" thick. (SI, NO: 11(c) P. 52)
| Steps | 1x12.0x4.0 | 48
| Path Toe | 2x44.0x1.50 | 192
| P/P Toe | 1x140.0x1.50 | 210
| C/Wall Patta | 1x270.0x0.50 | 135
|  | (+) Qty:- Same as Item No: (03) | 1104
1689
|  |  | @ | 3015.76 | %sft | 50936.1864 | 50936.1864
24 | Extra labour rate for making cement plaster pattas/band around straight or carved opening
& around the edges of roof slabs the width not less than 6" with fine finshing as directed
by Engineer Incharge. (SI, NO: 35 P.55)
| C/Wall | 1x270.0 | 270
270
|  |  | @ | 19.36 | P.rft | 5227.2 | 5227.2
25 | Cement pointing struck joints on walls.Ratio 1:2. (SI, NO: 19(a) P. 53)
| C/Wall | 1x270.0x4.0 | 1080
1080
|  |  | @ | 1287.44 | %sft | 13904.352 | 13904.352
Page NO: 05
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
26 | Filling watering and ramming earth under floor with new earth excavated from outside lead
upto one chain and lift upto 5feet. (SI, NO: 22 P.4)
| C/R Bed | 2x20.0x16.0x1.0 | 640
| Ver: Bed | 1x41.0x6.0x1.0 | 246
| Path Bed | 1x44.0x8.50x1.0 | 374
1260
|  |  | @ | 3630 | %0cft | 4573.8 | 4573.8
27 | Borrowpit excavation undressed lead upto 100ft. (SI, NO: 3 P. 1)
Ordinarry soil.
| Court Yard (I/S) | 1x75.0x44.0x1.50 | 4950
| Court Yard (I/S) | 1x26.0x30.50x1.50 | 1190
6140
|  |  | @ | 2117.5 | %0cft | 13001.45
28 | Laying Earth work compaction in 6" layer leveling & dressing complete. (SI, NO: 13-A P. 3)
|  | Qty same as above item(27) | 6140
|  |  | @ | 263 | %0cft | 1614.82
28 | Providing & laying HALLA or pattern tiles glazed 6"x 6" x1/4" on floor or wall facing in
required floor & pattern of STILE specification jointed in white cement & pigment over a
base of 1:2 grey cement mortar ¾" thick including washing & filling of joins with slaurry
of white cement and pigment in desired shape with finishing claning & cost of wax polish etc.
complete including cutting tiles to proper profile.(SI, NO: 61 P. 48)
| Main Gate Piller | 2x2x1.0x7.0 | 28
28
|  |  | @ | 47651.56 | %sft | 13342.4368 | 13342.4368
29 | Whit washing.(SI,NO: 26 P.54)
Three Coats.
|  | Qty same as above item (19) | 886
886
|  |  | @ | 425.84 | %sft | 3772.9424 | 3772.9424
31 | Primary coat of chalk under distempering.(SI,NO: 23 P.54)
| C/R I/S | 2x2x(20.0+16.0)x11.0 | 1584
| Ver: I/S | 1x2x(41.0+6.0)x11.0 | 1034
2618
Deduction
| Door | 2x4.0x7.0 | 56
| Windows | 6x4.50x4.0 | 108
| Notice Board | 2x8.0x4.0 | 64
| Ver: Opp: | 2x6.0x7.0 | 84
| Ver: Opp: | 4x6.0x5.0 | 120
432
|  | Net Qty:- 2618 - 432 = | 2186
|  |  | @ | 442.75 | %sft | 9678.515 | 9678.515
Page NO: 06
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
32 | Distempering Three Coats.. (SI,NO: 24 ( C) P.54)
|  | Qty same Item NO. (31) | 2186
|  |  | @ | 1079.65 | %sft | 23601.149 | 23601.149
33 | Colour washing Two Coats..(SI,NO: 25 P.54)
| C/Wall | 1x270.0x0.50 | 135
|  | Qty same Item NO. (21) | 1946
|  | Qty same Item NO: (25) | 1080
3161
|  |  | @ | 859.9 | %sft | 27181.439 | 27181.439
34 | Painting doors and windows any type.three coats. (SI,NO: 4(c/c) P. 70)
"A" | NEW SURFACE
| Door | 2x2.0x4.0x7.0 | 112
| Door | 1x2.0x2.50x7.0 | 35
| Windows | 6x2.0x4.50x4.0 | 216
363
|  |  | @ | 2116.41 | %sft | 7682.5683 | 7682.5683
35 | Painting Guard bars, gates iron bars gratings, railings including standard barces (etc) and
similar open work. (SI,NO: 4(d) P. 69)
OLD SURFACE
| M.Gate | 1x2.0x10.0x6.0 | 120
120
|  |  | @ | 674.6 | %sft | 809.52 | 809.52
36 | Providing and fixing G.I frames / chowkhats of size 7" x 2" or 4½" x 3" for door using/
window using 20 gauge G.I. sheet i/c welded hinges and fixing at site with necessary hold
fasts filling with cement sand slurry of tation 1:6 and repairing the jambs. The cost also i/c
carriage tools and plants used in making and fixing.(SI, NO: 28/29 P. 93)
"A" | Door Using
| C/R door"H" | 2x2.0x7.0 | 28
| C/R Door "V" | 2x1.0x7.0 | 14
42
|  |  | @ | 228.9 | P.rft | 9613.8 | 9613.8
"B" | Windows Using
| C/R Windows "H" | 1x2.0x4.50 | 9
| C/R Windows "V" | 1x4.0x3.67 | 15
24
|  |  | @ | 240.5 | P.rft | 5772 | 5772
[5 empty] | Total:- | 769047.3694
Mosaic tiles availbe in the market is of poor quaility and not durable heance of Provision of Marble
3/8" thick has been provided keeping in view the estibility of flooring w/o exceeding
of over all aproved cost.
Assistant Engineer
| Sub-Engeenir |  |  |  | Education Works Division
Nawabshah.
5 | Removing window and sky light with chowkats. (B, NO: 34)
|  | 1x7 | 7
7
|  |  | @ | 102.85 | P.No | 719.95
Page No: 02
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
6 | Excavation in foundation of building bridges and other structures including dagbelling
dressing refilling around structure with excavated earth watering and ramming lead upto
5ft. In ordinary soil. (SI, NO: 18 (b) P. 4)
| S/Tank | 1x8.0x6.0x5.0 | 240
240
|  |  | @ | 3176.25 | %0cft | 762.3 | 762.3
7 | Cement concrete brick or stone bllast 1½" to 2" gauge.(SI, NO: 4 (c) P. 15)
Ratio 1:5:10
| S/Tank | 1x8.0x6.0x0.50 | 24
| Lav: Bed | 1x5.0x4.0x0.33 | 7
| P/Form Bed | 1x50.0x12.0x0.37 | 222
253
|  |  | @ | 8694.95 | %cft | 21998.2235 | 21998.2235
8 | Damp proof course with cement sand and shingle concrete (1:2:4) including 2 coats of
asphltic mixture. (SI, NO: 28 P. 19)
3" thick
| C/Wall | 1x60.0x0.75 | 45
45
|  |  | @ | 4982.18 | %cft | 2241.981 | 2241.981
Page No: 03
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
Page No: 05
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
25 | Providing and laying 1" thick topping cement concrete (1:2:4) including surface finishing and
dividing into panels. (SI, NO: 16 P. 42)
"A" | 2" thick
| Over Roof | 1x43.25x26.25 | 1135
| " | 1x18.50x2.75 | 51
| " | 1x8.50x7.50 | 64
1250
|  |  | @ | 3275.5 | %sft | 40943.75 | 40943.75
Page No: 06
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
Page No: 07
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
"B" | OLD SURFACE
| Windows | 3x2x5.0x4.0 | 120
| Door | 2x2x4.0x7.0 | 112
232
|  |  | @ | 1160.06 | %sft | 2691.3392 | 2691.3392
Page No: 08
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
[5 empty] | Total:- | 1607452.2825
Mosaic tiles availbe in the market is of poor quaility and not durable heance of Provision of Marble
3/8" thick has been provided keeping in view the estibility of flooring w/o exceeding
of over all aproved cost.
Assistant Engineer
| Sub-Engeenir |  |  |  | Education Works Division
Nawabshah.
"B" | 3" thick
| P/Form Floor | 1x50.0x12.0 | 600
Page No: 06
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
600
|  |  | @ | 4411.82 | %sft | 26470.92 | 26470.92
29 | Providing & laying HALLA pattern tiles glazed 8"x 8" x ¼" on floor or wall facing in
required pattern of STILE specification jointed in white cement & pigment over a base of
1:2 grey cement mortar ¾" thick including washing & filling of joins with slaurry of white
cement & pigment in desired shape with finishing claning & cost of wax polish etc. complete
including cutting tiles to proper profile.(SI, NO: 62 P. 54)
| Ver: F/S Piller | 3x1.0x12.0 | 36
36
|  |  | @ | 34520.31 | %sft | 12427.3116 | 12427.3116
2 | Cement concrete brick or stone bllast 1½" to 2" gauge.(SI, NO: 4 (c) P. 15)
Ratio 1:5:10
| U.G tank | 1x12.0x10.0x0.50 | 60
| S/Tank | 2x12.0x8.0x0.50 | 96
| P/P Toe | 1x850.0x1.25x0.50 | 531
| Steps | 2x18.0x5.0x0.33 | 59
| Path Toe | 2x350.0x1.25x0.50 | 438
| P/P Bed | 1x850.0x2.25x0.33 | 631
| Path Bed | 1x350.0x13.50x0.37 | 1748
3563
|  |  | @ | 8694.95 | %cft | 309801.0685 | 309801.0685
3 | Pacca brick work in foundation and plinth in.1:6. (SI,NO: 4( I )e. P. 21)
| U.G Tank | 2x(12.0+8.0)x0.75x5.0 | 150
| S/Tank | 2x10.0x0.75x5.0 | 75
| " | 2x6.0x0.75x5.0 | 45
| P/P toe | 1x850.0x0.75x2.25 | 1434
| Steps | 2x18.0x5.0x1.0 | 180
| " | 2x18.0x(4.0+3.0+2.0)X0.50 | 162
| Path Toe | 2x350.0x0.75x2.25 | 1181
3227
|  |  | @ | 11948.36 | %cft | 385573.5772 | 385573.5772
4 | Filling watering and ramming earth under floor with new earth excavated from outside lead
upto one chain and lift upto 5feet. (SI, NO: 22 P.4)
| P/P Bed | 1x850.0x2.25x1.62 | 3098
Page No: 02
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
| Path Bed | 1x350.0x13.50x1.62 | 7655
10753
|  |  | @ | 3630 | %0cft | 39033.39 | 39033.39
5 | Borrowpit excavation undressed lead upto 100ft. (SI, NO: 3 P. 1)
Ordinarry soil.
| I/S Park | 1x100.0x40.0x2.0 | 8000
| " | 2x57.0x46.50x2.0 | 10602
18602
|  |  | @ | 2117.5 | %0cft | 39389.735
6 | Laying Earth work compaction (soft, ordinary or hard soil) (SI, NO: 13 P. 3)
|  | Qty same as above item(05) | 18602
|  |  | @ | 263 | %0cft | 4892.326
7 | 1st class deodar wood wrought. Joinery in doors and windows etc. fixed in position including
chowkats hold fasts h inges, iron tower blts. Chocks cleats, handles and cords with hooks,
etc. Deodar panelled or panelled and glazed or fully glazed. 1¾" thick. (SI, NO: 7(b) P.58)
only shuttrs.
| Door | 1x3.75x6.75 | 25
| Windows | 6x4x1.33x3.75 | 120
| Tower Door | 1x2.75x6.75 | 19
164
|  |  | @ | 902.93 | P.sft | 148080.52 | 148080.52
8 | Supplying & fixing in position iron / steel grill of ¾" x ¼" size flat iron of approved
designe including painting 3 coats etc. complete wight not tobe less than 3.7 Lbs/sq foot of
finished grill.(SI, NO: 26 P.97)
| Tower O/S | 1x6.0x4.0 | 24
| Ver: Opp: | 8x7.25x5.25 | 305
| " | 11x6.25x(0.50+0.75+0.50/2) | 40
| Ver: S/W Opp: | 4x5.50x5.25 | 116
| " | 4x4.50x(0.50+0.75/2) | 11
| " | 16x6.50x5.25 | 546
| " | 20x5.50x(0.50+0.75/2) | 68
| " | 13x8.50x5.25 | 580
| " | 13x7.50x(0.50+0.75/2) | 60
| Entt: | 1x7.25x7.50 | 54
| " | 1x6.25x(0.50+1.0+0.50/3) | 4
| " | 2x(2.0+1.0)x7.0 | 42
1850
|  |  | @ | 180.5 | P.sft | 333925 | 333925
9 | Providing & Fixing iron steel grill door with angle iron framme of 1½" x 1½" x¼" and flat
iron of ¾" x ¼" with approvd design and locking arrangement embeded in masonary as per
instruction of Engineer Incharge. (SI,NO: 31 P.94)
| " | 3x7.25x7.75 | 169
| " | 4x6.50x7.75 | 202
371
|  |  | @ | 231.6 | P.sft | 85923.6 | 85923.6
Page No: 03
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
10 | Pacca brick work in ground floor in Cement sand mortar 1:6. (SI, NO: 5( I )e P. 21)
| Stair Tower | 2x22.50x0.75x8.50 | 288
| " | 2x12.0x0.75x8.50 | 153
| OHT Piller | 6x1.50x0.75x2.0 | 14
| " | 4x0.75x0.75x2.0 | 5
| OHT Wall | 2x14.25x0.75x4.0 | 86
| " | 2x8.0x0.75x4.0 | 48
| D/Wall | 5x7.25x0.75x2.50 | 68
| Expansion Joints | 1x2x46.50x0.75x0.50 | 35
| " | 1x2x33.50x0.75x0.50 | 25
| " | 1x2x8.0x0.75x0.50 | 6
| D/Wall | 16x6.50x0.75x2.50 | 195
| " | 13x8.50x0.75x2.50 | 207
| Stair Railing | 1x(18.0+10.0)X0.37x3.0 | 20
1150
|  |  | @ | 12674.36 | %cft | 145755.14 | 145755.14
11 | Reinforced cement concrete work including all labour and material except the cost of steel
reinforcement and its labour for bending and binding which will be paid separately. This rate
also includes all kinds of forms moulds. Lifting shuttering curing rendering and finishing the
exposed surface (including screening and washing of shingle)
R.C. work in roof slab, beams columns rafts. Lintels and other structural members laid in
situ or precast laid in position completed in all respects. 1:2:4. (SI, NO: 6i P. 17)
| S/Tank Slab | 2x10.0x7.50x0.33 | 50
| U.G tank Slab | 1x12.0x9.50x0.42 | 48
| OHT B/Slab | 1x14.25x9.50x0.50 | 68
| T/Slab | 1x15.25x10.50x0.33 | 53
| Expansion Joints Slab | 1x46.0x1.50x0.25 | 17
| " | 1x33.50x1.50x0.25 | 13
| " | 1x8.0x1.50x0.75 | 3
| Tower Lintel | 2x12.0x0.75x0.75 | 14
| " | 2x22.50x0.75x0.75 | 25
| " Roof | 1x24.50x15.50x0.42 | 159
| D/Wall Slab | 5x7.25x1.25x0.25 | 11
| " | 16x6.50x1.25x0.25 | 33
| " | 13x8.50x1.25x0.25 | 35
529
|  |  | @ | 337 | P.cft | 178273 | 178273
12 | Fabrication of mild steel reinforcement for cement concrete including cutting bending,
laying in position making joints and fastenings including cost of binding wire (also includes
removal of rust from bars.) Using Tor Bars. (SI, NO: 8 (a) P.17)
| Qty: Same Item No: (11) R.C.Cx 529 x5.00/112 |  | 23.6161
|  |  | @ | 5001.97 | P.cwt | 118126.8808 | 118126.8808
Page No: 04
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
13 | Laying floor of approved with glazed tile ¼" thick cement 1:2 over ¾" thick cement
mortar 1:2 complete. (SI, NO: 24 P. 43)
| G.Lav: Floor | 4x5.0x4.0 | 80
| " Passage | 1x17.0x6.25 | 106
186
|  |  | @ | 27678.86 | %sft | 51482.6796 | 51482.6796
14 | White glazed tile ¼" thick dado jointed in white cment and laid over 1:2 cement sand
mortar ¾" thick including finishing. (SI, NO: 37 P.50)
| G.Lav: | 4x2x(5.0+4.0)x4.0 | 288
| " Passage | 2x17.0x4.0 | 136
| " | 1x6.25x4.0 | 25
449
Deduction
| Door | 4x2x2.50x4.0 | 40
| Door | 1x3.0x4.0 | 12
52
|  | Net Qty:- 449 - 52 = | 397
|  |  | @ | 28299.3 | %sft | 112348.221 | 112348.221
15 | P/F Verona grade-2 Marble flooring 12"x12"x1/2" in Bed over 3/4" thick cement mortor 1:3
etc complete in all respect i/c chemical polish (R.A) Attached
| Lab: Floor | 3x40.0x30.0 | 3600
| Stair Portion | 1x12.0x22.0 | 264
| Ver: Floor | 1x135.50x7.0 | 949
| Ver: Opp: | 3x7.25x1.25 | 27
| P/Form | 1x28.50x5.0 | 143
| Steps | 2x18.0x5.0 | 180
| Stair Steps | 22x5.0x1.50 | 165
| " Landing | 1x8.50x4.0 | 34
5362
|  |  | @ | 152.84 | %sft | 819528.08 | 819528.08
16 | Providing and fixing ⅜" thick marble tiles of approved quality & colour shade size
8" x 4/6" x 4" in dado skirting & facing removal / tucking of existing plaster surface etc.
over ½" thick of cement mortar 1:3 setting mortar base including filling the joints &
washing the tiles with white cement slurry, current, finishing cleaning and polishing etc.
complete.(SI,NO: 68 P.55)
| Lab: I/S Dado | 3x2x(40.0+30.0)x0.50 | 210
| Stair Portion | 1x12.0x0.50 | 6
| " | 2x22.0x0.50 | 22
| Ver: Dado | 2x135.50x0.50 | 136
| Steps Rieser | 4x18.0x0.50 | 36
| P/Form Step | 4x28.0x0.50 | 56
466
|  |  | @ | 186.04 | P.sft | 86694.64 | 86694.64
Page No: 05
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
17 | Cement concrete plain including placing compcting, finishing and curing, complete (including
screening and washing of stone aggregate without shuttering.). (SI, NO: 5 P.18)
Ratio 1:3:6
| Lab: Floor | 3x40.0x30.0x0.12 | 432
| Stair Portion | 1x12.0x22.0x0.12 | 32
| Ver: Floor | 1x135.50x7.0x0.12 | 114
| P/Form | 1x28.50x5.0x0.12 | 17
| Floor | 4x5.0x4.0x0.12 | 10
| Passage Floor | 1x6.29x17.0x0.12 | 13
618
|  |  | @ | 12595 | %cft | 77837.1 | 77837.1
18 | Providing and laying 1" thick topping cement concrete (1:2:4) including surface finishing and
dividing into panels. (SI, NO: 16 P. 42)
"A" | 2" thick
| Tower Roof | 1x24.50x15.50 | 380
| " P/P Floor | 1x850.0x3.0 | 2550
| U.G Tank | 1x10.50x8.0 | 84
3014
|  |  | @ | 3275.5 | %sft | 98723.57 | 98723.57
"B" | 3" thick
| Path Floor | 1x350.0x15.0 | 5250
5250
|  |  | @ | 4411.82 | %sft | 231620.55 | 231620.55
19 | Pacca brick work in other than building i/ c strcking of joints on walls upto 20 feet
height in:1:6. (SI, NO: 7( I )e P. 22)
| Raising C/Wall | 1x500.0x0.75x2.0 | 750
750
|  |  | @ | 12346.65 | %cft | 92599.875 | 92599.875
20 | Providing & fixing ornmental cement jalli 2" thick (1:2:4) without sheet.(SI,NO:11 P.18)
| Tower Opp: | 4x4.0x4.0 | 64
64
|  |  | @ | 226.02 | Psft | 14465.28 | 14465.28
21 | Cement plaster 1:6 upto 20" height.(b) ½" thick. (SI, NO: 13(b) P. 52)
| Tower I/S | 1x2x(21.0+12.0)X8.50 | 561
| " O/S | 2x(22.50+13.50)x8.0 | 576
| Railing | 2x(18.0+10.0)X3.0 | 168
| OHT I/S | 1x2x(12.75+8.0)x4.0 | 166
| " O/S | 1x2x(14.25+9.50)x4.0 | 190
| Piller | 6x2x(1.50+1.50)x2.0 | 72
Page No: 06
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
| D/Wall | 5x2x7.25x2.50 | 181
| " | 16x2x6.50x2.50 | 520
| " | 13x2x8.50x2.50 | 553
| U.G Tank (I/S) | 1x2x(10.50+8.0)x5.0 | 185
| " O/S | 1x2x(12.0+9.50)x1.50 | 65
| S/Tank O/S | 1x2x(10.0+7.50)x1.50 | 53
| P/P Toe | 1x850.0x1.25 | 1063
| P/P Toe | 2x350.0x1.25 | 875
| P/Form Toe | 2x46.50x1.25 | 116
| C/Wall | 1x2x500.0x2.0 | 2000
7344
|  |  | @ | 2206.6 | %sft | 162052.704 | 162052.704
22 | Cement plaster 1:4 upto 20" height.(a) ⅜" thick. (SI, NO: 11(a) P. 52)
|  | Qty: same as above item No:(21) | 7344
|  |  | @ | 2197.52 | %sft | 161385.8688 | 161385.8688
23 | Providing & laying HALLA or pattern tiles glazed 6"x 6" x½" on floor or wall facing in
required floor & pattern of STILE specification jointed in white cement & pigment over a
base of 1:2 grey cement mortar ¾" thick including washing & filling of joins with slaurry
of white cement and pigment in desired shape with finishing claning & cost of wax polish etc.
complete including cutting tiles to proper profile.(SI, NO: 61 P. 54)
| Ver: Piller | 18x1.0x11.0 | 198
198
|  |  | @ | 47651.56 | %sft | 94350.0888 | 94350.0888
24 | Cement pointing struck joints on walls.Ratio 1:2. (SI, NO: 19(a) P. 53)
| B/S | 1x(100.0+22.0)x11.0 | 1342
| W/S | 1x31.25x11.0 | 344
| S/S | 1x9.25x11.0 | 102
| S/S | 1x13.25x11.0 | 146
| E/S | 1x20.25x11.0 | 223
2157
Deduction
| W= Pannel | 14x7.0x11.0 | 1078
| " | 1x4.0x11.0 | 44
1122
|  | Net Qty:- 2157 - 1122 = | 1035
|  |  | @ | 1287.44 | %sft | 13325.004 | 13325.004
25 | Cement plaster 1:4 upto 20" height.(c) ¾" thick. (SI, NO: 11(c) P. 52)
| Vert: Patta | 38x10.50x0.50 | 200
| U/Roof | 1x123.0x0.50 | 62
| " | 1x32.25x0.50 | 16
| " | 1x(10.25+14.25)x0.50 | 12
| " | 1x20.25x0.50 | 10
Page No: 07
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
300
|  |  | @ | 3015.76 | %sft | 9047.28 | 9047.28
26 | Extra labour rate for making cement plaster pattas/band around straight or carved opening
& around the edges of roof slabs the width not less than 6" with fine finshing as directed
by Engineer Incharge. (SI, NO: 35 P.61)
|  | Qty Item No: (23) 300/0.50= | 600
600
|  |  | @ | 19.36 | P.rft | 11616 | 11616
27 | Two coats of bitumen laid hot using 34 lbs for %sft over roof and blinded with sand at one
Cft per % Sft. (SI, NO: 13 P.35)
| Tower Roof | 1x24.50x15.50 | 380
| Over Roof | 1x80.0x43.50 | 3480
| " | 1x32.58x16.17 | 527
| " | 1x20.58x17.17 | 353
| " | 1x43.75x43.50 | 1903
6643
|  |  | @ | 1887.4 | %sft | 125379.982 | 125379.982
28 | Whit washing.(SI,NO: 26 P.54)
Three Coats.
|  | Qty Item No: (27) | 6643
| T-Beam Offset | 6x2x30.0x2.50 | 900
7543
|  |  | @ | 829.95 | %sft | 62603.1285 | 62603.1285
29 | Primary coat of chalk under distempering.(SI,NO: 23 P.54)
| Tower I/S | 1x2x(21.0+12.0)x8.50 | 561
| Hall I/S | 3x2x(40.0+30.0)x11.0 | 4620
| Ver: I/S | 1x2x135.50x11.0 | 2981
| " O/S | 1x(100.0+13.25)x11.50 | 1302
| " | 1x8.0x11.50 | 92
| Stair Portion | 1x2x(12.0+22.0)x11.50 | 782
| G.Lav: | 4x2x(5.0+4.0)x4.0 | 288
| " | 1x2x(12.0+17.0)x7.50 | 435
11061
Deduction
| Door | 6x4x7.0 | 168
| Windows | 6x6.0x4.0 | 144
| N.Board | 3x12.0x4.0 | 144
| Ver: opp: | 7x7.25x5.25 | 266
| " | 3x7.25x7.75 | 169
| " | 1x5.50x5.25 | 29
920
|  | Net Qty:- 11061 - 920 = | 10141
|  |  | @ | 442.75 | %sft | 44899.2775 | 44899.2775
Page No: 08
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
30 | Distempering. (SI,NO: 24 P.60)
Three Coats.
|  | Qty same Item NO. (29) | 10141
|  |  | @ | 1079.65 | %sft | 109487.3065 | 109487.3065
31 | Colour washing.(SI,NO: 25 P.54)
Two Coats.
| Tower O/S | 1x2x(22.50+13.50)x8.50 | 612
| OHT O/S | 1x2x(14.25+9.50)x6.0 | 285
| W | 14x6.0x11.0 | 924
|  | Qty:- Same Item No: (25) | 300
2121
|  |  | @ | 859.9 | %sft | 18238.479 | 18238.479
32 | Painting doors and windows any type.three coats. (SI,NO: 4(b/c) P. 70)
NEW SURFACE
| Door | 6x2x4.0x7.0 | 336
| Windows | 20x2x6.0x4.0 | 960
| Door 2 | 2x2x3.0x7.0 | 84
| Door 3 | 4x2x2.50x7.0 | 140
1520
|  |  | @ | 2116.41 | %sft | 32169.432 | 32169.432
33 | Providing & fixing collapsible gate with channel framing of section ¾" x 5/16" at 4" i/c
revitted with ¾" x ⅛" flat iron patti placed diagonally & provided with top & bottom
T - section 1" x 1" x½" along with rollers also i/c locking arrangement & fixing in floor /
ceilling or wall etc. complete. (SI,NO: 32 P.99)
| Entt: | 1x11.25x8.0 | 90
90
|  |  | @ | 387.04 | Psft | 34833.6 | 34833.6
34 | Notice board made with cement.(SI, NO: 1 P. 100)
| C/R Board | 3x18.0x4.0 | 216
216
|  |  | @ | 58.11 | Psft | 12551.76 | 12551.76
[5 empty] | Total:- | 5981002.252
| Sub: Engineer |  |  | Assistant Engineer
Education Works Sub-Division
Nawabshah
Page No: 03
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
6 | Filling watering and ramming earth in floor with surplus earth from foundation lead upto one
chain and lift upto 5feet. (SI, NO: 21 P.5)
| 2/3 Qty: Same as Item No. 01 (-) 1443x2/3= |  | 962
962
|  |  | @ | 1512.5 | %0cft | 1455.025 | 1455.025
7 | Filling watering and ramming earth under floor with new earth excavated from outside lead
upto one chain and lift upto 5feet. (SI, NO: 22 P.5)
| C/R floor bed | 2x19.625x15.625x1.92 | 1178
| Ver: | 1x40.75x6.625x1.92 | 518
| Approach path | 1x100.0x10.0x0.63 | 630
2326
|  |  | @ | 3630 | %0cft | 8443.38 | 8443.38
8 | Supplying and filling sand under floor and plugging in wall.(SI,NO:29 P.31)
| C/R Floo Bed | 2x19.625x15.625x0.50 | 307
| Ver: | 1x40.75x6.625x0.50 | 135
442
|  |  | @ | 1141.25 | %cft | 5044.325 | 5044.325
9 | Damp proof course with cement sand and shingle concrete (1:2:4) including 2 coats of
asphltic mixture. (SI, NO: 27 P. 23)
3" thick
| C/Wall Plinth | 1x400.0x0.75 | 300
| Lav: I/Wall | 1x3x10.625x1.125 | 36
| " S/Wall | 1x3x4.625x1.125 | 16
| " P S/Wall | 1x2x2.625x1.125 | 6
358
|  |  | @ | 3982.18 | %sft | 14256.2044 | 14256.2044
10 | Pacca brick work in ground floor in Cement sand mortar 1:6. (SI, NO: 5( I )e P. 25)
| C/R L/Wall | 1x2x43.37x1.125(11+13+11/3) | 1138
| C/R S/Wall | 1x2x16x1.125x11.0 | 39
| " S/Wall | 1x16.0x1.125x13.0 | 234
| Ver: L/Wall | 1x43.37x1.125x6.50 | 717
| " S/Wall | 1x2x7.0x1.13x11.0 | 173
| " D/Wall | 4x6.50x0.75x3.0 | 58
| Ver: L/Wall | 1x43.37x1.125(1.50+3.50+1.50/3) | 106
| " | 2x6.0x1.125x0.75 | 10
| C/R B/S (W) | 2x2x6.0x0.75x0.75 | 14
| Ver: D/Wall | 5x5.50x0.75x0.50 | 10
| " | 5x4.50x0.75x0.50 | 8
| " Arech | (5x4.50x0.75x0.75/3) | 4
| Lav: Door | 2x2.50x0.75x7.0 | 26
| Vent: | 2x2.0x0.75x1.50 | 5
| Lintel | 1x10.25x0.75x1.0 | 8
688
|  | Net Qty:- 2771 (-) 688 = | 2083
|  |  | @ | 12674.36 | %cft | 264006.9188 | 264006.9188
11 | Pacca brick work in other than building i/ c strcking of joints on walls upto 20 feet
height in:1:6. (SI, NO: 7( I )e P. 26)
| C/Wall | 1x400.0x0.37x4.50 | 666
| Piller | 80x0.75x0.37x4.50 | 100
766
|  |  | @ | 12346.65 | %cft | 94575.339 | 94575.339
12 | Providing and fixing G.I frames / chowkhats of size 7" x 2" or 4½" x 3" for door using/
window using 20 gauge G.I. sheet i/c welded hinges and fixing at site with necessary hold
fasts filling with cement sand slurry of tation 1:6 and repairing the jambs. The cost also i/c
carriage tools and plants used in making and fixing.(SI, NO: 28/29 P. 98)
Door Using
| C/R door"H" | 2x4.0 | 8
| C/R Door "V" | 2x2x7.0 | 28
| Lav: Door "H" | 2x2.50 | 5
| Lav: Door "V" | 2x2x7.0 | 28
69
|  |  | @ | 228.9 | P.rft | 15794.1 | 15794.1
Windows Using
| C/R Windows "H" | 2x3x2x4.50 | 54
| c/R Windows "V" | 2x3x4x3.67 | 84
138
|  |  | @ | 240.5 | P.rft | 33189 | 33189
13 | Supplying & fixing in position iron / steel grill of ¾" x ¼" size flat iron of approved
designe including painting 3 coats etc. complete wight not tobe less than 3.7 Lbs/sq foot of
finished grill.(SI, NO: 26 P.97)
| C/R Windows | 2x3x3x1.29x3.58 | 83
| Lav: Vent: | 2x2.0x1.50 | 6
89
|  |  | @ | 180.5 | P.sft | 16064.5 | 16064.5
14 | Making & fixing steel grated doors with 1/16"thick sheeting including angle iron frame 2"x2"
⅜" and ¾" square bars 4" centre to centre with locking arrangement.(SI, NO: 24 P. 97)
| Main Gate | 1x10.0x6.0 | 60
|  |  | @ | 726.72 | P.sft | 43603.2 | 43603.2
Page No: 05
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
15 | Cement plaster 1:6 upto 20" height.(b) ½" thick. (SI, NO: 13(b) P. 58)
| C/R (I/S) Wall | 2x2x20.0(11.0+13.0) | 960
| " | 2x2x16.0(11.0+13.0) | 768
| Ver: (I/S) Wall | 1x2x41.125(11.0+13.0+11.0/3) | 959
| Ver: S/Wall | 1x2x7.0x11.0 | 154
| Ver: F/S O/Side | 1x43.37x(11.0+13.0+11.0/3) | 506
| C/R B/S Offset | 2x2x4.50x(11.013.0/2) | 216
| Ver: Steps | 1x15.0x6.50 | 98
| C/Wall (I/S) | 1x400.0x1.50 | 1800
| Piller | 1x80x2.0x0.37x4.50 | 266
| Plinth (I/S) | 1x400.0x1.50 | 600
| Lav: B | 2x2x(5.0+4.0)x(8.0+7.75) | 284
| Passage Wall | 1x10.25x8.0 | 82
| Plinth | 1x2x(10.625+10.625)x1.50 | 80
| Lav: Steps | 1x4.0x1.50 | 64
|  | Net Qty:- 7158 - 451 = | 6707
|  |  | @ | 2206.6 | %sft | 147996.662 | 147996.662
16 | Cement plaster 1:4 upto 20" height.(a) ⅜" thick. (SI, NO: 11(a) P. 58)
|  | Qty: same as above item No:(15) | 6707
|  |  | @ | 2197.52 | %sft | 147387.6664 | 147387.6664
17 | Cement plaster 1:4 upto 20" height.(c) ¾" thick. (SI, NO: 11(c) P. 58)
| C/R Plinth Pattas | 1x2x(43.75+26.75)x0.50 | 71
| Corner | 2x5x0.50(11.0+13.0/2) | 60
| C/Wall Pattas | 1x2x400.0x0.50 | 400
| " Corner | 4x4x0.50x4.0 | 32
| Lav: Block | 1(10.25+5.50)0.50 | 81
| Roof | 1(10.25+10.25+2.50+5.50) | 32
| Corner | (1+3)x0.50x7.50 | 15
691
|  |  | @ | 2590.5 | %sft | 17900.355 | 17900.355
18 | Cement pointing struck joints on walls.Ratio 1:2. (SI, NO: 19(a) P. 59)
| C/R B/S | 1x43.37(11.13+11.0/3) | 506
| F W/S | 1x2x25.37x11.0 | 558
| Ver: C/R Plinth (O/S) | 1x2x(43.37+26.75)2.0 | 280
Page No: 06
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
| C/Wall O/S | 1x400.0x4.0 | 1600
| " Plinth (O/S) | 1x400.0x1.25 | 500
| Lav: Block (O/S) | 1x10.25x7.75 | 79
| " | 1x2x5.50(7.75+8.0/2) | 87
| P. Wall (O/S) | 1(10.25+3.75)6.0 | 84
3694
Deduction
| C/R (B/S) "W" | 2x2x5.50x(11+13/2) | 264
| Lav: Vent: | 2x3.0x2.0 | 12
276
|  | Net Qty:- 3694 - 276 = | 3418
|  |  | @ | 1287.44 | %sft | 44004.6992 | 44004.6992
19 | Cement concrete plain including placing compcting, finishing and curing, complete (including
screening and washing of stone aggregate without shuttering.). (SI, NO: 5 P.18)
Ratio 1:3:6
| C/R Floor | 2x20.0x16.0x0.125 | 80
| Ver: | 1x41.125x7.0x0.125 | 36
| Lav: F/Bed | 2x5.0x4.0x0.12 | 48
164
|  |  | @ | 12595 | %cft | 20655.8 | 20655.8
20 | Providing and fixing ⅜" thick marble tiles of approved quality & colour shade size
8" x 4/6" x 4" in dado skirting & facing removal / tucking of existing plaster surface etc.
over ½" thick of cement mortar 1:3 setting mortar base including filling the joints &
washing the tiles with white cement slurry, current, finishing cleaning and polishing etc.
complete.(SI,NO: 68 P.55)
| C/R floor | 2x20.0x16.0 | 640
| Ver: floor | 1x41.125x7.0 | 288
| C/R Door Sill | 2x4.0x1.13 | 9
| Ver: Sill | 2x5.50x1.13 | 12
949
|  |  | @ | 186.04 | P.sft | 176551.96 | 176551.96
21 | Notice board made with cement.(SI, NO: 1 P. 100)
| C/R Balck Board | 2x8.0x4.0 | 64
64
|  |  | @ | 58.11 | P.sft | 3719.04 | 3719.04
22 | Providing and laying 1" thick topping cement concrete (1:2:4) including surface finishing and
dividing into panels. (SI, NO: 16 P. 47)
"A" | 1/1/2" thick
| Ver: C/R Roof | 1x46.37x29.375 | 1362
| Lav: | 1x12.25x8.50 | 104
1466
|  |  | @ | 2548.29 | %sft | 37357.9314 | 37357.9314
"B" | 2" thick
| Lav: Passage | 1x11.50x3.0 | 35
35
|  |  | @ | 3275.5 | %sft | 1146.425 | 1146.425
23 | 1st class deodar wood wrought. Joinery in doors and windows etc. fixed in position including
chowkats hold fasts h inges, iron tower blts. Chocks cleats, handles and cords with hooks,
etc. Deodar panelled or panelled and glazed or fully glazed. 1¾" thick. (SI, NO: 7(b) P.65)
only shuttrs.
| C/Room Door | 1x2x3.67x6.71 | 49
| " Windows | 2x3x3x1.29x3.67 | 85
| Lav: Door | 2x2.25x6.75 | 30
164
|  |  | @ | 1273.66 | P.sft | 208880.24 | 208880.24
Page No: 07
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
24 | Laying floor of approved with glazed tile ¼" thick cement 1:2 over ¾" thick cement
mortar 1:2 complete. (SI, NO: 24 P. 48)
| Lav: Floor | 2x5.0x4.0 | 40
| D/Sill | 2x2.25x0.83 | 4
44
|  |  | @ | 27678.86 | %sft | 12178.6984 | 12178.6984
25 | White glazed tile ¼" thick dado jointed in white cment and laid over 1:2 cement sand
mortar ¾" thick including finishing. (SI, NO: 37 P.50)
| Lav: I/S | 2x2x(5.0+4.0)x4.0 | 144
| Door Offset | 2x2x0.50 | 4
152
Deduction
| Lav: Door | 2x2.50x3.0 | 15
|  | Net Qty:- 152 - 15 = | 137
|  |  | @ | 28299.3 | %sft | 38770.041 | 38770.041
26 | Providing & laying HALLA or pattern tiles glazed 6"x 6" x½" on floor or wall facing in
required floor & pattern of STILE specification jointed in white cement & pigment over a
base of 1:2 grey cement mortar ¾" thick including washing & filling of joins with slaurry
of white cement and pigment in desired shape with finishing claning & cost of wax polish etc.
complete including cutting tiles to proper profile.(SI, NO: 61 P. 54)
| Ver: F/s Beam | 1x43.37x1.0 | 43
| Piller | 6x0.50x9.50 | 29
72
|  |  | @ | 47651.56 | %sft | 34309.1232 | 34309.1232
27 | Extra labour rate for making cement plaster pattas/band around straight or carved opening
& around the edges of roof slabs the width not less than 6" with fine finshing as directed
by Engineer Incharge. (SI, NO: 35 P.61)
| Corner | 5x2x11.0 | 110
| C/R Plinth | 1x2(43.75+26.75) | 141
| C/Wall Pattas | 1x2x400.0 | 800
| " | 4x4.0x4.0 | 64
| Lav: P.Wall | 1x2(12.62+11.625) | 49
| Roof | 1(10.25+5.50+5.50+10.25) | 32
| Corner | (3+1)x7.75 | 31
1227
|  |  | @ | 19.36 | P.rft | 23754.72 | 23754.72
28 | Two coats of bitumen laid hot using 34 lbs for %sft over roof and blinded with sand at one
Cft per % Sft. (SI, NO: 13 P.41)
| C/Room Over Roof | 1x46.375x29.375 | 1362
1362
|  |  | @ | 1887.4 | %sft | 25706.388 | 25706.388
29 | Supplying & fixing caligraphy tiles of approved size in required colour & design of tiles
specification jointed in white cement & pigment over a base of 1:2 Grey cement mortar 3/4"
thick & i/c washing & filling of joints with slurry white cement & pigment in desired shape
with finishing cleaning & coat of wax polsh etc. complete i/c cutting tiles to proper profile
including carrage upto site of work. (R.A)
| Ver: F/S O/S | 1x6.0 | 6 Nos
6 Nos
|  |  | @ |  | P.sft |  | 0
Page No: 08
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
30 | Whit washing.(SI,NO: 26 P.60)
Three Coats.
| C/R (I/S) | 2x20.0x16.0 | 640
| Ver: F/S O/S | 1x41.125x7.0 | 288
| Tie Beam | 2x2x20.0x1.75 | 140
| Roof Chajja | 1x2x46.37x1.50 | 139
| Side | 1x2x26.37x1.50 | 79
| Lav: | 2x5.0x4.0 | 40
1326
|  |  | @ | 829.95 | %sft | 11005.137 | 11005.137
31 | Extra labour rate making grooves of 1" x ¼" or ¾" x ¼" plastered surface with true
edges both vertically & horizontly with uniform depth & with groove base smoothly finished
etc. complete as per instruction of Engineer Incharge.(SI,NO: 34 P.61)
| Ver: F/S | 2x31.0x2.0 | 124
| " | 5x31x1.25 | 194
| " (V) | 5x57x0.25 | 71
389
|  |  | @ | 7.71 | P.rft | 2999.19 | 2999.19
32 | Primary coat of chalk under distempering.(SI,NO: 23 P.59)
|  | Qty: Same as Item No (16) | 6707
|  |  | @ | 442.75 | %sft | 29695.2425 | 29695.2425
33 | Distempering. (SI,NO: 24 P.60)
Three Coats.
|  | Qty same Item NO. (32) | 6707
|  |  | @ | 1079.65 | %sft | 72412.1255 | 72412.1255
34 | Colour washing.(SI,NO: 25 P.60)
Two Coats.
|  | Qty Same Item No: (18) | 3416
3416
|  |  | @ | 859.9 | %sft | 29374.184 | 29374.184
35 | Colour washing of two coats over one coat white washed surface.(SI,NO: 25 P.60)
|  | Qty Same Item No. (17) | 616
616
|  |  | @ | 416.63 | %sft | 2566.4408 | 2566.4408
32 | Painting doors and windows any type.three coats. (SI,NO: 4(b/c) P. 76)
NEW SURFACE
| C/R Door | 2x2x4.0x7.0 | 112
| " Windows | 2x3x2x4.50x4.0 | 216
| Lav: Door | 2x2x2.50x7.0 | 70
398
|  |  | @ | 1160.06 | %sft | 4617.0388 | 4617.0388
Page No: 09
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
33 | Painting Guard bars, gates iron bars gratings, railings including standard barces (etc) and
similar open work. (SI,NO: 4(d) P. 76)
NEW SURFACE
| M.Gate | 1x2x10.0x6.0 | 120
120
|  |  | @ | 674.6 | %sft | 809.52 | 809.52
[6 empty] | 2760022 | 5919498.5289
Mosaic tiles availbe in the market is of poor quaility and not durable heance of Provision of Marble
3/8" thick has been provided keeping in view the estibility of flooring w/o exceeding
of over all aproved cost.
|  | District Officer |  |  | Deputy District Officer
| Sub-Engeenir | Education works |  |  | Education works
|  | Works & services Department |  |  | Works & services Department
|  | Shaheed Benazir Abad |  |  | Nawabshah.
8 | Applying floating caot of cement 1/32" thick. (SI, NO: 14 P.59)
| Ver: | 1x68.50x7.0 | 480
480
|  |  | @ | Rs.361.08 | %sft | Rs. 1733.00
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
17 | Applying chemical polishing on exising moasic / arble flooring / dado i/c cleaning grinding
with carborandum stone / sand paper and applying chemical polish as per requirement
(SI,NO:70 P.55)
| Office | 1x10.0x14.0 | 140
140
|  |  | @ | Rs.16.62 | P.sft | Rs. 2327.00
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
24 | Borrowpit excavation undressed lead upto 100ft. (SI, NO: 3 P. 1)
Ordinarry soil.
| I/Side C/yard | 1x25.0x13.0x0.50 | 2145
| " | 1x96.0x65.0x0.50 | 3088
| " | 1x32.50x30.75x0.50 | 500
3751
|  |  | @ | Rs.847.00 | %0cft | Rs. 3177.00
25 | Laying Earth work compaction (soft, ordinary or hard soil) (SI, NO: 13 P. 3)
|  | Qty same as above item(24) | 3751
|  |  | @ | Rs.123.40 | %0cft | Rs. 463.00
26 | Scraping ordinary distemper, oil, bound distemper or paint on walls. (SI,NO: 54(b) P.15)
| Class Room I/Side | 4x2x(18+14)x10.0 | 2560
| Ver: I/Side | 1x2(68.50+7)x10.0 | 1510
| Office I/Side | 1x2x(10+14)x10.0 | 480
4550
|  |  | @ | Rs.108.90 | %sft | Rs. 4555.00
27 | Whit washing.(SI,NO: 26 P.60)
Two Coats.
| Lav: Ceiling | 3x5.0x5.0 | 75
| " Chajja | 1x2x20.0x1.0 | 40
| " | 1x2x6.50x1.0 | 13
| C/Room | 2x89.0x1.50 | 267
| " | 2x25.0x1.50 | 75
470
|  |  | @ | Rs.89.74 | %sft | Rs. 422.00
29 | Painting doors and windows any type.three coats. (SI,NO: 4(b/c) P. 76)
OLD SURFACE
| C/room Door | 5x2x4.0x7.0 | 280
| " Windows | 14x2x4.50x4.0 | 504
| " | 1x2x3.0x4.0 | 24
| " Door | 3x2.50x7.0 | 53
861
|  |  | @ | Rs.550.36 | %sft | Rs. 4739.00
30 | Painting Guard bars, gates iron bars gratings, railings including standard barces (etc) and
similar open work. (SI,NO: 4(d) P. 76)
NEW SURFACE
| Main Gate | 1x2x10.0x6.0 | 120
120
|  |  | @ | Rs.584.54 | %sft | Rs. 701.00
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
33 | Painting Guard bars, gates iron bars gratings, railings including standard barces (etc) and
similar open work. (SI,NO: 4(d) P. 76)
OLD SURFACE
| W Grill | 14x3x1.25x3.75 | 197
| " | 1x2x1.25x3.75 | 9
206
|  |  | @ | Rs.326.13 | %sft | Rs. 672.00
38 | Preparing surface & painting with Emulision paint.(SI,NO: 29 P.78)
| C/R I/Side | 4x2x(18+14)x3.0 | 768
| Ver: I/Side | 1x2x(68.50+7)x3. | 453
| Office I/Side | 1x2x(10+14)x3.0 | 144
1365
|  |  | @ | Rs.608.53 | %sft | Rs. 8306.00
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
39 | Duroceming of a approved make and shade in 3 coats wall serubbed into the surface i/c
finishing sommth at any height any floor.(SI,NO: 33 P.60)
| Ver: F/Side | 1x86.0x12.0 | 1032
1032
|  |  | @ | Rs.643.30 | %sft | Rs. 6639.00
Total Rs:- 461227.00
11 | Supplying & fixing Girder @ site.
| Ver: Roof | (7.0x8.0x8.0x/112) | 4
|  |  | @ | Rs.2400.00 | P.cwt | Rs. 9600.00
12 | Supplying & fixing T-Iron @ site.
| T= | (5x40.0x2.35/112) | 4.196
|  |  | @ | Rs.2300.00 | P.cwt | Rs. 9650.00
13 | Erecting rolled steel beams or old rails in roof etc. erection & fixing position.(SI,NO: 6 P.96)
|  | Qty Item No: 11+12 = | 8.196
|  |  | @ | Rs.76.71 | P.cwt | Rs. 629.00
14 | 2nd class tile roofing cosisting of 4" earth & 1" mud plaster with gobri leeping over ½"
thick cement plaster. 1:6 with 34 lbs. of hot bitumen coating sand blindd provided over one
layer of 12" x6" x2" tiles laid in 1:6 cement mortar including 1:2 cement pointing under
neath of tils complete including curing etc.(SI,NO: 2 P.38)
| Ver roof | 1x40.0x7.50 | 300
|  |  | @ | Rs.2779.87 | %sft | Rs. 8340.00
17 | Providing and fixing ⅜" thick marble tiles of approved quality & colour shade size
8" x 4/6" x 4" in dado skirting & facing removal / tucking of existing plaster surface etc.
over ½" thick of cement mortar 1:3 setting mortar base including filling the joints &
washing the tiles with white cement slurry, current, finishing cleaning and polishing etc.
complete.(SI,NO: 68 P.55)
| C/R floor | 2x18.0x14.0 | 504
| Veranda floor | 1x37.75x6.0 | 227
| Door sill | 2x4.0x1.25 | 10
|  | 2x2.0x(18.0+14.0)x0.50 | 64
805
|  |  | @ | Rs.74.65 | P.sft | Rs. 60093.00
20 | Plain G.I. sheet iron spouts fixed in place including painting. (SI,NO: 25 P.42)
| Over Roof | 2 Nos | 2 Nos
|  |  | @ | Rs.142.10 | Each | Rs. 284.00
25 | Providing and laying single per layer of polythene sheet 0.13 mm thick for water proffing as
per specification & instructions of Engineer Incharge.(SI,NO: 38 P.44)
| Over roof | 1x40.0x7.50 | 300
|  |  | @ | Rs.3.64 | P.sft | Rs. 1092.00
29 | Lime Neru plaster 1:2 with fine finsh of Neru plaster mixed with 10% of cement.
(SI,NO: 7 P.58)
| Over Roof | 1x37.75x22.0 | 831
|  | ½" thick | @ | Rs.613.58 | %sft | Rs. 2099.00
30 | Mud plaster on floor or roof 1" thick. (SI,NO: 2 P.57)
|  | 1x37.75x16.0 | 604
|  |  | @ | Rs.224.75 | %sft | Rs. 1357.00
35 | Colour washing.(SI,NO: 25 P.60)
Two Coats.
| C/R O/S | 1x2.0x(40.0+25.50)x11.0 | 1397
|  |  | @ | Rs.103.79 | %sft | Rs. 1450.00
3 | Dismantling cement concrete reinforced separating reinforcement from concrete cleaning
and straightening the same. (SI, NO: 20 P.11)
| C/R roofing slab | 1x28.50x25.50x0.42 | 305
| T-beam | 1x22.25x0.75x1.50 | 25
330
|  |  | @ | Rs.2613.60 | %cft | Rs. 8626.00
4 | Removing door with chowkat. (A, P.NO:13)
| C/R Door | 01 Nos
01 Nos
|  |  | @ | Rs.82.28 | P.No | Rs. 82.00
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
26 | Borrowpit excavation undressed lead upto 100ft. (SI, NO: 3 P. 1)
| C/ wall I/side | 1x50.0x40.0x1.0 | 2000
|  |  | @ | Rs.847.00 | %0cft | Rs. 1694.00
27 | Laying Earth work compaction (soft, ordinary or hard soil) (SI, NO: 13 P. 3)
|  | Qty asme as above item(26) | 2000
|  |  | @ | Rs.123.40 | %0cft | Rs. 247.00
28 | Scraping ordinary distemper, oil, bound distemper or paint on walls. (SI,NO: 54(b) P.15)
| C/R I/Side wall | 1x2x(20.0+16.0)x(11.50+11.0)/2 | 810
| C/R I/Side wall | 1x2x(20.0+6.0)x11.50+11.0)/2 | 594
| Ver: F/Side O/side | 1x22.25x11.50 | 256
| Deduction |  | 1660
| Door | 1x4.0x7.0 | 28
| Windows | 1x4.50x4.0 | 18
46
| Net Qty. | 1660-46.00= | 1614
|  | Allowed 40% | 646
|  |  | @ | Rs.108.90 | %sft | Rs. 703.00
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
29 | Whit washing.(SI,NO: 26 P.60)
Two Coats.
| C/R I/side | 1x20.0x16.0 | 320
| Veranda | 1x20.0x6.0 | 120
| Tie Beam | 1x2.0x16.0x1.50 | 48
488
|  |  | @ | Rs.89.74 | %sft | Rs. 438.00
30 | Distempering. (SI,NO: 24 P.60)
Two Coats.
|  | Qty same item No: I (28) | 1614
1614
|  |  | @ | Rs.204.22 | %sft | Rs. 3296.00
31 | Colour washing.(SI,NO: 25 P.60)
Two Coats.
| C/room O/side 1x2x(22.25+25.37)x(11.50+11.0)/2 |  | 1071
|  | Qty same item No: I (20) | 1800
2871
|  |  | @ | Rs.103.79 | %sft | Rs. 2980.00
32 | Painting doors and windows any type.three coats. (SI,NO: 4(b/c) P. 76)
NEW SURFACE
| C/Room Door | 1x2x4.0x7.0 | 56
56
|  |  | @ | Rs.978.95 | %sft | Rs. 548.00
OLD SURFACE
| C/Room "W" | 3x2.0x4.50x4.0 | 108
108
|  |  | @ | Rs.550.36 | %sft | Rs. 594.00
33 | Painting Guard bars, gates iron bars gratings, railings including standard barces (etc) and
similar open work. (SI,NO: 4(d) P. 76)
NEW SURFACE
| M.Gate | 1x2.0x8.0x6.0 | 96
96
|  |  | @ | Rs.584.54 | %sft | Rs. 561.00
34 | Providing & laying HALLA or pattern tiles glazed 6"x 6" x½" on floor or wall facing in
required floor & pattern of STILE specification jointed in white cement & pigment over a
base of 1:2 grey cement mortar ¾" thick including washing & filling of joins with slaurry
of white cement and pigment in desired shape with finishing claning & cost of wax polish etc.
complete including cutting tiles to proper profile.(SI, NO: 61 P. 54)
| Main Gate Piller | 2x1.50x7.00 | 21
21
|  |  | @ | Rs.17091.69 | %sft | Rs. 3589.00
Total Rs:- 310601.00
Deputy District Officer
| Sub-Engeenir |  |  |  | Education works
Works & services Department
Nawabshah.
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
15 | Erection & removal of centering for R.C.C. or plain cement concrete works of Deodar Wood
(2nd-class).(SI,NO: 18b (ii) P.21)
| Qty same item No: 14(B) 810.0/0.50 x 2.0 |  | 3240
|  |  | @ | Rs.1405.75 | %sft | Rs. 45546.00
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
Deduction
| Lav: I/S Wall | 1x2.0x2.0(5.0+4.0)x3.0 | 108
| Passge | 1x(9.50+3.0+9.50)3.0 | 66
174
|  | Net Qty 793-174= | 619
|  |  | @ | Rs.536.14 | %sft | Rs. 3319.00
20 | Painting doors and windows any type.three coats. (SI,NO: 4(b/c) P. 76)
| Lav: Door | 1x2.0x2.0x2.50x7.0 | 70
|  |  | @ | Rs.978.95 | %sft | Rs. 685.00
21 | Whit washing.(SI,NO: 26 P.60)
Three Coats.
| Lav: slab | 1x2.0x4.0x5.0 | 40
|  |  | @ | Rs.115.18 | %sft | Rs. 46.00
22 | Primary coat of chalk under distempering.(SI,NO: 23 P.59)
| Passge | 2x2.0x(4.0+5.0)x(7.75+7.50/2) | 275
| " | 1x(9.50+3.0+9.50)x(+6.0+7.5/2) | 149
| O/S | 1x(6.50+10.50+6.50)x7.50 | 176
| " | 1x(3.75+6.75)x6.0 | 63
663
|  |  | @ | Rs.58.85 | %sft | Rs. 390.00
23 | Distempering. (SI,NO: 24 P.60)
Three Coats.
|  | Qty Same item No: (22) | 663
|  |  | @ | Rs.263.51 | %sft | Rs. 1747.00
Deputy District Officer
| Sub-Engeenir |  |  |  | Education works
Works & services Department
Nawabshah.

## Material
MATERIAL STATEMENT
Name of Work:- Repair / Renovation, Rehabilitation, of Primary / Middle / High Schools in Distt: Shaheed Benazirabad (ADP- 475 , 2016-17 Programme) @ GBPS Chakar Ali Siyal @ Village Gul Hassan Siyal Tal: Daur
S.No | Particulars | Quantity | Cement | Sand | Stone | Bajri | Steel | Brick | Filling
1 | Cement Concrete brick stone 1:5:10 | 409 | 32 | 200 | 400
2 | Pacca Brick Work 1:6 | 2148 | 74 | 552 |  |  |  | 28998
3 | Reinforced Cement Concrete 1:2:4 | 753 | 133 | 331 |  | 663
4 | Fabrication | 33.616/20 |  |  |  |  | 1.68
5 | Cement Plaster 1:6 1/2" thick | 3848 | 20 | 154
6 | Cement Plaster 3/8" ratio 1:4 | 3848 | 22 | 115
7 | Cement Plaster 3/4" ratio 1:4 | 1242 | 14 | 69
8 | Cement Pointing 1:2 | 1350 | 10 | 24
9 | C.C Topping 2" Thick Ratio 1:2:4 | 1805 | 54 | 134 |  | 265
10 | C.C Topping 3" Thick Ratio 1:2:4 | 696 | 31 | 77 |  | 153
11 | DPC 1:2:4 3" Thick | 339 | 15 | 37 |  | 75
12 | Earth filling | 2586 | [6 empty] | 2586
Qunatity |  |  | 405 | 1693 | 400 | 1156 | 1.68 | 28998 | 2586
Rate |  |  | 68.13 | 4288.44 | 4158.2 | 4744.28 | 760 | 930.14 | 407
Amount |  |  | 27593 | 72603 | 16633 | 54844 | 1277 | 26972 | 10525
Total Amount Rs: 210447.00
Assistant Engineer
| Sub-Engeenir | [5 empty] | Education Works Sub-Division
Nawabshah.

## Sumary o Cost
Summry of Cost
Name of Work:- |  | Repair / Renovation, Rehabilitation, of Primary / Middle / High Schools in Distt: Shaheed Benazirabad (ADP- 475 , 2016-17 Programme) @ GBPS Chakar Ali Siyal @ Village Gul Hassan Siyal Tal: Daur
Part "A" Civil Work
| 1 | Cost of Schedule Item |  |  | Rs. | 1545130
| 2 | Cost of Non-Schedule Item |  |  | Rs. | 278449
| 3 | Add: Carriage of Material |  |  | Rs. | 210447
|  |  | Total Part "A" |  | Rs. | 2034026 | 1378873
Part "B" W/S & S/Fitting
| 4 | Cost of Schedule Item |  |  | Rs. | 17672
| 5 | Cost of Non-Schedule Item |  |  | Rs. | 18470
|  |  | Total Part "B" |  | Rs. | 36142
| 6 | Add: 2.0% Contigency on S.I |  |  | Rs. | 30903
|  |  | G. Total (A+B) |  | Rs. | 2101071
|  |  | Say as Rs:- |  | Rs. | 2.101 (M)
| Sub: Engineer |  |  | Assistant Engineer
Education Works Sub-Division
Nawabshah

## Financial Reviv
Financial Review
Name of Work:- Repair / Renovation, Rehabilitation, of Primary / Middle / High Schools in Distt: Shaheed Benazirabad (ADP- 475 , 2016-17 Programme) @ GBPS Chakar Ali Siyal @ Village Gul Hassan Siyal Tal: Daur
S.No. | Description | PC-I Cost | Amount Taken for Estimate | Amount of Technical Sanction under submission
01) | Main Building | 1522560 | 1522560 | 2101000
02) | W/S & S/F | 37440 | 37440
03) | C/Wall | 419400 | 419400
04) | Main Gate | 47500 | 47500
05) | Electrification | 129792 | __
| Total:- | 2156692 | 2026900 | 2101000
| Say" Rs. | 2.157 (M)
Excess/Saving on PC-I = 2026900.00 - 2101000.00 = 74100.00 Excess
i.e 74100 x 100 =3.65% Excess from PC-I provision which is within 15% permissible Limit.
. 2026900
Assistant Engineer
| Sub-Engineer |  | Education Works Sub-Division
Nawabshah
02) | Electrification | 67396
03) | W/S & S/F | 34860
04) | C/Wall with Gate | 173100
05) | Path | 125000
| Total:- | 4713740 | 1522560 | 2101000

## Rough Cost
Rough Cost Estimate
Name of Work:- Repair / Renovation, Rehabilitation, of Primary / Middle / High Schools in Distt: Shaheed Benazirabad (ADP- 475 , 2016-17 Programme) @ GBPS Chakar Ali Siyal @ Village Gul Hassan Siyal Tal: Daur
S.NO:- | Description | Plinth Area |  | Cost of Construction |  | Cost of W/S & S/F |  | Cost of Electric |  | Total
|  |  |  | Rate | Amount | Rate | Amount | Rate | Amount
1 | Main Building i/c Lav: Block | 1248 | Sft | 1220 | 1522560 | 30 | 37440 | 104 | 129792 | 1689792
2 | C/Wall | 300 | Rft | 1398 | 419400 |  |  |  |  | 419400
3 | Main Gate | 1 | No | 47500 | 47500 |  |  |  |  | 47500
[9 empty] | Total:- | 2156692
[8 empty] | Say: in Million |  | 2.157 (M)
Assistant Engineer
Education Works Sub-Division
[5 empty] | Nawabshah |  |  |  | Executive Engineer
Education Works Division
Shaheed Benazirabad

## W S & S F
SCHEDULE "B" W S & S F
Name Of Work:- Repair / Renovation, Rehabilitation, of Primary / Middle / High Schools in Distt: Shaheed Benazirabad (ADP- 475 , 2016-17 Programme) @ GBPS Chakar Ali Siyal @ Village Gul Hassan Siyal Tal: Daur
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
1 | P/F equating type white glazed of flushing cistern with internal fitting & flush pipe with
with bend & making requisite number of holes in wall plinth & floor for pipe connection &
making good in cement concrete 1:2:4
with 4" dia white glazed earthen ware trap & plastic thumble.(SI,NO: 1 - B (ii) P.1)
| 1 | NO. | 1 | 4846.6 | Each | 4846.6
2 | S/F long BIB - COCK of superior quality with C.P. head ½" dia. (SI,NO: 13(a) P.19)
| 2 | NO. | 2 | 1109.46 | Each | 2218.92
3 | Providing & fixing handle volves(china) (SI,NO: 5 P.17)
¾" dia
| 1 | NO. | 1 | 271.92 | Each | 271.92
4 | Providing G.I.pipes specials and clamps etc i/c fixing cutting and fitting complete with and
i/c the cost of breaking through walls and roof making good etc painting two coats after
cleaning the pipe etc with whit zink paint with pigment to match the colour of the building &
testing with water to a pressure head of 200 feet and handling.(SI,NO: 1 P.11)
"A" | ½" dia
| 20 | rft | 20 | 73.21 | P.rft | 1464.2
"B" | ¾" dia
| 30 | rft | 30 | 95.79 | P.rft | 2873.7
5 | Providing R.C.C. pipes with collers class "B" digging the trnches to requird and fixing in
position i/c cutting fitting and jointing with maxphaltic composition and cement mortor 1:1
and testing with water pressure to a head of 4" feet above the top of heighst and refilling
with excavated staff.(SI,NO.2 P.24)
6" dia
| 6 | rft | 6 | 199.25 | P.rft | 1195.5
6 | Boring for tube well in wall bearing nails from ground level upto 100 ft.or 30.5 meter depth
i/c making and with drawing of casing pipe.(SI,NO: 1 P. 41)(PHE)
| 30 | rft | 30 | 160 | P.rft | 4800
7 | Providing Fixing water pumping set with Diamond moter and pump 1HP 1400PRM Single Phase
220 volts 2"x1/1/2" suction and deilevary 40ft head i/c base Plate and also making C:C: 1:3:6
plate form of required base size and fixing with nuts & bolts etc. complete in all respects.
| 1 | NO. | 1 | 18470 | Each | 18470
[5 empty] | Total:- | 36142
Executive Engineer
| Contractor |  |  |  | Education Works Division
Shaheed Benazir Abad
2 | P/F 6"x2" or 6"x3" C.I.floor trap of the approved self cleaning design with C.I.screw/down
grating with or without a vent arm complet with and i/c making rquisite number of holes
in walls plinth & floor for pipe cinnections & making good in CC 1:2:4.(SI,NO: 23 P.05)
| 1 | NO. | 1 | 2042.43 | Each | 2042.43
3 | Providing G.I.pipes specials and clamps etc i/c fixing cutting and fitting complete with and
i/c the cost of breaking through walls and roof making good etc painting two coats after
cleaning the pipe etc with whit zink paint with pigment to match the colour of the building &
testing with water to a pressure head of 200 feet and handling.(SI,NO: 1 P.11)
"A" | ½" dia
| 20 | rft | 20 | 64.88 | P.rft | 1297.6
"B" | ¾" dia
| 25 | rft | 25 | 86.36 | P.rft | 2159
4 | Providing R.C.C. pipes with collers class "B" digging the trnches to requird and fixing in
position i/c cutting fitting and jointing with maxphaltic composition and cement mortor 1:1
and testing with water pressure to a head of 4" feet above the top of heighst and refilling
with excavated staff.(SI,NO.2 P.21)
6" dia
| 15 | rft | 15 | 199.25 | P.rft | 2988.75
5 | Boring for tube well in wall bearing nails from ground level upto 100 ft.or 30.5 meter depth
i/c making and with drawing of casing pipe.(SI,NO: 1 P.36)(PHE)
| 60 | rft | 60 | 160 | P.rft | 9600
6 | S/F cancealed TEE STOP COCK of sup: quality with crystal head ½" dia.(SI,NO:14(b) P.15)
| 1 | NO. | 1 | 843.92 | Each | 843.92
7 | S/F long BIB - COCK of superior quality with C.P. head ½" dia. (SI,NO: 13(a) P.19)
| 2 | NO. | 2 | 1109.46 | Each | 2218.92
8 | P/F 4" dia C.I. soil & vent pipes i/c cutting and fitting and extra painting to match the
colour of the building(SI,NO: 1 P.8)
| 10 | rft | 10 | 333.29 | P.rft | 3332.9
9 | P/F 4"x4" dia C.I. branch of the required degree with access floor rubber washer 3/8" tick
and bolts and nuts extra painting to match the colour of the building. (SI,NO: 5 P.8)
| 2 | NO. | 2 | 224.6 | Each | 449.2
10 | P/F in position Nyloon connections complete with 1/2"dia brass stop cock with pair of brass
nuts and lining joints to nyloon connection.(SI,NO: 23 P.6)
| 2 | NO. | 2 | 447.15 | Each | 894.3
11 | Providing & fixing handle volves(china) (SI,NO: 8 P.14)
"A" | ½" dia
| 2 | NO. | 2 | 200.42 | Each | 400.84
"B" | ¾" dia
| 2 | NO. | 2 | 271.92 | Each | 543.84
[5 empty] | Total:- | 36465
Non-Schedule Items
12 | P/F water pumping set 1H.P. 2800 PRM Single phase 220 volts 1-1/4"x 1" suction & delievery
40 feet head i/c base plat form required size and fixing with nuts and both complete in all
respect. (SI,NO: 11 P.30)
| 1 | NO. | 1 | 5494.59 | Each | 5494.59
13 | P/F Plastic Poly Pipe Complete. (N.S.I)
| 80 | rft | 80 | 25 | P.rft | 2000
[5 empty] | Total:- | 7494.59
Executive Engineer
| Contractor |  |  |  | Education Works Division
Shaheed Benazir Abad
6 | Add: extra labour for concealed G.I.pipe & fiiting i/c making recess in the wall for pipe and
making good in cement mortor etc complete. (SI,NO: 2, P.11)
| 25 | Rft | 25 | 7.82 | P.rft | 195.5
Page NO: 02
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
9 | Providing Fixing water pumping set with Rehber moter and pump 1HP 1400PRM Single Phase
220 volts 2"x1/1/2" suction and deilevary 40ft head i/c base Plate and also making C:C: 1:3:6
plate form of required base size and fixing with nuts & bolts etc. complete in all respects.
| 1 | NO. | 1 | 14709 | Each | 14709
[5 empty] | Total:- | 35566
| Sub: Engineer |  |  | Assistant Engineer
Education Works Sub-Division
Nawabshah
6 | Boring for tube well in wall bearing nails from ground level upto 100 ft.or 30.5 meter depth
i/c making and with drawing of casing pipe.(SI,NO: 1 P.36)(PHE)
| 30 | rft | 30 | 160 | P.rft | 4800
[5 empty] | Total:- | 20070
Executive Engineer
| Contractor |  |  |  | Education Works Division
Shaheed Benazir Abad
Executive Engineer
| Contractor |  | Education Works Division
Shaheed Benazirabad
Executive Engineer
| Contractor |  |  |  | Education Works Division
Shaheed Benazirabad
2 | P/F 6"x2" or 6"x3" C.I.floor trap of the approved self cleaning design with C.I.screw/down
grating with or without a vent arm complet with and i/c making rquisite number of holes
in walls plinth & floor for pipe cinnections & making good in CC 1:2:4.(SI,NO: 23 P.05)
|  | 2 NO. | @ | Rs.244.35 | Each | Rs. 489.00
3 | S/F long BIB - COCK of superior quality with C.P. head ½" dia. (SI,NO: 15(a) P.15)
|  | 2 NO. | @ | Rs.211.00 | Each | Rs. 422.00
4 | P/F 4" dia C.I. soil & vent pipes i/c cutting and fitting and extra painting to match the
colour of the building(SI,NO: 1 P.8)
|  | 12 NO. |  | Rs.103.40 | P.rft | Rs. 1241.00
5 | Providing & Fixing 4" dia C.I.Terminal guard including extra painting to match the colour of
the building. (SI,NO: 11 P.9)
|  | 2 NO. | @ | Rs.115.10 | Each | Rs. 230.00
6 | S/F cancealed TEE STOP COCK of sup: quality with crystal head ½" dia.(SI,NO:14(b) P.15)
|  | 2 NO. | @ | Rs.252.10 | Each | Rs. 504.00
7 | Providing G.I.pipes specials and clamps etc i/c fixing cutting and fitting complete with and
i/c the cost of breaking through walls and roof making good etc painting two coats after
cleaning the pipe etc with whit zink paint with pigment to match the colour of the building &
testing with water to a pressure head of 200 feet and handling.(SI,NO: 1 P.11)
| ½" dia | 50 rft | @ | Rs.25.20 | P.rft | Rs. 1260.00
| ¾" dia | 50 rft | @ | Rs.34.40 | P.rft | Rs. 1720.00
| 1" dia | 40 rft | @ | Rs.46.50 | P.rft | Rs. 1860.00
8 | Providing R.C.C. pipes with collers class "B" digging the trnches to requird and fixing in
position i/c cutting fitting and jointing with maxphaltic composition and cement mortor 1:1
and testing with water pressure to a head of 4" feet above the top of heighst and refilling
with excavated staff.(SI,NO.2 P.21)
| 4" dia | 12 rft | @ | Rs.48.00 | P.rft | Rs. 576.00
| 6" dia | 12 rft | @ | Rs.72.40 | P.rft | Rs. 869.00
7 | P/F water pumping set 1H.P. 2800 PRM Single phase 220 volts 1-1/4"x 1" suction & delievery
40 feet head i/c base plat form required size and fixing with nuts and both complete in all
respect. (R.A)
| 1 | NO. | 1 | 5494.59 | Each | 5494.59
Page No: 02
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
9 | Providing & fixing handle volves(china) (SI,NO: 8 P.14)
| 3/4" dia | 1 NO. | @ | Rs.102.95 | Each | Rs. 103.00
| 1/2" dia | 1 NO. | @ | Rs.75.45 | Each | Rs. 75.00
10 | Boring for tube well in wall bearing nails from ground level upto 100 ft.or 30.5 meter depth
i/c making and with drawing of casing pipe.(SI,NO: 1 P.36)(PHE)
|  | 80 rft | @ | Rs.91.85 | P.rft | Rs. 7348.00
11 | P/F water pumping set 1H.P. 2800 PRM Single phase 220 volts 1-1/4"x 1" suction & delievery
40 feet head i/c base plat form required size and fixing with nuts and both complete in all
respect. (SI,NO: 11 P.30)
1 NO.
|  |  | @ | Rs. 5115.00 | Each | Rs. 5115.00
Total Rs:- 25950.00
1 | Providing R.C.C. pipes with collers class "B" digging the trnches to requird and fixing in
position i/c cutting fitting and jointing with maxphaltic composition and cement mortor 1:1
and testing with water pressure to a head of 4" feet above the top of heighst and refilling
with excavated staff.(SI,NO.2 P.21)
| 9" dia | 1x24 | 24
|  |  | @ | Rs. 115.20 | P.rft | 2765
[5 empty] | Total Rs. | 2765
| Sub: Engineer |  |  | Assistant Engineer
Education Works Sub-Division
Nawabshah
5 | Providing & Fixing 22"x16" lavatory basin in white cement glazed earthen ware complete with
& i/c the cost of W.I. or C.I. cantilever brackets 6" inches built into walls painted white in two
coats after a primary coat of red lead paint a pair of ½" dia chorme plated piler traps.1½" dia
rubber plug and chrome platted piller taps. 1½" dia rubber plug and chrome brass waster of
. | approved pattern.1¼" dia malloable iron c.p. brass unions making and making traps, malloable
iron & floor for pipe connection & making good in cement concrete 1:2:4 (Standard
Pattern).(SINO.12 P.3)
|  | 1x2 | 2 Nos
|  |  | @ | Rs.1233.65 | Each | Rs. 2467.00
6 | Add: extra for labour for providing and fixing of earthen ware pedestal white or coloured
glazed (Foreign or equivalent) (SI,NO: 9 P.3)
|  | 1x2 | 2 Nos
|  |  | @ | Rs.416.55 | Each | Rs. 833.00
7 | S/F Sawan typ piller cock of superior quality single C.P. head ½" dia.(SI,NO: 18 (a) P.16)
|  | 1x2 | 2 Nos
|  |  | @ | Rs.273.90 | Each | Rs. 548.00
8 | P/F in position Nyloon connections complete with 1/2"dia brass stop cock with pair of brass
nuts and lining joints to nyloon connection.(SI,NO: 23 P.6)
|  | 1x6 | 6 Nos
|  |  | @ | Rs.77.85 | Each | Rs. 467.00
10 | S/F in jet shower with rod of superior quality with C.P head 1/2" dia.(SI,NO: 17 P.15)
|  | 1x1 | 1 Nos
|  |  | @ | Rs.197.10 | Each | Rs. 197.00
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
15 | Providing and fixing M.S clamps of the approved desigen to 4" dia C.I pipe sockets including
the cost of cutting and making good to wall or M.S bolts & nuts, 4" into wall including pipe
distance pieces extra painting to match the colour of the building.
|  | 1x8.0 | 8 Nos
|  |  | @ | Rs. 56.75 | Each
16 | P/F 4"x4" dia C.I. branch of the required degree with access floor rubber washer 3/8" tick
and bolts and nuts extra painting to match the colour of the building. (SI,NO: 5 P.8)
|  | 1x4 | 4 Nos
|  |  | @ | Rs.233.80 | Each | Rs. 935.00
17 | P/F 4" dia C.I.plain bend the required degree i/c extra painting to match the colour of the
building. (SI,NO: 10, P.9)
|  | 1x6 | 6 Nos
|  |  | @ | Rs.168.40 | Each | Rs. 1010.00
18 | Providin & Fixing 4" dia C.I. Offset of various length including extra painting to match the
colour of the buildings (SI,NO: 20 P.10)
|  | 1x4 | 4 Nos
|  |  | @ | Rs.171.20 | Each | Rs. 685.00
20 | P/F water pumping set 1H.P. 2800 PRM Single phase 220 volts 1-1/4"x 1" suction & delievery
40 feet head i/c base plat form required size and fixing with nuts and both complete in all
respect. (SI,NO: 11 P.30)
|  | 1x1 | 1 Nos
|  |  | @ | Rs. 5115.00 | Each | Rs. 5115.00
21 | Add: extra labour for concealed G.I.pipe & fiiting i/c making recess in the wall for pipe and
making good in cement mortor etc complete. (SI,NO: 2, P.11)
|  | 1x60.0 | 60
| ½" dia |  | @ | Rs.03.60 | P.rft | Rs. 216.00
22 | Providing & Fixing Chrome plated brass Twoel rail complete with brackets fixing on wooden
claets with 1" long C.P. brass screws.
3/4" dia round or square (Superior Pattern)
|  | 1x2 | 2 Nos
|  |  | @ | Rs.270.10 | Each | Rs. 540.00
S.NO | Description | Measurement | Quantity | Rate | Unit | Amount
23 | P/F 15" x 12" bevelled edge mirror of belgium glass complete with 1/8"thick hard board and
C.P screws fixed to wooden plate.(SI,NO:3, P.7)
Standard Pattern
|  | 1x2 | 2 Nos
|  |  | @ | Rs.663.30 | Each | Rs. 1327.00
Total:- Rs. 47442.00
Deputy District Officer
| Sub-Engeenir |  |  |  | Education works
Works & services Department
Nawabshah.