## Sheet1
PROCUREMENT PLAN 2016-17
IN RESPECT OF BUILDINGS DIVISION SUKKUR
S.No | ADP No. | Name of Scheme | Estimated Cost | Source of Funds ADP / Non ADP | Proposed procurement method | Cost of New works | Funds for New works | Nature of procurement | Timing of procurement
[9 empty] | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
|  | ADP 2016-17 | [5 empty] | ADP 2016-17
1 |  | Eid Gah to Girls College Paver Block Pipe Line Cross Sukkur. | [5 empty] | Eid Gah to Girls College Paver Block Pipe Line Cross Sukkur.
|  | Civil Work | 1 | District ADP | N.CB | 1 | 1 | Civil Work | 0.25 | 0.25 | 0.25 | 0.25
2 |  | Construction of Dispensary Village Mohammad Bachal. (Internal Electrification) | [5 empty] | Construction of Dispensary Village Mohammad Bachal. (Internal Electrification)
|  | Electric Work | 0.2 | District ADP | N.CB | 0.2 | 0.2 | Electric Work | 0.05 | 0.05 | 0.05 | 0.05
3 |  | Construction of Dispensary Village Manzoor Metlo Tauka Pano AKil. (Internal Electrification) | [5 empty] | Construction of Dispensary Village Manzoor Metlo Tauka Pano AKil. (Internal Electrification)
|  | Electric Work | 0.2 | District ADP | N.CB | 0.2 | 0.2 | Electric Work | 0.05 | 0.05 | 0.05 | 0.05
4 |  | Construction of Dispensary Village Moule Dino Mirbahar Tauka Pano AKil. (Internal Electrification) |  |  | N.CB |  |  | Construction of Dispensary Village Moule Dino Mirbahar Tauka Pano AKil. (Internal Electrification)
|  | Electric Work | 0.2 | District ADP |  | 0.2 | 0.2 | Electric Work | 0.05 | 0.05 | 0.05 | 0.05
5 |  | Construction of Dispensary Village Salhani Tauka Pano AKil. (Internal Electrification) |  |  | N.CB |  |  | Construction of Dispensary Village Salhani Tauka Pano AKil. (Internal Electrification)
|  | Electric Work | 0.2 | District ADP | N.CB | 0.2 | 0.2 | Electric Work | 0.05 | 0.05 | 0.05 | 0.05
6 |  | Construction of Dispensary Village Waheed Kalhoro Tauka Pano AKil. (Internal Electrification) | [5 empty] | Construction of Dispensary Village Waheed Kalhoro Tauka Pano AKil. (Internal Electrification)
|  | Electric Work | 0.2 | District ADP | N.CB | 0.2 | 0.2 | Electric Work | 0.05 | 0.05 | 0.05 | 0.05
7 |  | Construction of Dispensary Village Mubarakpur Tauka Pano AKil. (Internal Electrification) | [5 empty] | Construction of Dispensary Village Mubarakpur Tauka Pano AKil. (Internal Electrification)
|  | Electric Work | 0.2 | District ADP | N.CB | 0.2 | 0.2 | Electric Work | 0.05 | 0.05 | 0.05 | 0.05
8 |  | Construction of Community Hall @ UC-Nauraja Taluka Pano Akil (Internal Electrification) | [5 empty] | Construction of Community Hall @ UC-Nauraja Taluka Pano Akil (Internal Electrification)
|  | Electric Work | 0.1 | District ADP | N.CB | 0.1 | 0.1 | Electric Work | 0.025 | 0.025 | 0.025 | 0.025
9 |  | Construction of Park & Mosque & Village Ammenuddin Shah UC-Hingoro Taluka Pano Akil (Internal Electrification) | [5 empty] | Construction of Park & Mosque & Village Ammenuddin Shah UC-Hingoro Taluka Pano Akil (Internal Electrification)
|  | Electric Work | 0.1 | District ADP | N.CB | 0.1 | 0.1 | Electric Work | 0.025 | 0.025 | 0.025 | 0.025
10 |  | Construction of Imam Bargah Military Road Sukkur (Internal Electrification) | [5 empty] | Construction of Imam Bargah Military Road Sukkur (Internal Electrification)
|  | Electric Work | 0.3 | District ADP | N.CB | 0.3 | 0.3 | Electric Work | 0.075 | 0.075 | 0.075 | 0.075
11 |  | Remaining Work of District Bar Sukkur & Repair of Old Bar Sukkur. (Internal Electrification) | [5 empty] | Remaining Work of District Bar Sukkur & Repair of Old Bar Sukkur. (Internal Electrification)
|  | Electric Work | 0.5 | District ADP | N.CB | 0.5 | 0.5 | Electric Work | 0.125 | 0.125 | 0.125 | 0.125
12 |  | Maintenance & Rehabilitation of Dargah & Graveyard Pir Bhawal Shah Bukhari UC-14 Small Industries Sukkur (Internal & External Electrification) | [5 empty] | Maintenance & Rehabilitation of Dargah & Graveyard Pir Bhawal Shah Bukhari UC-14 Small Industries Sukkur (Internal & External Electrification)
|  | Electric Work | 0.35 | District ADP | N.CB | 0.35 | 0.35 | Electric Work | 0.0875 | 0.0875 | 0.0875 | 0.0875
13 |  | Remaining Work of Community Hall @ Village Pedaish Ali Shah Taluka Rohri. (Internal Electrification) | [5 empty] | Remaining Work of Community Hall @ Village Pedaish Ali Shah Taluka Rohri. (Internal Electrification)
|  | Electric Work | 0.2 | District ADP | N.CB | 0.2 | 0.2 | Electric Work | 0.05 | 0.05 | 0.05 | 0.05
14 |  | Renovation of Dargah Makki Shah Sukkur (Internal Electrification) | [5 empty] | Renovation of Dargah Makki Shah Sukkur (Internal Electrification)
|  | Electric Work | 0.2 | District ADP | N.CB | 0.2 | 0.2 | Electric Work | 0.05 | 0.05 | 0.05 | 0.05
15 |  | Construction of Boundary Wall Pir Gul Shah near Dharejo Mohalla & Construction of Internal Paths & Shed Graveyard Mughal UC-15 Old Sukkur (Internal Electrification) | [5 empty] | Construction of Boundary Wall Pir Gul Shah near Dharejo Mohalla & Construction of Internal Paths & Shed Graveyard Mughal UC-15 Old Sukkur (Internal Electrification)
|  | Electric Work | 0.05 | District ADP | N.CB | 0.05 | 0.05 | Electric Work | 0.0125 | 0.0125 | 0.0125 | 0.0125
16 |  | Construction of Nuagaz Pir Ward-01 UC-02 Sukkur (Internal Electrification) | [5 empty] | Construction of Nuagaz Pir Ward-01 UC-02 Sukkur (Internal Electrification)
|  | Electric Work | 0.1 | District ADP | N.CB | 0.1 | 0.1 | Electric Work | 0.025 | 0.025 | 0.025 | 0.025
17 |  | Renovation of Masjid Mahar Mohalla Village Gosarji Sukkur (Internal Electrification) |  |  | N.CB |  |  | Renovation of Masjid Mahar Mohalla Village Gosarji Sukkur (Internal Electrification)
|  | Electric Work | 0.1 | District ADP |  | 0.1 | 0.1 | Electric Work | 0.025 | 0.025 | 0.025 | 0.025
18 |  | Renovation of Various Rounds About @ Sukkur City. (Internal Electrification) |  |  | N.CB |  |  | Renovation of Various Rounds About @ Sukkur City. (Internal Electrification)
|  | Electric Work | 0.1 | District ADP |  | 0.1 | 0.1 | Electric Work | 0.025 | 0.025 | 0.025 | 0.025
19 |  | Installation of CCTV Camera for Security Purpose & Important & Sensetive Places of Sukkur City (Internal Electrification) |  |  | N.CB |  |  | Installation of CCTV Camera for Security Purpose & Important & Sensetive Places of Sukkur City (Internal Electrification)
|  | Electric Work | 0.4 | District ADP |  | 0.4 | 0.4 | Electric Work | 0.1 | 0.1 | 0.1 | 0.1
20 |  | Construction of Auditorium / Internal Paths of IBA Public School Sukkur (Internal Electrification) |  |  | N.CB |  |  | Construction of Auditorium / Internal Paths of IBA Public School Sukkur (Internal Electrification)
|  | Electric Work | 1 | District ADP |  | 1 | 1 | Electric Work | 0.25 | 0.25 | 0.25 | 0.25
21 |  | Renovation & Extension of SSP Office Sukkur (Internal Electrification) |  |  | N.CB |  |  | Renovation & Extension of SSP Office Sukkur (Internal Electrification)
|  | Electric Work | 0.05 | District ADP | N.CB | 0.05 | 0.05 | Electric Work | 0.0125 | 0.0125 | 0.0125 | 0.0125
22 |  | Construction & Rehabilitation / Renovation of Chistain Community Hall @ Ayoub Gate UC-13 Sukkur. (Internal Electrification) | [5 empty] | Construction & Rehabilitation / Renovation of Chistain Community Hall @ Ayoub Gate UC-13 Sukkur. (Internal Electrification)
|  | Electric Work | 0.4 | District ADP | N.CB | 0.4 | 0.4 | Electric Work | 0.1 | 0.1 | 0.1 | 0.1
|  | M&R 2016-17 |  |  | N.CB |  |  | M&R 2016-17
23 |  | M&R Office of the Executive Engineer Buildings Division Sukkur. | [5 empty] | M&R Office of the Executive Engineer Buildings Division Sukkur.
|  | Civil Work | 0.527 | M&R Programme | N.CB | 0.527 | 0.527 | Civil Work | 0.13175 | 0.13175 | 0.13175 | 0.13175
24 |  | M&R Office of the Assistant Engineer Highways Sukkur. | [5 empty] | M&R Office of the Assistant Engineer Highways Sukkur.
|  | Civil Work | 0.5 | M&R Programme | N.CB | 0.5 | 0.5 | Civil Work | 0.125 | 0.125 | 0.125 | 0.125
25 |  | M&R Office of the Assistant Engineer Building Division Sukkur. | [5 empty] | M&R Office of the Assistant Engineer Building Division Sukkur.
|  | Civil Work | 0.45 | M&R Programme | N.CB | 0.45 | 0.45 | Civil Work | 0.1125 | 0.1125 | 0.1125 | 0.1125
|  | Electric Work | 0.05 | M&R Programme |  | 0.05 | 0.05 | Electric Work | 0.0125 | 0.0125 | 0.0125 | 0.0125
26 |  | M&R Office of the Superintending Engineer Works & Services Sukkur. |  |  | N.CB |  |  | M&R Office of the Superintending Engineer Works & Services Sukkur.
|  | Civil Work | 0.4 | M&R Programme | N.CB | 0.4 | 0.4 | Civil Work | 0.1 | 0.1 | 0.1 | 0.1
27 |  | M&R Office of the Assistant Engineer Building Pano Akil. | [5 empty] | M&R Office of the Assistant Engineer Building Pano Akil.
|  | Civil Work | 0.3 | M&R Programme | N.CB | 0.3 | 0.3 | Civil Work | 0.075 | 0.075 | 0.075 | 0.075
28 |  | M&R to Staff Quarter Revenue Colony Sukkur. (___________________). | [5 empty] | M&R to Staff Quarter Revenue Colony Sukkur. (___________________).
|  | Civil Work | 0.4 | M&R Programme | N.CB | 0.4 | 0.4 | Civil Work | 0.1 | 0.1 | 0.1 | 0.1
29 |  | M&R to Staff Quarter Revenue Colony Sukkur. (___________________). |  |  | N.CB |  |  | M&R to Staff Quarter Revenue Colony Sukkur. (___________________).
|  | Civil Work | 0.4 | M&R Programme |  | 0.4 | 0.4 | Civil Work | 0.1 | 0.1 | 0.1 | 0.1
30 |  | M&R to Staff Quarter Revenue Colony Sukkur. (___________________). |  |  | N.CB |  |  | M&R to Staff Quarter Revenue Colony Sukkur. (___________________).
|  | Civil Work | 0.4 | M&R Programme | N.CB | 0.4 | 0.4 | Civil Work | 0.1 | 0.1 | 0.1 | 0.1
31 |  | M&R to Staff Quarter Revenue Colony Sukkur. (___________________). | [5 empty] | M&R to Staff Quarter Revenue Colony Sukkur. (___________________).
|  | Civil Work | 0.4 | M&R Programme | N.CB | 0.4 | 0.4 | Civil Work | 0.1 | 0.1 | 0.1 | 0.1
32 |  | M&R to Staff Quarter Revenue Colony Sukkur. (___________________). |  |  | N.CB |  |  | M&R to Staff Quarter Revenue Colony Sukkur. (___________________).
|  | Civil Work | 0.4 | M&R Programme |  | 0.4 | 0.4 | Civil Work | 0.1 | 0.1 | 0.1 | 0.1
33 |  | M&R to Various Staff Quarters Revenue Colony Sukkur. |  |  | N.CB |  |  | M&R to Various Staff Quarters Revenue Colony Sukkur.
|  | Electric Work | 0.234 | M&R Programme |  | 0.234 | 0.234 | Electric Work | 0.0585 | 0.0585 | 0.0585 | 0.0585
34 |  | M&R to RHC Bachal Shah Miani Sukkur |  |  | N.CB |  |  | M&R to RHC Bachal Shah Miani Sukkur
|  | Civil Work | 1 | M&R Programme |  | 1 | 1 | Civil Work | 0.25 | 0.25 | 0.25 | 0.25
|  | Electric Work | 0.2 | M&R Programme | N.CB | 0.2 | 0.2 | Electric Work | 0.05 | 0.05 | 0.05 | 0.05
EXECUTIVE ENGINEER
BUILDINGS DIVISION
SUKKUR
EXECUTIVE ENGINEER
BUILDINGS DIVISION
SUKKUR