## schedule-B
SCHEDULE-B
NAME OF WORK:- CONSTRUCTION DISPENSARY ABDUL REHMAN SOOMRO TALUKA B.S.KARIM DISTRICT T.M.KHAN (EXT: DEVELOPMENT).
S.No. | Name of Items | Quantity |  | Rate (Rs.) | Unit | Amount (Rs.)
01. | Excavation in foundation of Bldg: bridge & other structures i/c dagbelling dressing refilling around str:with excavated earth watering & ramming lead upto 5 ft in ordanary siol (S.I.18 P.5) | 737.595 | Cft | 3176.25 | %OCft | 2342.7861
02. | C.C.Brick or Stone Bllast 1-1/2" to 2" gauge (1:5:10) (S.I.4 P.17) | 627.944 | Cft | 9416.28 | %Cft | 59128.9606
03. | P.B.Work in foundation & Plinth C.Sand Mortar 1:6 (s.I.4 P.25) | 860.5275 | Cft | 11948.36 | %Cft | 102818.9236
04. | Cement plaster 1:4 upto 20'ft: height 3/4" thick.(S.I.No:11(c) /P-51) | 1157.87 | Sft | 3015.76 | %Sft | 34918.5803
05. | P/L 3" thick topping c.C (1:2:4) i/c surface finishing & dividing into panels (S.I.16 P.47) | 1357.555 | Sft | 4411.82 | %Sft | 59892.883
06. | F/Watering & Ramming earth U/Floor with new earth excavated from outside lead upto one chain & lift upto 5 ft (S.I.22 P.5) | 13573.4125 | Cft | 3630 | %Ocft | 49271.4874
07. | Lead 7 miles | 13573.4125 | Cft | 804.52 | %Cft | 109200.8182
|  | Total Amount |  |  |  | 417574.4392
|  | Add Cartage |  |  |  | 64486.4624 | /=
|  | Total Amount (at Par) |  |  |  | 482060.9016 | /=
|  | SAY |  |  |  | 482000 | /=
NOTE: -
Any error or ommission in the Schedul "B" will be governed by the schedul of rates.
No. premium will be allowed on Non-Schedule items.
Cartage will not be paid for any meterials.
Mat: use in the work of finished product can be got tested from any approved lab: at the discreation of the XEN or his representitive & all expanses in conn: with such testing should be born by the cont exclusivaly without any re-imburament or cleim against the Government on his account.
EXECUTIVE ENGINEER
BUILDINGS DIVISION
TANDO MOHAMMAD KHAN
CONTRACTOR

## Abstract Sheet (hidden)
ABSTRACT SHEET
NAME OF WORK:- CONSTRUCTION DISPENSARY ABDUL REHMAN SOOMRO TALUKA B.S.KARIM DISTRICT T.M.KHAN (EXT: DEVELOPMENT).
S.No. | Name of Items | Quantity |  | Rate (Rs.) | Unit | Amount (Rs.)
01. | Excavation in foundation of Bldg: bridge & other structures i/c dagbelling dressing refilling around str:with excavated earth watering & ramming lead upto 5 ft in ordanary siol (S.I.18 P.5) | 737.595 | Cft | 3176.25 | %OCft | 2342.7861
02. | C.C.Brick or Stone Bllast 1-1/2" to 2" gauge (1:5:10) (S.I.4 P.17) | 627.944 | Cft | 9416.28 | %Cft | 59128.9606
03. | P.B.Work in foundation & Plinth C.Sand Mortar 1:6 (s.I.4 P.25) | 860.5275 | Cft | 11948.36 | %Cft | 102818.9236
04. | Cement plaster 1:4 upto 20'ft: height 3/4" thick.(S.I.No:11(c) /P-51) | 1157.87 | Sft | 3015.76 | %Sft | 34918.5803
05. | P/L 3" thick topping c.C (1:2:4) i/c surface finishing & dividing into panels (S.I.16 P.47) | 1357.555 | Sft | 4411.82 | %Sft | 59892.883
06. | F/Watering & Ramming earth U/Floor with new earth excavated from outside lead upto one chain & lift upto 5 ft (S.I.22 P.5) | 13573.4125 | Cft | 3630 | %Ocft | 49271.4874
07. | Lead 7 miles | 13573.4125 | Cft | 804.52 | %Cft | 109200.8182
|  | Total Amount |  |  |  | 417574.4392 | /=
|  | Add Cartage |  |  |  | 64486.4624 | /=
|  | Total Amount (at Par) |  |  |  | 482060.9016 | /=
|  | SAY |  |  |  | 482000 | /=
SUB-ENGINEER
ASSISSTANT ENGINEER
BUILDINGS SUB-DIVISION
TANDO MOHAMMAD KHAN

## Measurement Sheet (hidden)
MEASUREMENT SHEET
NAME OF WORK:- CONSTRUCTION DISPENSARY ABDUL REHMAN SOOMRO TALUKA B.S.KARIM DISTRICT T.M.KHAN (EXT: DEVELOPMENT).
S.No. | Description | Measurement | [11 empty] | Quantity
|  | No. |  |  | Length |  | Width |  |  | Height/Depth
01. | Excavation of foundation of building bridges and other structure…..
| P/Prot B/F | 1 | × | 2 | ×( | 55.37 | + | 35.50 | )× | 1.50 | × | 1.50 | ═ | 408.915 | Cft
| Path F/S | 1 | × | 2 | × | 40.00 | × | 1.50 | × | 1.50 |  |  | ═ | 180 | Cft
| Lav.Block F/S | 1 | × | 1 | × | 44.58 | × | 1.50 | × | 1.50 |  |  | ═ | 100.305 | Cft
| " " " | 1 | × | 1 | × | 21.50 | × | 1.50 | × | 1.50 |  |  | ═ | 48.375 | Cft
[10 empty] | Total |  |  | ═ | 737.595 | Cft
02. | Cement Concrete brick or stone ballast 1.1/2" to 2" gauge ratio (1:5:10)…… | [11 empty] | ═
| P/Prot B/F | 1 | × | 2 | ×( | 55.37 | + | 35.50 | )× | 1.50 | × | 0.50 | ═ | 136.305 | Cft
| Path F/S | 1 | × | 2 | × | 40.00 | × | 1.50 | × | 0.50 |  |  | ═ | 60 | Cft
| Lav.Block F/S | 1 | × | 1 | × | 44.58 | × | 1.50 | × | 0.50 |  |  | ═ | 33.435 | Cft
| " " " | 1 | × | 1 | × | 21.50 | × | 1.50 | × | 0.50 |  |  | ═ | 16.125 | Cft
Under Bed
| P/Prot U/Bed | 1 | × | 2 | ×( | 55.37 | + | 35.50 | )× | 3.0 | × | 0.33 | ═ | 179.9226 | Cft
| Path F/S | 1 | × | 40.00 | × | 12.25 | × | 0.33 |  |  |  |  | ═ | 161.7 | Cft
| Lav.Block F/S | 1 | × | 44.58 | × | 2.75 | × | 0.33 |  |  |  |  | ═ | 40.4564 | Cft
[10 empty] | Total |  |  | ═ | 627.944 | Cft
03. | Pacca Brick work in foundation in cement sand mortar 1:4 ratio….. | [11 empty] | ═
| P/Prot B/F | 1 | × | 2 | ×( | 55.37 | + | 35.50 | )× | 0.75 | × | 3.50 | ═ | 477.0675 | Cft
| Path F/S | 1 | × | 2 | × | 40.00 | × | 0.75 | × | 3.50 |  |  | ═ | 210 | Cft
| Lav.Block F/S | 1 | × | 1 | × | 44.58 | × | 0.75 | × | 3.50 |  |  | ═ | 117.0225 | Cft
| " " " | 1 | × | 1 | × | 21.50 | × | 0.75 | × | 3.50 |  |  | ═ | 56.4375 | Cft
[12 empty] | Total | ═ | 860.5275 | Cft
04. | Cement plaster 1:4 upto 20'ft: height 3/4" thick.
| P/Prot B/F | 1 | × | 2 | ×( | 55.37 | + | 35.50 | )× | 3.50 |  |  | ═ | 636.09 | Sft
| Path F/S | 1 | × | 2 | × | 40.00 | × | 0.75 | × | 3.50 |  |  | ═ | 285.25 | Sft
| Lav.Block F/S | 1 | × | 1 | × | 44.58 | × | 0.75 | × | 3.50 |  |  | ═ | 158.655 | Sft
| " " " | 1 | × | 1 | × | 21.50 | × | 0.75 | × | 3.50 |  |  | ═ | 77.875 | Sft
[12 empty] | Total | ═ | 1157.87 | Sft
05 | P/L 3" thick C.C topping (1:2:4)………
(a) 3" thick
| P/Prot B/F | 1 | × | 2 | ×( | 55.37 | + | 35.50 | )× | 3.75 |  |  | ═ | 681.525 | Sft
| Path F/S | 1 | × | 40.00 | × | 13.0 | [6 empty] | ═ | 520 | Sft
| Lav.Block F/S | 1 | × | 44.58 | × | 3.50 | [6 empty] | ═ | 156.03 | Sft
[12 empty] | Total | ═ | 1357.555 | Sft
06 | F/Watering ramming earth U/Floor….
| F/S |  |  | 1 | × | 87.00 | × | 85.00 | × | 2.50 |  |  | ═ | 18487.5 | Cft
[12 empty] | Total | ═ | 18487.5 | Cft
Deduction
| M/Bldg |  |  | 1 | × | 55.37 | × | 35.50 | × | 2.50 |  |  | ═ | 4914.0875 | Cft
|  |  | NET QTY: |  | ( | 18487.5 | ─ | 4914.0875 | ) |  |  | Total | = | 13573.4125 | Cft
| SUB-ENGINEER | [6 empty] | ASSISSTANT ENGINEER
BUILDINGS SUB-DIVISION
TANDO MOHAMMAD KHAN

## Rate Analysis (R.A.A) (hidden)
(Rate Analysis)
NAME OF WORK:- CONSTRUCTION DISPENSARY ABDUL REHMAN SOOMRO TALUKA B.S.KARIM DISTRICT T.M.KHAN (EXT: DEVELOPMENT).
Cartage of Hill Sand from Bolahri Quarry to Site of work
[6 empty] | M | F |  | 1 Mile = 8 Furlog
| 01. From Quarry to N.H.Way. |  |  |  |  | 3 | 0 |  | 1Furlong = 660 foot
| 02. From Quarry to 113/0 122/0 of N.H.Way. |  |  |  |  | 9 | 0
| 03. From 0/0 4/4 of Hyd: Ring Road. |  |  |  |  | 4 | 4
| 04. From 2/0 21/4 of Hyd:T.M.Khan. |  |  |  |  | 19 | 4
| 05. From 0/0 0/0 T.M.Khan to Site. |  |  |  |  | 18 | 0
[5 empty] | Total | 53 | 8 | 1
[5 empty] | Say total | 54 |  | 54
Lead
| 01. Carriage of 1st 6 miles |  |  |  | Rs:- | 771.96
| 02. Remaining |  | 48 | miles
|  | @Rs. | 32.56 | per %cft | Rs:- | 1562.88
[5 empty] | Total | 2334.84 |  |  |  | 2334.84
Cartage of Stone Metal from Onger to Site of work
[6 empty] | M | F
| 01. From Quarry to N.H.way. |  |  |  |  | 3 | 0
| 02. From Quarry to 103/0 122/0 of N.H.Way. |  |  |  |  | 19 | 0
| 03. From 0/0 4/4 of Hyd: Ring Road. |  |  |  |  | 4 | 4
| 04. From 2/0 21/4 of Hyd:T.M.Khan. |  |  |  |  | 19 | 4
| 05. From 0/0 0/0 T.M.Khan to Site. |  |  |  |  | 18 | 0
[5 empty] | Total | 63 | 8 | 1
[5 empty] | Say total | 64 |  | 64
Lead
| 01. Carriage of 1st 6 miles |  |  |  | Rs:- | 771.96
| 02. Remaining |  | 58 | miles
|  | @Rs. | 32.56 | per %Cft | Rs:- | 1888.48
[5 empty] | Total | 2660.44 |  |  |  | 2660.44
Cartage of Bajri from T.M.Khan to Site of work
[6 empty] | M | F
| 01. From Quarry to 14/0 of N.H.way. |  |  |  |  | 14 | 0
| 02. From Quarry 110/40 to 122/0 of N.H.Way. |  |  |  |  | 11 | 4
| 03. From 0/0 4/4 of Hyd: Ring Road. |  |  |  |  | 4 | 4
| 04. From 2/0 21/4 of Hyd:T.M.Khan. |  |  |  |  | 19 | 4
| 05. From 0/0 0/0 T.M.Khan to Site. |  |  |  |  | 18 | 0
[5 empty] | Total | 66 | 12 | 2
[5 empty] | Say total | 68 |  | 68
Lead
| 01. Carriage of 1st 6 miles |  |  |  | Rs:- | 771.96
| 02. Remaining |  | 62 | miles
|  | @Rs. | 32.56 | per %cft | Rs:- | 2018.72
[5 empty] | Total | 2790.68 |  |  |  | 2790.68
Cartage of Cement from Zeal Pak Factory to Site of work
[6 empty] | M | F
| 01. From 2/0 21/4 of Hyd:T.M.Khan. |  |  |  |  | 17 | 4
| 02. From 0/0 0/0 T.M.Khan to Site. |  |  |  |  | 18 | 0
[5 empty] | Total | 35 | 4 | 1
[5 empty] | Say total | 36 |  | 36
Lead
| 01. Carriage of 1st 3 miles |  |  |  | Rs:- | 7.53
| 02. Remaining |  | 33 | miles
|  | @Rs. | 0.6 | per bag | Rs:- | 19.8
[5 empty] | Total | 27.33 |  |  |  | 27.33
Cartage of Brick from Kilen to Site of work
[6 empty] | M | F
| 01. From Brick Kilen 0/0 5/0 of Tando Fazal Sery Road |  |  |  |  | 5 | 6
| 02. From Sery Road 13/4 to 21/4 of Hyd:T.M.Khan. |  |  |  |  | 8 | 0
| 03. From 0/0 0/0 T.M.Khan to Site. |  |  |  |  | 18 | 0
[5 empty] | Total | 31 | 6 | FALSE
[5 empty] | Say total | 32 |  | 31
Lead
| 01. Carriage of 1st 6 miles |  |  |  | Rs:- | 771.96
| 02. Remaining |  | 26 | miles
|  | @Rs. | 32.56 | per O% Nos. | Rs:- | 846.56
[5 empty] | Total | 1618.52 |  |  |  | 1618.52
Cartage of Steel from Hyd. City to Site of work
[6 empty] | M | F
| 01. From 2/0 21/4 of Hyd:T.M.Khan. |  |  |  |  | 19 | 4
| 02. From 0/0 25/0 T.M.Khan to Site. |  |  |  |  | 18 | 0
[5 empty] | Total | 37 | 4 | 1
[5 empty] | Say total | 38 |  | 38
Lead
| 01. Carriage of 1st 6 miles |  |  |  | Rs:- | 411.38
| 02. Remaining |  | 32 | miles
|  | @Rs. | 20.5 | per Ton | Rs:- | 656
[5 empty] | Total | 1067.38 |  |  |  | 1067.38
SUB-ENGINEER |  |  |  |  | ASSISTANT ENGINEER
BUILDINGS SUB DIVISION
TANDO MUHAMMAD KHAN

## Cartage (hidden)
Material Cartage Satement
NAME OF WORK:- CONSTRUCTION DISPENSARY ABDUL REHMAN SOOMRO TALUKA B.S.KARIM DISTRICT T.M.KHAN (EXT: DEVELOPMENT).
Sr.# | Description | Qty: | Cement |  | Hill Sand |  | Stone Metal |  | Stone Bajri |  | Steel |  | Bricks
01. | C.C. (1:4:8) | 627.944 | 7.8 | 48.9796 | 48 | 301.4131 | 94.76 | 595.0397 | - | - | - | - | - | -
02. | Masonary 1:6 | 860.5275 | 3.44 | 29.6021 | 25.7 | 221.1556 | - | - | - | - | - | - | 1350 | 11617.1213
03.. | P/L C.C.Topping 3" | 1357.555 | 4.4 | 59.7324 | 11 | 149.3311 | - | - | 22 | 298.6621 | - | - | - | -
04. | C/Plaster 3/4" thick ratio 1:4 | 1157.87 | 0.5 | 5.7894 | 7 | 81.0509 | - | - | - | - | - | - | - | -
| Total Quantity: | - | - | 144.1035 | - | 752.9506 | - | 595.0397 | - | 298.6621 | - | 0 | - | 11617.1213
| Rate as per R.A.A |  |  | 27.33 |  | 2334.84 |  | 2660.44 |  | 2790.68 |  | 1067.38 |  | 1618.52
| Amount |  |  | 3938.3499 |  | 17580.1921 |  | 15830.6738 |  | 8334.7035 |  | 0 |  | 18802.5431
| Total Rs |  |  | 64486.4624 |  | /=
64486.4624
| SUB-ENGINEER | [8 empty] | ASSISTANT ENGINEER
BUILDINGS SUB DIVISION
TANDO MUHAMMAD KHAN

## Detailed Sheet (hidden)
Detailed Sheet
NAME OF WORK:- CONSTRUCTION DISPENSARY ABDUL REHMAN SOOMRO TALUKA B.S.KARIM DISTRICT T.M.KHAN (EXT: DEVELOPMENT).
S.No | Name of Components | Plinth Area in Sft | Cost of Constt: |  | Cost of W/S S/F |  | E.I Work |  | Sui Gas |  | Total
|  |  | Rate | Amount | Rate | Amount | Rate | Amount | Rate | Amount
1 | Main Building | 657 | 1150 | 755550 | [6 empty] | 755550
2 | Parking Shade | 100 | 1150 | 115000 | [6 empty] | 115000
3 | Ext:Drainage |  |  | 50000 | [6 empty] | 50000
4 | W/S S/F |  |  |  |  | 100000 |  |  |  |  | 100000
5 | Electrification | [6 empty] | 150000 |  |  | 150000
6 | Ext:Development |  |  | 100000 | [6 empty] | 100000
7 | Steel Gate (10×6) |  | 1 | 89000 | [6 empty] | 89000
8 | Paved Courtyard | 600 | 700 | 42000 | [6 empty] | 42000
9 | Total | [9 empty] | 1401550
|  |  | ASSISTANT EXECUTIVE ENGINEER |  |  |  |  | EXECUTIVE ENGINEER
| SUB-ENGINEER |  | BUILDINGS SUB DIVISION |  |  |  |  | BUILDINGS DIVISION
|  |  | TANDO MUHAMMAD KHAN |  |  |  |  | TANDO MUHAMMAD KHAN