**STATUS OF COMPOUND WALL SCHEMES AS STOOD ON 30-09- 2016**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **mS.NO:** | **NAME OF SCHMEES** | **NO: OF UNITS** | **APPROVED COST** | **EXPEND: ON**  **30-09-2016** | **ALLOCATION**  **2016-2017** | **RELEASE**  **2016-2017** | **PHYSICAL PROGRESS** |
| 1/734 | Raising/Construction of watch Tower & Boundary Wall at RRF Base Al-Falah and Naval Colony Base, Karachi. | **3 Nos:** | **805.239** | **265.603** | **123.00** | **123.000** |  |
| A | Al-Falah 4450 Rft:Wall  6 Nos: Watch  Tower  2 Nos: Gate |  |  |  |  |  | i) 2100 Rft: Wall Completed  ii) 2000 Rft: wall Progress  iii) 3 Nos Watch Tower in Progress  iv) 3 Nos: to be started  v) 2 Nos: Gates to be installed  vi) Unit to be completed by  June 2017 |
| B | Naval Base 10700 Rft:Wall  6 Nos: Watch  Tower |  |  |  |  |  | i) 2000 Rft: Wall Completed  ii) 4000 Rft: wall Progress  iii) 3 Nos Watch Tower in Progress  iv) 3 Nos: Watch Tower to be started |
| C | P.H.Q. Garden 2080  Rft:Wall  4 Nos:  Watch  Tower |  |  |  |  |  | i) 2300 Rft: Wall Completed  ii) 3 Nos Watch Tower completed  iii) 1 No: Watch Tower finishing  stage  v) 2 Nos: Gates to be installed  vi) Unit to be completed by  June 2017 |