**STATEMENT OF DEVELOPMENT SCHEMES TO BE COMPLETED IN THE YEAR 2016-17**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **S.NO**  **ADP NO:** | **NAME OF SCHEMES** | **Approved cost**  **(M )** | **ALLOCATION**  **2016-17** | **RELEASE**  **2016-17** | **EXPENDITURE** | **PHYSICAL PROGAMMES** |
| 1/730 | **Construction of Buildings for Sindh Police @ various Location under Police Package** | **474.736** | **39.863** | **39.863** | **434.873** | **i) 2 No: units Viz Layari & Keamari**  **Completed & Handed over**  **in2013** |
| a) | **Town complex in Karachi (Layari, Keamari & Landhi** |  |  |  |  | **ii) Unit @ Landhi at G/floor to be**  **completed by June in 2017** |
| b) | **C.C.P.O Complex Karachi** |  |  |  |  | **i) . Completed & Handed over 2013** |
| c) | **09 Police Stations in Hyderabad Regions** |  |  |  |  | **i) . 06 Nos: Units completed &**  **Handed over** |
| i) | **Rural Police Station Jati.** |  |  |  |  | ii) **Unit @ Bhit shah finishing in**  **Progress to be completed by**  **June 2016** |
| ii) | **Rural Police Station Sujawal** |  |  |  |  |  |
| iii) | **Rural Police Station Mirpur Bathoro** |  |  |  |  |  |
| iv) | **Rural Police Station Ghora Bari** |  |  |  |  |  |
| v) | **Rural Police Station K.N. Shah** |  |  |  |  |  |
| vi) | **Rural Police Station Johi** |  |  |  |  |  |
| Vii) | **Rural Police Station Bhit Shah** |  |  |  |  | ii) **Unit @ Bhit shah finishing in**  **Progress to be completed by**  **June 2016** |
| d) | **Constt of D.P.O Residence @ Kandhkot & Kamber** |  |  |  |  | **i) . Finishing in Progress** |
| f) | **Constt: of 20 Bedded Hospital at Police Line Sukkur.** |  |  |  |  | **ii) Unit to completed by June 2017** |
| 3/732 | **Construction of ( 07 Nos ) Police Posts on Highway ( KPT, PQA ) Karachi** | **15.000** | **4.817** | **4.817** | **10.183** |  |
| i) | **Police Post at KPT Route (04 )** |  |  |  |  | **i) 04 No: Units finishing in Progress** |
| ii) | **Police Post at PQA Route ( 03 )** |  |  |  |  | **ii) 03 No: Units upto plinth level**  **iii) Scheme to be completed by**  **June 2017** |
| 4/733 | **Construction of Police Station B-Section Tando Adam District Sanghar.** | **53.761** | **1.000** | **1.000** | **53.761** | **i) Ready for Handed over** |
| 4/735 | **Construction of Police Station(Category-C) & Bachelor Barracks (Ground+1) at Nindo District Badin** | **37.198** | **22.849** | **22.849** | **14.349** | **i) Roofing in Progress.** |
| 5/736 | **Construction of Police (Category-C) at Kambhra District Ghotki.** | **25.626** | **1.000** | **0.500** | **25.626** | **i) Colouring in Progress** |
| 6/737 | **Construction of Police Station (Category-C) @ with Bachelor Barracks (Ground+1) at Jahanwah Village Sheranpur Taluka & District Shikarpur.** |  |  |  |  | **i) Completed Ready for Handed**  **over** |
| 7/738 | **Renovation/Construction of DIG House Sukkur** | **13.500** | **6.651** | **6.651** | **6.849** | **i) 90% work completed** |

Executive Engineer Superintending Engineer

Sindh Police Department Karachi Police Department Government of

Sindh Karachi