## DWE MBldg
SHEDULE-B
Name of work:- |  | Construction of One Class Rooom Building for Shelterless /Addition of One Class Room / Repair & Renovation & C/Wall in Existing Primary Schools Taluka Nagarparkar & Chachro District Tharparkar (20-Units) Under Community Development Programme 2016-17 For Sustainable Development Goals (SDGs) NA-230 @ GBPS Rathi Kolhi U/C HarhoTaluka Nangarparkar.
S.N: | ITEM OF WORK |  | QTY |  |  |  | RATE |  |  | UNIT |  |  |  | AMOUNT
1 | Excavation in foundation of Building, Bridges and other structures i/c degbelling dressing, refilling around structure with excavated earth watering and ramming (In ordinary soil) lead upto 5 ft .(S.I.No: 18-b, P.No: 4)
|  |  |  | 745 | Cft. |  | @ Rs: |  | 3176.25 |  |  | %0 Cft. |  | Rs. | 2366 | /=
(Rs. Three Thousand One Hundred Seventy Six & Ps. Twenty Five only)
2 | Cement concrete brick or stone ballast 1½” to 2” guage ratio 1:6:12. (S.I.No.4-d, P.No.15).
|  |  |  | 435 | Cft. |  | @ Rs: |  | 8122.95 |  |  | % Cft. |  | Rs. | 35335 | /=
(Rs. Eight Thousand One Hundred Twenty Two & Ps. Ninety Five Only)
3 | Pacca brick work in foundation and plinth in cement sand morter (1:6) Ratio.(S.I.No: 4-e, P.No: 21)
|  |  |  | 807 | Cft. |  | @ Rs: |  | 11948.36 |  |  | % Cft. |  | Rs. | 96423 | /=
(Rs. Eleven Thousand Nine Hundred Fourty Eight & Ps. Thirty six)
4 | Reinforced cement concrete work including all labour and material except the cost of steel reinforcement and its labour for bending and binding which will be paid separately.This rate also includes all kinds of forms moulds: lifting shuttering curring rendering and finishing the exposed surface including screening and washing of shingle.R.C work in roof slab, beams, columns rafts, lintels and other structural members laid in situ or pre-cost laid in position complete in all respects.Ratio 1:2:4. (S.I.No: 6-a/I, PNo: 17)
|  |  |  | 74 | Cft. |  | @ Rs: |  | 337 |  |  | Per Cft. |  | Rs. | 24938 | /=
(Rs. Three Hundred Thirty Seven Only)
5 | Fabrication of mild steel reinforcement for cement concrete including cutting, bending, laying in position, making joints and fastenings including cost of binding wire (also includes removal of rust from bars).
A | Using Tor Bars (S.I.No. 8-b, P.No. 17).
|  |  |  | 2.64 | Cwt | @ Rs: |  | 5001.7 |  |  | P.Cwt |  |  | Rs. | 13204 | /=
(Rs. Five Thousand One & Ps. Seventy Only)
B | Using M.S Bars (S.I.No. 8-a, P.No. 17).
|  |  |  | 0.33 | Cwt | @ Rs: |  | 4820.2 |  |  | P.Cwt |  |  | Rs. | 1591 | /=
(Rs. Four Thousand Eight Hundred Twenty & Ps. Twenty Only)
6 | Filling, watering and ramming earth in floors with surplus earth from foundation lead upto one chain and lift upto 5 feet . (S.I.No: 21, P.No: 4).
|  |  |  | 497 | Cft. |  | @ Rs: |  | 1512.5 |  |  | %0 Cft. |  | Rs. | 752 | /=
(Rs. One Thousand Five Hundred Twelve & Ps. Fifty only)
7 | Filling, watering and ramming earth under floor with new earth (Excavated from outside) lead up to one chain and lift upto 5 feet. (S.I.No. 22, P.No: 4).
|  |  |  | 420 | Cft. |  | @ Rs: |  | 3630 |  |  | %0 Cft. |  | Rs. | 1525 | /=
(Rs. Three Thousand Six Hundred Thirty Only)
8 | Pacca brick work in mud mortar in building in Ground floor. (S.I.No. 1-b, P.No: 20).
|  |  |  | 1226 | Cft. |  | @ Rs: |  | 9954.31 |  |  | % Cft. |  | Rs. | 122040 | /=
(Rs. Nine Thousand Nine Hundred Fifty Four & Ps. Thirty One Only)
9 | Supplying Girder .( Sh: of material Vol-III Part-III S.I.No.140, P.No:12).
|  |  |  | 19.29 | Cwt | @ Rs: |  | 3850 |  |  | P.Cwt |  | Rs. |  | 74267 | /=
(Rs. Three Thousand Eight Hundred Fifty Only)
10 | Supplying T-Iron .( Sh: of material Vol-III Part-III S.I.No.144, P.No:12).
|  |  |  | 7.25 | Cwt | @ Rs: |  | 3575 |  |  | P.Cwt |  | Rs. |  | 25919 | /=
(Rs. Three Thousand Five Hundred Seventy Five Only)
11 | Errection rolled steel beams or old rails in roof etc, erection and fixing in position. (S.I.No. 6, P.No. 91).
|  |  |  | 26.54 | Cwt | @ Rs: |  | 186.34 |  |  | P.Cwt |  | Rs. |  | 4945 | /=
(Rs. One Hundred Eight Six & PS. Thirty Four Only)
12 | First class tile roofing consisting of 4" earth and 1" mud plaster with Gobri leaping over 1/2" thick cement plaster 1:6 with 34 Lbs. Of hot bitumen coating sand blinded provided over 2 layers of tiles 12"x6"x1 1/4" laid in 1:6 cement mortar with 1/2" thick sand witched layer 1:6 cement mortar including 1:2 cement pointing underside of tiles complete including curing etc. (S.I.No. 1, P.No. 33 ).
|  |  |  | 380 | Sft. | @ Rs: |  | 11443.1 |  |  | %Sft. |  | Rs. |  | 43484 | /=
(Rs. Eleven Thousand Four Hundred Fourty Three & Ps. Ten Only)
13 | Providing and fixing iron steel grill doors with angle iron frame 1½” X 1½” X 1/4" with approved design and looking arrangement embeded in Masonry as per instruction of Engineer/Incharge (S.I.No: 31, P.No: 94).
|  |  |  | 92 | Sft | @ Rs: |  | 231.6 |  |  | P.Sft |  | Rs. |  | 21307 | /=
(Rs. Two Hundred Thirty One & Ps. Sixty Only))
14 | Supplying and fixing in position iron/steel grill of 3/4" X 1/4" size flat iron of approved design including painting 3 coats etc. complete (weight not to be less then 3.7 lbs/ sq. foot of finished grill. (S.I.No. 26, P.No. 93).
|  |  |  | 81 | Sft | @ Rs: |  | 180.5 |  |  | P.Sft |  | Rs. |  | 14621 | /=
(Rs. One Hundred Eighty & PS. Fifty Only)
15 | Cement plaster 1:6 ratio 1/2" thick upto 12' ft height (S.I.No.13-b, P.No.52).
|  |  |  | 2692 | Sft. | @ Rs: |  | 2206.6 |  |  | %Sft. |  | Rs. |  | 59402 | /=
(Rs. Two Thousand Two Hundred Six & Ps. Sixty Only)
16 | Providing and laying HALA pattern tiles glazed ( 8”x 8”x 1/4” ) on floor or wall facing in required patern of STILE specification jointed in white cement and pigment over a base of 1:2 grey cement mortor 3/4” thick including washing and filling joints with slurry of white cement and pigment in desired shape with finishing, cleaning and cost of wax polish etc complete including cutting tiles to prper profile . ( S.I.No: 62, P.No 48 )
|  |  |  | 107 | Sft. | @ Rs: |  | 34520.31 |  |  | %Sft. |  | Rs. |  | 36937 | /=
(Rs. Thirty Four Thousand Five Hundred Twenty & Ps. Thirty One Only)
17 | Cement plaster 1:4 ratio 3/8" thick upto 12' ft height (S.I.No.11-a, P.No. 52).
|  |  |  | 2585 | Sft. | @ Rs: |  | 2197.52 |  |  | %Sft. |  | Rs. |  | 56806 | /=
(Rs. Twenty One Hndred Ninety Seven & Ps. Fifty Two Only)
18 | Laying floor of approved with glazed tile ¼” thick in white cement 1:2 over ¾” thick cement morter 1:2 complete. (S.I.No. 24, P.No.43).
|  |  |  | 370 | Sft. | @ Rs: |  | 27678.86 |  |  | %Sft. |  | Rs. |  | 102412 | /=
(Three thousand One hundred Seventy six Rupees and Twenty five paisa)
19 | Cement tile (8"x8"x3/4") laid in 1:2 cement mortar over a bed of 3/4" thick cement mortar 1:2 (S.I.No: 13, P.No: 41)
|  |  |  | 417 | Sft. | @ Rs: |  | 10916.65 |  |  | %Sft. |  | Rs. |  | 45522 | /=
(Rs.Ten thousand Nine hundred Sixteen Rupees and Sixty five paisa Only)
20 | Providing and laying 2" thick topping cement concrete (1:2:4) including surface finishing and dividing into panels. (S.I.No. 16-c, P.No.42).
|  |  |  | 12 | Sft. | @ Rs: |  | 3275.5 |  |  | %Sft. |  | Rs. |  | 393 | /=
(Rs. Thir Two Hundred Seventy Five & Ps. Fifty Only
21 | Making notice board made with cement sand.
|  |  |  | 32 | Sft. | @ Rs: |  | 58.11 |  |  | P.Sft. |  | Rs. |  | 1860 | /=
(Rs. Fifty Eight & Ps. Eleven Only)
22 | Khasi Parnalas in cement and sand mortar (1:2) 12" out side width finished smooth with a floating coat of neat cement. (S.I.No.17, P.No.36).
|  |  |  | 22 | Rft. | @ Rs: |  | 70.34 |  |  | P.Rft. |  | Rs. |  | 1547 | /=
(Rs. Seventy & Ps. Thirty four only)
22 | White wash three coats. (S.I.No. 26-c, P.No: 54 ).
|  |  |  | 360 | Sft. | @ Rs: |  | 829.95 |  |  | %Sft. |  | Rs. |  | 2988 | /=
(Rs. Eight Hundred Twenty Nine & Ps. Ninety Five Only)
23 | Colour wash two coats i/c one coat of white wash .(S.I.No. 25-b+26-a, P.No. 54).
|  |  |  | 2105 | Sft. |  | @ Rs: |  | 1276.53 |  |  | %Sft. |  | Rs. | 26871 | /=
(Rs. One Thousand Two Hundred Seventy Six & Ps. Fifty Three Only)
24 | Painting new surface guards, bars, gates, iron bars, gratings,railings(including standards braces,etc).And similar open work three coats (S.I.No. 5-d, P.No: 70 ).
|  |  |  | 427 | Sft. | @ Rs: |  | 1270.83 |  |  | %Sft. |  | Rs. |  | 5426 | /=
(Rs. One Thousand Two Hundred Seventy & Ps. Eighty Three Only)
[10 empty] | Total |  |  | Rs. |  | 822881 | /=
________________________ % Above / Below on the Rates of CSR ADD / Ded: ________% Rs ________________
[10 empty] | Total |  |  | Rs.
Total (A\ = (a+b) in words & figures_______________________________________________________________
________________________________________________________________________________________________
CONTRACTOR