## APP 2016-2017
ANNUAL PROCUREMENT PLAN (Revised)
(WORKS, GOODS & SERVICES)
(FINANCIAL YEAR 2016-2017)
OFFICE OF THE EXECUTIVE ENGINEER EDUCATION WORKS DIVISION MATIARI
Sr. No: | Description of Procurement | Quantity (where applicable) | Estimated Unit Cost (where applicable) | Estimated Total Cost | Funds Allocated | Source of Funds (ADP/ Non-ADP) | Proposed Procurement Method | Timing of Procurement |  |  |  | Remarks
[8 empty] | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
1 | (Provincial ADP No: 251) Establishment of Public Schools in Sindh @ Tando Allahyar, Matiari, Sanghar (T.ADAM), Tando Muhammad Khan & Ghotki (05 Units) 2008-09 Program @ UC Bhitshah Taluka Hala District Matiari (01 Unit) @ Package # 01 a) Hostel Block (Ground Floor) (W/S & S/F) b) Principal Residence (W/S & S/F) | --- | --- | 1.7 | 25 | Provincial ADP | National Competitive Bidding Method | Yes | --- | --- | --- | Subject to release of funds
2 | (Provincial ADP No: 251) Establishment of Public Schools in Sindh @ Tando Allahyar, Matiari, Sanghar (T.ADAM), Tando Muhammad Khan & Ghotki (05 Units) 2008-09 Program @ UC Bhitshah Taluka Hala District Matiari (01 Unit) @ Package # 02 a) Hostel Block (Ground Floor) (Internal E.I. Work) b) Principal Residence (E.I. Work) | --- | --- | 2.5 |  | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
3 | (Provincial ADP No: 251) Establishment of Public Schools in Sindh @ Tando Allahyar, Matiari, Sanghar (T.ADAM), Tando Muhammad Khan & Ghotki (05 Units) 2008-09 Program @ UC Bhitshah Taluka Hala District Matiari (01 Unit) Vice Principal Residence (Bungalow) | --- | --- | 12.5 |  | Provincial ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
4 | (Provincial ADP No: 251) Establishment of Public Schools in Sindh @ Tando Allahyar, Matiari, Sanghar (T.ADAM), Tando Muhammad Khan & Ghotki (05 Units) 2008-09 Program @ UC Bhitshah Taluka Hala District Matiari (01 Unit) Pump room i/c Boring, W/S & S/F, Machine Set | --- | --- | 2.5 |  | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
5 | (Provincial ADP No: 251) Establishment of Public Schools in Sindh @ Tando Allahyar, Matiari, Sanghar (T.ADAM), Tando Muhammad Khan & Ghotki (05 Units) 2008-09 Program @ UC Bhitshah Taluka Hala District Matiari (01 Unit) Mosque | --- | --- | 5 |  | Provincial ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
6 | (Provincial ADP No: 251) Establishment of Public Schools in Sindh @ Tando Allahyar, Matiari, Sanghar (T.ADAM), Tando Muhammad Khan & Ghotki (05 Units) 2008-09 Program @ UC Bhitshah Taluka Hala District Matiari (01 Unit) Academic Block (E.I. Work) | --- | --- | 2.2 |  | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
7 | (Provincial ADP No: 252) Up-Gradation of Middle School to High Schools in Sindh (115 Units) 2008-09 Programme in District Matiari (05 Units) @ GGMS Sahib Samoo (W/S & S/F) | --- | --- | 0.2 | 6 | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
8 | (Provincial ADP No: 252) Up-Gradation of Middle School to High Schools in Sindh (115 Units) 2008-09 Programme in District Matiari (05 Units) @ GMS Allah Bux Balal (E.I. Work) | --- | --- | 0.5 |  | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
9 | (Provincial ADP No: 252) Up-Gradation of Middle School to High Schools in Sindh (115 Units) 2008-09 Programme in District Matiari (05 Units) @ GBMS Gulab Rahu (Science Lab: & lav: Block Portion) | --- | --- | 9 |  | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
10 | (Provincial ADP No: 254) Establishment of Single Section High Schools in Sindh (53 Units) (2008-09 Progm) in District Matiari (02 Units) @ GBHS Matiari City No: II (Int: Services & Ext: Development) |  |  | 6 | 2 | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
11 | (Provincial ADP No: 254) Establishment of Single Section High Schools in Sindh (53 Units) (2008-09 Progm) in District Matiari (02 Units) @ GGHS Hala City No: II (E.I. Work) |  |  | 1 |  | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
12 | (Provincial ADP No: 254) Establishment of Single Section High Schools in Sindh (53 Units) (2008-09 Progm) in District Matiari (02 Units) @ GGHS Hala City No: II (Ext: Development & W/S) |  |  | 3 |  | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
13 | (Provincial ADP No: 255 A) Up-Gradation of Middle School to High School in Sindh 2007-08 Programme (07 Units) @ GMS Faqir Nooh Hothiani (Ext: Development) | --- | --- | 1.6 | 5 | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
14 | (Provincial ADP No: 255 A) Up-Gradation of Middle School to High School in Sindh 2007-08 Programme (07 Units) @ GMS Faqir Nooh Hothiani (E.I. Work) | --- | --- | 0.2 |  | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
15 | (Provincial ADP No: 255 A) Up-Gradation of Middle School to High School in Sindh 2007-08 Programme (07 Units) @ GGMS Sekhat (E.I. Work) | --- | --- | 0.2 |  | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
16 | (Provincial ADP No: 255 B) Up-Gradation of High School to Higher Secondary School in Sindh 2007-08 Programme (03 Units) @ GBHS Tajpur (Lav: Block & Int: Services) | --- | --- | 4 |  | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
17 | (Provincial ADP No: 255 B) Up-Gradation of High School to Higher Secondary School in Sindh 2007-08 Programme (03 Units) @ GBHS Khyber (E.I. Work) | --- | --- | 0.5 |  | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
18 | (Provincial ADP No: 255 B) Up-Gradation of High School to Higher Secondary School in Sindh 2007-08 Programme (03 Units) @ GBHS Bhaledino Kaka (E.I. Work) | --- | --- | 0.5 |  | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
19 | (Provincial ADP No: 256 B) Construction of Science Laboratories in Existing Secondary/ Higher Secondary Schools 2007-08 Prog: (12 Units) @ GBHS MDM (E.I. Work) | --- | --- | 0.1 | 1 | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
20 | (Provincial ADP No: 257) Rehabilitation of Existing High / Higher Secondary Schools in Sindh (250 Units) (2008-09 Progm) in District Matiari (08 Units) @ GBHS Qasim Ji Wasi (External Development) | --- | --- | 1 | 2 | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
21 | (Provincial ADP No: 257) Rehabilitation of Existing High / Higher Secondary Schools in Sindh (250 Units) (2008-09 Progm) in District Matiari (08 Units) @ GBHS Makhdoom Ghulam Hyder (Ren: & Ext: Development) | --- | --- | 2 |  | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
22 | (Provincial ADP No: 288) Re-construction of Government Boys High School (GBHS) Makhdoom Ghulam Hyder, GBHS Saeed Khan Leghari Taluka Hala & Government Boys High School Panjmoro, Taluka Saeedabad, (03 Units) Distt Matiari @ GBHS Panjmoro (E.I. Work) | --- | --- | 0.8 | 27.741 | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
23 | (Provincial ADP No: 288) Re-construction of Government Boys High School (GBHS) Makhdoom Ghulam Hyder, GBHS Saeed Khan Leghari Taluka Hala & Government Boys High School Panjmoro, Taluka Saeedabad, (03 Units) Distt Matiari @ GBHS Panjmoro (Renovation, C/Wall & Ext: Dev) | --- | --- | 5 |  | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
24 | (Provincial ADP No: 288) Re-construction of Government Boys High School (GBHS) Makhdoom Ghulam Hyder, GBHS Saeed Khan Leghari Taluka Hala & Government Boys High School Panjmoro, Taluka Saeedabad, (03 Units) Distt Matiari @ GBHS Saeed Khan Leghari (Repair & Renovation) | --- | --- | 12 |  | Provincial ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
25 | (District ADP No: 98/98 b) Addition of Class Room in Existing Primary School in District Matiari (2006-2007) Programme (12 Classrooms) (12 Units) & Construction / Re-Construction of Dangerous Primary / Elementary Schools in Taluka Hala & Saeedabad District Matiari (04 Units) (Revised) Package # 3 @ a) GBPS Bego Kaka (E.I. Work) b) GBPS Mehmood Chandio (E.I. Work) | --- | --- | 0.4 | 2 | District ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
26 | (District ADP No: 100/100 b) Construction of Building for Existing Shelterless Primary School (04-Units) (2008-2009 Program) & Construction / Re-Construction of Dangerous Primary / Elementary Schools in Taluka Matiari, Hala & Saeedabad District Matiari (04 Units) @ GBPS Ishaque Tagar (Ext: Dev:, W/S & S/F) | --- | --- | 0.18 | 0.579 | District ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
27 | (District ADP No: 100/100 b) Construction of Building for Existing Shelterless Primary School (04-Units) (2008-2009 Program) & Construction / Re-Construction of Dangerous Primary / Elementary Schools in Taluka Matiari, Hala & Saeedabad District Matiari (04 Units) @ GBPS Ishaque Tagar (E.I. Work) | --- | --- | 0.1 |  | District ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
28 | (District ADP No: 100/100 b) Construction of Building for Existing Shelterless Primary School (04-Units) (2008-2009 Program) & Construction / Re-Construction of Dangerous Primary / Elementary Schools in Taluka Matiari, Hala & Saeedabad District Matiari (04 Units) @ GGPS Tayab Dahri (E.I. Work) | --- | --- | 0.15 |  | District ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
29 | (District ADP No: 101 b) Up-Gradation of Primary School to Middle Schools in Taluka Matiari (01 Unit) (2008-2009 Program) & Construction / Re-Construction of Dangerous Primary / Elementary Schools (07 Units) in Taluka Hala & Matiari District Matiari (Revised) @ GBPS Mohammad Ali Sangrasi (E.I. Work) | --- | --- | 0.1 | 1 | District ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
30 | (District ADP No: 103 a) Construction of Government Girls Primary School @ Village Suleman Khatiyan shifted to GGPS Dato Junejo Taluka & District Matiari (E.I. Work) | --- | --- | 0.1 | 1.5 | District ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
31 | (District ADP No: 3) Construction of Building for Existing Shelterless Primary School and Construction / Re-Construction of Existing Primary School in District Matiari 2015-16 Programme (02-Units) @ GPS Kareem Bux Khoso UC Matiari (Shelterless) (E.I. Work) | --- | --- | 0.2 | 2.5 | District ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
32 | (District ADP No: 104 b) Construction / Re-Construction of Dangerous High Schools (02 Units) in Taluka Hala & Matiari District Matiari @ GBDC Matiari ( E.I. Work) | --- | --- | 0.2 | 2.642 | District ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
33 | (District ADP No: 1) Rehabilitation & Missing Facilities Lav: Block in Existing Grils Primary / Boys Primary Schools / Secondary Schools in Taluka & District Matiari (2015-16 Programme) (24-Units) Package # 4 @ a) GGPS Soomar Chand (Rehabilitation & Lav: Block) (E.I. Work) b) GGPS Hashmi Masjid (Rehabilitation & Lav: Block) (E.I. Work) | --- | --- | 0.35 | 2 | District ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
34 | (District ADP No: 1) Rehabilitation & Missing Facilities Lav: Block in Existing Grils Primary / Boys Primary Schools / Secondary Schools in Taluka & District Matiari (2015-16 Programme) (24-Units) Package # 5 @ a) GGPS Bau Khan Pathan (Lav: Block) b) GBPS Wasi Baqadar Shah (Lav: Block) c) GGPS Gahelo Porath (Lav: Block) | --- | --- | 1.29 |  | District ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
35 | (District ADP No: 1) Rehabilitation & Missing Facilities Lav: Block in Existing Grils Primary / Boys Primary Schools / Secondary Schools in Taluka & District Matiari (2015-16 Programme) (24-Units) Package # 6 @ a) GBPS Mir Muhammad Jahejo (Lav: Block) b) GGPS Nobat Mari (Lav: Block) c) GGPS Pinyo Khidri (Lav: Block) | --- | --- | 1.26 | 2 | District ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
36 | (District ADP No: 1) Rehabilitation & Missing Facilities Lav: Block in Existing Grils Primary / Boys Primary Schools / Secondary Schools in Taluka & District Matiari (2015-16 Programme) (24-Units) Package # 7 @ a) GBPS Safal Panhwer (Lav: Block) b) GGPS Sher Muhammad Thora (Lav: Block) c) GGPS Wahab Shah (Lav: Block) d) GBPS Loung Khan Jiskani (Lav: Block) | --- | --- | 1.72 |  | District ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
37 | (District ADP No: 1) Rehabilitation & Missing Facilities Lav: Block in Existing Grils Primary / Boys Primary Schools / Secondary Schools in Taluka & District Matiari (2015-16 Programme) (24-Units) @ GGPS Bair Masjid (Rehabilitation & Lav: Block) | --- | --- | 3.4 |  | District ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
38 | (District ADP No: 2) Provision Missing Facilities of Compound Wall and Lav: Block in Existing Girls & Boys Primary / Secondary Schools in Taluka & District Matiari. 2015-16 Programme (19-Units) @ GGPS Muhammad Yousif Arain (Compound Wall & Lav: Block) | --- | --- | 1.53 | 1.84 | District ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
39 | (District ADP No: 2) Provision Missing Facilities of Compound Wall and Lav: Block in Existing Girls & Boys Primary / Secondary Schools in Taluka & District Matiari. 2015-16 Programme (19-Units) @ GBPS Darya Khan Talpur (Compound Wall & Lav: Block) | --- | --- | 2 |  | District ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
40 | (District ADP No: 2) Provision Missing Facilities of Compound Wall and Lav: Block in Existing Girls & Boys Primary / Secondary Schools in Taluka & District Matiari. 2015-16 Programme (19-Units) @ GGPS Qasim Ji Wasi (Lav: Block) | --- | --- | 0.43 |  | District ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
41 | (District ADP No: 2) Provision Missing Facilities of Compound Wall and Lav: Block in Existing Girls & Boys Primary / Secondary Schools in Taluka & District Matiari. 2015-16 Programme (19-Units) Package # 8 @ a) GGPS Penar Hamopota (Lav: Block) b) GGPS Shaikh Tear (Lav: Block) c) GGPS Jumo Khoso (Lav:Block) | --- | --- | 1.29 |  | District ADP | ---- do ---- | Yes | --- | --- | --- | ---- do ----
42 | (New Provincial ADP No: 167 of 2016-17) Rehabilitation, Improvement / Renovation & Provision for Missing Facilities in Existing Primary / Elementary School @ District Level in District Matiari (04 Units) @ GBPS Mudho Kaka | --- | --- | 5.136 | 5 | Provincial ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
43 | (New Provincial ADP No: 167 of 2016-17) Rehabilitation, Improvement / Renovation & Provision for Missing Facilities in Existing Primary / Elementary School @ District Level in District Matiari (04 Units) @ GBPS Mochi Mohalla | --- | --- | 6.445 |  | Provincial ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
44 | (New Provincial ADP No: 167 of 2016-17) Rehabilitation, Improvement / Renovation & Provision for Missing Facilities in Existing Primary / Elementary School @ District Level in District Matiari (04 Units) @ GBPS Urdu Saeedabad | --- | --- | 11.959 |  | Provincial ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
45 | (New Provincial ADP No: 167 of 2016-17) Rehabilitation, Improvement / Renovation & Provision for Missing Facilities in Existing Primary / Elementary School @ District Level in District Matiari (04 Units) @ GGPS Amin Lakho | --- | --- | 5.373 |  | Provincial ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
46 | (New Provincial ADP No: 196 of 2016-17) Construction of Building for Shelterless Primary School District Matiari (06 Units) @ GBPS Siddique Chohan | --- | --- | 4.263 | 5 | Provincial ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
47 | (New Provincial ADP No: 196 of 2016-17) Construction of Building for Shelterless Primary School District Matiari (06 Units) @ GBPS Mehmood Arain | --- | --- | 4.263 | 5 | Provincial ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
48 | (New Provincial ADP No: 196 of 2016-17) Construction of Building for Shelterless Primary School District Matiari (06 Units) @ GBPS Aijaz Unar | --- | --- | 4.326 |  | Provincial ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
49 | (New Provincial ADP No: 196 of 2016-17) Construction of Building for Shelterless Primary School District Matiari (06 Units) @ GBPS Mir Khan Jamali | --- | --- | 4.366 |  | Provincial ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
50 | (New Provincial ADP No: 196 of 2016-17) Construction of Building for Shelterless Primary School District Matiari (06 Units) @ GBPS Syed Shamusddin Shah | --- | --- | 4.344 |  | Provincial ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
51 | (New Provincial ADP No: 196 of 2016-17) Construction of Building for Shelterless Primary School District Matiari (06 Units) @ GBPS Bachal Goth | --- | --- | 4.349 |  | Provincial ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
52 | (New Provincial ADP No: 313 of 2016-17) Rehabilitation, Improvement / Renovation & Provision for Missing Facilities in Existing Secondary / Higher Secondary Schools @ District Level in District Matiari (01 Unit) @ GBHS New Saeedabad | --- | --- | 20 | 10 | Provincial ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
53 | (New Provincial ADP No: 427 of 2016-17) Construction of Building for Existing Degree College @ Mansoorah District Matiari (01 Unit) Main Building (Ground Floor) | --- | --- | 24.98 | 20 | Provincial ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
54 | (New Provincial ADP No: 427 of 2016-17) Construction of Building for Existing Degree College @ Mansoorah District Matiari (01 Unit) Compound Wall | --- | --- | 5.703 |  | Provincial ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
55 | (New Provincial ADP No: 428 of 2016-17) Rehabilitation & Provision of Missing Facilitates in Existing Colleges in Hyderabad Division (Hyderabad, Matiari, Jamshoro, T.M. Khan, Badin, Dadu, Thatta, Sujawal & T.Allahyar) in District Matiari (01 Unit) @ GGDC Hala | --- | --- | 4.7 | 5 | Provincial ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
56 | (New Provincial ADP No: 434 of 2016-17) Construction of Auditorium Hall in Existing Girls Degree College Hala (01 Unit) | --- | --- | 4.7 | 5 | Provincial ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
57 | (Provincial ADP No: 251 of 2016-17) Establishment of Public Schools in Sindh @ Tando Allahyar, Matiari, Sanghar (T.ADAM), Tando Muhammad Khan & Ghotki (05 Units) 2008-09 Program @ UC Bhitshah Taluka Hala District Matiari (01 Unit) Hostel Block (Dining Hall) | --- | --- | 17 | 35 | Provincial ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
58 | (Provincial ADP No: 288 of 2016-17) Re-construction of Government Boys High School (GBHS) Makhdoom Ghulam Hyder, GBHS Saeed Khan Leghari Taluka Hala & Government Boys High School Panjmoro, Taluka Saeedabad, (03 Units) Distt Matiari @ GBHS Panjmoro (Face Lifting & Path) | --- | --- | 1.659 | 27.741 | Provincial ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
59 | (New District ADP No: 01 of 2016-17) Construction of Additional Classroom in Boys Primary School @ Shafi Muhammad Dahri Taluka Hala District Matiari (2016-17 Program) Main Building (Civil Work) | --- | --- | 3.099 | 3 | District ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
60 | (New District ADP No: 02 of 2016-17) Construction of Additional Classroom in Boys Primary School @ Yaqoob Shahid, Bhithshah Taluka Hala District Matiari (2016-17 Program) Main Building (Civil Work) | --- | --- | 3.097 | 3 | District ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
61 | (New District ADP No: 03 of 2016-17) Provision of Missing Facilities of Compound Wall & Lav: Block in Existing Secondary School @ GBHS Tajpur Taluka & District Matiari (2016-17 Program) | --- | --- | 3.7 | 3.7 | District ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
62 | (District ADP No: 123 of 2016-17) Up-Gradation of Middle School to High Schools in Taluka Hala (01 Unit) (2008-2009 Prog) (Revised) @ GBMS K.K Nizamani (Main Building Balance Work, Lav: Block & C/Wall) | --- | --- | 4.178 | 1 | District ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
63 | (District ADP No: 124 of 2016-17) Rehabilitation & Missing Facilities Lav: Block in Existing Girls Primary / Boys Primary Schools / Secondary Schools in Taluka & District Matiari (2015-16 Programme) (24-Units) @ GGPS Bau Khan Pathan (Lav: Block) | --- | --- | 0.43 | 3 | District ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
64 | (District ADP No: 124 of 2016-17) Rehabilitation & Missing Facilities Lav: Block in Existing Girls Primary / Boys Primary Schools / Secondary Schools in Taluka & District Matiari (2015-16 Programme) (24-Units) @ GGPS Bair Masjid (Rehabilitation & Lav: Block) | --- | --- | 4.173 |  | District ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
65 | (District ADP No: 125 f 2016-17) Provision Missing Facilities of Compound Wall and Lav: Block in Existing Girls & Boys Primary / Secondary Schools in Taluka & District Matiari. 2015-16 Programme (19-Units) @ GBPS Photo Dahri (Lav: Block) | --- | --- | 0.43 | 2.52 | District ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
66 | (District ADP No: 125 f 2016-17) Provision Missing Facilities of Compound Wall and Lav: Block in Existing Girls & Boys Primary / Secondary Schools in Taluka & District Matiari. 2015-16 Programme (19-Units) @ GGPS Baqil Pota (Lav: Block) | --- | --- | 0.43 |  | District ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
67 | (District ADP No: 125 f 2016-17) Provision Missing Facilities of Compound Wall and Lav: Block in Existing Girls & Boys Primary / Secondary Schools in Taluka & District Matiari. 2015-16 Programme (19-Units) @ GGPS Muharrum Khaskheli (Lav: Block) | --- | --- | 0.43 |  | District ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
68 | (District ADP No: 125 f 2016-17) Provision Missing Facilities of Compound Wall and Lav: Block in Existing Girls & Boys Primary / Secondary Schools in Taluka & District Matiari. 2015-16 Programme (19-Units) @ GBPS Darya Khan Talpur (Compound Wall & Lav: Block) | --- | --- | 2 |  | District ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
69 | (District ADP No: 125 f 2016-17) Provision Missing Facilities of Compound Wall and Lav: Block in Existing Girls & Boys Primary / Secondary Schools in Taluka & District Matiari. 2015-16 Programme (19-Units) @ GGPS Shaikh Tear (Lav: Block) | --- | --- | 0.43 |  | District ADP | ---- do ---- | --- | --- | Yes | --- | ---- do ----
Executive Engineer
Education Works Division Matiari