## Financial Review
FINANCIAL REVIEW
NAME OF WORK:- |  |  | ESTABLISHMENT OF GOVT. GIRLS DEGREE COLLEGE GULSHAN-E-MAYMAR SHIFTED TO SECTOR 5-A/3, NORTH KARACHI.
| P.C-1 Cost | [6 empty] | 46.777 | million
P.C-1 Break Up
1 | Main Building | [6 empty] | 25367456
2 | Auditorium | [6 empty] | 8127648
3 | Add. Of 15% External Development | [6 empty] | 5024265
4 | C/Wall Arrow Grill in/c 2 iron gate & Guard Room | [6 empty] | 1906100
5 | Sertvices (U.G.Tank,O.H.Tank,P.Room and Electric Motor | [6 empty] | 952000
6 | External Drainage & Water Supply | [6 empty] | 500000
7 | Energization Charges for Elec:Sui Gas & Water Connection | [6 empty] | 1500000
8 | Soil Investigation | [6 empty] | 200000
9 | Termite Proofing | [6 empty] | 200000
10 | Face Lifting | [6 empty] | 1500000
11 | Land Escaping and Plantation | [6 empty] | 1000000
12 | Road and Path | [6 empty] | 500000
|  |  |  | Total Cost of Civil Work |  |  |  | 46777469
Provision of P.C-1
| P.C-1 Cost | [6 empty] | 46777469
| Add. 15% Premisible Limit | [6 empty] | 7016620.35
|  |  |  | Total Cost of Estimate |  |  |  | 53794089.35
| Description of Works |  | Tech:Sanction | Expdtre |  | Anticipated | Comp. Cost | Saving
| Main Building |  | 0 | 7671126 |  | -7671126 | 0 | 0 | Work in Progress
| Ext. Development |  | 3550000 | 0 |  | 3550000 | 3550000 | 0
|  |  | 3550000 | 7671126 | 0 | -4121126 | 3550000 | 11221126
STATEMENT SHOWING OF EXCESS / SAVING
P.C-1 Provision |  | Upto date Expenditure |  |  |  | Excess |  | Saving
53794089.35 |  | 3550000 |  |  |  | ---- |  | 50244089.35
Deputy City Officer
Education Works New Karachi Town
[5 empty] | DEPUTY CITY OFFICER |  | City District Government Karachi
EDUCATION WORKS NEW KARACHI TOWN
KARACHI

## Abstract
SCHEDULE 'B'
NAME OF WORK:- |  | MAINTINANCE / REPAIR OF GOVT:BOYS ELEMENTARY SCHOOL 15/A-3 BUFFERZONE AT 7D-2 NORTH KARACHI (SEMIS CODE 408130186)
S.No | DESCRIPTION OF ITEM. |  | QNTY | Rate | Unit | Amount
1 | Removing cement or lime plaster
|  |  | 215 | 121 | %Sft | 260.15
2 | Scraping ordinary distemper and oil bound distemper or paint on walls.S.I54-B/P-13
|  |  | 13972.9 | 226.84 | %Sft | 31696.1264
3 | SCRAPING , BRUSHING AND REMOVING OLD PAINT FROM METAL SURFACE S.I-68/3
|  |  | 322.74 | 605 | %Sft | 1952.577
4 | BRUSHING AND SCRAPING BLUSTER OF OLD PAINTS FROM WOOD WORK
|  |  | 424.5 | 151.25 | %Sft | 642.0562
5 | Nicking concrete surface (S.I.18/17)
|  |  | 4255.52 | 272.25 | %Sft | 11585.6532
6 | DISMANTLING CEMENT BLOCK MASONARY 1:3:6. (S.I. 14/P-11)
|  |  | 3740.95 | 1134.38 | %Cft | 42436.5886
7 | EXCAVATION IN FOUNDATION OF BUILDING BRIDGES AND OTHER STRUCTURE I/C DEGABILLING DRESSING REFILLING, AROUND STRUCTURE WITH EXCAVATED EARTH WATERIG AND RAMMING LEAD UPTO 5 FT IN ORDINARY SOIL (S.I.NO:18-B/P-5).
|  |  | 5544.25 | 3176.25 | %0Cft | 17609.9241
8 | CEMENT CONCRETE BRICK STONE BALLAST 1 1/2" TO 2" GUAGE RATIO1:4:8 (S.I.17/4b)
|  |  | 1586.88 | 9416.28 | % Cft | 149425
9 | R.C.C WORK IN/C ALL LABOUR & MATERIAL EXCEPT THE COST OF STEEL R/F & BENDING & BINDING WHICH WILL BE PAID SEPARATELY. R.C.C WORK ROOF SLAB BEAMS COLUMNS RAFTS LINTEL AND OTHER STRUCTURE MEMBER LAID IN SITU OR PRE CAST LAID IN POSITION COMPLETE IN ALL RESPECT RATIO 1:2:4. (S.I.6-A-II/P-18)
|  |  | 3156.96 | 337 | P.Cft | 1063896
10 | ERRECTION & REMOVAL OF VERTICAL CENTERING FOR R.C.C PLAIN OR CEMENT CONCRETE WORK OF PARTAL WOOD (2ND CLASS) (S.I.NO.18-B/P-21).
|  |  | 5765.94 | 3127.41 | %Sft | 180324.5842
11 | CEMENT CONCERETE PLAIN IN/C PLACING COMPACTING FINISHING CURING COMPLETE & SCREENING & WASHING OF STONE AGGREGATE WITHOUT SHUTTERING RATIO 1:3:6 (S.I.NO.5-H P-18).
|  |  | 1931.59 | 12595 | %Cft | 243283.7605
12 | P/l 1:3:6 c.c solid block masonry wall 6" below in thickness set in 1:6 c.m in G.F super structure I/c raking out joints & curing etc, complete. (S.I.No: 23/ 22)
|  |  | 3629.74 | 15771.01 | %Cft | 572446.6584
13 | CEMENT PLASTER 1:4 UPTO 20 HEIGHT (C) 3/4" THICK. (S.I.NO.11(c) P-58)
|  |  | 20428.7 | 3015.76 | %Sft | 616080.5631
14 | PREPARING THE SURFACE AND PAINTING WITH WEATHER COAT I/C RUBBING THE SURFACE WITH RUBBING BRICK / AND SAND PAPER, FILLING WITH VOIDS WITH WEATHER COAT OF APPROVED MAKE. (S.I.NO.38.A/P-56).
|  |  | 20428.7 | 2576.95 | %Sft | 526437.3847
15 | Distempering 2 Coats S.I54/24-b)
|  |  | 3164.26 | 1043.9 | %Sft | 33031.7101
16 | Painting With Enemal paint on masonary wall. (S.I.56/41).
|  |  | 9145.65 | 1402.37 | %Sft | 128255.8519
17 | PAINTING OLD SURFACES PAINTING GUARD BARS, GATES IRON BARS GRATINGS, RAILINGS IN/C STANDARD BRACES (ETC) AND SIMILAR OPEN WORK. (FIRST COAT & EACH SUBSEQUENT COAT). (S.I. 4-D/75)
|  |  | 834.74 | 674.6 | %Sft | 5631
18 | PAINTING OLD SURFACE PAINTING DOORS & WINDOWS ANY TYPE. (S.I.4-C/P-68)
|  |  | 424.5 | 1160.06 | %Sft | 4924
19 | Providing and laying topping cement concrete 1:2:4 including surface finishing and dividing into panels 2" thick. (S.I.No. 16 (b) / p-47)
|  |  | 522 | 3275.5 | %Sft | 17098.11
20 | P/F COLOUR CREATE TO WALL SURFACE TO PROVIDE, DURABLE CRUST AND AESTHETICS HAVING THICKNESS UPTO 3/4" WITH SPECIFIED COLOUR HAVING WATER, FIRE & TERMITE RESISTANCE (UPTO 20' HEIGHT) (S.I.NO.44/P-63).
|  |  | 3665.14 | 6319.5 | %Sft | 231618.5223
21 | Rubbing and Polishing of old mosaic floor(S.I.43/26)
|  |  | 3164.26 | 1228.92 | %Sft | 38886.224
22 | Filling watering and ramming new earth from out side lead upto one chain and lift upto 5 feet (S.I.4/22)
|  |  | 16125 | 3630 | %0Cft | 58533.75
23 | Add Lead Upto 10 Miles.
|  |  | 16125 | 1065 | %Cft | 171731.25
|  |  | Total Cost Rs. |  |  | 4059214.2932
NON SCHEDULE ITEMS
1 | Removing old debries rubbish construction remenants all kind and size beyond munciple limit and clearance of space in/c loading unloading etc complete as directed by Engineer Incharge (10 miles) carriage of material.
|  |  | 3740.95 | 902.2 | %Cft | 33750.8509
2 | Difference of Sulphate Resistant Cement.
|  |  | 938.17 | 40 | P.Bag | 37526.8
|  |  | Total |  |  | 71277.6509
Fancy Items
1 | Split tile 1/4"thick matt glazed or double glazed jointed in white cement and lead over 1:2 grey cement sand mortar 3/4"thick in/c finishing complete (Flooring and Facing)(S.I.49/69)
|  |  | 887.96 | 21021.11 | % Sft | 186659.0484
|  |  | Total Cost Rs. |  |  | 186659.0484
Steel Work
1 | P/F iron steel grill using solid square bars of size 1/2"x1/2" placed at 4" including and frame of flate iron patti of 3/4'' x 3/4'' inclusing circle shape at 1-0 part equlvalent fitted with screw and pins i/c 3 coat with first coat of red oxide paint etc.s.i30-p-94)
|  |  | 84.06 | 194.16 | P.Sft | 16321
2 | FABRICATION OF STEEL R/F FOR C.C IN/C CUTTING BENDING LAYING IN POSITION MAKING AND FASTENING IN/C COST OF BINDING WIRE (ALSO IN/C REMOVAL OF RUST FROM BARS)(S.I.NO.7 (A & B)/P-20) ( Deformed Bars)
|  |  | 197.31 | 5001.7 | P.Cwt | 986885
|  |  | Total Cost Rs. |  |  | 986885

## Summary of Cost
SUMMARY OF COST
NAME OF WORK:- |  | MAINTINANCE / REPAIR OF GOVT:BOYS ELEMENTARY SCHOOL 15/A-3 BUFFERZONE AT 7D-2 NORTH KARACHI (SEMIS CODE 408130186)
CIVIL WORK
| COST OF Schedule |  |  |  | Rs: | 5309298
| COST OF Non Schedule |  |  |  | Rs: | 71278
| ADD PREMIUNM 10 % Steel Work |  |  |  | Rs: | 100320
| LESS PREMIUNM 20 % TILES |  |  |  | Rs: | 37331.6
| COST OF CARRIAGE |  |  |  | Rs: | 297947
| BOURING |  |  |  | Rs: | 247111
| Net Amount |  |  | Total | Rs: | 5988622.4
[5 empty] | Rs. In Million | 5.9886
Sub-Engineer
|  |  | Assistant Engineer |  | Executive Engineer
|  |  | Education Works Sub-Division New Karachi |  | Education Works Division-II
|  |  | Karachi |  | Karachi

## Measurement
E S T I M A T E
NAME OF WORK:- |  | MAINTINANCE / REPAIR OF GOVT:BOYS ELEMENTARY SCHOOL 15/A-3 BUFFERZONE AT 7D-2 NORTH KARACHI (SEMIS CODE 408130186)
S.No | Description. | [11 empty] | Qty |  | Total
1 | Removing cement or lime plaster.(S.I.14/53)
| Building Ext F/S Plinth |  |  |  |  | 1 | x | 60.57 | x | 3.5 |  |  | = | 211.995
| Offset |  |  |  |  | 1 | x | 1 | x | 3 |  |  | = | 3
214.995
[10 empty] | @Rs |  | 121 |  | %Sft | 260.144
2 | Scraping ordinary distemper and oil bound distemper or paint on walls.S.I.(13/54-b)
G-Floor Internal
| C/Room Ceilling | 1 | x | 1 | x | 22.42 | x | 15.92 |  |  |  |  | = | 356.9264
| " | 1 | x | 1 | x | 19.92 | x | 15.92 |  |  |  |  | = | 317.1264
| Beam | 1 | x | 2 | x | 15.75 | x | 2 |  |  |  |  | = | 63
| H.M Office | 1 | x | 1 | x | 15.92 | x | 11.67 |  |  |  |  | = | 185.7864
| W.C | 1 | x | 1 | x | 7.42 | x | 4.82 |  |  |  |  | = | 35.7644
| Lav Block | 1 | x | 1 | x | 7.42 | x | 10.42 |  |  |  |  | = | 77.3164
| Ver Ceilling | 1 | x | 1 | x | 20.42 | x | 6 |  |  |  |  | = | 122.52
| '' | 1 | x | 1 | x | 20 | x | 7 |  |  |  |  | = | 140
| Window Shade | 5 | x | 2 | x | 6 | x | 1.5 |  |  |  |  | = | 90
| '' | 1 | x | 2 | x | 7 | x | 1.5 |  |  |  |  | = | 21
[12 empty] | Total A |  | 1409.44
F-Floor Internal
| C/Room Ceilling | 1 | x | 1 | x | 22.42 | x | 15.92 |  |  |  |  | = | 356.9264
| " | 1 | x | 1 | x | 19.92 | x | 15.92 |  |  |  |  | = | 317.1264
| " | 1 | x | 1 | x | 19.42 | x | 15.92 |  |  |  |  | = | 309.1664
| Beam | 2 | x | 2 | x | 15.92 | x | 2 |  |  |  |  | = | 127.36
| Ver Ceilling | 1 | x | 1 | x | 20.42 | x | 6 |  |  |  |  | = | 122.52
| " | 1 | x | 1 | x | 20 | x | 7 |  |  |  |  | = | 140
| Window Shade | 6 | x | 2 | x | 5 | x | 1.5 |  |  |  |  | = | 90
| '' | 1 | x | 2 | x | 7 | x | 1.5 |  |  |  |  | = | 21
| Chujja | 1 | x | 2 | x ( | 63.57 | + | 26.67 | ) x | 1.5 |  |  | = | 270.72
[12 empty] | Total B |  | 1754.8192
G-Floor Internal Wall
| C/R Wall | 1 | x | 2 | x ( | 22.42 | + | 15.92 | ) x | 11.16 |  |  | = | 855.7488
| '' | 1 | x | 2 | x ( | 19.92 | + | 15.72 | ) x | 11.16 |  |  | = | 795.4848
| H.M.Office | 1 | x | 2 | x ( | 15.92 | + | 11.67 | ) x | 11.16 |  |  | = | 615.8088
| H.M.W.C | 1 | x | 2 | x ( | 4.42 | + | 4.82 | ) x | 7 |  |  | = | 129.36
| Lav Block | 1 | x | 2 | x ( | 3.42 | + | 10.42 | ) x | 7 |  |  | = | 193.76
| W.C | 2 | x | 2 | x ( | 5 | + | 3.42 | ) x | 7 |  |  | = | 235.76
| Verandah | 2 | x | 1 | x | 40.42 | x | 11.16 |  |  |  |  | = | 902.1744
| Offset | 1 | x | 1 | x | 6 | x | 11.16 |  |  |  |  | = | 66.96
| " | 1 | x | 1 | x | 7 | x | 11.16 |  |  |  |  | = | 78.12
[12 empty] | Total C |  | 3873.1768
F-Floor Internal Wall
| C/R Wall | 1 | x | 2 | x ( | 22.42 | + | 15.92 | ) x | 11 |  |  | = | 843.48
| " | 1 | x | 2 | x ( | 19.92 | + | 15.92 | ) x | 11 |  |  | = | 788.48
| " | 1 | x | 2 | x ( | 19.42 | + | 15.92 | ) x | 11 |  |  | = | 777.48
| Verandah | 2 | x | 1 | x | 40.42 | x | 11 |  |  |  |  | = | 889.24
| S/Wall | 1 | x | 1 | x | 6 | x | 11 |  |  |  |  | = | 66
| " | 1 | x | 1 | x | 7 | x | 11 |  |  |  |  | = | 77
[12 empty] | Total D |  | 3441.68
G-Floor External
| Building | 1 | x | 2 | x ( | 60.57 | + | 23.67 | ) x | 11.25 |  |  | = | 1895.4
| Offset | 1 | x | 1 | x | 1 | x | 11.25 |  |  |  |  | = | 11.25
[12 empty] | Total E |  | 1906.65
F-Floor External
| Building | 1 | x | 2 | x ( | 60.57 | + | 23.67 | ) x | 11.25 |  |  | = | 1895.4
| Offset | 1 | x | 1 | x | 1 | x | 11.25 |  |  |  |  | = | 11.25
[12 empty] | Total F |  | 1906.65
| Qty A+B+C+D+E+F+G) |  |  | 1409.44 | + | 1754.8192 | + | 3873.1768 | + | 3441.68 | + | 1906.65
|  |  | + | 1906.65 | [8 empty] | = | 14292.416
Deduction
| Door | 6 | x | 1 | x | 4 | x | 3 |  |  |  |  | = | 72
| Window | 1 | x | 1 | x | 6 | x | 4 |  |  |  |  | = | 24
| Door | 2 | x | 1 | x | 4 | x | 4 |  |  |  |  | = | 32
| D/Wall | 3 | x | 1 | x | 3.5 | x | 7 |  |  |  |  | = | 73.5
| Ent Opp | 2 | x | 1 | x | 4.67 | x | 6 |  |  |  |  | = | 56.04
| D/Wall | 1 | x | 1 | x | 4.33 | x | 6 |  |  |  |  | = | 25.98
| Ent Opp | 2 | x | 1 | x | 2 | x | 9 |  |  |  |  | = | 36
[12 empty] | Total G |  | 319.52
|  |  |  | 14292.416 | - | 319.52 | [7 empty] | 13972.896
[10 empty] | @Rs |  | 226.88 |  | %Sft | 31701.7064
3 | Scraping brushing and removing old paint from mtal surface (P.No.68/S.I-3)
G-Floor
| Window Grill |  |  | 5 | x | 1 | x | 4 | x | 4 |  |  | = | 80
| '' '' |  |  | 1 | x | 1 | x | 4 | x | 4 |  |  | = | 16
| D/wall |  |  | 1 | x | 1 | x | 4.67 | x | 6 |  |  | = | 28.02
| '' '' |  |  | 1 | x | 1 | x | 4.37 | x | 6 |  |  | = | 26.22
| Entrance Door |  |  | 1 | x | 1 | x | 6 | x | 8.75 |  |  | = | 52.5
[12 empty] | Total A |  | 202.74
F-Floor
| Window Grill |  |  | 6 | x | 1 | x | 4 | x | 4 |  |  | = | 96
| '' '' |  |  | 1 | x | 1 | x | 6 | x | 4 |  |  | = | 24
[12 empty] | Total B |  | 120
| Net Qty A+B |  |  | 202.74 | + | 120 |  |  |  |  | Total |  | = | 322.74
[10 empty] | @Rs |  | 605 |  | % Sft | 1953
4 | BRUSHING AND SCRAPING BLUSTER OF OLD PAINTS FROM WOOD WORK (S.I.-2/P-68)
G-Floor
| C/Room Window |  |  | 8 | x | 1 | x | 4 | x | 4 |  |  | = | 128
| '' '' |  |  | 1 | x | 1 | x | 6 | x | 4 |  |  | = | 24
| Door |  |  | 4 | x | 1 | x | 3.5 | x | 7 |  |  | = | 98
| '' '' |  |  | 3 | x | 1 | x | 2.5 | x | 7 |  |  | = | 52.5
[12 empty] | Total A |  | 302.5
F-Floor
| Window Grill |  |  | 6 | x | 1 | x | 4 | x | 3 |  |  | = | 72
| '' '' |  |  | 2 | x | 1 | x | 4 | x | 4 |  |  | = | 32
| '' '' |  |  | 1 | x | 1 | x | 6 | x | 3 |  |  | = | 18
[12 empty] | Total B |  | 122
| Net Qty A+B |  |  | 302.5 | + | 122 |  |  |  |  | Total |  | = | 424.5
[10 empty] | @Rs |  | 151.25 |  | %Sft | 642.0562
5 | Nikking Concrete Surface (S.I/P18/17a)
| Building | 1 | x | 2 | x ( | 60.67 | + | 23.67 | )x | 25 |  |  | = | 4217
| Chajja Build | 1 | x | 2 | x ( | 60.67 | + | 23.67 | )x | 1.5 |  |  | = | 253.02
[12 empty] | Total A |  | 4470.02
Deduction
| D/Wall G+F | 3 | x | 1 | x | 4.67 | x | 6 |  |  |  |  | = | 84.06
| '' '' '' | 3 | x | 1 | x | 4.33 | x | 6 |  |  |  |  | = | 77.94
| Ent Gate | 1 | x | 1 | x | 6 | x | 8.75 |  |  |  |  | = | 52.5
[12 empty] | Total B |  | 214.5
| Net Qty (A-B) |  |  | 4470.02 | - | 214.5 | [7 empty] | 4255.52
[10 empty] | @Rs |  | 272.25 |  | %Sft | 11585.6532
6 | P/F iron steel grill using solid square bars of size 1/2"x1/2" placed at 4" including and frame of flate iron patti of 3/4'' x 3/4'' inclusing circle shape at 1-0 part equlvalent fitted with screw and pins i/c 3 coat with first coat of red oxide paint etc.s.i30-p-94)
| F-F D/Wall |  |  | 3 | x | 4.67 | x | 6 |  |  |  |  | = | 84.06
[12 empty] | Total |  | 84.06
[10 empty] | @Rs |  | 194.16 |  | P.sft | 16321.0896
7 | DISMANTLING CEMENT BLOCK MASONARY. (S.I. 14/P-11)
C/WLL
| F/ B C/Wall | 2 | x | 320 | x | 0.42 | x | 6.16 |  |  |  |  | = | 1655.808
| Stair | 1 | x | 265 | x | 0.42 | x | 6 |  |  |  |  | = | 667.8
| '' | 1 | x | 165 | x | 0.42 | x | 6.16 |  |  |  |  | = | 426.888
| Pillars | 64 | x | 0.82 | x | 0.33 | x | 6 |  |  |  |  | = | 103.9104
| '' | 63 | x | 0.82 | x | 0.33 | x | 6 |  |  |  |  | = | 102.2868
| Plinth F/B | 2 | x | 320 | x | 0.82 | x | 1 |  |  |  |  | = | 524.8
| '' S/Wall | 1 | x | 265 | x | 0.82 | x | 1 |  |  |  |  | = | 217.3
| '' '' | 1 | x | 165 | x | 0.82 | x | 1 |  |  |  |  | = | 135.3
[12 empty] | Total 'A' |  | 3834.0932
Deduction
| M.Gate | 1 | x | 22 | x | 0.42 | x | 6.16 |  |  |  |  | = | 56.9184
| '' '' | 1 | x | 14 | x | 0.42 | x | 6.16 |  |  |  |  | = | 36.2208
[12 empty] | Total 'B' |  | 93.1392
| Net Qty. (A - B) |  |  | 3834.0932 | - | 93.1392 | [6 empty] | = | 3740.954
[10 empty] | @Rs |  | 1134.38 |  | %oCft | 42437
8 | Removing old debries rubbish construction remenants all kind and size beyond munciple limit and clearance of space in/c loading unloading etc complete as directed by Engineer Incharge (10 miles) carriage of material.
| Qty same as item No. 01 | [11 empty] | = | 3740.954
3740.954
[10 empty] | @Rs |  | 902.2 |  | %Cft | 33750.887
9 | EXCAVATION IN FOUNDATION OF BUILDING BRIDGES AND OTHER STRUCTURE I/C DEGABILLING DRESSING REFILLING, AROUND STRUCTURE WITH EXCAVATED EARTH WATERIG AND RAMMING LEAD UPTO 5 FT IN ORDINARY SOIL (S.I.NO:18-B/P-5).
C- C/Wall
| Footing C/Wall |  |  | 103 | x | 3.5 | x | 3.5 | x | 3 |  |  | = | 3785.25
| Gate Column Footing |  |  | 10 | x | 4 | x | 3.5 | x | 3 |  |  | = | 420
| For B/W Footing |  |  | 103 | x | 6.5 | x | 2 | x | 1 |  |  | = | 1339
[12 empty] | Total |  | 5544.25
[10 empty] | @Rs |  | 3176.25 |  | %oCft | 17610
10 | CEMENT CONCRETE BRICK STONE BALLAST 1 1/2" TO 2" GUAGE RATIO1:4:8 (S.I.17/4b)
| Footing C/Wall |  |  | 103 | x | 3.5 | x | 3.5 | x | 0.5 |  |  | = | 630.875
| Gate Column Footing |  |  | 10 | x | 4 | x | 3.5 | x | 0.5 |  |  | = | 70
| For B/W Footing |  |  | 103 | x | 6.5 | x | 2 | x | 0.5 |  |  | = | 669.5
| Building P/Prot F/Side | 1 | x | 27.25 | x | 2.57 | x | 0.5 |  |  |  |  | = | 35.0162
| " " | 1 | x | 27.33 | x | 2.57 | x | 0.5 |  |  |  |  | = | 35.1191
| " " S/S | 2 | x | 23.67 | x | 2.57 | x | 0.5 |  |  |  |  | = | 60.8319
| B/Side | 1 | x | 66.57 | x | 2.57 | x | 0.5 |  |  |  |  | = | 85.5425
[12 empty] | Total |  | 1586.8846
[10 empty] | @Rs |  | 9416.28 |  | % Cft | 149426
11 | R.C.C WORK IN/C ALL LABOUR & MATERIAL EXCEPT THE COST OF STEEL R/F & BENDING & BINDING WHICH WILL BE PAID SEPARATELY. R.C.C WORK ROOF SLAB BEAMS COLUMNS RAFTS LINTEL AND OTHER STRUCTURE MEMBER LAID IN SITU OR PRE CAST LAID IN POSITION COMPLETE IN ALL RESPECT RATIO 1:2:4. (S.I.6-A-II/P-18)
C/Wall
| C/Wall Footing |  |  | 103 | x | 3 | x | 3 | x | 1 |  |  | = | 927
| Column footing |  |  | 10 | x | 3.5 | x | 3 | x | 1 |  |  | = | 105
| Padistal |  |  | 114 | x | 0.67 | x | 0.67 | x | 2 |  |  | = | 102.3492
| Plinth Beam |  |  | 10 | x | 100 | x | 0.67 | x | 1.5 |  |  | = | 1005
| Plinth Beam |  |  | 1 | x | 70 | x | 0.67 | x | 1.5 |  |  | = | 70.35
| S/S Column |  |  | 114 | x | 0.67 | x | 0.67 | x | 8 |  |  | = | 409.3968
| Coping |  |  | 10 | x | 100 | x | 0.67 | x | 0.75 |  |  | = | 502.5
| '' '' |  |  | 1 | x | 70 | x | 0.67 | x | 0.754 |  |  | = | 35.3626
3156.9586
[10 empty] | @Rs |  | 337 |  | P.Cft | 1063895
12 | FABRICATION OF STEEL R/F FOR C.C IN/C CUTTING BENDING LAYING IN POSITION MAKING AND FASTENING IN/C COST OF BINDING WIRE (ALSO IN/C REMOVAL OF RUST FROM BARS)(S.I.NO.7 (A & B)/P-20) ( Deformed Bars)
| Qty Same as I.No.11 | [12 empty] | 3156.9586
3156.9586
[5 empty] | 3156.9586 |  | x | 7 | [5 empty] | 197.3099
112
[10 empty] | @Rs |  | 5001.7 |  | P.Cwt | 986885
13 | ERRECTION & REMOVAL OF VERTICAL CENTERING FOR R.C.C PLAIN OR CEMENT CONCRETE WORK OF PARTAL WOOD (2ND CLASS) (S.I.NO.18-B/P-21).
| C/Wall U. P /Beam |  |  | 103 | x | 2 | x | 9.33 | x | 3 |  |  | = | 5765.94
5765.94
[10 empty] | @Rs |  | 3127.41 |  | % Sft | 180325
14 | CEMENT CONCERETE PLAIN IN/C PLACING COMPACTING FINISHING CURING COMPLETE & SCREENING & WASHING OF STONE AGGREGATE WITHOUT SHUTTERING RATIO 1:3:6 (S.I.NO.5-H P-18).
| C/Wall U. P /Beam | 103 | x | 1 | x | 9.33 | x | 0.67 | x | 3 |  |  | = | 1931.5899
1931.5899
[10 empty] | @Rs |  | 12595 |  | % Sft | 243284
15 | P/L 1:3:6 C.C SOLID BLOCK MASONARY WALL 6" BELOW IN THICKNESS SET IN 1:6 C.M IN G.F. SUPER STRUCTURE I/C RAKING OUTJOINTS & CURING ETC, COMPLETE. (S.I.NO: 23/P-22)
| C/Wall | 10 | x | 100 | x | 0.5 | x | 8 |  |  |  |  | = | 4000
| Building P/Prot F/Side | 1 | x | 27.25 | x | 0.5 | x | 0.75 |  |  |  |  | = | 10.2188
| " " | 1 | x | 27.33 | x | 0.5 | x | 0.75 |  |  |  |  | = | 10.2487
| " " S/S | 2 | x | 23.67 | x | 0.5 | x | 0.75 |  |  |  |  | = | 17.7525
| B/Side | 1 | x | 66.57 | x | 0.5 | x | 0.75 |  |  |  |  | = | 24.9638
4063.1838
B- Deduction
| Collumn |  |  | 108 | x | 0.67 | x | 0.5 | x | 8 |  |  | = | 289.44
| Gate |  |  | 1 | x | 22 | x | 0.5 | x | 8 |  |  | = | 88
| '' |  |  | 1 | x | 14 | x | 0.5 | x | 8 |  |  | = | 56
433.44
| Net Qty. ( A - B ) |  |  | 4063.1838 | (-) | 433.44 | [6 empty] | = | 3629.7438
[10 empty] | @Rs |  | 15771.01 |  | % Cft | 572447
16 | CEMENT PLASTER 1:4 UPTO 20 HEIGHT (C) 3/4" THICK. (S.I.NO.11(c) P-58)
| C/Wall | 10 | x | 2 | x | 100 | x | 10 |  |  |  |  | = | 20000
| Column | 1 | x | 2 | x | 32 | x | 10 |  |  |  |  | = | 640
| '' '' | 108 | x | 4 | x | 0.08 | x | 8 |  |  |  |  | = | 276.48
| P/Prot F/Side Edging |  |  | 1 | x | 27.75 | x | 1 |  |  |  |  | = | 27.75
| " " |  |  | 1 | x | 27.82 | x | 1 |  |  |  |  | = | 27.82
| S/Wall |  |  | 2 | x | 23.67 | x | 1 |  |  |  |  | = | 47.34
| B/Side |  |  | 1 | x | 66.57 | x | 1 |  |  |  |  | = | 66.57
| Plate Form Steeps Riz |  |  | 1 | x | 17.16 | x | 0.5 |  |  |  |  | = | 8.58
| " " |  |  | 2 | x | 10 | x | 0.5 |  |  |  |  | = | 10
| " " |  |  | 1 | x | 15.16 | x | 0.5 |  |  |  |  | = | 7.58
| " " |  |  | 2 | x | 9 | x | 0.5 |  |  |  |  | = | 9
| " " |  |  | 1 | x | 13.16 | x | 0.5 |  |  |  |  | = | 6.58
| " " |  |  | 2 | x | 8 | x | 0.5 |  |  |  |  | = | 8
| " " |  |  | 1 | x | 7 | x | 0.5 |  |  |  |  | = | 3.5
| " " |  |  | 2 | x | 6 | x | 0.5 |  |  |  |  | = | 6
| Plat Form |  |  | 1 | x | 7 | x | 0.5 |  |  |  |  | = | 3.5
21148.7
B- Deduction
| Gate | 1 | x | 22 | x | 2 | x | 10 |  |  |  |  | = | 440
| '' | 1 | x | 2 | x | 14 | x | 10 |  |  |  |  | = | 280
720
| Net Qty. ( A - B ) |  |  | 21148.7 | (-) | 720 | [6 empty] | = | 20428.7
[10 empty] | @Rs |  | 3191.76 |  | % Sft | 652035
17 | PREPARING THE SURFACE AND PAINTING WITH WEATHER COAT I/C RUBBING THE SURFACE WITH RUBBING BRICK / AND SAND PAPER, FILLING WITH VOIDS WITH WEATHER COAT OF APPROVED MAKE. (S.I.NO.38.A/P-56).
| Qty. same as I.No.10 | [11 empty] | = | 20428.7
20428.7
[10 empty] | @Rs |  | 2567.95 |  | % Sft | 524599
18 | DISTEMPERING TWO COATS (S.I.NO.54/24-b).
| Qty:Same I.No.2-a+b | [12 empty] | 3164.2592
[12 empty] | Total |  | 3164.2592
[10 empty] | @Rs |  | 1043.9 |  | %Sft | 33031.7018
19 | Preparing the surface and painting with plastic emulsion approved make old surface 2 coats (S.I.56/41)
| Same I.No.4-C+D+E+F | [12 empty] | 11128.1568
11128.1568
Deduction
| Door | 6 | x | 1 | x | 4 | x | 3 |  |  |  |  | = | 72
| Window | 1 | x | 1 | x | 6 | x | 4 |  |  |  |  | = | 24
| Door | 2 | x | 1 | x | 4 | x | 4 |  |  |  |  | = | 32
| D/Wall | 3 | x | 1 | x | 3.5 | x | 7 |  |  |  |  | = | 73.5
| Ent Opp | 2 | x | 1 | x | 4.67 | x | 6 |  |  |  |  | = | 56.04
| D/Wall | 1 | x | 1 | x | 4.33 | x | 6 |  |  |  |  | = | 25.98
| Ent Opp | 2 | x | 1 | x | 2 | x | 9 |  |  |  |  | = | 36
| '' '' '' | 1 | x | 1 | x | 63.57 | x | 1.5 |  |  |  |  | = | 95.355
| Chajja Build | 1 | x | 63.57 | x ( | 11.25 | + | 11.25 | + | 2.16 | ) |  | = | 1567.6362
[12 empty] | Total G |  | 1982.5112
|  |  |  | 11128.1568 | - | 1982.5112 | [7 empty] | 9145.6456
[10 empty] | @Rs |  | 1402.23 |  | %Sft | 128243
20 | Painting old Surface Painting guards bars gates iron bars grating railings standard braces(etc) and Simmilar open work Each Subsequent coat ( S.I No.4-d/P-69).
| M.Gate | 2 | x | 2 | x | 12 | x | 8 |  |  |  |  | = | 384
| M.Gate | 2 | x | 2 | x | 4 | x | 8 |  |  |  |  | = | 128
| Qty:Same I.No.3 | [12 empty] | 322.74
[12 empty] | Total |  | 834.74
[10 empty] | @Rs |  | 674.6 |  | %Sft | 5631.156
21 | PAINTING OLD SURFACE PAINTING DOORS & WINDOWS ANY TYPE. (S.I.68/4-c)
| Qty same as item 4 | [11 empty] | = | 424.5
[12 empty] | Total |  | 424.5
[10 empty] | @Rs |  | 1160.06 |  | %Sft | 4924
22 | Providing and laying topping cement concrete 1:2:4 including surface finishing and dividing into panels 2" thick. (S.I.No. 42/16-c)
| P/Prot F/Side |  |  | 1 | x | 27.75 | x | 3.08 |  |  |  |  | = | 85.47
| " " |  |  | 1 | x | 27.82 | x | 3.08 |  |  |  |  | = | 85.6856
| S/Wall |  |  | 2 | x | 23.67 | x | 3.08 |  |  |  |  | = | 145.8072
| B/Side |  |  | 1 | x | 66.57 | x | 3.08 |  |  |  |  | = | 205.0356
[12 empty] | Total |  | 521.9984
[10 empty] | @Rs |  | 3275.5 |  | %Sft | 17098.0576
23 | Split tile 1/4"thick matt glazed or double glazed jointed in white cement and lead over 1:2 grey cement sand mortar 3/4"thick in/c finishing complete (Flooring and Facing)(S.I.49/69)
| Plate Form Steeps Riz |  |  | 1 | x | 17.16 | x | 0.5 |  |  |  |  | = | 8.58
| " " |  |  | 2 | x | 10 | x | 0.5 |  |  |  |  | = | 10
| " " |  |  | 1 | x | 15.16 | x | 0.5 |  |  |  |  | = | 7.58
| " " |  |  | 2 | x | 9 | x | 0.5 |  |  |  |  | = | 9
| " " |  |  | 1 | x | 13.16 | x | 0.5 |  |  |  |  | = | 6.58
| " " |  |  | 2 | x | 8 | x | 0.5 |  |  |  |  | = | 8
| " " |  |  | 1 | x | 7 | x | 0.5 |  |  |  |  | = | 3.5
| " " |  |  | 2 | x | 6 | x | 0.5 |  |  |  |  | = | 6
| Plat Form |  |  | 1 | x | 7 | x | 0.5 |  |  |  |  | = | 3.5
| '' '' '' | 1 | x | 1 | x | 63.57 | x | 1.5 |  |  |  |  | = | 95.355
| Plate Form Steeps |  |  | 1 | x | 17.16 | x | 1 |  |  |  |  | = | 17.16
| " " |  |  | 2 | x | 10 | x | 1 |  |  |  |  | = | 20
| " " |  |  | 1 | x | 15.16 | x | 1 |  |  |  |  | = | 15.16
| " " |  |  | 2 | x | 9 | x | 1 |  |  |  |  | = | 18
| " " |  |  | 1 | x | 13.16 | x | 1 |  |  |  |  | = | 13.16
| " " |  |  | 2 | x | 8 | x | 1 |  |  |  |  | = | 16
| " " |  |  | 1 | x | 7 | x | 1 |  |  |  |  | = | 7
| " " |  |  | 2 | x | 6 | x | 1 |  |  |  |  | = | 12
| Plat Form |  |  | 1 | x | 7 | x | 6 |  |  |  |  | = | 42
| Building | 1 | x | 2 | x ( | 60.67 | + | 23.67 | )x | 3.5 |  |  | = | 590.38
[12 empty] | Total |  | 908.955
Deduction
| Ent Gate | 1 | x | 1 | x | 6 | x | 3.5 |  |  |  |  | = | 21
21
| Net qty A-B |  |  |  |  | 908.955 | - | 21 |  |  |  | TOTAL | = | 887.955
[10 empty] | @Rs |  | 21021.11 |  | % Sft | 186658
P/F COLOUR CREATE TO WALL SURFACE TO PROVIDE, DURABLE CRUST AND AESTHETICS HAVING THICKNESS UPTO 3/4" WITH SPECIFIED COLOUR HAVING WATER,FIRE & TERMITE RESISTANCE (UPTO 20' HEIGHT) (S.I.NO.44/63).
| Building | 1 | x | 2 | x ( | 60.67 | + | 23.67 | )x | 25 |  |  | = | 4217
| Chajja Build | 1 | x | 2 | x ( | 60.67 | + | 23.67 | )x | 1.5 |  |  | = | 253.02
[12 empty] | Total |  | 4470.02
Deduction
| D/Wall G+F | 3 | x | 1 | x | 4.67 | x | 6 |  |  |  |  | = | 84.06
| '' '' '' | 3 | x | 1 | x | 4.33 | x | 6 |  |  |  |  | = | 77.94
| Ent Gate | 1 | x | 1 | x | 6 | x | 8.75 |  |  |  |  | = | 52.5
| Building | 1 | x | 2 | x ( | 60.67 | + | 23.67 | )x | 3.5 |  |  | = | 590.38
804.88
| Net qty A-B |  |  |  |  | 4470.02 | - | 804.88 |  |  |  | TOTAL | = | 3665.14
[10 empty] | @Rs |  | 6319.5 |  | % Sft | 231619
25 | Rubbing and Polishing of old mosaic floor(S.I.43/26)
| Qty same as item 2A+B | [11 empty] | = | 3164.2592
[12 empty] | Total |  | 3164.2592
[10 empty] | @Rs |  | 1228.92 |  | %Sft | 38886
26 | Filling watering and ramming new earth from out side lead upto one chain and lift upto 5 feet (S.I.4/22)
| Open Ground |  |  | 2 | x | 50 | x | 25 | x | 1.83 |  |  | = | 4575
| Open Ground |  |  | 2 | x | 40 | x | 30 | x | 1.75 |  |  | = | 4200
| Open Ground |  |  | 4 | x | 35 | x | 30 | x | 1.75 |  |  | = | 7350
[12 empty] | Total |  | 16125
[10 empty] | @Rs |  | 3630 |  | %oCft | 58534
B | Add Lead Upto 10 Miles.
| Qty same as item 25 | [11 empty] | = | 16125
[12 empty] | Total |  | 16125
[10 empty] | @Rs |  | 1065 |  | %Cft | 171731
25 | Difference of Sulphate Resistant Cement.
| C.C. 1:4:8 Item 2 |  |  | 1586.8846 | x | 9.5 |  | % |  |  |  |  | = | 150.754
| C.C. Plain 1:3:6 Item 6 |  |  | 1931.5899 | x | 12 |  | % |  |  |  |  | = | 231.7908
| R.C.C 1:2:4 Item 4 |  |  | 3156.9586 | x | 17.6 |  | % |  |  |  |  | = | 555.6247
938.1695
[10 empty] | @Rs |  | 40 |  | P.Sft | 37527
[14 empty] | Total | 5380576.8024
| Sub-Engineer |  |  |  |  | Assistant Engineer | [7 empty] | Executive Engineer
[6 empty] | Education Works Sub-Division New Karachi | [7 empty] | Education Works Division-II
[6 empty] | Karachi | [7 empty] | Karachi

## Sheet3
CARRIAGE OF MATERIAL
NAME OF WORK:- |  | MAINTINANCE / REPAIR OF GOVT:BOYS ELEMENTARY SCHOOL 15/A-3 BUFFERZONE AT 7D-2 NORTH KARACHI (SEMIS CODE 408130186)
S.No | Item of work | Quantity | Cement Bages |  |  | Hill Sand % Cft |  |  | Shingle/Crush Stone % Cft |  |  | Stone Ballast % Cft |  |  | Steel
1 | C.C. 1:4:8 | 1586.8846 | 151 |  |  | 762 |  |  | 0 |  |  | 1523 |  |  | -
2 | C.C Plain 1:2:4 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | - |  |  | -
3 | C.C Plain 1:3:6 | 1931.5899 | 232 |  |  | 850 |  |  | 1700 |  |  | - |  |  | -
4 | R.C.C 1:1-1/2:3 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | - |  |  | -
5 | R.C.C 1:2:4 | 3156.9586 | 556 |  |  | 1389 |  |  | 2778 |  |  | - |  |  | -
6 | C.C. 1:3:6 B/M FOUND + S.S. | 3629.7438 | 436 |  |  | 1688 |  |  | 3376 |  |  | - |  |  | -
7 | Cement Plaster | 20428.7 | 204 |  |  | 1021 |  |  | - |  |  | - |  |  | -
8 | Mosaic tiles + dado, Marble | 0 | 0 |  |  | 0 |  |  | - |  |  | - |  |  | -
9 | C.C.Topping 1:2:4 2" Thick | 521.9984 | 10 |  |  | 22 |  |  | - |  |  | - |  |  | -
10 | C.C.Topping 1:2:4 3" Thick | 0 | 0 |  |  | 0 |  |  | 0 |  |  | - |  |  | -
11 | Random Masonary | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | -
12 | Steel | 0 | - |  |  | - |  |  | - |  |  | - |  |  | 0
| Total Quantity |  | 1589 |  |  | 5732 |  |  | 7854 |  |  | 1523 |  |  | 0
FOR FROM |  |  | Lucky Cement |  |  | SAND QUARY |  |  | MANGHO PIR QUERRY |  |  | MANGHO PIR QUERRY |  |  | Steel
LEAD IN MILES |  | Miles | 35 |  |  | 48 |  |  | 25 |  |  | 28 |  |  | 10
FROM |  |  | 1 | to | 2 | 1 | to | 6 | 1 | to | 6 | 1 | to | 6 | 1 | to | 3
Total |  |  | 7.53 |  |  | 771.96 |  |  | 771.96 |  |  | 771.96 |  |  | 771.96
7TH & SUBSEQUENT |  |  | 33 | X | 0.6 | 42 | X | 32.56 | 19 | X | 32.56 | 22 | X | 32.56 | 4 | x | 32.56
|  |  | 19.8 |  |  | 1366.52 |  |  | 618.64 |  |  | 716.32 |  |  | 130.24
Total Rate |  |  | 27.33 |  |  | 2139.48 |  |  | 1390.6 |  |  | 1488.28 |  |  | 902.2
Total Amount |  |  | 43427 |  |  | 122635 |  |  | 109218 |  |  | 22667 |  |  | 0
[7 empty] | Total:-Amount Rs: |  |  |  |  | 297947
Sub-Engineer
|  |  | Assistant Engineer | [8 empty] | Executive Engineer
|  |  | Education Works Sub-Division New Karachi | [8 empty] | Education Works Division-II
|  |  | Karachi | [8 empty] | Karachi

## Sheet1
BOARING ITEMS
NAME OF WORK:- |  | MAINTINANCE / REPAIR OF GOVT:BOYS ELEMENTARY SCHOOL 15/A-3 BUFFERZONE AT 7D-2 NORTH KARACHI (SEMIS CODE 408130186)
BOURING
S.No | Description of Item |  | Qty. | Rate | Unit | Amount
1 | Boring of tube well in all water bearing soils from ground levelupto 100ft or 30.50 meter depth in/c sinking & with drawing of casing of pipe (250mm 10'' dia) (p/41/1) Public Health Engeneering Schedule of Rates.
|  |  | 100 | 639 | P.Rft | 63900
2 | Boring of tube well in all water bearing soils from depth 100.1 to 200ft or 30.51 to 61 meter below ground level in/c sinking & with drawing of casing of pipe (250mm 10'' dia) (p/42/2b) Public Health Engeneering Schedule of Rates.
|  |  | 75 | 724 | P.Rft | 54300
3 | Supplaying & installing PVC stariners 'B' Class of approved design quality & make in/c necessory socket etc, complete ( 250mm 10'' dia ) P/43/9) Public Health Engineering Schedule of Rates.
|  |  | 175 | 322.35 | P.Rft | 56411
4 | Shrounding with graded Bajri ( 3.8 to 1/8'' ) or ( 9 to 3mm ) in below bore & blind pipes for the following diameter of stainer ( 250 mm 10'' dia )P/45/13-b) Public Health Engineering Schedule of Rates.
|  |  | 175 | 154 | P.Rft | 26950
5 | Providing & Fixing uPVC Pipe (PAK ARAB or equivalent) Schedule 40 on surface or concealled masonary / cement concrete or R.c.c upto required height jointing by using approved solvent (AGM or equivalent) etc complete. This rate also in/c all kind of labour, material, cartage etc as per approved by Engineer Incharge.
| 1" dia |  | 224.66 | 92 | P.Rft | 20669
6 | P/F P.V.C Elbow 90* (PAK ARAB or equivalent) dia of approved quality and design of various size fixed to Upvc pipe using approved adhensive compound upto required height etc complete. This rate also in/c all kind of labour, material, cartage etc as per approved by Engineer Incharge.
| 1" dia |  | 10 | 140 | Each | 1400
7 | P/F uP.V.C Socket (PAK ARAB or equivalent) make of approved quality and design of various size fixed to Upvc pipe using approved adhensive compound upto required height etc complete. This rate also in/c all kind of labour, material, cartage etc as per approved by Engineer Incharge.
| 1" dia |  | 17 | 55 | Each | 935
8 | P/F uP.V.C Union ''Solvent'' (PAK ARAB or equivalent) Schedule 40 make of approved quality and design of various size fixed to Upvc pipe using approved adhensive compound upto required height etc complete. This rate also in/c all kind of labour, material, cartage etc as per approved by Engineer Incharge.
| 1" dia |  | 4 | 471 | Each | 1884
9 | P/F uP.V.C Tee ''Solvent'' (PAK ARAB or equivalent) Schedule 40 make of approved quality and design of various size fixed to Upvc pipe using approved adhensive compound upto required height etc complete. This rate also in/c all kind of labour, material, cartage etc as per approved by Engineer Incharge.
| 1" dia |  | 5 | 160 | Each | 800
9 | Proving & Fixing Handle Valve ( china ). (S.I.No: 17/5-3).
| 1" dia |  | 2 | 475.42 | Each | 951
10 | Proving & Fixing Ball Valve with unsoldered copper Ball made to B.B.S. 1212 (S.I.No: 6/iii/P-18).
|  |  | 1 | 510.84 | Each | 511
11 | Providing & Fixing Deepwell Motor set 1400 RPMSingle Pahase 240 Volts section 20ft height including base plate and along with nuts and bolts complete in all respect as approved by Engineer Incharge (Sameer Pump). (M.R)
|  |  | 1 | 18400 | Each | 18400
|  |  | Total |  | = | 247111

## Sheet2
A B S T R A C T
NAME OF WORK:- |  | RE-CONSTRUCTION OF COMPOUND WALL @ GOVERNMENT DEGREE GIRLS COLLEGE AT SECTOR 11B NORTH KARACHI
S.No | Description of Items |  | Qty. | Rate | Unit | Amount
PART " C " FINISHING WORKS
1 | GLAZED TILES DADO 1/4" THICK LAID IN PIGMENT OVER 1:2 CEMENT SAND MORTAR 3/4" THICK IN/C FINISHING (S.I.NO.37/P-50)
|  |  | #REF! | 28299.3 | % Sft | #REF!
|  |  | Total Cost :- |  |  | #REF!
Sub-Engineer
Assistant Engineer
Education Works Sub-Division New Karachi
Karachi

## Sheet5
A B S T R A C T
NAME OF WORK:- |  | RE-CONSTRUCTION OF COMPOUND WALL @ GOVERNMENT DEGREE GIRLS COLLEGE AT SECTOR 11B NORTH KARACHI
S.No | Description of Items |  | Qty. | Rate | Unit | Amount
PART " D " NON SCHEDULE ITEM WORKS
1 | MAKING AND FIXING "FENCE OF 3/8" SQAURE MILD STEEL BAR WITH LANCES" 3 NOS. OF 2 SIDED EQUILATERAL TREIANGLAR FLAT HAMMERED STEEL LANES EACH AT THE TIP OF 1' (OVERALL) 1/2" SQUAE WELDED WITH 1 1/2" x 1 1/2" x 1/4" ANGLE HORIZONTAL ANGLE IRON AND 1 1/2" SQUARE BARS AT 3" C/C AT THE ROOT EMBDED 6" DEEP IN STRUCTURE HAVING 2 NO HOLD FASTS OF 1" x 1/4" FLAT STEEL BARS, WELDED HORIZONTALLY AT 6" ABOVE BOTTOM COMPLETE AS PER THE DIRECTIONS OF ENGINEER INCHARGE I/C PAINTING 3 COATS (R.A APPROVED).
|  |  | #REF! | 950 | P.Rft | #REF!
2 | DIFFERENCE OF USING SULPHATE RESISTANT CEMENT INSTEAD OF ORDINARY PORTLAND CEMENT (R.A.APPROVED).
|  |  | #REF! | 40 | P.Bag | #REF!
|  |  | Total Cost :- |  |  | #REF!
Sub-Engineer
Assistant Engineer
Education Works Sub-Division New Karachi
Karachi

## Carriage
CARRIAGE OF MATERIAL
NAME OF WORK:- |  | MAINTINANCE / REPAIR OF GOVT:BOYS ELEMENTARY SCHOOL 15/A-3 BUFFERZONE AT 7D-2 NORTH KARACHI (SEMIS CODE 408130186)
S.No | Item of work | Quantity | Cement Bages |  |  | Hill Sand % Cft |  |  | Shingle/Crush Stone % Cft |  |  | Stone Ballast % Cft |  |  | Steel
1 | C.C. 1:4:8 | 16125 | 1532 |  |  | 7740 |  |  | 0 |  |  | 15480 |  |  | 0
2 | C.C Plain 1:3:6 | #REF! | 27 |  |  | 106 |  |  | 212 |  |  | - |  |  | -
3 | C.C Plain 1:2:4 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | - |  |  | -
4 | R.C.C 1:2:4 | #REF! | 2214 |  |  | 5535 |  |  | 11070 |  |  | - |  |  | -
5 | C.C. 1:3:6 B/M FOUND + S.S. | 3629.7438 | 436 |  |  | 1688 |  |  | 3376 |  |  | - |  |  | -
6 | Cement Plaster 1:4 3/4" | 21148.7 | 211 |  |  | 1057 |  |  | - |  |  | - |  |  | -
7 | Mosaic tiles + dado | 0 | 263 |  |  | 1316 |  |  | - |  |  | - |  |  | -
8 | C.C.Topping 1:2:4 2" Thick | #REF! | #REF! |  |  | #REF! |  |  | #REF! |  |  | - |  |  | -
9 | Random Rubble Mosonery | 0 | - |  |  | - |  |  | - |  |  | 0 |  |  | -
10 | Febrication | #REF! | - |  |  | - |  |  | - |  |  | - |  |  | #REF!
| Total Quantity |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | 15480 |  |  | #REF!
FOR FROM |  |  | DADBHAI / PAK LAND |  |  | SAND QUARY |  |  | BILAL CRUSHER |  |  | MANGHO PIR QUERRY |  |  | Earth
LEAD IN MILES |  | Miles | 22 |  |  | 57 |  |  | 25 |  |  | 28 |  |  | 10
FROM |  |  | 1 | to | 2 | 1 | to | 6 | 1 | to | 6 | 1 | to | 6 | 1 | to | 2
Total |  |  | 7.53 |  |  | 771.96 |  |  | 771.96 |  |  | 771.96 |  |  | 771.96
7TH & SUBSEQUENT |  |  | 20 | X | 0.16 | 51 | X | 32.56 | 19 | X | 32.56 | 22 | X | 32.56 | 4 | x | 32.56
|  |  | 12 |  |  | 1660.56 |  |  | 618.64 |  |  | 716.32 |  |  | 130.24
Total Rate |  |  | 19.53 |  |  | 2432.52 |  |  | 1390.6 |  |  | 1488.28 |  |  | 902.2
Total Amount |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | 230386 |  |  | #REF!
[7 empty] | Total:-Amount Rs: |  |  |  |  | #REF!
Sub-Engineer
Assistant Engineer
Education Works Sub-Division New Karachi
Karachi