## Procurement Plan
OFFICE OF THE EXECUTIVE ENGINEER BUILDINGS WORKS & SERVICES DEPARTMENT KHAIRPUR
PROCUREMENT PLAN FOR THE YEAR 2016-17
SR. NO. | ADP | NAME OF WORK | ALLOCATION 2016-17 | RELEASE 2016-17 | UTILIZATION / PROCUREMENT PROGRESS PLAN |  |  |  | REMARKS
[5 empty] | JULY TO DECEMBER 2016 | FEBRUARY TO MARCH 2017 | MARCH TO APRIL 2017 | MAY TO JUNE 2017
INFORMATION TECHNOLOGY SECTOR
1 | 729 | Rehabilitation of I.T Training Center Kumb Taluka Kotdiji. | 0.75 | 0.375 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
PHYSICAL, PLANNING & HOUSING SECTOR
2 | 730 | Rehabilitation /Construction of Revenue Complex/House at Taluka Kingri. | 5 | 2.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
3 | 731 | Construction of Mukhtiarkar House at Gambat Taluka Gambat. | 1.875 | 0.937 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
4 | 732 | Construction of Assistant Commissioner /Mukhtiarkar Office Sobhodero Taluka Sobhodero. | 5 | 2.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
5 | 733 | Construction of Assistant Commissioner House Sobhodero @ Ranipur Taluka Sobhodero. | 2.5 | 1.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
6 | 734 | Rehabilitation / Construction of Revenue Complex at Taluka Faiz Ganj. | 5 | 2.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
7 | 735 | Rehabilitation / Construction of Revenue Complex at Taluka Nara. | 5 | 2.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
8 | 736 | Rehabilitation/ Construction of Mukhtiarkar Office /House Taluka Kotdiji. | 2.5 | 1.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
9 | 739 | Renovation and Rehabilitation of Ghulstan-e-Manzil (DDMA Cell) near Vegetable Fruit Market Mall Road Taluka & District Khairpur. | 0.45 | 0.225 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
10 | 740 | Construction of Additional Work of District Government Secretriate Khairpur Taluka & District Khairpur. | 1.725 | 0.862 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
COMMUNITY DEVELOPMENT SECTOR
11 | 749 | Provision of Body Building/Fitness Equipment for Gents Modern Gymkhana Khairpur Taluka & District Khairpur. | 0.625 | 0.312 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
12 | 750 | Construction of Compound wall for Graveyard Derwaish Jee Masjid at Mir Ali Bazar Taluka Khairpur. | 0.625 | 0.312 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
13 | 752 | Rehabilitation/Renovation of Bungalow No.A-1/15 at Scarp Colony Taluka Khairpur. | 0.54 | 0.27 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
14 | 753 | Construction of Compound wall for Graveyard of Marwari Community Situated near Pir Muhammad Shah Bukhari Muhalla Dabbar Taluka & District Khairpur. | 0.57 | 0.285 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
15 | 767 | Construction of Compound wall of Eidgah Mohalla Deedar Katohar UC Shadi Shaheed Taluka Khairpur. | 0.625 | 0.312 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
16 | 775 | Construction of Compound wall Gillani Dargah Badshah UC Tando Masti Taluka Khairpur. | 0.625 | 0.312 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
17 | 776 | Construction of Compound wall for Graveyard at Village Mangial Fakeer UC Hajina Shah Taluka & District Khairpur. | 0.75 | 0.375 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
18 | 777 | Construction of Compound wall i/c Gate Imam Bargah Mir Ali Bazar near Wassan House Taluka & District Khairpur. | 0.625 | 0.312 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
19 | 778 | Construction of Eidgah at Therhi Taluka & District Khairpur. | 0.5 | 0.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
20 | 781 | Construction of Main Enterance Gate at Naka Stop Wada Machyoon Taluka & District Khairpur. | 0.435 | 0.217 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
21 | 784 | Additional work of Imam Bargah Ali Raza Shah Thallo UC Khairpur Taluka Khairpur. | 0.625 | 0.312 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
22 | 785 | Construction of Dargah Syed Bhoral Shah near Sanhro wah Taluka Khairpur. | 0.625 | 0.312 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
23 | 787 | Construction of Compound wall & Dargah Syed Surkh Badshah Taluka & District Khairpur. | 0.625 | 0.312 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
24 | 789 | Construction of Compound wall Eidgah at Village Jhalooji UC Hajina Shah Taluka Khairpur. | 0.625 | 0.313 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
25 | 792 | Construction of Compound wall for Graveyard at Village Sadoro Janwari Taluka Khairpur. | 0.375 | 0.187 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
26 | 795 | Construction of Compound wall of Imam Bargah Bab-Ul-Hawaij Maitla Mohalla at Luqman Khairpur. | 0.5 | 0.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
27 | 796 | Re-Construction of Imam Bargah Imam Hussain (AS) at Village Sajjan Khan Rind Deh Bugro Taluka & District Khairpur. | 0.625 | 0.313 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
28 | 798 | Construction of Compound wall of Imam Bargah Gulshan Abbas Muhalla Nizamani Ward No.20 Khairpur. | 0.5 | 0.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
29 | 799 | Construction of Compound wall of Imam Bargah Mohalla Bukhari Taluka & District Khairpur. | 0.875 | 0.438 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
30 | 800 | Construction of Compound wall of Imam Bargah Shaheed Abad Colony Taluka Khairpur. | 0.5 | 0.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
31 | 802 | Construction of Compound wall of Eidgah at Jinnah Colony Ward No.23 Taluka Khairpur. | 0.625 | 0.313 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
32 | 803 | Construction of Compound wall of Dargah Syed Inayat Shah near RTC Center Taluka & District Khairpur. | 0.625 | 0.313 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
33 | 806 | Construction of Tomb of Dargah Jam Fakir at Village Kouro Khan Phulpoto Taluka & District Khairpur. | 0.75 | 0.375 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
34 | 807 | Construction of Dargah Shaheed Syed Sajjad Hussain Shah Muhalla Syed Bachal Shah Bukhari Taluka Khairpur. | 0.875 | 0.438 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
35 | 808 | Construction of Dargah Syed Gareeb Shah City Khairpur Taluka & District Khairpur. | 1 | 0.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
36 | 809 | Construction of Dargah, Musafir Khana Syed Waryal Shah UC Bukhari Taluka & District Khairpur. | 0.625 | 0.313 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
37 | 810 | Remaining Boundary wall and widening of Dargah Pir Shah Hussain Badshah Uc Khanpur Taluka & District Khairpur. | 0.75 | 0.375 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
38 | 811 | Rehabilitation of Dargah Hazrat Shah Warand Shah Bukhari Taluka & District Khairpur. | 0.75 | 0.375 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
39 | 812 | Providing of Paver Block for Sindhi Karballa near Old National Highway Taluka Khairpur. | 1 | 0.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
40 | 813 | Rehabilitation Compound wall Imam Bargah Abdul Fazal Abbas and Graveyard of Dargah Mehar Ali Shah Abra Muhalla Luqman Khairpur. | 0.625 | 0.313 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
41 | 814 | Remaining work Construction of Compound wall Dargah Koral Shah near Mumtaz College Taluka & District Khairpur. | 0.625 | 0.313 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
42 | 815 | Construction of Compound wall & Hall i/c Repair of Musafir & C.C Block of Imam Bargah at Dilshad Colony near Naz High School Khairpur. | 0.625 | 0.313 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
43 | 816 | Remaining work of Dargah Khanan Shah Taluka & District Khairpur. | 0.625 | 0.313 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
44 | 818 | Construction of Compound wall for Graveyard at Dargah near CNG Station at Muhammad Shah TC Baberloi Taluka & District Khairpur. | 0.72 | 0.36 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
45 | 819 | Additional Work of Ladies Modern Gym-Khana Taluka & District Khairpur. | 1.25 | 0.625 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
46 | 820 | Remaining work of Compound wall of Sufi Sarmast Graveyard at UC Bhurgari Taluka Khairpur. | 0.375 | 0.187 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
47 | 822 | Construction of Boundary wall, Musafir Khana & Paving Block at Dargah Pir Syed Inayat Shah Bukhari Taluka & District Khairpur. | 0.625 | 0.313 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
48 | 823 | Construction of Compound wall for Graveyard & Imam Bargah at Village Pir Bux Solangi TC Therhi-II Taluka Khairpur. | 1 | 0.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
49 | 824 | Construction of Compound wall Graveyard at Village Allah Bux Katohar UC Bugro Taluka & District Khairpur. | 0.5 | 0.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
50 | 825 | Construction of Compound wall of Eidgah at Village Badai Machyoon UC Machyoon Taluka Khairpur. | 0.625 | 0.313 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
51 | 826 | Rehabilitation of Dargah Syed Jind Wado near Railway Station Taluka Khairpur. | 1 | 0.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
HEALTH SECTOR
52 | 832 | Construction of Government Dispensary at Kot Jubo Taluka Nara. | 1 | 0.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
53 | 835 | Construction of Government Dispensary at Village Qutubuddin Phulpoto Taluka Khairpur. | 1 | 0.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
54 | 839 | Construction of Government Dispensary at Village Badai Solangi UC Machyoon Taluka Khairpur. | 1 | 0.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
55 | 45 | Extension / Rehabilitation of Dargah Sachal Sarmast Taluka Gambat District Khairpur. | 27.287 | 13.644 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
56 | 18 | Construction of Boundary wall in Order to save the Land of Khairpur Khajoor Mandi from encroachement Taluka & District Khairpur. | 8.8 | 4.4 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
EXECUTIVE ENGINEER (BUILDINGS) WORKS & SERVICES DEPARTMENT KHAIRPUR