## Procurement Plan
OFFICE OF THE EXECUTIVE ENGINEER BUILDINGS WORKS & SERVICES DEPARTMENT KHAIRPUR
PROCUREMENT PLAN FOR THE YEAR 2016-17
SR. NO. | ADP | NAME OF WORK | ALLOCATION 2016-17 | RELEASE 2016-17 | UTILIZATION / PROCUREMENT PROGRESS PLAN |  |  |  | REMARKS
[5 empty] | JULY TO DECEMBER 2016 | FEBRUARY TO MARCH 2017 | MARCH TO APRIL 2017 | MAY TO JUNE 2017
PHYSICAL, PLANNING & HOUSING SECTOR
1 | 741 | Construction of Union Council Office Ali Muhammad Machi @ Nangerja UC Ali Muhammad Machi Taluka Kotdiji. | 0.675 | 0.337 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
2 | 742 | Construction of Union Council Office Atta Muhammad Hami @ Narodhoro UC Atta Muhammad Hami Taluka Kotdiji. | 0.675 | 0.338 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
3 | 743 | Construction of Union Council Office Goondariro @ Rajpari UC Goondariro Taluka Kotdiji. | 0.675 | 0.338 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
4 | 744 | Construction of Union Council Office Talpur Wada UC Talpur Wada Taluka Kotdiji. | 0.675 | 0.338 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
5 | 745 | Construction of Union Council Office UC Ripri Taluka Gambat. | 1 | 0.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
COMMUNITY DEVELOPMENT SECTOR
6 | 747 | Construction of Compound wall of Graveyard Syed Muhammad Ali Shah Johar Kotdiji Main City Taluka Kotdiji. | 0.4 | 0.2 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
7 | 748 | Construction of Compound wall, Earth Filling and Lavatory Block etc for Eidgah Deh Daraza Sharief Taluka Gambat. | 0.5 | 0.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
8 | 751 | Construction of Compound wall of Eidgah at Village Ellahi Bux Shambani Taluka Kotdiji. | 0.625 | 0.312 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
9 | 754 | Construction of /Remaining work of Dargah Sachal Shah Jillani UC Drib Mehar Shah Taluka Kingri. | 1 | 0.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
10 | 755 | Construction of Hujra of Bibi Pak Daman & Openyard UC Drib Mehar Shah Taluka Kingri. | 1.25 | 0.625 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
11 | 756 | Construction of Compound wall for Dargah Pir Qasim Shah Taluka Kingri. | 0.5 | 0.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
12 | 762 | Construction of Compound wall Eidgah at Village Muhammad Larik Taluka Gambat. | 0.5 | 0.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
13 | 763 | Construction of Compound wall at Eidgah (Syed Abdul Rahim Jeelani / Atta Muhammad Hami Village Sohu Kanasra UC Kotdiji Taluka Kotdiji. | 0.375 | 0.187 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
14 | 764 | Construction of Compound wall for Graveyard at Village Layari UC Layari Taluka Kotdiji. | 0.5 | 0.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
15 | 765 | Construction of Compound wall for Graveyard at Village Baghyal Khan Chandio UC Bapho Taluka Kotdiji. | 0.5 | 0.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
16 | 766 | Construction of Compound wall Imam Bargah at Village Ghous Bux Gaho Muhalla Sanwal Gaho UC Ali Muhammad Machi Taluka Kotdiji. | 0.5 | 0.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
17 | 768 | Construction of Compound wall of Imam Bargah Mohalla Bukhari (Syed Gayoor Abbas Shah) UC Deh Sohu Taluka Kotdiji. | 0.438 | 0.219 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
18 | 769 | Construction of Compound wall of Imam Bargah Mohalla Hayat Shaikh UC Shadi Shaheed Taluka Kotdiji. | 0.625 | 0.312 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
19 | 770 | Construction of Compound wall of Imam Bargah at Village Mithri Muhalla Mumtaz Shah UC Deh Sohu Taluka Kotdiji. | 0.5 | 0.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
20 | 771 | Construction of Remaining work of Compound wall of Imam Bargah at Village Mureed Hussain Mahar UC Atta Muhammad Hami Taluka Kotdiji. | 0.5 | 0.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
21 | 772 | Remaining work of Construction of Compound wall for Graveyard Mohalla Ali Abad Halepoto UC Fatehpur Taluka Kotdiji. | 0.42 | 0.21 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
22 | 773 | Construction of Compound wall of Eidgah at Village Jhango Wassan Mohalla Karam Hussain Wassan Taluka Kotdiji. | 0.75 | 0.375 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
23 | 774 | Construction of Compound wall and Remaining work of Masjid Dargah Syed Ashique Ali Shah Jeelani at Deh Sohu Taluka Kotdiji. | 0.733 | 0.366 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
24 | 779 | Construction /Remaining work of Dargah Shah Hussain UC Muhbat wah Taluka Kotdiji. | 0.5 | 0.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
25 | 780 | Remaining work of Graveyard at Village Muhammad Soomar Muhalla Taluka Kotdiji. | 0.5 | 0.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
26 | 782 | Construction of Compound wall for Graveyard Fakir Nadeem Gopang Taluka Faiz Ganj. | 0.625 | 0.312 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
27 | 783 | Construction of Compound wall Dargah Naghay Shah & Musafir Khana Manganwari UC Manganwari Taluka Kingri. | 0.625 | 0.312 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
28 | 786 | Construction of Compound wall of Eidgah @ Khabar Fakir UC Kolab Jeal Taluka Kingri. | 0.5 | 0.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
29 | 788 | Construction of Compound wall for Graveyard Construction of Mazar at Village UC Kotlo Taluka Kotdiji. | 0.375 | 0.187 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
30 | 791 | Construction of Compound wall for Graveyard at Bhumbra Muhalla UC Naseer Fakir Jalalani Taluka Kotdiji. | 0.5 | 0.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
31 | 793 | Construction of Compound wall Imam Bargah Babar Wada UC Ahdi Rajper Taluka Kotdiji. | 0.5 | 0.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
32 | 797 | Construction of Compound wall of Imam Bargah at Village Baloch Abad UC Mahesar Wada Taluka Kingri. | 0.5 | 0.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
33 | 801 | Construction of Compound wall Dargah Dinal Shah Masoom at Kolab Jeal Taluka Kingri. | 0.625 | 0.313 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
34 | 804 | Construction of Compound wall of Eidgah Ali-Un-Murtaza Bhutta Mohalla Taluka Kotdiji. | 0.475 | 0.238 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
35 | 821 | Construction of Compound wall of Graveyard Pir Muzafar Hussain Shah at Village Allah Dino Bhutto Deh Rukrani UC Rasool Abad Taluka Sobhodero. | 0.625 | 0.313 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
HEALTH SECTOR
36 | 827 | Rehabilitation of Basic Health Unit Zafar Abad UC Kandiyari Taluka Faiz Ganj. | 0.75 | 0.375 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
37 | 828 | Construction of Compound wall for (SIUT) Cancer Hospital near Baberloi Taluka & District Khairpur. | 10 | 5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
38 | 829 | Rehabilitation of Government Dispensary at Abad near Bungalow Town Kotdiji Taluka Kotdiji. | 0.625 | 0.313 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
39 | 831 | Rehabilitation of Basic Health Unit Sami Taluka Sobhodero. | 1 | 0.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
40 | 833 | Construction of Government Dispensary at Village Ghulam Rasool Sangi UC Akri Taluka Faiz Ganj. | 1 | 0.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
41 | 834 | Construction of Government Dispensary at Village Naseer Fakir Jalalani Taluka Kotdiji. | 1 | 0.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
42 | 836 | Construction of Government Dispensary at Village Jhango Wassan Muhalla Karam Hussain Wassan Taluka Kotdiji. | 1 | 0.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
43 | 837 | Construction of Government Dispensary at Village Fateh Ali Lashari Taluka Kotdiji. | 1 | 0.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
44 | 838 | Construction of Government Dispensary at Village Khair Muhammad Burdi Taluka Kotdiji. | 1 | 0.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
45 | 840 | Construction of Government Dispensary at Village Rind Hajana UC Mithri Taluka Kotdiji. | 1 | 0.5 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
AGRICULTURE SECTOR
46 | 841 | Construction of Government Veterinary Dispensary at Village Khush Khair Muhammad Taluka Faiz Ganj. | 0.875 | 0.438 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
RSW-311
47 |  | Providing & Installation of Solar Energy Street Light at Various Union Councils of Tehsil Sobhodero District Khairpur. | 14.2 | 14.2 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
48 |  | Providing & Installation of Solar Energy Street Light at Various Union Councils of Tehsil Gambat District Khairpur. | 8.115 | 8.115 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
EXECUTIVE ENGINEER (BUILDINGS) WORKS & SERVICES DEPARTMENT KHAIRPUR