## Detailed Estimate
Schedule B
Name of Scheme:- |  | RENOVATION / REHABILITATION / RECONSTRUCTION / ADDITIONAL FACILITIES TO EXISTING PRIMARY / ELEMENTARY SCHOOLS TALUKA SEHWAN @ GBPS Ghulam Muhammad Gachal
Item No. | Quantity | Description of Item | Rate | Unit | Amount | 416940.9174
1 | 405 | Dismentling brick work in lime cement mortar | 1285.63 | %Cft | 5206.8015
2 | 960 | Dismentling 2nd class roofing tiles | 378.13 | %Sft | 3630.048
3 | 11.5 | Dismentling rolled steel beam iron rails etc | 126.04 | P.wct | 1449.46
4 | 7.642 | Suppplying Girder at the site of work (SOM Item 140/P.72) | 3850 | P.cwt | 29421.7
5 | 12.714 | Suppplying Teer at the site of work (SOM Item 141/P.72) | 3575 | P.cwt | 45452.55
6 | 22.928 | Erection rolled supplying beam (S.No.6/P.90) | 186.34 | P.cwt | 4272.4035
7 | 960 | 2nd class tiles roofing consisting of 4'' earth and 1'' mud plaster with gobri leeping over 1/2'' thick cement plaster 1:6 with 34 lbs of hot bitumen coating snad blinded provided over 2 layer of tiles 12''x6''x2'' laid in 1:6 cement mortor i/c 1:2 cement pointing under nearth of tiles complete i/c curing etc (S.No.2/P.32) | 7607.25 | %Sft | 73029.6
8 | 405 | Pacca brick work in ground floor in cement sand mortar 1:6 (S.NO. 5 e/P.20) | 12674.36 | %Cft | 51331.158
9 | 147 | R.C.C work including all labour and material except the cost of steel reinforcement and i/c cutting beding which will be paid s separately. R.C.C work in roof slab, beams, columns, rafts,precast Ratio 1:2:4 | 337 | P.Cft | 49539
10 | 7.218 | Fabrication of miled steel reinforcement for cutting, bending and binding which will joint and fasteing wire removal of removal of rust from bars. | 5001.7 | P.Cwt | 36102.2706
11 | 1175 | Cement Plaster 1/2'' thick ration 1:6 (S.No.13 b/P.51) | 2206.6 | %Sft | 25927.55
12 | 1175 | Cement Plaster 3/8'' thick ration 1:4 (S.No.11 a/P.51) | 2197.52 | %Sft | 25820.86
13 | 960 | Lime Neru Plaster 1:2 with fine finish of neru plaster mixed with 10% of cement | 1428.35 | %Sft | 13712.16
14 | 3 | RCC spout | 161.45 | P. No | 484.35
15 | 4409 | Distempering Two coats. | 1043.9 | %Sft | 46025.551
17 | 489 | Painting old surfaces (c) Painting Gurad Bars 2 coats. | 674.6 | %Cft | 3298.794
18 | 176 | Preparing surface and painting guard bars gates of iron bars i/c standards braces etc and similar open work | 1270.83 | %Sft | 2236.6608
|  | Dismentling C.C Plain 1:3:6 | 1306.8 | %Cft | 0
|  | Dismentling R.CC reinforcement saparating reinforcement | 5445 | %Cft | 0
|  | Excavation in foundation of building, bridges and other structure including dagbelling dressing, refilling around structure with excavated earth, watering and ramming. Lead upto 5 ft (b) In ordinary soil. (S.I.No. 18(b)/C-1) | 3176.25 | %oCft | 0
|  | Cement concrete brick or stone ballast 1." to 2" gauge 1:5:10. | 8694.95 | %Cft | 0
|  | Pacca brick work in foundation and plinth in cement sand mortar 1:6 | 11948.36 | %Cft | 0
|  | Pacca brick work in other than building in cement sand mortar 1:6 | 12346.65 | %Cft | 0
|  | S/F Sand under floor and plugging in wall 1:2 | 1141.25 | %Cft | 0
P/F G.I fram chowkats size 7''x2'' or 4''x3'' for doors and window using 20 gauge G.I Sheet i/c welded hinger and fixing at site with necessary hold fasts i/c all carriage tools and plants used etc.
|  | Door | 228.9 | P.Rft | 0
|  | Providing and fixing iron / steel grill of 1/4"x3/4" size iron of approved etc fixed in position i/c holds fasts to be less than 3.lbs/ Square foot finished grill. . (S.I.No. 26/P.92) | 180.5 | P.Sft | 0
|  | First class deodar wood wrought, joinery in doors and windows joinery in fixed in position i/c chowkats hold fasts 3/4'' | 902.93 | P.Sft | 0
|  | Cement Concrete plain i/c placing compacting finishing ration 1:3:6 | 12595 | %Cft | 0
|  | Lying floor of approved colored galazed tiles 1/4'' thick dedo laid in cement concrete and pigment. | 27747.06 | %Sft | 0
|  | Glazed tiles 1/4'' thicks laid in pigment over 1:2 cement sand mortar 3/4'' thick i/c finishing (S.No.38 / P.38) | 28299.3 | %Sft | 0
|  | P/L Coloured cement tiles (Pattern 8''x8''x3/4'') of approved shade and pattern laid flat in 1:2 grey cement mortar over a bed of 3/4'' thick grey cement mortar 1;2 | 10964.99 | %Sft | 0
|  | laying white marbel flooring dressed on the the surface without winding set in lime mortar 1:2 i/c rubbing and polishing of the joints 3/4'' thick flooring (S.No. 28/P.42) | 567.48 | Psft | 0
|  | Providing and fixing 3/8'' thick marble tiles of approved quality and colour and shade size 8"x4" /6''/4" in dado skirting and facing removal / tucking of existing plaster surface etc. over 1/2'' thick base of cement mortar 1:3 setting of tiles in sulry of white cement over mortar base i/c filling the joint and washing the tiles with white cement slury currint finishing cleaning and (1) for new work (S.No.68/P.48) | 186.04 | P.sft | 0
|  | P/L tiles glazed 1/4'' on floor or wall facing in required colour and pattern of STILL specification jointed in white cement and pigment over base of 1:2 grey cement mortar 3/4 thick i/c washing and filling of joints with sulary of white cement pigment in desired shape with finishing clearing and cost of wax polish etc completed | 34520.31 | %Sft | 0
|  | Supplying and Fixing calligraphic (6x6)x1/4'' size in required color and design of tile specification base of 1:2 grey cement mortor 3/4'' above and i/c washing and filling of joints with solem white cement and pigment desired shape with finishing cleaning adn cost of wax polish etc complete | 222 | P.No | 0
|  | 1 1/2'' Thick | 2548.29 | %Sft | 0
Providing and laying 1'' thick topping cement concret (1:2:4) i/c surface finishing and dividing into panels (d) 3'' thick (S.No.16 d/P.41)
|  | 3'' Thick | 4411.82 | %Sft | 0
|  | 2'' Thick | 3275.5 | %Sft | 0
|  | Making & Fixing grated door with 1/16'' thick sheeting i/c angle iron frame 2''x2'' 3/8'' square bars 4'' center to center with locking arrangement. | 726.72 | P.Sft | 0
|  | Primary coats of chalk under distemper.(S.No.23 /P.53) | 442.75 | %Sft | 0
|  | Distempering three coats. (S.No. 24c/P.53) | 1079.65 | %Sft | 0
|  | Add: Extra labour rate for making cement plaster patta/bend around or opening a around the edges or roof slab Engineer Incharge. | 19.36 | P.Sft | 0
|  | Painting new surfaces (c) Preparing surface and painting of doors and windows any type (including edges) (I&ii) 3 coats. (S.I.No. 5/P.68) | 2116.41 | %Sft | 0
|  | Painting old surfaces (c) Painting doors and windows any type (including edges) (I&ii) 3 coats. | 1160.06 | P.Sft | 0
|  | White wash One coats. | 416.63 | %Sft | 0
|  | Colour washing of two coats. | 859.9 | %Sft | 0
|  | Preparing the surface and painting with weather coat i/c rubbing the surface with rubbing bricks / sand paper filling the viod with chalk/plaster of paris painting with weather coat of approved make new surface. | 2567.95 | %Sft | 0
|  | Removing door with chowket. (S.I.No. 33(a)/C-2) | 142.18 | P.No | 0
|  | Removing Window with Chowkhats | 102.85 | P.No | 0
|  | Pacca brick work in ground floor in cement sand mortar 1:6 | 12674.36 | %Cft | 0
|  | Making Notice board made with cement (S.I No. 1 P.94) | 58.11 | Psft | 0
Providing and laying 1'' thick topping cement concret (1:2:4) i/c surface finishing and dividing into panels (d) 3'' thick (S.No.16 d/P.41)
|  | 2'' Thick | 3275.5 | %Sft | 0
|  | Two Coat of bitumen laid hot using 34 lbs for % Sft Ober Roof and blinded with sand at one Cft Per %Sft | 1887.4 | %Sft | 0
|  | Cement Pointing struck joints on wall Ratio 1:2 (S.No.19 c /P.52) | 1287.44 | %Sft | 0
|  | Window | 240.5 | P.Rft | 0
|  | Pacca brick work in ground floor in cement sand mortor ratio 1:6. (S.No: 5 e /P.20) | 13112.99 | %Cft | 0
|  | R.C.C work including all labour and material except the cost of steel reinforcement and i/c cutting beding which will be paid s separately. R.C.C work in roof slab, beams, columns, rafts,precast Ratio 1:2:4 (1st Floor) | 349 | P.Cft | 0
|  | Extra labour for lifting of stell above first floor for every additional floor (S.I.No.29P/18) | 151.25 | P.Cwt | 0
|  | CC Plain i/c placing compting finishing and curing ratio 1:2:4 | 14429.25 | %Cft | 0
|  | S/F Procelien tile siz 18''x18'' on bed of 3/4'' thickness mortor ratio 1:2 (R.A) | 335 | P.Sft | 0
|  | Dismentling brick work in lime cement mortar | 1134.38 | %Cft | 0
|  | White wash three coats. (S.No. 26a/P.53) | 829.95 | %Sft | 0
|  | Cement concrete brick or stone ballast 1 1/2" guage ratio 1:4:8 | 9416.28 | %Cft | 0
|  | Erection and removal of centering for RCC or plain cement concrete works of deodar wood | 3127.41 | %Cft | 0
|  | Filling watering and remainng earth in floor with surplus earth from foundation lead upto one chain and lift upto 5 ft | 1512.5 | %0Cft | 0
|  | Providing and fixing iron / steel grill using solid square bars of size 3/4"x1/2" placed at 4" c/c and frame of flat iron patti 3/4"x3/4" including circle shape at 1-0 apart equivalent fitted with screws or pins including painting 3 coats. | 194.16 | Psft | 0
|  | Providing and fixing iron steel grill door with angle iron frame of 1 1/2'' x 1 1/2'' x 1/4" and flat iron of 3/4'' x 1/4" with approved design and locking arrangement embeded in Masonary as per Instruction of Engineer in charge. (S.I.No. 31/P.93) | 231.6 | P.Cft | 0
|  | S/F Procelien tile siz 24''x24'' on bed of 3/4'' thickness mortor ratio 1:2 (R.A) | 466 | P.Sft | 0
|  | Painting new surfaces (c) Preparing surface and painting of doors and windows any type (including edges) (I&ii) 3 coats. (S.I.No. 5/P.68) | 2116.41 | %Sft | 0
|  | 3'' Thick | 4411.82 | %Sft | 0
|  | Providing and laying Hala or pattern tiles glazed 6"x6"x1/2" on floor or wall facing in required pattern of Stile specification jointed in white cement and pigment over a base of 1:2 gray cement mortar 3/4" thick including washing and filling of joints with slurry of white cement and pigment in desired shape with finishing, cleaning and cost of waxpolish etc. S.No. 61/P47) | 34520.31 | %Sft | 0
|  | Consturction of innaugration marble stone 3x2x1/2 of Development Works (R.A) | 6440 | P.Job | 0
|  | Glazed tiles 1/4'' thicks laid in pigment over 1:2 cement sand mortar 3/4'' thick i/c finishing (S.No.38 / P.38) | 28999.3 | %Sft | 0
|  | Removing ventilators and wooden sunsheds etc(S.I.No. 34 P/12) | 51.43 | Each No | 0
|  | Random rubble masonary (uncoursed) (a) dry masonary (S.No: 1-a P-26) | 13323.75 | %Cft | 0
|  | Erection and removal of centering for RCC or plain cement concrete works of deodar wood (2nd class) | 7000 | %Sft | 0
|  | Filling watering and remainng earth under floor with new earth (Excavated from out side) lead upto one chain and lift upto 5 ft | 3630 | %0Cft | 0
|  | Extra labour rate for making grooves of 1''x1/4 or 3/4'' x 1/2'' plastered surface with true edges both vertically and hoizontly with uniform depth and with groove base smoothly finished etc complete as per direction of Engineer Incharge | 7.71 | P.Rft | 0
|  | Providing and laying Hala or pattern tiles glazed 6"x6"x1/2" on floor or wall facing in required pattern of Stile specification jointed in white cement and pigment over a base of 1:2 gray cement mortar 3/4" thick including washing and filling of joints with slurry of white cement and pigment in desired shape with finishing, cleaning and cost of waxpolish etc. S.No. 62/P47) | 47651.56 | %Sft | 0
|  | Construction of standard open Drain conutte block of C.C (1:2:4) in situ to the design profile i/c cost of mould as per drawing i/c applying floating cost of cement 1/32'' thick to the exposed face complete smooth curing etc completed as per detailed drawing. |  | P.Sft | 0
|  | A type Drain | 94 | P.Rft | 0
|  | B type Drain | 174 | P.Rft | 0
|  | Cement concrete brick or stone ballast 1 1/2" guage ratio 1:4:8 | 9416.28 | %Cft | 0
|  | Dismantling Stone Masonary in lime or cement | 907.5 | %Cft | 0
|  | Dismentling C.C Plain 1:2:4. | 3327.5 | %Cft | 0
|  | Coursed Rubble Masonry including hammer dressed in ground floor or 20 ft height of uncovered wall (d) (iv) in cement sand mortar 1:6 (S.I.No.2/P.26) | 25321 | %Sft | 0
|  | Damp Proof Course with (cement sand and shingle concrete 1:2:4) i/c 2 coats of asphaltic mixture © 3'' thick (S.No.28/P.18) | 4982.18 | %Cft | 0
Providing and laying 1'' thick topping cement concret (1:2:4) i/c surface finishing and dividing into panels (d) 3'' thick (S.No.16 d/P.41)
|  | Coursed Rubble Masonry including hammer dressed in ground floor or 20 ft height of uncovered wall (d) (iii) in cement sand mortar 1:6 (S.I.No.4(d)/iii/C-6) | 26288.46 | %Cft | 0
|  | Suppplying Teer at the site of work (SOM Item 141/P.72) | 3575 | P.cwt | 0
|  | Pointing flush on stone work (ii) in cement mortar 1:3 (S.No.20 c /P.52) | 1758.08 | %Sft | 0
|  | Preparing surface and painting guard bars gates of iron bars i/c standards braces etc and similar open work (3 Coat) | 896.39 | %Sft | 0
|  | Removing cement plaster or lime plaster | 121 | %Sft | 0
|  | Applying floating coat of Hi Bond (Universal) as bond coat as an adhesive link between old & fresh concrete or plaster as directed by engineer incharge | 1029.05 | %Sft | 0
|  | White wash Two coats. | 425.84 | %Sft | 0
|  | Rehandling of earth works (SNO.9b P/2) | 1058.75 | %0cft | 0
|  | Fixing doors including chowkats | 279.51 | Each No | 0
|  | Fixing Window including chowkats | 139.76 | Each No | 0
|  | Cement Plaster 3/4'' thick ration 1:4 (S.No.11 c/P.51) | 3015.76 | %Sft | 0
|  | RCC spout i/c fixing in position 2 1/2''x6''x5'' (S.No. 38/P.44) | 261.25 | Each No | 0
|  | Cement Pointing struck joints on wall Ratio 1:2 | 1287.44 | %Sft | 0
|  | Ordinary distemper, lot bound distember or paint on walls | 226.88 | %Sft | 0
|  | Khapriel of cement concret 12''x8''x1'' of approved design / shape laid flat in 1:2 grey cement mortar over a bed of 3/4'' thick cement mortar 1:2 (S.I.No.39P.No.37) | 8977.9 | %Sft | 0
|  | Applying flooting coat 1/32'' thick (S.No. 14, P-52) | 660 | %Sft | 0
|  | Dismentling rolled steel beam iron rails etc | 60.5 | P.wct | 0
|  | RCC spout i/c fixing in position with top and bottom khuras (S.No. 27/P.18) | 524.98 | Each No | 0
|  | Coloured Cement tiles 8''x8''x8'' of approved dark shade laid flat in 1:2 cement mortar over 3/4'' bending mortar 1:2 | 10962.34 | %Sft | 0
|  | Removing mud plaster from wall | 60.5 | %Cft | 0
|  | Mud Plaster on floor or roof 1'' thick | 555 | %sft | 0
|  | Replacing kaller eaten bricks.(S.No.57/P-104) | 36.63 | Each No | 0
|  | Painting New surface (d) Preparing surpace and painting guard bars, gates of iron bars, gratings, railings (including standards barces, etc) And similar open work. (S.No: 5 d P.68) | 1662.21 | %Sft | 0
|  | Khuras on roof 2'x2'x6'' (S.No.18/P.35) | 358.68 | Each No | 0
|  | RCC(F.Floor) | 349.1 | P.Cft | 0
|  | Lime Neru Plaster 1:4'' thick with fine finish of neru plaster mixed with 10% of cement | 1007.25 | %Sft | 0
P/F G.I fram chowkats size 7''x2'' or 4''x3'' for doors using 20 gauge G.I Sheet i/c welded hinger and fixing at site with necessary hold fasts i/c all carriage tools and plants used etc.
|  | Providing and fixing cement paving block flooring having size 197x97x60(mm) of city quddra / coble with pigment having strenth b/w 5000 psi to 8500 psi i/c filling the joints with hill sand and laying in specified manner / pattern and design etc (S.I.No. 72-P/48) | 223.97 | P.sft | 0
|  | Supplying Manuare S.I.No. 44/P-103 | 298.12 | P.Cart | 0
|  | Turfing lawns (excluding cost of turf) | 272.25 | %Sft | 0
|  | P/applying hi bond (sealer) water proofing polymenr modified commotitions sluries (WPMCS) to be used as water profing anticorosing, water resistance or curing membrance for fresh concret having thickness upto 2mm in two coats upto 20'' highet testured or trowel finish grey or coloureed i/c preparing the surface for applicatoin as directed by Engineer Incharge | 2282.77 | %Sft | 0
|  | Providing & fixing glass strips 4mm for flooring upto 1" depth I/c fixing in flooring with cement in specified pattern & design (S.No: 75 P/49) | 11.16 | P.Sft | 0
|  | Supplying & fixing in position Aluminium channels framing for hinged doors or Alcop made with 5 mm thick tinted glass glazing (Belgium) and Alpha (Japan) locks i/c handles, stoppers etc (b) Deluxe Model (Bronze). (S.I.No.83(b)/P107) | 1507.66 | P.Sft | 0
|  | Supplying & fixing in position Aluminium channels framing for slidding windows & ventilators of Alcop made with 5 mm thick tinted glass glazing (Belgium) and Aluminium fly screen i/c handles, stoppers & locking arrangrment etc complete (b) Deluxe Model (Bronze). (S.I.No.84(b)/C-18) | 1647.69 | P.Sft | 0
|  | Providing and fixing iron callapsible gate with channel framing of section 3/4"x5/16" 4" i/c revitted with 3/4"x1/8" flat iron patti placed diagonally and provided with top & bottom T-sectio n1"x1"x1/8" alongwith rollers also i/c locking arrangement and fixing in floor / ceiling or wal etc completed | 387.04 | P.Sft | 0
|  | First class teak wrought joinery in wire gauze doors windows with frames and 22 jstandard galvanized wire gauze 144 mesh per square inch i/c brass fitting completed (S.No 4©/57) | 345.53 | Psft | 0
|  | S/F Procelien tile siz 24''x24'' on bed of 3/4'' thickness mortor ratio 1:2 (R.A) | 466 | P.Sft | 0
|  | Khasi Parnalla in C/s Marter 1.2 12 o/s width finished. | 70.34 | P.Rft | 0
|  | Preparing the surface and painting with matt finish i/c rubbing the surface with bathy silicon carbide rubbing bricks filling the viod with zink/chalk/plaster of paris mixture applying first coat premix making the surface smooth and then painting 3-coats.with matt finish of approved make etc complete(New surface) (S.I.No. 36AP/-54) | 3444.38 | %Sft | 0
|  | Providing grey cement skirting are dado 3/8 thick i/c rounding of corner and spraighpening of top edge and finishing to smooth surface after after plastering | 2967.39 | %Sft | 0
|  | Cement plaster 1/2" thick upto 12' height 1:6. (S.No: 13 b /P.51) | 2346.6 | %Sft | 0
|  | Providing and fixing ornamental cement jalli 2'' thick 1:2:4 without steel (S,1,P/17) | 226.02 | P.Sft | 0
|  | Two coats of bitumen laid hot using 34 Lbs for % Sft. Ober roof and blinded with sand at one Cft Per %Sft. | 431.21 | %Sft | 0
|  | Making & Fixing grated door completed with locking arrangment angle iron fream 2''x2'' 3/8'' square bars 4'' center to center with locking arrangement.(S.No.23/P91) | 594.57 | P.Sft | 0
|  | Borrowpit excavation undressed lead upto 100 ft (a) in ordinary soil (S.I.No. 3(a)-P/01) | 2117.5 | %o Cft | 0
|  | Dressing & Leveling of earth work to designed section etc complete (b) Ordinary or hard soil (S.I. No. (b) P-03) | 187.55 | %o Cft | 0
|  | Earth work compaction (Soft, ordinary or hard soil) (c) compaction by rolling (this does not i/c hire charges of the roller (i) soft or sandy soil laying earth in 6'' layers leveling and dressing complete (S.No. 13 c ii P/4) | 756 | %o Cft | 0
|  | P/L 2'' thick topping in cement concrete 1:2:4 i/c surface finishing and dividing into panells. | 3275.5 | %Sft | 0
|  | Provinding and Fixing china verona marble (12''x12''x3/8'') (R.A) | 186 | P.Sft | 0
|  | Provinding and Fixing china verona marble (12''x12''x3/8'') (R.A) | 95 | P.Sft | 0
|  | Provinding and lying single per layer polythene sheet 0.13 mm thick for water proffing as per specification and insttruction of Engineer Incharge | 10.7 | P.Sft | 0
|  | Bottom, Khuras of brick masonary in cement mortor (1:6) 4'x2xx4 1/2 over 3'' cc 1:1:8 | 649.83 | Each No | 0
|  | Cement plaster 1:6 upto 12'' heightt 3/4 thick | 2590.5 | %Sft | 0
|  | Provinding and lying 1:3:6 cement concrete solid block masonary wall 6'' and below in thickness set in 1:6 cement mortar n ground floor super structure i/c raking out joint & curing etc complete (S.No.23/P.18) | 14621.44 | %Cft | 0
|  | Laying Murum flooring consisting of 1'' layer of fine powedery or flakay variety of murum laid over 6'' good hard layer murum spreading over 9'' thick sub-base comprising of hand packed rubble or broken bricks properly watered and rammed provided over well rammed (S.I.No. 1-P/39 | 3918.2 | %Sft | 0
|  | P/F angle iron vertical plats for barbed wire fencing or size 2''x2''x 1/4 embeded inRCC masonary pillar i/c making cuts / holder @ 12'' i.c fixing in pillars by chieselling and filling the with cement sand mortar sapring & finishing the surface | 169.18 | P.Rft | 0
|  | P/F barbed wire fencing with 12 gauge-4 point @ 6'' apart barbed wire i/c straightening & fixing in angle iron vertical posts. | 8.38 | P.Rft | 0
|  | Dressing & Leveling of earth Filling & make lawn | 181.5 | %Sft | 0
|  | Cement Plaster 3/8'' thick ration 1:4 (S.No.11 a/P.51) | 2283.93 | %Sft | 0
|  | 2nd class tiles roofing consisting of 4'' earth and 1'' mud plaster with gobri leeping over 1/2'' thick cement plaster 1:6 with 34 lbs of hot bitumen coating snad blinded provided over 2 layer of tiles 12''x6''x2'' laid in 1:6 cement mortor i/c 1:2 cement pointing under nearth of tiles complete i/c curing etc (S.No.2/P.32) | 4820.82 | %Sft | 0
|  | Coursed Rubble Masonry including hammer dressed in ground floor or 20 ft height of uncovered wall (d) (iv) in cement sand mortar 1:6 (S.I.No.2/P.27) | 25321 | %Cft | 0
|  | Window | 240.5 | P.Rft | 0
|  | Erection rolled supplying beam (S.No.6/P.90) | 168 | P.cwt | 0
|  | Hand rail (Railing) for chhaja / stair case of pavalion fixing charges transportation from Karachi made with 2'' dia MS Pioe 18'' gauge as per direction of Engineer Incharge (RA) | 650 | P.Rft | 0
|  | Extra labour for pacca brick work in piers and abetments above 20' | 438.63 | %Cft | 0
|  | Pacca brick work in 2nd floor | 13687.74 | %Cft | 0
|  | Cement plaster 1/2' thick upto 20' height 1:6 (2nd Floor) | 2308.85 | %Sft | 0
|  | Cement plaster 3/8' thick upto 20' height 1:4 (2nd Floor) | 2299.77 | %Sft | 0
|  | Add: Extra labour rate for making cement plaster patta/bend around or opening a around the edges or roof slab Engineer Incharge.(2nd Floor) | 1071.4 | %Sft | 0
|  | P/L 1'' Thick topping in cement concrete 1:2:4 i/c surface finishing and dividing into panells (3rd Floor) 1 1/2 thick | 3619.69 | %Sft | 0
|  | Window | 240.5 | P.Rft | 0
|  | S/F in postion iron steel grill 1/4'' size flat i/c approved design and painting three coat weight not to be then 3.7lb sq of the fininshed | 155 | P.Sft | 0
|  | Providing and laying tiles glazed 8"x8"x1/4" on floor or wall facing in required colour & pattern of STILE specification jointed in white cement and pigment over a base of 1:2 gray cement mortar 3/4" thick including washing and filling of joints with slurry of white cement and pigment in desired shape with finishing, cleaning and cost of wax polish etc complete including cutting tiles to proper profile. (S.I.No. 60/P.46) | 30509.77 | %Sft | 0
|  | Cement Concrete tile laid flat in 1:2 cement mortar over 3/4'' thick bed of cement mortar 1:2 | 6153.07 | %Sft | 0
|  | Preparing and painting with weather coat of approved make to old weather coat surface | 2118.33 | %Sft | 0
|  | S/F procelien tile siz 21''x21'' on bed of 1/4'' thickness mortor ratio 1:2 (R.A) | 320 | P.Sft | 0
|  | Providing and laying tiles glazed 8"x8"x1/4" on floor or wall facing in required colour & pattern of STILE specification jointed in white cement and pigment over a base of 1:2 gray cement mortar 3/4" thick including washing and filling of joints with slurry of white cement and pigment in desired shape with finishing, cleaning and cost of wax polish etc complete including cutting tiles to proper profile. (S.I.No. 60/P.46) | 27678 | %Sft | 0
|  | Erection and removal of centering for RCC or plain cement concrete works of deodar wood (2nd class) | 3227.41 | %Cft | 0
|  | P/Lying floor of approved with galazed tiles 1/4'' thick grey cement 1:2:4 over 3/4'' thick cement mortar etc completed. | 27678.86 | %Sft | 0
Weather Coat (2 Coat) New Surface
|  | A | 1948.1 | %Sft | 0
|  | B | 1498.48 | %Sft | 0
|  | Providing and fixing cement paving block flooring having size 197x97x60(mm) of city quddra / coble shape with natural colour with pigment having strenth b/w 5000 psi to 8500 psi i/c filling the joints with hill sand and laying in specified manner / pattern and design etc (S.I.No. 71-P/48) | 199.77 | P.sft | 0
|  | Removing cement plaster or lime plaster | 58.08 | %Sft | 0
|  | Dismentling C.C Plain 1:2:4. | 1306 | %Cft | 0
|  | Earth work compaction (Soft, ordinary or hard soil) (a) laying earth in 6'' layers leveling and dressing complete (S.No. 13 a P/3) | 263 | %0Cft | 0
|  | Earth work compaction (Soft, ordinary or hard soil) (c) compaction by rolling (this does not i/c hire charges of the roller (i) soft or sandy soil laying earth in 6'' layers leveling and dressing complete (S.No. 13 c P/3) | 635.25 | %0Cft | 0
|  | Fixing Door with Chowkats | 147.74 | P.No | 0
|  | Fixing Window with Chowkats | 73.87 | P.No | 0
|  | 2nd class tiles roofing over 1/2'' thick cement plaster 1:6 with 34 lbs of hot bitumen coating snad blinded provided over 2 layer of tiles 12''x6''x2'' laid in 1:6 cement mortor i/c 1:2 cement pointing under nearth of tiles complete i/c curing etc (S.No.2/P.32) | 6708.22 | %Cft | 0
|  | Filling watering and remainng earth under floor with new earth (Excavated from out side) lead upto one chain and lift upto 5 ft | 272.25 | %Sft | 0
|  | Window | 240.5 | P.Rft | 0
|  | Dismentling pacca brick work in lime cement mortar | 617.1 | %Cft | 0
|  | Provinding and lying 1:3:6 cement concrete solid block masonary wall 6'' and below in thickness set in 1:6 cement mortar n ground floor super structure i/c raking out joint & curing etc complete (S.No.24/P.18) | 15771.01 | %Cft | 0
|  | First class deodar wood wrought, joinery in doors and windows etc, fixed in position including chowkats, hold fasts, hinges, iron tower bolts, chocks, cleats, handles and cords with hooks etc. Deodar panelled or panelled and glazed or fully glazed (b)1.75" thick . (S.I.No. 7(b)/P.57) |  | P.Sft | 0
|  | Filling watering and ramming earth in floor earth surplus earth from (Excavated from outside) lead upto one chain and lift upto five feet. |  | %oCft | 0
|  | Supplying pit sand i/c compacting watering ramming(R.A.A) |  | %Sft | 0
|  | Making grooves |  | P.Rft | 0
|  | 1st class deodar wood wrought joinery in wire guze door and window with 22 SWG galavized wire guze 144 mesh per suquare inch iron fitting complete |  | P.Sft | 0
|  | S/F in postion iron steel grill 3/8''x3/8x4''c/c (R.A) |  | P.Rft | 0
|  | Painting new surfaces (c) Preparing surface and painting of doors and windows any type (including edges) (I&ii) 3 coats. |  | %Sft | 0
|  | P/L 1-1/2'' thick topping in cement concrete 1:2:4 i/c surface finishing and dividing into panells. |  | %Sft | 0
|  | Preparing the surface and applying rock wall / shield (Natural Wall Texture) coating to provide durable crust to wall, thickness b/w 2 mm to 32 mm (1/8'' thick) with acrylic co-polymer emulsion, selected marble chips, adhesive and bactercdes water resistance and fire and termite resistance (upto 20'-0 hieght (S.No 4., P/55) | 4504.5 | %Sft | 0
|  | laying white marbel flooring fine the surface without winding set in lime mortar 1:2 i/c rubbing and polishing of the joints. |  | Psft | 0
|  | White wash one coat |  | %Sft | 0
|  | Bottom, Khuras of brick masonary in cement mortor (1:6) 4'x2xx4 1/2 over 3'' cc 1:1:8 | 649.83 | Each No | 0
|  | Excavation in foundation of building, bridges and other structure including dagbelling dressing, refilling around structure with excavated earth, watering and ramming. Lead upto 5ft (b) in ordinary Soil.(S.I.No. 18(b)/C-1) | 3554.38 | %0Cft | 0
|  | 1st Floor |  | P.Cwt | 0
|  | 1st Floor |  | %Cft | 0
|  | 2nd class tiles roofing |  | %Cft | 0
|  | P/F 3/8'' thick marble tiles or glazed in lime mortar 1:2 |  | P.Sft | 0
|  | Removing door with chowket. (S.I.No. 33(a)/C-2) |  | %Sft | 0
|  | Mosaic tiles of white cement 8'' x 8'' x1 of approved sahed with khapch laid flat in 1 : 2 white cement mortar over a bed of 3/4'' thick grey cement 1:2 | 14090.74 | %Sft | 0
|  | Preparing surface and painting guard bars gates of iron bars surface 3 ocats. |  | %Sft | 0
|  | Providing and laying Hand Made Kashi Tiles, on wall facing in required pattern jointed in gray cement over a base of 1:2 gray cement mortar 3/4" thick including washing and filling of joints with slurry of white cement and pigment in desired shape with finishing, cleaning and cost of wax polish etc complete as per directions of Engineer Incharge. (R.A) |  | P.Sft | 0
|  | P/L 1 1/2'' thick topping in cement concrete 1:2:4 i/c surface finishing and dividing into panells. |  | %Sft | 0
|  | Dismentling C.C Plain 1:3:6. |  | %Cft | 0
|  | Cement concrete plain i/c placing compacting and finishing complete i/c screening and washing of stone aggreagate without shuttering 1:2:4 ratio . |  | %Cft | 0
|  | Mosaic cheque tiles of 11'' x 8'' x1-1/4 of approved shade laid flat in 1:2 grey cement mortar over bed of 3/4'' thick grey cement 1:2 |  | %Sft | 0
|  | Providing & fixing curab stone along road side (R.A) |  | P.No | 0
|  | Construction of standard open type Drain conutte block of C.C |  | P.Sft | 0
|  | Providing & fixing collour create jto wall |  | %Sft | 0
|  | Supplyin of Manure |  | P.car load | 0
|  | Lying floor of approved with galazed tiles 3/4'' thick white cement 1:2:4 over 3/4'' thic cement mortar completed. |  | %Sft | 0
|  | Dismantling cement block masonary |  | %Cft | 0
|  | 2nd class roofing tiles. |  | %Cft | 0
|  | lying floor of approved with glazed tiles 1/4'' thick in white cement 1:2 over 3/4'' thick cement mortar 1:2 completed |  | %Sft | 0
P/F G.I fram chowkats size 7''x2'' or 4''x3'' for doors using 20 gauge G.I Sheet i/c welded hinger and fixing at site with necessary hold fasts i/c all carriage tools and plants used etc.
|  | Colour washing of 1st coats. |  | %Sft | 0
|  | Providing and laying Hala or pattern tiles glazed 6"x6"x1/4" on floor or wall facing in required pattern of Stile specification jointed in white cement and pigment over a base of 1:2 gray cement mortar 3/4" thick including washing and filling of joints with slurry of white cement and pigment in desired shape with finishing, cleaning and cost of waxpolish etc. |  | %Cft | 0
|  | Construction of Innaugration marble stone 3x2x1/2 of Development |  | P.Job | 0
|  | P/L tiles matt and glazed or double on wall of floor or walls and facing in required pattern and design in jointed with high bond of required base i/c washing and filling of joints with sllurry of white cement & pigment in desired shap with finishing cleaning etc complete. |  | Psft | 0
P/L 2'' thick topping in cement concrete 1:2:4 i/c surface finishing and dividing into panells
|  | P/L topping in cement concrete 1:2:4 i/c surface finishing and dividing into panells (2'' Thick) |  | %Sft | 0
|  | Mud Plaster on floor or roof 1'' thick |  | %Sft | 0
|  | P/F with sunken iron screw wooden approve d desing etc |  | P.Sft | 0
|  | Painting new surfaces (c) Preparing surface and painting of doors and windows any type 2coats. |  | %Sft | 0
|  | Cement Plaster 1/2'' thick upto 20'' highet 1:4 ratio |  | %Sft | 0
|  | Cement Plaster 3/4'' thick upto 20'' highet 1:3 ratio |  | %Sft | 0
|  | Providing and laying calligraphic tile of approved size in required colour and design of tile specified jointed in white cement and pigment over a base of 1:2 gray cement mortar 3/4'' thick i/c washing and filling of joints with slurry white cement and pigment in directed shape with finishing cleaning and cost of waxpolish etc complete. |  | Psft | 0
|  | Teak wood wrought framed and fixed in place i/c chowkats hold fasts tower bolts chocks cleans handles cords with hooks cost of naild and screw etc complete. |  | Psft | 0
|  | White or coloured glass work 1/16'' thick on wall of approved pattern and design fixed over a base of plaseter of paris and glases fixed with guage i/c filling joints and making even surface. |  | Psft | 0
|  | Providing & Laying Nasurpur Kashi tiles 8''x8''x3/4 on floor or wall facing in required colour jointed in white cement and pigment over a base of 1:2 gray cement mortar 3/4" thick including washing and finishing the joints with slurry and pigment in specified shape with finishing cleaning etc complete. |  | Psft | 0
|  | French polishing etc completed (a) on new work. |  | %Sft | 0
|  | Providing and fixing plaster of paris ceiling border of 8" - 10" width of specified design & thickness including fixing besides ceiling with nails / screws with jetties. (S.I No. 44/C-7) |  | P.Rft | 0
|  | Painting new surfaces (c) Preparing surface and painting of doors and windows any type (including edges) (I&ii) 3 coats. (S.I.No. 5(c)/I&ii/C-11) |  | %Sft | 0
|  | Supplying and fixing false ceiling of plaster of paris in pannels including making frame work of Deodar wood including painting with solignum paint. (S.I No. 52/C-10) |  | %Sft | 0
White wash Two coats.
|  | P/L 2'' thick topping in cement concrete 1:2:4 i/c surface finishing and dividing into panells. |  | %Sft | 0
|  | Providing and laying Hala or pattern tiles 8"x 8"x1/4" on floor or wall facing in required coloured and patterns. |  | %Sft | 0
|  | Making grooves |  | %Sft | 0
|  | Provinding and lying Khaprail tile 8''x12'' for water proffing as per specification and insttruction of Engineer Incharge |  | %Sft | 0
|  | Preparing the surface and painting with weather coat i/c rubbing the surface with rubbing bricks / sand paper filling the viod with chalk/plaster of paris painting with weather coat of approved make new surface. | 2568.95 | %Sft | 0
|  |  |  | Total | 416942
__________% Above / Below on the Rates of CSR. |  |  | Amount to be added / deducted on
basis of premium quoted Total (b)
Total a+b Rs. (a) ___________________ Rs. (b) _______________ = Rs. _______________________
Total (A)= a+b In Words & Fiqure ______________________________________________________
_____________________________________________________________________________________
EXECUTIVE ENGINEER
| CONTRACTOR |  |  | EDUCATION WORKS DIVISION
JAMSHORO

## 111118
PART "B" WATER SUPPLY & S/FITTING
S.NO: | Item of Work |  |  | Qnty | Rate | Unit | Amount
1 | P/F Squating type white glazed earthen were w.e pan with including the cost of flushing cistern with internal fitting and flush Pipe with bend & making requisite number of holes in walls plinth & floor for pipe connections & making good in cement concerete 1:2:4 (S.I.NO: 1 (b) P/1)
|  |  | = | 2 | 4802.9 | P.No | 9605.8
2 | P/F 24x18 lavatory bason in white glazed earthen with i/c the cost of W/I or C/I contelever brackets 6" built into walls, painted white in two costs after a primary coat of red paint a pair of 1/2 dia chorm plated piller traps 1/6 rubber superior quality etc complete (S.I.No: 8 P/3)
|  |  | = | 0 | 4253.9 | P.No | 0
3 | Add Extra labour for P/Fitting of earthen ware pedestal while or coloured glazed superior quality (S.I.No: 11 P/3)
|  |  | = | 0 | 2533.47 | P.No | 0
:
4 | P/F 6"x2" C.I floor trap of the approved self cleanbing & desigin i/c acrewed down grating with of without making required No of holes in walls plinth & floor for pipe connection & making secro in C.C (S.I.No: 20 P/6)
|  |  | = | 2 | 2042.43 | P.No | 4084.86
5 | P/F in position nylon connection complete with 1/2 dia bross bib cock with pair of bross nuts & bults lining joints to nylon connection (S.I.No: 20 P/6)
|  |  | = | 2 | 447.15 | P.No | 894.3
6 | P/F 15"x12" beveled edge mirror of belgium glass complete with 1/8" thick hard board and C.P screws fixed to wooden plant standard. (S.I.No: 4 P/7)
|  |  | = | 0 | 1161.6 | P.No | 0
7 | Supplying & Fixing soap tray of made plastic of each superior quality and design with fine finishing with c.p screws etc. complete (S.I.NO: 6 P/8
|  |  | = | 1 | 169.4 | P.No | 169.4
8 | P/F 4" dia C.I soil vent pipe i/c cutting fitting & extra paint match colour of the building (S.I.No: 1 P/9)
|  |  | = | 12 | 333.29 | P.rft | 3999.48
9 | P/F 4"x4" dia C.I branch of the required degree with accessaries doors rubber washer 3/4" thick bolts & nuts & extra painting to match colour of the building (S.I.No: 3 P/9)
|  |  | = | 2 | 702 | P.No | 1404
10 | P/F 4"x4" x4" dia C.I branch of the required degree with accessaries doors rubbers washer 3/4" thick bolts & nuts & extra painting to match colour of the building (S.I.No: 4 P/9)
|  |  | = | 2 | 270.6 | P.No | 541.2
11 | P/F 4" dia C.I terminal guard Each including extra painting to match the colour of the building (S.I.NO: 11 P/10)
|  |  | = | 2 | 389.7 | P.No | 779.4
12 | Providing G.I pipe speclals & clamps etc including fixing cutting and fitting complete with and i/c the cost of breaking rough wall and roof making good etc painting two coats after cleaning the pipe etc white zink point with pigment to match the colour of building (S.I.NO: 1 P/12)
| 1/2" dia |  | = | 100 | 73.21 | P.rft | 7321
| 3/4" dia |  | = | 50 | 95.79 | P.rft | 4789.5
| 1" dia |  | = | 20 | 128.55 | P.rft | 2571
| 1 1/2' dia |  | = | 80 | 188.97 | P.rft | 15117.6
| 1 1/2" dia |  | = | 0 | 188.97 | P.rft | 0
13 | Add extra labour for concealed G.I Pipe & fittings I/C making recess in the wall for Pipe & making good in cement mortor etc. complete (S.I.NO: 2 P/12)
| (I) | 1/2" dia | = | 30 | 7.82 | P.rft | 234.6
| (II) | 3/4" dia | = | 20 | 8.45 | P.rft | 169
| (III) | 1" dia | = | 0 | 9.96 | P.rft | 0
14 | Providing and Fixing handle valves (china) (S.I.NO: 5 P/17)
| (I) | 1/2" dia | = | 1 | 200.42 | P.rft | 200.42
| (II) | 3/4" dia | = | 1 | 271.92 | P.rft | 271.92
15 | S/Fixing cancealed tee-stop cock of superir Each quality with c.p head 1/2" dia. (S.I.NO: 12 (b) P/18)
|  |  | = | 2 | 889.46 | P.NO | 1778.92
16 | S/Fixing long bib-cock of superir quality Each with c.p head 1/2" dia (S.I.NO: 13 P/19)
|  |  | = | 2 | 1109.46 | P.NO | 2218.92
17 | Supplying & Fixing swan type piller cock of Each Superior quality single c.p head 1/2" dia (S.I.NO: 16 P/19)
|  |  | = | 1 | 795 | P.NO | 795
18 | S/F fiber glass tank of approved quality and design and wall thicness as specifiesd I/C cost of nutes, bolts and fixing in plateform of cement concerete 1:3:6 and makin connections for in let & out-let & over flow Pipe etc. copmlete (250g)(S.I.NO:3 P/21)
|  |  | = | 0 | 21989.61 | P.NO | 0
18 | Providing, Laying uPVC pipes of Class 'D' fixing in trench i/c cutting, fitting and jointing with solvent cement i/c tsting with water to a head of 122 meter or 400 ft. (S.No: 6-b P-C-II/24)
|  |  | = | 0 | 19 | P.NO | 0
19 | Providing R.C.C pipe with collars class "B" and digging the to required depth & fixing in position i/c cutting fitting & jointing with maxphalt composition cement mortor 1:1 and testing with water pressure to a head of 4" feet above the top of the heightest pipe & refilling excavated staff 6" pipe class "B" (S.No: 2 (e) P/23 C-10)
| 3" dia |  | = | 0 | 113.97 | P.rft | 0
| 4" dia |  | = | 0 | 146.57 | P.rft | 0
| 6" dia |  | = | 30 | 199.25 | P.rft | 5977.5
| 12" dia |  | = | 0 | 401.97 | P.rft | 0
20 | Construction of main hole i/c inspection of chamber & required depth 3/6" wall etc. complete
|  |  | = | 3 | 14748 | P.NO | 44244
21 | P/L U P V C Pressare pipe of class B i/c cutting fitting and jointing.
| 3" dia |  | = | 0 | 90 | P.Rft | 0
| 4" dia |  | = | 10 | 136 | P.Rft | 1360
| 6" dia |  | = | 10 | 259 | P.Rft | 2590
22 | P/F water pumping set wit seimen motor and jawed pump 1 H.P 1400 PRM single Phase 220 Vikts 1"x1-1/2" suction and delivery 40 ft head i/c base plate and also making C.C 1:3:6 plate farm of required size and fixing nuts and bolts complete in all respect (R.A)
|  | 1 No | = | 1 | 14417.7 | P.NO | 14417.7
23 | P/F hand Pump with all accessaries wooden shown i/c boring cutting etc. (R.A)
| Filter |  | = | 10 | 76.05 | P.rft | 760.5
| H.Pump Machine |  | = | 1 | 1441.65 | P.No | 1441.65
[6 empty] | Total | 127737.67
|  | Total N.S.I |  |  |  |  | 16619.85
[5 empty] | Total S.I |  | 111117.82
__________% Above / Below on the Rates of CSR. |  |  | Amount to be added / deducted on
basis of premium quoted Total (b)
W&S & S/F(a) ___________________ Rs. (b) _______________ = Rs. ______________________
Total (A)= a+b In Words & Fiqure ______________________________________________________
_____________________________________________________________________________________
EXECUTIVE ENGINEER
| CONTRACTOR |  |  | EDUCATION WORKS DIVISION
JAMSHORO