## Sheet1
REVISED ANNUAL PROCUREMENT PLAN
WORKS & SERVICES DEPARTMENT
(FINANCIAL YEAR 2016-2017)
OFFICE OF THE EXECUTIVE ENGINEER HIGHWAYS DIVISION KASHMORE @ KANDHKOT
Sr | ADP | Description of Procurement | Quality | Estimted | Estimated | Fund | Source of | Proposed | Timining of Procurement |  |  |  | Remarks
No | No: |  | (Where | unit cost | Total | Allocated | Funds | Procurement | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
|  |  | Applicable) | (Where | Cost |  | ADP/ | Method
|  |  |  | Applicable) |  |  | Non ADP
1 |  | Widening road fro Clock Tower Chowk to Grid Station Kashmore road (Kandhkot Town) Mile 0/4-1/4+330" | -- | -- | 20 | 5 | District ADP | National Competitive Bidding Method | -- | Yes | -- | -- | --
2 |  | Widening Clock Tower Chowk to Main Primary School Kandhkot (mile 0/0-0/4+330") i/c approaches (Phase-II) | -- | -- | 12.715 | 3.1787 | District ADP | .--do-- | -- | Yes | -- | -- | --
3 |  | Widening Kandhkot by pass road @ Jholy Lal Petrole Pump to National bank Kandhkot mile 0/0-0/4+330") (Phase-II) | -- | -- | 12.65 | 3.1625 | District ADP | .--do-- | -- | Yes | -- | -- | --
4 |  | Widening of road from Raja Petrole Pump Chowk to Kandhkot by pass Kandhkot Town mile 0/0-0/2 | -- | -- | 6.9 | 1.725 | District ADP | .--do-- | -- | Yes | -- | -- | --
5 |  | Rehabilitation/Repair of road from Indus Highway to Village Wahid Bux Khan Bijarani Taluka Tangwani mile 0/0-1/0 (in portion). | -- | -- | 2.5 | 0.625 | District ADP | .--do-- | -- | Yes | -- | -- | --
6 |  | Re-Consditioing/Repair of road in village Gulzar Ahmed Bahlkani Deh Uner U/C manjhi Taluka Tangwani | -- | -- | 1 | 0.25 | District ADP | .--do-- | -- | Yes | -- | -- | --
7 |  | Rehabilitation / Re-Considitioning of road from Village Ahmed Khan Sundrani Bhanner to PPL road mile 0/0-1/0 = 1.61 K.M Taluka Kandhkot | -- | -- | 10 | 2.5 | District ADP | .--do-- | -- | Yes | -- | -- | --
8 |  | Rehabilitation/ Re-Conditioning of road from Sheralabad road to Village Daho road mile 0/0-1/0= 1.5 K.M Taluka Kandhkot | -- | -- | 10 | 2.5 | District ADP | .--do-- | -- | Yes | -- | -- | --
9 |  | Rehabilitation/Re-Conditioning of road from NHA to Doli Chowk via Baboo Malik, Sath Muhammad Hassan Mirani, Khuda Bux Soomro & Mushtaque Ahmed Soomro House mile 0/0-02 Taluka Kandhkot. | -- | -- | 10 | 2.5 | District ADP | .--do-- | -- | Yes | -- | -- | --
10 |  | repair of road Ghulam Qader Machhi road to Rasool Bux Chachar road Taluka Kashmore (mile 3/0-4/0 in portion) | -- | -- | 3 | 0.75 | District ADP | National Competitive Bidding Method | -- | Yes | -- | -- | --
11 |  | Construction / Re-Consitioning of road Adio Wah Sui Line Purani upto Ghulam Hussain Mazari Taluka Kashmore (Phase-I) | -- | -- | 6 | 1.5 | District ADP | .--do-- | -- | Yes | -- | -- | --
12 |  | Repair of road from Murad wah to Muhammad Arif Jakhrani road Taluka Kashmore road mile 0/0-0/5 | -- | -- | 3.8 | 0.95 | District ADP | .--do-- | -- | Yes | -- | -- | --
13 |  | Rapir of road from Kandhkot Saifal road to Old Alif Khan Bijarani Taluka Tangwani mile 0/0-0/6 = 1.1 K.M) | -- | -- | 5 | 1.25 | District ADP | .--do-- | -- | Yes | -- | -- | --
14 |  | Reapir & Renovation/Widening of Geehalpur road Murad wah to New R.D-45 road Bridge of Kashmore Town Taluka Kashmore road mile 0/0-0/5. | -- | -- | 15 | 3.75 | District ADP | .--do-- | -- | Yes | -- | -- | --
15 |  | Construction and Repair of road from R.D-45 @ Village Qader Khan Mazari Taluak Kashmore Phase-I | -- | -- | 7.5 | 1.875 | District ADP | .--do-- | -- | Yes | -- | -- | --
16 |  | Construction and Repair of road from manghar Phatk upto Village Atthar Khan and Hafeez Khan Domki Taluka Kashmore road mile 0/0-2/0 (in portion) | -- | -- | 3 | 0.75 | District ADP | .--do-- | -- | Yes | -- | -- | --
17 |  | Reapir/ Re-Conditioning of road from Kandhkot Shafi Muhammad Khoso road to Village Muhammad Hassan / Ali Dost Bangwar u/c Doulatpur Taluka Kandhkot mile 0/0-02 = 0.40 K.M) | -- | -- | 1.995 | 0.49875 | District ADP | .--do-- | -- | Yes | -- | -- | --
18 |  | Rehabilitation / Re-Conditioning of road Ghulam Qader Shaikh 36" mile u/c Lashari Taluka Tangwani mile 1/7-2/4 | -- | -- | 3.479 | 0.86975 | District ADP | .--do-- | -- | Yes | -- | -- | --
19 |  | Construction of Protection wall of road Mir rasool Bux Khan Chachar Taluka Kashmore | -- | -- | 3.6 | 0.9 | District ADP | .--do-- | -- | Yes | -- | -- | --
20 |  | Construction of Link road from Abdul Ghani Bijarani road to Village Sachal Gujrani and Ali Khan Cholyani Taluka Tangwani | -- | -- | 9 | 2.25 | District ADP | .--do-- | -- | Yes | -- | -- | --
21 |  | Construction of Link road from Wali Muhammad Bangwar road to Village Abdul Sattar bangwar Taluka Kashmore road mile 0/0-0/1 | -- | -- | 1.5 | 0.375 | District ADP | National Competitive Bidding Method | -- | Yes | -- | -- | --
22 |  | Construction of road Jaan Muhammad Khoso to Village Bagan Khan Gadahi Taluka Tangwani mile 0/0-2/0 = 2.50 K.M) | -- | -- | 20 | 5 | District ADP | .--do-- | -- | Yes | -- | -- | --
23 |  | Construction of road karampur Magsi to Village haji Arab Khan Jaffery Taluka Tangwani mile 0/0-0/5 = 1.0 K.M) | -- | -- | 9 | 2.25 | District ADP | .--do-- | -- | Yes | -- | -- | --
24 |  | Construction fo road in BHU at Village Muhammad Arif Khan Jakhrani Taluka Kashmore | -- | -- | 4.7 | 1.175 | District ADP | .--do-- | -- | Yes | -- | -- | --
25 |  | Construction of road from Karampur Magsi road to Village Dodico u/c karampur Taluka Tangwani road mile 0/0-0/3+330" | -- | -- | 5 | 1.25 | District ADP | .--do-- | -- | Yes | -- | -- | --
26 |  | Construction of road from B-Section Police Station to Village Rais Ghulam Hyder Awan upto House of Nisar Ahmed awan Taluka kandhkot road mile 0/0-0/2 | -- | -- | 2.5 | 0.625 | District ADP | .--do-- | -- | Yes | -- | -- | --
27 |  | Construction of road from back side of Anaj mandhi road to Connect Suhrab Khan Pathan Kandhkot Town (330 rft) | -- | -- | 4.21 | 1.0525 | District ADP | .--do-- | -- | Yes | -- | -- | --
28 |  | Construction for road from Jakhrani House to Back side of Gurdwara Kandhkot Town (250 rft) | -- | -- | 0.976 | 0.244 | District ADP | .--do-- | -- | Yes | -- | -- | --
29 |  | Construction of road from Ali dad Mazari road to Village Bakhmir Khan Mazari Taluka Kashmore road mile 0/0-0/1 + 140") | -- | -- | 2 | 0.5 | District ADP | .--do-- | -- | Yes | -- | -- | --
30 |  | Construction for oad from Ali dad to raod to Village Gul Muhammad Mazari Taluka Kashmore mile 0/0-0/0 + 600") | -- | -- | 1.5 | 0.375 | District ADP | .--do-- | -- | Yes | -- | -- | --
31 |  | Construction of road in Village Abdul Karim Khoso U/C & Deh Line Purani Taluka Kashmore | -- | -- | 2 | 0.5 | District ADP | .--do-- | -- | Yes | -- | -- | --
32 |  | Construction of road in Village Waqif Khan Bajkani Taluka Tangwani (phase-I) | -- | -- | 1.5 | 0.375 | District ADP | .--do-- | -- | Yes | -- | -- | --
33 |  | Construction of road from Khahi road to Village Alan Khan Bangwar u/c R.B Chachar Taluka Kashmore (phase-I) | -- | -- | 3 | 0.75 | District ADP | National Competitive Bidding Method | -- | Yes | -- | -- | --
34 |  | Construction of road from NHA to Mir Abdul Fattah Khan Teghani House u/c Mangi Taluka Kandhkot mile 0/0-01 + 540") | -- | -- | 3.5 | 0.875 | District ADP | .--do-- | -- | Yes | -- | -- | --
35 |  | Construction of road from Geehalpur road @ Murad wah to Chachar Muhallah Kashmore Taluka Kashmore road mile 0/0-0/1+440") | -- | -- | 2 | 0.5 | District ADP | .--do-- | -- | Yes | -- | -- | --
36 |  | Construction of road from Khair Shah road to Village Rasool Bux Menik Taluka Kandhkot mile 0/0-0/1+240") | -- | -- | 2 | 0.5 | District ADP | .--do-- | -- | Yes | -- | -- | --
37 |  | Construction of road from Banhoo Faquir road to Village Shafquat Hussain urf Sobo bangwar Taluka Kandhkot mile 0/0-0/1 + 240") (Portion-I) | -- | -- | 2 | 0.5 | District ADP | .--do-- | -- | Yes | -- | -- | --
38 |  | Construction of road from Kandhkot malguzar road to Village Illahi Bux Khan lashari Taluka Kandhkot mile 0/0-0/1+240" (Phase-I) | -- | -- | 2 | 0.5 | District ADP | .--do-- | -- | Yes | -- | -- | --
39 |  | Construction of Link road from Village Rais Muhammad Umar Bhutto via Rais Abdul Khalique Bhutto to Jam Mearal Sangi u/c badani Taluka Kashmore 0/0-0/6 | -- | -- | 10 | 2.5 | District ADP | .--do-- | -- | Yes | -- | -- | --
40 |  | Construction of Link road from Kandhkot Malguzar road to Village Mehboob Khan Jakhrani u/c Rasaldar Taluka Kandhkot (Phase-I) | -- | -- | 2.5 | 0.625 | District ADP | .--do-- | -- | Yes | -- | -- | --
41 |  | Construction of road from left side Ghouspur minor to Siyano Ogahi Taluka Kandhkot mile 0/0-0/1 | -- | -- | 5 | 1.25 | District ADP | .--do-- | -- | Yes | -- | -- | --
42 |  | Construction of road inVillage Chairmen Illahi Bux Khan u/c Masuwala Taluka kashmore | -- | -- | 2.5 | 0.625 | District ADP | .--do-- | -- | Yes | -- | -- | --
43 |  | Construction of road in Village Hashim Khan Khoso Taluka Kashmore mile 0/0-0/1+290" | -- | -- | 2.5 | 0.625 | District ADP | .--do-- | -- | Yes | -- | -- | --
44 |  | Construction of road Village Rafique Ahmed Khan Jakhrani Taluka Kashmore (Phase-I) | -- | -- | 5.5 | 1.375 | District ADP | .--do-- | -- | Yes | -- | -- | --
45 |  | Construction of road in Village Molvi Abdul Sattar Taluka Kashmore mile 0/0-0/1+90" | -- | -- | 2.5 | 0.625 | District ADP | National Competitive Bidding Method | -- | Yes | -- | -- | --
46 |  | Construction of road G.M Khan Khoso Taluka Kashmore road mile 0/0-0/6 | -- | -- | 1 | 0.25 | District ADP | .--do-- | -- | Yes | -- | -- | --
47 |  | Construction of road in Village D.C Malik upto Ashraf Khan Khoso Taluka Kashmore | -- | -- | 2 | 0.5 | District ADP | .--do-- | -- | Yes | -- | -- | --
48 |  | Construction of road to Village Kaloo Khan Mazari u/c Sodhi Taluka Kashmore road mile 0/0-0/1+320" | -- | -- | 2.5 | 0.625 | District ADP | .--do-- | -- | Yes | -- | -- | --
49 |  | Construction of road in Village Jani Khan Chachar Taluka Kashmore (phase-I) | -- | -- | 6 | 1.5 | District ADP | .--do-- | -- | Yes | -- | -- | --
50 |  | Construction of Dual Carriage way road from New District Session Judge Office Kandhkot back side of District Level Complex Kandhkot Town road mile 0/0-0/1+40") | -- | -- | 3 | 0.75 | District ADP | .--do-- | -- | Yes | -- | -- | --
51 |  | Construction of Graveyard Road Kahiro Ghair Taluka Kashmore (phase-I) | -- | -- | 7.5 | 1.875 | District ADP | .--do-- | -- | Yes | -- | -- | --
52 |  | Construction of Bridge over Touj Shakh near Govt: Primary School Wazir Ali Bangwar Taluka kandhkot | -- | -- | 1.5 | 0.375 | District ADP | .--do-- | -- | Yes | -- | -- | --
53 |  | Construction of Bridge Over Suhryani Shakh @ Gajee Khan Golo and Nabid Dad Golo U/C Kumberi Taluka Kashmore | -- | -- | 1 | 0.25 | District ADP | .--do-- | -- | Yes | -- | -- | --
54 |  | Construction of Bridge Over Sindh Dhoro Shakh @ Village Hakim Ali Bangwar Taluka Kashmore | -- | -- | 2 | 0.5 | District ADP | .--do-- | -- | Yes | -- | -- | --
55 |  | Construction of 20" rft Bridge @ Village Mansab Khan Cholyani u/c Saeedo Kot Taluka Tangwani | -- | -- | 1 | 0.25 | District ADP | .--do-- | -- | Yes | -- | -- | --
56 |  | Construction of Bridge over Murad wah @ Village Ghulam Murtaza Khoso (Sultan) Taluka Kashmore | -- | -- | 1 | 0.25 | District ADP | .--do-- | -- | Yes | -- | -- | --
57 |  | Construction of Bridge Over C.P Shakh @ Village Amir Hussain Golato u/c Rasaldar Taluka Kandhkot | -- | -- | 2 | 0.5 | District ADP | .--do-- | -- | Yes | -- | -- | --
58 |  | Construction of Bridge Over Muhammad Arif Khan Minor @ Village Darya Khan Jakhrani Deh Silachi Taluka Kashmore | -- | -- | 2.5 | 0.625 | District ADP | National Competitive Bidding Method | -- | Yes | -- | -- | --
59 |  | Construction of Bridge Over Muhammad Arif Khan Minor @ Village Anwar beg Khan Jakhrani Deh Silachi Taluka Kashmore | -- | -- | 2.5 | 0.625 | District ADP | .--do-- | -- | Yes | -- | -- | --
60 |  | Construction of Bridge Over Bahduran Minor @ Village Manthar Chachar Taluka Kashmore | -- | -- | 1.5 | 0.375 | District ADP | .--do-- | -- | Yes | -- | -- | --
61 |  | Construction of Bridge Over Silachi @ Village Iqrar Khan Jakhrani Taluka Kashmore | -- | -- | 2 | 0.5 | District ADP | .--do-- | -- | Yes | -- | -- | --
62 |  | Construction of Bridge Over Touj Shakh @ Village Rafique Khan Khoso Taluka Kashmore | -- | -- | 1.5 | 0.375 | District ADP | .--do-- | -- | Yes | -- | -- | --
63 |  | Construction of Bridge Janib Khan Muhammadani Taluka Kashmore | -- | -- | 0.3 | 0.075 | District ADP | .--do-- | -- | Yes | -- | -- | --
64 |  | Construction of Bridge (08 rft) in Village Hafiz Dhani Bux Golo Taluka Kashmore | -- | -- | 0.6 | 0.15 | District ADP | .--do-- | -- | Yes | -- | -- | --
65 |  | Construction of Bridge/Culvert @ Village Muhammad Usman Jakhrani Taluka Kashmore | -- | -- | 0.3 | 0.075 | District ADP | .--do-- | -- | Yes | -- | -- | --
66 |  | Repair of Bridge Over Pharti Shakha Chhijhan Pull Taluka kashmore | -- | -- | 0.5 | 0.125 | District ADP | .--do-- | -- | Yes | -- | -- | --
67 |  | Construction of 20' rft Bridge Over Sindh Dhoro Shakh @ Village Hazoor Bux Golo u/c malheer Taluka Kandhkot | -- | -- | 1 | 0.25 | District ADP | .--do-- | -- | Yes | -- | -- | --
68 |  | Construction of 20" rft Bridge Over C.P Shakh @ Village Nazir Ahmed Golato u/c Rasaldar Taluka Kandhkot | -- | -- | 1 | 0.25 | District ADP | .--do-- | -- | Yes | -- | -- | --
69 |  | Construction of 20" rft Bricge over Sindh Dhoro Shakh @ Village Hakim Ali Sabzoi Taluka Kandhkot |  |  | 0.9 | 0.225 | District ADP | .--do-- | -- | Yes | -- | -- | --
70 |  | Construction of 20" rft Bridge Over Raj Wah u/c Jafferabad Taluka Tangwani |  |  | 1 | 0.25 | District ADP | .--do-- | -- | Yes | -- | -- | --
71 |  | Construction of Culverts (Water Course Bridge) @ Village Abdul Hakeem Nindwani u/c Saifal Taluk Tangwani |  |  | 1 | 0.25 | District ADP |  | -- | Yes | -- | -- | --
72 |  | Construction of Culverts in Village Pahar Din Bajkani U/C Lalui Taluka Tangwani |  |  | 0.2 | 0.05 | District ADP | National Competitive Bidding Method | -- | Yes | -- | -- | --
73 |  | Construction of Culverts in Village Raban Khan Dahani Taluka Tangwani |  |  | 0.5 | 0.125 | District ADP | .--do-- | -- | Yes | -- | -- | --
74 |  | Construction of Culverts in Village Mir Hassan Khan Nindwani Taluka Tangwani |  |  | 0.5 | 0.125 | District ADP | .--do-- | -- | Yes | -- | -- | --
75 |  | Construction of Culverts in various Villages @ Mehboob Ali, Khair Bux, Mir Jakhrani, Muhammad Ismail & Muhammad Khan jakhrani U/C Malguzar Taluka Kandhkot |  |  | 1.5 | 0.375 | District ADP | .--do-- | -- | Yes | -- | -- | --
76 |  | Construction of Culvert in fron of Jahangir Deh Bhanner u/c Gublo Taluka Kandhkot |  |  | 0.5 | 0.125 | District ADP | .--do-- | -- | Yes | -- | -- | --
77 |  | Construction of Culverts in Village Jean Golo Bhanner u/c Gublo Taluka Kandhkot |  |  | 0.5 | 0.125 | District ADP | .--do-- | -- | Yes | -- | -- | --
78 |  | Construction of Culverts @ Village Muhammad Hanief Jakhrani, Toula Khan Jakhrani & Saif Din Jakhrani Taluka Kashmore |  |  | 0.3 | 0.075 | District ADP | .--do-- | -- | Yes | -- | -- | --
79 |  | Construction of Culverts @ Village Noor Hassan Khan Jakhrani, Arbab Ali Jakhrani, Lal Khan Jakhrani & Noor Ahmed Khan jakhrani Taluka Kashmore |  |  | 0.6 | 0.15 | District ADP | .--do-- | -- | Yes | -- | -- | --
80 |  | Construction of Retaining wall of road @ Village Mehboob Khan Bangwar Taluka Kashmore |  |  | 0.665 | 0.16625 | District ADP | .--do-- | -- | Yes | -- | -- | --
81 |  | Construction of Retaining wall in Village Lal Bux Mirani u/c Ghouspur Taluka Kandhkot |  |  | 0.5 | 0.125 | District ADP | .--do-- | -- | Yes | -- | -- | --
82 |  | Construction of Retaining wall in Village Pirano Khan Qambrani Taluka Kandhkot |  |  | 1 | 0.25 | District ADP | .--do-- | -- | Yes | -- | -- | --
83 |  | Construction of Retaining wall in Village Siyano Ogahi to Joghi Bageri Taluka Kandhkot |  |  | 6 | 1.5 | District ADP | .--do-- | -- | Yes | -- | -- | --
84 |  | Construction of Safety wall/retaining Wall in Village Ali Muhammad Ogahi Taluka Kandhkot |  |  | 2 | 0.5 | District ADP | .--do-- | -- | Yes | -- | -- | --
85 |  | Const of road from Rasool Bux Chachar to village Ghulam Akbar Chachar Taluka Kashmore (Remaining Work) |  |  | 1.5 | 0.375 | District ADP | .--do-- | -- | Yes | -- | -- | --
86 |  | Construction of Culverts in village Ahmed Nawaz Khan Jakhrani Taluka Kashmore |  |  | 0.8 | 0.2 | District ADP | National Competitive Bidding Method | -- | Yes | -- | -- | --
87 |  | Const of road from Karampur Nakka (Stand) via Gird Statin to coonect Muhamamd Yaqoob Bajirani Taluka Tangwani (Remaining Work) |  |  | 3 | 0.75 | District ADP | .--do-- | -- | Yes | -- | -- | --
88 |  | Rehabilitation of road / Filling Cuts & Earth Work from Karampur Magsi road (Mandhani Chowk) to Jamal Pull Taluka Tangwani road mile 0/0-8/0 |  |  | 10 | 10 | M.P.A Priority | .--do-- | -- | Yes | -- | -- | --
89 |  | Const / Earth Work road from Karampur Magsi road to village Abdul Hafeez Khan Bijrani via Dodico Taluka Tangwani |  |  | 3 | 3 | M.P.A Priority | .--do-- | -- | Yes | -- | -- | --
90 |  | Re-conditioning / Repair of road from 36th mile to village Saeed Ahmed Khan Rind Taluka Tangwani road mile 0/0-1/0 |  |  | 5 | 5 | M.P.A Priority | .--do-- | -- | Yes | -- | -- | --
91 |  | Const of Retaining Wall in village Wahid Bux Bijarani Taluka Tangwani |  |  | 3 | 3 | M.P.A Priority | .--do-- | -- | Yes | -- | -- | --
92 |  | Const of link road from Kandhkot Malguzar road to Mureed Khan Khoso road mile 1/4-2/6 |  |  | 15.5 | 15.5 | Provincial ADP | .--do-- | -- | Yes | -- | -- | --
93 |  | Const of Kashmore road to village Sarwar Khan U/C Akhero Taluka Kandhkot road mile 0/0-2/4 = 4.00 Km |  |  | 20 | 20 | Provincial ADP | .--do-- | -- | Yes | -- | -- | --
94 |  | Const of road from Khair Shakh to village Gaman Khan U/C Akhero Taluka Kandhkot road mile 0/0-2/4 = 4.22 Km |  |  | 20 | 20 | Provincial ADP | .--do-- | -- | Yes | -- | -- | --
95 |  | Const of road from Ghouspur Tangwani road to village Nazar Muhammad Bajkani via Baar Jaffery Taluka Tangwani road mile 0/0-2/0 = 3.22 Km |  |  | 20 | 20 | Provincial ADP | .--do-- | -- | Yes | -- | -- | --
96 |  | Rehabilitation / Reconditioning of road from village Dari Azizullah Shaikh House to Makhwani road (Phase-II) (mile 0/0-0/2+380'). |  |  | 5 | 5 | M.P.A Priority | .--do-- | -- | -- | Yes | -- | --
97 |  | Const of road from NHA to village Muhammad Mureed Bajkani Taluka Kandhkot ( mile 0/0-0/1 |  |  | 2 | 2 | M.P.A Priority | National Competitive Bidding Method | -- | -- | Yes | -- | --
98 |  | Rehabilitation / Reconditioning of road from NHA Ghouspur City Ghareeb Das Mandir (Dr Azeem Malik) various streets of Ghouspur City mile (0/0-0/1) |  |  | 3 | 3 | M.P.A Priority | .--do-- | -- | -- | Yes | -- | --
99 |  | Const of road links villages Mir Alam Khan, Barkat Khan & Haji Abdul Baqui Khan Khoso Taluka Kashmore road mile 0/0-1/4 |  |  | 20 | 20 | M.P.A Priority | .--do-- | -- | -- | Yes | -- | --
100 |  | M&R Karampur Magsi road Re-decking of Slab of Mossa Allah Abad Shakh |  |  | 3.9865 | 3.9865 | M&R Programme | .--do-- | -- | -- | -- | Yes | --
101 |  | M&R Kashmore Badani road to Qabil Mazari road mile 0/0-1/0 ( In portion) |  |  | 2.5 | 2.5 | M&R Programme | .--do-- | -- | -- | -- | Yes | --
102 |  | M&R Indus Highways Dari Makhwani road mile 0/0-0/3 ( In portion) |  |  | 3 | 3 | M&R Programme | .--do-- | -- | -- | -- | Yes | --
103 |  | M&R Muhammad Usman road ( Masonry Structure) |  |  | 0.9865 | 0.9865 | M&R Programme | .--do-- | -- | -- | -- | Yes | --
104 |  | M&R Kashmore Badani road to Qabil Mazari road mile 1/0-2/0 ( In portion) |  |  | 2.5 | 2.5 | M&R Programme | .--do-- | -- | -- | -- | Yes | --
105 |  | Reconstrcution of 12 Nos Culverts in various villages Taluka Tangwani & Taluka Kashmore |  |  | 2.2 | 2.2 | M&R Programme | .--do-- | -- | -- | -- | Yes | --
106 |  | Constof 06 Nos Culverts in village Liaquat Ali Dombki road mile 0/0-0/5 |  |  | 1 | 1 | District ADP | .--do-- | -- | -- | -- | Yes | --
EXECUTIVE ENGINEER
HIGHWAY DIVISION
KASHMORE @ KANDHKOT