## P.Plan 2016-17
REVISED PROCUREMENT PLAN 2016-2017 (HIGHWAYS DIVISION KAMBER-SHAHDADKOT)
CONSTRUCTION/RECONDITIONING OF ROADS & MASONARY STRUCTURES DISTRICT KAMBER-SHAHDADKOT.
S.No. | Description of Procurement | Quantity (Where applicable) | Estimated unit cost (where applicable) (in Million) | Estimated total cost | Funds allocated (in Million) | Source of funds (ADPs/Non ADPs) | Proposed Procurement metohd | Timing of Procurement |  |  |  | Remarks
[8 empty] | 1st Qtr: | 2nd Qtr: | 3rd Qtr: | 4th Qtr:
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Widening/Reconditioning of road from Waggan Warah road @ mile 8/0 to village Jakhar U/C Warah Taluka Warah Mile 0/0-1/5. | 3 | 20 | 19.997 | 5 | ADP Program | Single Stage/One Envelope Method | 1.25 | 1.25 | - | -
2 | Constructon of link road from village Aitbar Khan Chandio Disposal to Government Primary Boys School Aitbar Khan Chandio Mile 0/0-0/4. | 1 | 10 | 9.999 | 2.5 | ADP Program | Single Stage/One Envelope Method | 0.625 | 0.625 | - | -
3 | Reconditioning of road form Police Station Gaji Khuhawar Mohalla mile 0/0-0/4+330'. | 0.9 | 5 | 4.875 | 1.25 | ADP Program | Single Stage/One Envelope Method | 0.3125 | 0.3125 | - | -
4 | Construction of Metaled road and C.C. Drain from House of Qurban Ali Soomro to Dost Ali road main Nala mile 0/0-0/5. | 0.2 | 10 | 9.434 | 2.5 | ADP Program | Single Stage/One Envelope Method | 0.625 | 0.625 | - | - |  | CONSTRUCTION OF METALED ROAD AND C.C. DRAIN FROM HOUSE OF QURBAN ALI SOOMRO TO DOST ALI ROAD MAIN NALA MILE 0/0-0/5.
5 | Reconditioning of link road from Dhani Bux Odhano Kario Sabar Khan to village Murad Bhatti mile 0/0-1/0. | 1.6 | 10 | 9.629 | 2.5 | ADP Program | Single Stage/One Envelope Method | 0.625 | 0.625 | - | -
6 | Construction of link road from Abdullah Chandio to village Suprio Jatoi mile 0/0-0/5. | 1 | 9 | 8.888 | 2.25 | ADP Program | Single Stage/One Envelope Method | 0.5625 | 0.5625 | - | -
7 | Construction of link road from Patuja road to Mir Abdul Jaleel Brohi mile 0/0-1/2. | 2 | 18 | 17.983 | 4.5 | ADP Program | Single Stage/One Envelope Method | 1.125 | 1.125 | - | -
8 | Construction of link road from Kandi to village Noreez Khan Chandio mile 0/0-1/3. | 2.2 | 20 | 19.975 | 5 | ADP Program | Single Stage/One Envelope Method | 1.25 | 1.25 | - | -
9 | Reconditioning/Raising of road from Indus Highway road to village Choudero mile 0/0-0/4+330'. | 0.9 | 10 | 9.997 | 2.5 | ADP Program | Single Stage/One Envelope Method | 0.625 | 0.625 | - | -
10 | Construction of link road from village Mehar Ali Patujo to Main road Kamber-Shahdadkot near Behram Town mile 0/0-0/6+330' | 1.3 | 10 | 9.5 | 2.5 | ADP Program | Single Stage/One Envelope Method | 0.625 | 0.625 | - | -
11 | Rehabilitation of road from Qubo Saeed Khan road to Nabi Shah road Mile 0/5-2/4. | 3 | 15 | 14.491 | 3.75 | ADP Program | Single Stage/One Envelope Method | 0.9375 | 0.9375 | - | -
12 | Construction of approach to Pre-Stress Bridge at village Murad Ali Mastoi (80'Rft). | 0 | 3.039 | 3.039 | 0.6 | ADP No.410 | Single Stage/One Envelope Method | 0.15 | - | - | -
13 | Reconditioning of road from Kamber to Dost Ali road Taluka Kamber mile 5/6-6/7. | 1.8 | 7.998 | 7.998 | 8 | ADP No.59 | Single Stage/One Envelope Method | 2 | - | - | -
14 | Construction of link road from Miro Khan Purano Tharo road to village Ali Hassan Mastoi Taluka Miro Khan mile 0/3-0/5. | 0.4 | 2.8 | 2.8 | 2.8 | ADP No.151 | Single Stage/One Envelope Method | 0.7 | - | - | -
15 | M&R Kamber-Larkana road at Railway Phatak Kamber to Shell Petrol Pump mile 0/0-0/2+480'. | 0.5 | 25.4 | 24.5056 | 25.4 | M&R Program | Single Stage/One Envelope Method | 6.35 | 6.35 | 6.35 | 6.35
16 | M&R of road from Larkana-Kamber road to village Dost Muhammad Metlo mile 0/0-2/0 (in portions). | 3.2 | 2.6 | 2.6 | 2.6 | M&R Program | Single Stage/One Envelope Method | 0.65 | 0.65 | 0.65 | 0.65
17 | Construction/Reconditioning of road from Miro Khan Sijawal road @ Point Police Chowki Sim Shakh to village Abdul Hameed Tunio road Rasool Bux Brohi, Doulat-Ji-Wandh via Punhal Tunio Mile 0/0-5/1. | 8.2 | 65 | 62.931 | 16.25 | Provincial ADP | Single Stage/One Envelope Method | 0 | 8.125 | 0 | 0
18 | Reconditioning of road from Nasirabad to village Miandad Chinjni U/c Miandad Chinjni Mile 0/0-3/1 (Provincial ADP Program 2016-2017). | 5 | 40 | 39.778 | 10 | Provincial ADP | Single Stage/One Envelope Method | 0 | 5 | 0 | 0
19 | Repair/Reconditioning of link road from Dost Ali to Wahid Dino Kalhoro Meenhal Shakh Mile 0/0-3/4 (Provincial ADP Program 2016-2017). | 5.6 | 30 | 29.889 | 7.5 | Provincial ADP | Single Stage/One Envelope Method | 0 | 3.75 | 0 | 0
20 | Construction of approach to Pre-Stress Bridge at Lehgari village (80'Rft) Taluka Miro Khan (ADP Program 2016-2017). | 0 | 8.853 | 8.853 | 8.7 | ADP Program | Single Stage/One Envelope Method | 2.175 | 2.175 | 2.175 | 0
21 | Reconditioning of road from Indus Highway road to village Choudero Deera U/c Deera Taluka Nasirabad Mile 0/6-1/3 (ADP Program 2016-2017). | 1 | 7.28 | 7.28 | 9.8 | ADP Program | Single Stage/One Envelope Method | 2.45 | 2.45 | 2.45 | 0
22 | Construction of Retaining Wall (270'Rft) at village Arzi Bhutto Buxio Sario (ADP No.23). | 0 | 0.965 | 0.965 | 3.5 | ADP Program | Single Stage/One Envelope Method | 0.875 | 0.875 | 0.875 | 0
23 | Construction of 10.0'ft span Bridge over Raj Wah Shakh near Session Court Kamber (ADP No.23). | 0 | 0.446 | 0.446 | 3.5 | ADP Program | Single Stage/One Envelope Method | 0.875 | 0.875 | 0.875 | 0
24 | Re-decking of Slab 10.0'ft Span Bridge over Sim Drain near village Sadique Junejo Taluka Miro Khan (ADP No.23). | 0 | 0.211 | 0.211 | 3.5 | ADP Program | Single Stage/One Envelope Method | 0.875 | 0.875 | 0.875 | 0
25 | Re-decking of Slab 3.0'ft Span Culverts (2 No.) from Nau Tharo Mubarak Kalhoro road Taluka Miro Khan (ADP No.23). | 0 | 0.178 | 0.178 | 3.5 | ADP Program | Single Stage/One Envelope Method | 0.875 | 0.875 | 0.875 | 0
26 | Repair of road from Dost Ali road to village Allah Bux Mugheri U/c Kalar Taluka Kamber mile 0/0-0/1. | 0.2 | 1 | 0.99 | 1 | Community Development program | Single Stage/One Envelope Method | 0.25 | 0.25 | 0.25 | 0.25
27 | Repair of road from Dost Ali road to Khan-Jo-Goth Dargah Shah Ismail road U/c Kalar Taluka Kamber mile 0/0-0/1+200'. | 0.2 | 1 | 0.988 | 1 | Community Development program | Single Stage/One Envelope Method | 0.25 | 0.25 | 0.25 | 0.25
Executive Engineer
Highways Division
Kamber-Shahdadkot