## List
LIST OF SCHOOL BUILDINGS
ADP-166 Rehabilitation, Improvement / Renovation & Provision for Missing Facilities in Existing Primary / Elementary Schools
(Rs. in Million)
Sr. No. | Name of Schools | Taluka
1 | GBPS. Ahmed Memon. | T.M.Khan.
2 | GGPS. Khuda Bux Khoso. | T.M.Khan.
3 | GBPS. Allah Dino Samejo. | T.M.Khan.
4 | GBPS. Qaboolpur. | T.M.Khan.
5 | GBPS. Noor Mohammad Khor. | T.M.Khan.
6 | GBPS. Gul Khan Nizamani. | T.M.Khan.
7 | GBPS. Misri Abro. | T.G.Hyder
8 | GBPS. Vikio Khamriyo. | B.S.Karim
9 | GBPS. Wangai Maheri. | T.G.Hyder
10 | GBPS. Haji Abdullah Lashari. | B.S.Karim
11 | GBPS. Guhram Wassan. | T.G.Hyder
12 | GBPS. Jamal Shoro. | B.S.Karim
13 | GBPS. Saeed Pur | B.S.Karim
| ASSISTANT ENGINEER | EXECUTIVE ENGINEER
| EDUCATION WORKS SUB-DIVISIN | EDUCATION WORKS DIVISIN
| T.M.KHAN | T.M.KHAN

## REVENUE
#REF!
LIST OF FURNITURE
S. No. | Item Description | Qty. (Nos.) | Unit Rate (Rupees) | Amount (Rupees)
A | Furniture
1 | Dual Desk | 40 | 8800 | 352000
2 | Chair | 6 | 4500 | 27000
3 | Tables | 2 | 12000 | 24000
4 | Steel Alimirah | 1 | 22000 | 22000
| TOTAL |  |  | 425000
| RS. IN MILLION: |  |  | 0.425
| Unit Cost | No. of Unit | Total Cost
| 0.425 | 12 | 5.1

## Activity Plan
ADP-166 Rehabilitation, Improvement / Renovation & Provision for Missing Facilities in Existing Primary / Elementary Schools
WORK / ACTIVITY PLAN (BART CHART)
| YEAR | CAPITAL COST. | REVENUE | 1% 3RD PARTY | TOTAL.
| 2016-2017 | 10 | 0 | 0 | 10
| 2017-2018 | 19.9602 | 0 | 0 | 19.9602
| TOTAL:- | 29.9602 | 0 | 0 | 29.9602

## Escalation
ESCALATION CHARGES
ADP-166 Rehabilitation, Improvement / Renovation & Provision for Missing Facilities in Existing Primary / Elementary Schools
SR. | YEAR | ALLOCATION | ESCALATION | ESCALATION CHARGES | TOTAL COST
NO. |  |  |  |  | (RS. IN MILLION
1 | 2016-2017 | 10 | --- | --- | 10
2 | 2017-2018 | 18.742 | 6.5% | 1.2182 | 19.9602
| TOTAL: | 28.742 |  | 1.2182 | 29.9602

## G.Abs
A B S T R A C T
ADP-166 Rehabilitation, Improvement / Renovation & Provision for Missing Facilities in Existing Primary / Elementary Schools
(Rs. in Million)
Sr. No. | Name of Schools | Cost
1 | GBPS. Ahmed Memon. | 0.835
2 | GGPS. Khuda Bux Khoso. | 1.043
3 | GBPS. Allah Dino Samejo. | 3.693
4 | GBPS. Qaboolpur. | 1.6
5 | GBPS. Noor Mohammad Khor. | 2.524
6 | GBPS. Gul Khan Nizamani. | 2.871
7 | GBPS. Misri Abro. | 0.558
8 | GBPS. Vikio Khamriyo. | 2.464
9 | GBPS. Wangai Maheri. | 2.602
10 | GBPS. Haji Abdullah Lashari. | 3.245
11 | GBPS. Guhram Wassan. | 1.414
12 | GBPS. Jamal Shoro. | 1.175
13 | GBPS. Saeed Pur | 4.718
| Total: | 28.742
| ASSISTANT ENGINEER | EXECUTIVE ENGINEER
| EDUCATION WORKS SUB-DIVISIN | EDUCATION WORKS DIVISIN
| T.M.KHAN | T.M.KHAN

## Recurring
RECURRING COST
Sr. No | Name of the post | BPS | Basic pay | No. of post | Per Month | Total Per Year
1 | H S T | 16 | 3805 | 1 | 3805 | 45660
2 | J S T | 14 | 3100 | 2 | 6200 | 74400
3 | O T | 14 | 3100 | 1 | 3100 | 37200
4 | Naib Qasid. | 1 | 1870 | 1 | 1870 | 22440
5 | Chowkidar | 1 | 1870 | 1 | 1870 | 22440
[5 empty] | Total : | 202140
REGULAR ALLOWANCES FOR STAFF
Sr . No. | Name of post | Grade | No. of post | H.R.A | M.A | S.R./Ad:Relief(15+15=30%) | Washing Allow: | 25% Add:Adhoc Relief | Total per Month | Total Per Year
1 | H S T | 16 | 1 | 563 | 210 | 1142 | -- | 634 | 2549 | 30588
2 | J S T/ O T | 14 | 3 | 459 | 210 | 930 | -- | 516 | 2115 | 25380
1 | Naib Qasid | 1 | 1 | 276 | 210 | 561 | 30 | 311 | 1388 | 16656
2 | Chowkidar | 1 | 1 | 276 | 210 | 561 | 30 | 311 | 1388 | 16656
[9 empty] | Total : | 89280
[9 empty] | G.Total: | 291420

## Ab
ABSTRACT
ADP-166 Rehabilitation, Improvement / Renovation & Provision for Missing Facilities in Existing Primary / Elementary Schools
Sr. No. | Name of Building |  | Cost
1 | Main Building |  | #REF!
2 | 10% External Development Charges |  | #REF!
| Total Main Building: |  | #REF!
2 | #REF! |  | #REF!
|  | Total: | #REF!
| Say Rs. in Million: |  | #REF!
| Unit Cost | No. of Unit | Total Cost
| #REF! | 1 | #REF!
| ASSISTANT ENGINEER |  | EXECUTIVE ENGINEER
| EDUCATION WORKS SUB-DIVISIN |  | EDUCATION WORKS DIVISIN
| T.M.KHAN |  | T.M.KHAN

## Sheet8
ABSTRACT SHEET
Rehbalitation , Improvement / Renovation & provision for Missing Facilities existing primary / Elementary school at GBPS. Saeedpur Taluka B.S.Karim District Tando Mohammad Khan.
S.NO: | NAME OF OF COMPONENT. | AMOUNT
IN RS:
1 | Main Building . | 7342940
1 | Compound Wall. | 1067500
| Total | 8410440
| Rs. ( In Million). | 8.4104
ASSISTANT ENGINEER
EDUCATION WORKS SUB-DIVISION
T.M.KHAN

## Sheet1
DETAIL SHEET
ADP-166 Rehabilitation, Improvement / Renovation & Provision for Missing Facilities in Existing Primary / Elementary Schools @ GBPS. Saeed pur Taluka B.S.Karim Distt: T.M.Khan.
Sr. No. | Name of Building | Plinth Area | Cost of Construction |  | Cost of Water Sewerage & Sanitation |  | Cost of Electrification |  | Cost of Sui Gas |  | Grand Total
|  |  | Rate | Amount | Rate | Amount | Rate | Amount | Rate | Amount
A | Main Building
i) | Main Building i/c Lav: Block | 2470 | 2781 | 6870200 | 155 | 382850 | 140 | 345800 | 0 | 0 | 7598850
Sft
ii) | Verona Marble | 1856 | 310.43 | 576158.08 | [6 empty] | 576158.08
Sft
i) | Lav: Block | 125 | 1640 | 205000 | [6 empty] | 205000
Sft
|  |  |  | 6870200 |  | 382850 |  | 345800 |  | 0 | 7598850
[10 empty] | Total | 7598850
B | Compound Wall
i) | Compound Wall | 450 | 1700 | 765000 | 0 | 0 | 0 | 0 | 0 | 0 | 765000
iii) | Main Gate | 1 | 47500 | 47500 | 0 | 0 | 0 | 0 | 0 | 0 | 47500
| Total C/W & Gate | [9 empty] | 812500
| Grand Total: | [9 empty] | 8411350
| Rs. In Million: | [9 empty] | 8.4114
|  |  |  | ASSISTANT ENGINEER |  |  |  |  | EXECUTIVE ENGINEER
|  |  |  | EDUCATION WORKS SUB-DIVISION |  |  |  |  | EDUCATION WORKS DIVISION
|  |  |  | T.M.KHAN |  |  |  |  | T.M.KHAN

## Sheet2
ABSTRACT SHEET
Rehbalitation , Improvement / Renovation & provision for Missing Facilities existing primary / Elementary school at GBPS. Saeedpur Taluka B.S.Karim District Tando Mohammad Khan.
S.NO: | NAME OF BUILDINGS |  | COST OF | NO: OF | AMOUNT
|  |  | ONE UNIT | UNIT | IN RS:
1 | Main Building i/c Lav: Block |  | 7598850 | 1 | 7598850
2 | Compound Wall i/c Main Gate. |  | 812500 |  | 812500
|  |  | Total |  | 8411350
|  |  |  | Say Rs (in Million):- | 8.4114
|  | ASSISTANT ENGINEER |  | EXECUTIVE ENGINEER
|  | EDUCATION WORKS SUB-DIVISION |  | EDUCATION WORKS DIVISION
|  | T.M.KHAN |  | T.M.KHAN

## Estimate.
| NAME OF WORK:- | Rehbalitation , Improvement / Renovation & provision for Missing Facilities existing primary / Elementary school at GBPS. Saeedpur Taluka B.S.Karim District Tando Mohammad Khan.
MEASUREMENT SHEET.
S.No | Description | MEASUREMENT | [10 empty] | Quantity
|  | No. |  |  |  | Length |  | Width |  | Height/ Depth
01 | Dismentling cement concrete reinforced separating refinorcement for cleaning and sarighening the same (S.I.No.20/P-10).
| Roof Slab. | 1 | x | 1 | x | 96.83 | x | 25.5 | x | 0.5 |  | = | 1234.5825 | 00
| C/Wall Gate Col: | 1 | x | 2 | x | 1.5 | x | 1.5 | x | 7 |  | = | 31.5 | 00
[13 empty] | 1266.0825 | 00
02 | Dismentling brick work in lime or cement mortor (S.I.No.13/P-10).
| M/B. L/Wall. | 1 | x | 3 | x | 96.83 | x | 1.13 | x | 12 |  | = | 3939.0444 | 00
| M/B. S/Wall. | 1 | x | 6 | x | 16 | x | 1.13 | x | 12 |  | = | 1301.76 | 00
| Ver: S/Wall. | 1 | x | 2 | x | 6 | x | 1.13 | x | 12 |  | = | 162.72 | 00
| C/Wall. | 1 | x | 2 | x | 130 | x | 0.37 | x | 6 |  | = | 577.2 | 00
| C/Wall. | 1 | x | 2 | x | 99.25 | x | 0.37 | x | 6 |  | = | 440.67 | 00
| Lav: | 1 | x | 3 | x | 10.25 | x | 0.75 | x | 8 |  | = | 184.5 | 00
| Lav: | 1 | x | 3 | x | 4 | x | 0.75 | x | 8 |  | = | 72 | 00
[13 empty] | 6677.8944 | 00
Deducation.
| Door. | 1 | x | 5 | x | 4 | x | 1.13 | x | 7 |  | = | 158.2 | 00
| Windows. | 5 | x | 3 | x | 4 | x | 1.13 | x | 4 |  | = | 271.2 | 00
| Opp: | 1 | x | 5 | x | 8 | x | 1.13 | x | 8 |  | = | 361.6 | 00
| Ver: | 1 | x | 2 | x | 4.5 | x | 1.13 | x | 8 |  | = | 81.36 | 00
| Lav: Door. | 1 | x | 2 | x | 2.5 | x | 0.75 | x | 7 |  | = | 26.25 | 00
| M/gate. | 1 | x | 1 | x | 10 | x | 0.37 | x | 6 |  | = | 22.2 | 00
[13 empty] | 920.81 | 00
| Net Qty: |  |  |  |  | 6677.8944 |  | ( - ) |  | 920.81 |  |  | 5757.0844 | 00
03 | Excavation of foundation of building bridges and other structure i/c dagbelling dressing refilling around structure with excavated lead upto one chain and lift upto 5' feet.(S.I.NO:18(b)P-4).
| Lav:/L/Wall. | 1 | x | 3 | x | 94 | x | 1.5 | x | 3.5 |  | = | 1480.5 | 00
| Lav:/ S /Wall. | 1 | x | 6 | x | 15.63 | x | 1.5 | x | 3.5 |  | = | 492.345 | 00
| Lav:/ S /Wall. | 1 | x | 2 | x | 5.63 | x | 1.5 | x | 3.5 |  | = | 59.115 | 00
| Lav:/ S /Wall. | 1 | x | 4 | x | 10 | x | 1.5 | x | 0.5 |  | = | 30 | 00
[13 empty] | 2061.96 | 00
04 | Cement Concret brick or stone ballast 1-1/2" to 2"guage Ratio1:4:8(S.I.No:4/B/P-14).
| C/R. U / Floor. | 1 | x | 5 | x | 17.67 | x | 15.67 | x | 0.42 |  | = | 581.4667 | 00
| Ver: | 1 | x | 1 | x | 93.83 | x | 5.67 | x | 0.42 |  | = | 223.4468 | 00
| Path. | 1 | x | 1 | x | 125 | x | 60 | x | 0.5 |  | = | 3750 | 00
| Path. | 1 | x | 1 | x | 125 | x | 10 | x | 0.5 |  | = | 625 | 00
| Path. | 1 | x | 1 | x | 30 | x | 25 | x | 0.5 |  | = | 375 | 00
[13 empty] | 5554.9135 | 00
05 | Pacca brick work in foundation or plinth in cement sand morter1:6 (S.I.No.41/E/P-20)
| C/R L/Wall. | 1 | x | 3 | x | 94 | x | 1.5 | x | 3.5 |  | = | 1480.5 | 00
| C/R S/Wall. | 1 | x | 6 | x | 15.63 | x | 1.5 | x | 3.5 |  | = | 492.345 | 00
| Ver: S/Wall. | 1 | x | 2 | x | 5.63 | x | 1.5 | x | 3.5 |  | = | 59.115 | 00
| Steps. | 1 | x | 4 | x | 10 | x | 1.5 | x | 0.5 |  | = | 30 | 00
[13 empty] | 2061.96 | 00
06 | R.C.C. work i/c all labour and material except the cost of steel reinforcement and its labour for bending binding which will be paid separately. This rate also i/c all kinds of forms moulds lifting shuttering curing rendering washing of shingle surface. (a) R.C.C work in roof slabs, beams, columns, rafts, lintels and other structural members laid in situ or precast laid in position, complete in all respects Ratio 1:2:4 (S.I No 6/p -18).
| P.Beam L/Wall. | 1 | x | 3 | x | 94 | x | 1.5 | x | 1.5 |  | = | 634.5 | .00
| P.Beam S/Wall. | 1 | x | 6 | x | 15.63 | x | 1.5 | x | 1.5 |  | = | 211.005 | .00
| " Ver: S/Wall. | 1 | x | 2 | x | 5.63 | x | 1.5 | x | 1.5 |  | = | 25.335 | .00
| Lintel . L/Wall. | 1 | x | 3 | x | 96.83 | x | 1.13 | x | 1.5 |  | = | 492.3805 | .00
| Lintel . S/Wall. | 1 | x | 6 | x | 16 | x | 1.13 | x | 1.5 |  | = | 162.72 | .00
| " Ver: S/Wall. | 1 | x | 2 | x | 6 | x | 1.13 | x | 1.5 |  | = | 20.34 | .00
| Roof Slab. | 1 | x | 1 | x | 99.83 | x | 28.5 | x | 0.5 |  | = | 1422.5775 | .00
| Beam. | 1 | x | 5 | x | 18.25 | x | 1 | x | 1.75 |  | = | 159.6875 | .00
| OHT Slab. | 1 | x | 2 | x | 9 | x | 4 | x | 0.5 |  | = | 36 | .00
[13 empty] | 3164.5455 | .00
07 | Fabrication of mild steel reinforcement for R.C.C i/c its labour for cutting bending binding and laying in position making joints and fastening i/c the cost of binding wire also removal of rust from bars (S.I.No. 7/ P- 19)
(A) | TOR BARS | R.C.C x 5.0 |  |  | = | 3164.5455 | x | 5.5 | = | 155.4018 |  | = | 155.4018 | .00
|  | 112 |  |  |  | 112
[12 empty] | = | 155.4018 | .00
08 | Filling, watering, and ramming earth under floors with new earth excavated from outside lead upto 1 chain and lift upto 5'ft (s.I.NO:22/P-05).
| C/Room I/S. | 5 | x | 17.67 | x | 15.67 | x | 3 |  |  |  | = | 4153.3335 | 00
| Ver: | 1 | x | 93.83 | x | 5.67 | x | 3 |  |  |  | = | 1596.0483 | 00
| MB. O/S. | 1 | x | 125 | x | 10 | x | 2.5 |  |  |  | = | 3125 | 00
| " F/Side. | 1 | x | 125 | x | 60 | x | 2.5 |  |  |  | = | 18750 | 00
| " F/Side. | 1 | x | 30 | x | 25 | x | 2.5 |  |  |  | = | 1875 | 00
[13 empty] | 4153.3335 | .00
09 | Add: Extra lead 06 (Miles).
| Qty: same as item No.8. | [10 empty] | = | 4153.3335 | 00
[12 empty] | = | 4153.3335 | 00
10 | Pacca brick work in Ground Floor i/c stricking of joints upto 20 ft: hieght in cement sand mortor ratio 1:6 (S.I. No. 05/P-24)
| C/R/L/Wall | 3 | x | 94.83 | x | 1.13 | x | 10.5 |  |  |  | = | 3375.4739 | 00
| C/R/S/Wall | 6 | x | 16 | x | 1.13 | x | 10.5 |  |  |  | = | 1139.04 | 00
| Ver:/S/Wall. | 2 | x | 6 | x | 1.13 | x | 10.5 |  |  |  | = | 142.38 | 00
| OHT. | 2 | x | (9.0+4.0) |  |  | x | 0.75 | x | 4 |  | = | 78 | 00
[13 empty] | 4734.8939 | 00
DEDUCTION
| C/R. Door. | 1 | x | 5 | x | 4 | x | 1.13 | x | 7 |  | = | 158.2 | 00
| C/R. Windows. | 5 | x | 3 | x | 4.5 | x | 1.13 | x | 4 |  | = | 305.1 | 00
| Opp: | 1 | x | 6 | x | 6 | x | 1.13 | x | 8 |  | = | 325.44 | 00
| Opp: | 1 | x | 2 | x | 4.25 | x | 1.13 | x | 8 |  | = | 76.84 | 00
[13 empty] | 865.58 | 00
|  |  | Net Qty: |  |  |  |  | 4734.8939 |  | ( - ) | 865.58 | = | 3869.3139 | .00
11 | Cement Plaster 1:6 upto 20 ft. hight 1/2" thick (S.I.No. 13(b)/P - 57)
| C/Room I/S. | 5 | x | 2 | x | (18.0+16.0) |  |  | x | 12 |  | = | 4080 | .00
| Ver: | 1 | x | 2 | x | (94.50+6.0) |  |  | x | 12 |  | = | 2412 | .00
| O/S. B/F. | 1 | x | 2 | x | (96.83+25.50) |  |  | x | 12 |  | = | 2935.92 | .00
[12 empty] | = | 9427.92 | .00
12 | Cement Plaster 1:4 upto 20 ft. hight 3/8" thick (S.I.No. 11(a)/P - 57)
| Same Qty : as Item.No(13) as above. | [10 empty] | = | 9427.92 | .00
| M/Bldg: | 1 | x | 2 | x | (94.0+25.83) |  |  | x | 3.5 |  | = | 703.5 | .00
[13 empty] | 10131.42 | .00
13 | Providing and laying 2" thick topping cement concrete 1:2:4 I/c surface finishing and dividing into panells.(S.I.No:16/C/P-47).
| O/Roof | 1 | x | 99.83 | x | 28.5 | [5 empty] | = | 2845.155 | .00
[13 empty] | 2845.155 | .00
14 | Laying white marble flooring fine dreassed on the surface without winding set in lime mortor 1:2 i/c rubbing and polishing of the joints 3/4" thick flooring (S.I No 28-a/P-43)
| C/Room. | 4 | x | 18 | x | 16 | [5 empty] | = | 1152 | .00
| Ver: | 1 | x | 94.5 | x | 6 | [5 empty] | = | 567 | .00
| Door. | 5 | x | 4 | x | 1.13 | [5 empty] | = | 22.6 | .00
| Ver: | 6 | x | 6 | x | 1.5 | [5 empty] | = | 54 | .00
| Steps. | 1 | x | 10 | x | 6 | [5 empty] | = | 60 | .00
[13 empty] | 1855.6 | .00
15 | P/L Hala or patterned tiles glazed 8"x8"and 1/4" on floor or walls facing in required pattern of Stile specification jointed in white cement and pigment over a base of 1:2 grey cement mortar 3/4" thick I/c washing and filling of joints with slurry of white cement and pigment in desired shade with finishing, cleaning and wax polish etc complete i/c cutting tile to proper profile (S .I. No 62 /P-54)
| M/Bldg: F/Side. | 1 | x | 96.83 | x | 12 | [5 empty] | = | 1161.96 | .00
| Side. | 1 | x | 2 | x | 6 | x | 12 |  |  |  | = | 144 | .00
[13 empty] | 1305.96 | .00
16 | Laying floor of approved with glazed tiles 1/4" thick laid in white cement and pigment on a bed of 3/4" thick cement mortor (S.I No 25/P-49)
| Office Floor. | 1 | x | 18 | x | 16 | [5 empty] | = | 288 | .00
[13 empty] | 288 | .00
17 | White glazed tiles 1/4" thick dadoo jointed in white cement and laid over 1:2 cement sand mortor 3/4" thick i/c finishing (S.I.No. 37/P-49)
| Office . | 1 | x | 2 | x | (18.0+16.0) |  |  | x | 5 |  | = | 340 | .00
[12 empty] | = | 340 | .00
18 | Providing and laying 3" thick topping cement concrete 1:2:4 I/c surface finishing and dividing into panells.(S.I.No:16/C/P-47).
| M/B. O/Side. | 1 | x | 125 | x | 60 | [5 empty] | = | 7500 | .00
| M/B. O/Side. | 1 | x | 125 | x | 10 | [5 empty] | = | 1250 | .00
| M/B. O/Side. | 1 | x | 30 | x | 25 | [5 empty] | = | 750 | .00
[13 empty] | 9500 | .00
19 | First class deodar wood wrought joinery in doors & windows fixed in position with chowkads i/c cleats cords hooks iron tower bolts hinges holds fasts deodar panelled or glazed or fully glazed 1-3/4" thick (S.I.No7/P-64)
| C/R Door | 1 | x | 5 | x | 4 | x | 7 |  |  |  | = | 140 | .00
| C/R. Windows. | 5 | x | 3 | x | 4.5 | x | 4 |  |  |  | = | 270 | .00
[13 empty] | 410 | .00
20 | S/F iron steel grill of 3/4" and 1/4" size flate iron of approved design i/c painting 3 coats etc. complete( weight not less than 3.7 Lb./ Sq: ft: of finished grill) (S.I.No.26/P-97)
| Window, | 6 | x | 3 | x | 4.5 | x | 4 |  |  |  | = | 324 | .00
[13 empty] | 324 | .00
21 | Primary coat of chalk under distemper (S.I.No.23/P-58)
| Same Qty : as Item.No(11) as above.= |  |  |  |  | 9427.92 | [5 empty] | = | 9427.92 | .00
| Same Qty : as Item.No(14) as above.= |  |  |  |  | 1855.6 | [5 empty] | = | 1855.6 | .00
[13 empty] | 9427.92 | .00
22 | Distempering 03 coats . (S.I.No. 24(b )/P-60)
| Same Qty : as Item.No( 21 ) as above. | [10 empty] | = | 9427.92 | .00
23 | Painting new surface preparing surface and door & window any type i/c edges. (S.I.No.5(c )/ P-76)
| Same Qty : as Item.No(19) as above.= |  |  |  |  | 410 | x | 2 |  |  |  | = | 820 | .00
[13 empty] | 820 | .00
SUB-ENGINEER.
ASSISTANT ENGINEER
EDUCATION WORKS
(SUB-DIVISION) T.M.KHAN
EXECUTIVE ENGINEER
EDUCATION WORKS
(DIVISION) T.M.KHAN

## Carriage
CARRIAGE STATEMENT
| Name of work:- | Rehbalitation , Improvement / Renovation & provision for Missing Facilities existing primary / Elementary school at GBPS. Saeedpur Taluka B.S.Karim District Tando Mohammad Khan.
S.# | NAME OF ITEMS |  | Qty:: | Cement P.Bage | Hill Sand % Cft. | Stone Ballast % Cft. | Shingle %Cft. | Steel / 5 Ton | Brick %0 No. | Sand / Earth % Cft.
1 | Cement Concrete 1:4:8 |  | 5554.9135 | 533.2717 | 2666.3585 | 5332.7169
2 | R.C.C. 1:2:4 |  | 3164.5455 | 604.4282 | 1518.9819 |  | 2784.8001
3 | Steel |  | 155.4018 |  |  |  |  | 7.7701
4 | Pacca Brick Work 1:6 |  | 5931.2739 | 204.0358 | 1524.3374 |  |  |  | 8007.2197
5 | C.C.Plian 1 : 2 : 4 |  | 0 | 0 | 0 |  | 0
6 | Cement Plaster 1:6 1/2", |  | 9427.92 | 49.968 | 377.1168
7 | Cement Plaster 1:4 3/8", |  | 10131.42 | 57.7491 | 303.9426
8 | Cement Plaster 1:4 3/4", |  | 0 | 0 | 0
9 | C.C Topping (1: 2 : 4 ) 3" Thick |  | 2845.155 | 125.1868 | 312.967 |  | 625.9341
10 | C.C Topping (1: 2 : 4 ) 2" Thick |  | 0 | 0 | 0 |  | 0
11 | C.C Topping (1: 2 : 4 ) 1-1/2" Thick |  | 0 | 0 | 0 |  | 0
12 | Cement pointing 1:2 |  | 0 | 0 | 0
13 | Mosaic Tiles |  |  | 0 | 0
14 | Pit Sand/ Sweet Earth
15 | D.P.C.
TOTAL QUANTITY:- |  |  |  | 1574.6396 | 6703.7042 | 5332.7169 | 3410.7342 | 7.7701 | 8007.2197 | 0
FOR HYDERABAD CITY |  |  | FROM | Hyd: | Bholari | Onger | T.B.Khan | Hyd: | T.Fazal
LEAD IN MILES |  |  | PACCA | 27 | 41 | 52 | 55 | 27 | 19
KATCHA
RATE AS PER SCHEDULE OF CARRAGE (PART IV,FIFTH EDITION, 2004) PUBLICATION NO.37(A) PACCA.
1st Mile |  |  | Rs. | 6.1 | 407 | 407 | 407 | 407 | 325.6 | 407
2nd Mile |  |  | Rs. | 1.43 | 95.52 | 95.52 | 95.52 | 95.52 | 76.4 | 95.52
3rd Mile |  |  | Rs. | --- | 76.89 | 76.89 | 76.89 | 76.89 | 61.51 | 76.89
4th Mile |  |  | Rs. | --- | 70.45 | 70.45 | 70.45 | 70.45 | 56.36 | 70.45
5th Mile |  |  | Rs. | --- | 64.43 | 64.43 | 64.43 | 64.43 | 51.54 | 64.43
6th Mile |  |  | Rs. | --- | 57.67 | 57.67 | 57.67 | 57.67 | 46.13 | 57.67
TOTAL (A) |  |  | Rs. | 7.53 | 771.96 | 771.96 | 771.96 | 771.96 | 617.54 | 771.96
B) | 7TH & SUBSEQUENT MILES |  | Rs. | 0.6 | 32.56 | 32.56 | 32.56 | 32.56 | 26.05 | 32.56 | 12.6 | 1139.6 | 1497.76 | 1595.44 | 683.76 | 338.65 | -195.36
TOTAL RATE (A+B) |  |  | Rs. | 20.13 | 1911.56 | 2269.72 | 2367.4 | 1455.72 | 956.19 | 576.6
TOTAL QUANTITY:- |  |  |  | 1574.6396 | 6703.7042 | 5332.7169 | 3410.7342 | 7.7701 | 8007.2197 | 0
TOTAL AMOUNT:- |  |  | Rs. | 31697.4952 | 128145.3271 | 121037.7423 | 80745.7211 | 11311.0747 | 7656.4234 | 0
[7 empty] | G-TOTAL:- |  | 380593.7838
SUB-ENGINEER
ASSISTANT ENGINEER
EDUCATION WORKS
(SUB-DIVISION) T.M.KHAN

## AB Sheet
NAME OF WORK:-
ABSTRACT SHEET.
S.No | Description | Quantity |  | Rate. | Unit. | Amount
01 | Dismentling cement concrete reinforced separating refinorcement for cleaning and sarighening the same (S.I.No.20/P-10). | 1266.0825 | Cft | 5445 | %.Cft | Rs: | 68938.1921
02 | Dismentling brick work in lime or cement mortor (S.I.No.13/P-10). | 5757.0844 | Cft | 1285.63 | %Cft | Rs: | 74014.8042
03 | Excavation of foundation of building bridges and other structure i/c dagbelling dressing refilling around structure with excavated lead upto one chain and lift upto 5' feet.(S.I.NO:18(b)P-4). | 2061.96 | Cft | 3176.25 | %.OCft | Rs: | 6549.3005
04 | Cement Concret brick or stone ballast 1-1/2" to 2"guage Ratio1:4:8(S.I.No:4/B/P-14). | 5554.9135 | Cft | 9416.25 | %.Cft | Rs: | 523064.5379
05 | Pacca brick work in foundation or plinth in cement sand morter1:6 (S.I.No.41/E/P-20) | 2061.96 | Cft | 11948.36 | %.Cft | Rs: | 246370.4039
06 | R.C.C. work i/c all labour and material except the cost of steel reinforcement and its labour for bending binding which will be paid separately. This rate also i/c all kinds of forms moulds lifting shuttering curing rendering washing of shingle surface. (a) R.C.C work in roof slabs, beams, columns, rafts, lintels and other structural members laid in situ or precast laid in position, complete in all respects Ratio 1:2:4 (S.I No 6/p -18). | 3164.5455 | Cft | 337 | P.Cft | Rs: | 1066451.8503
07 | Fabrication of mild steel reinforcement for R.C.C i/c its labour for cutting bending binding and laying in position making joints and fastening i/c the cost of binding wire also removal of rust from bars (S.I.No. 7/ P- 19) | 155.4018 | Cwt | 5001.7 | P.Cwt | Rs: | 777273.1351
08 | Filling, watering, and ramming earth under floors with new earth excavated from outside lead upto 1 chain and lift upto 5'ft (s.I.NO:22/P-05). | 4153.3335 | Cft | 3630 | %.Cft | Rs: | 15076.6006
09 | Add: Extra lead 06 (Miles). | 4153.3335 | Cft | 771.96 | %.Cft | Rs: | 32062.0733
10 | Pacca brick work in Ground Floor i/c stricking of joints upto 20 ft: hieght in cement sand mortor ratio 1:6 (S.I. No. 05/P-24) | 3869.3139 | Cft | 12674.36 | %.Cft | Rs: | 490410.7669
11 | Cement Plaster 1:6 upto 20 ft. hight 1/2" thick (S.I.No. 13(b)/P - 57) | 9427.92 | Cft | 2206.6 | %.Cft | Rs: | 208036.4827
12 | Cement Plaster 1:4 upto 20 ft. hight 3/8" thick (S.I.No. 11(a)/P - 57) | 10131.42 | Sft | 2197.52 | % Sft | Rs: | 222639.9808
13 | Providing and laying 2" thick topping cement concrete 1:2:4 I/c surface finishing and dividing into panells.(S.I.No:16/C/P-47). | 2845.155 | Sft | 3275.5 | % Sft | Rs: | 93193.052
14 | Laying white marble flooring fine dreassed on the surface without winding set in lime mortor 1:2 i/c rubbing and polishing of the joints 3/4" thick flooring (S.I No 28-a/P-43) | 1855.6 | Sft | 567.48 | P.Sft | Rs: | 1053015.888
15 | P/L Hala or patterned tiles glazed 8"x8"and 1/4" on floor or walls facing in required pattern of Stile specification jointed in white cement and pigment over a base of 1:2 grey cement mortar 3/4" thick I/c washing and filling of joints with slurry of white cement and pigment in desired shade with finishing, cleaning and wax polish etc complete i/c cutting tile to proper profile (S .I. No 62 /P-54) | 1305.96 | Cft | 34520.31 | % Sft | Rs: | 450821.4405
16 | Laying floor of approved with glazed tiles 1/4" thick laid in white cement and pigment on a bed of 3/4" thick cement mortor (S.I No 25/P-49) | 288 | S.ft | 27678.86 | %.Sft | Rs: | 79715.1168
17 | White glazed tiles 1/4" thick dadoo jointed in white cement and laid over 1:2 cement sand mortor 3/4" thick i/c finishing (S.I.No. 37/P-49) | 340 | S.ft | 28253.61 | %.Sft | Rs: | 96062.274
18 | Providing and laying 3" thick topping cement concrete 1:2:4 I/c surface finishing and dividing into panells.(S.I.No:16/C/P-47). | 9500 | S.ft | 4411.82 | P.Sft | Rs: | 419122.9
19 | First class deodar wood wrought joinery in doors & windows fixed in position with chowkads i/c cleats cords hooks iron tower bolts hinges holds fasts deodar panelled or glazed or fully glazed 1-3/4" thick (S.I.No7/P-64) | 410 | S.ft | 1273.76 | P.Sft | Rs: | 522241.6
20 | S/F iron steel grill of 3/4" and 1/4" size flate iron of approved design i/c painting 3 coats etc. complete( weight not less than 3.7 Lb./ Sq: ft: of finished grill) (S.I.No.26/P-97) | 324 | S.ft | 231.6 | P.Sft | Rs: | 75038.4
21 | Primary coat of chalk under distemper (S.I.No.23/P-58) | 9427.92 | S.ft | 442.75 | % Sft | Rs: | 41742.1158
22 | Distempering 03 coats . (S.I.No. 24(b )/P-60) | 9427.92 | S.ft | 1079.65 | % Sft | Rs: | 101788.5383
23 | Painting new surface preparing surface and door & window any type i/c edges. (S.I.No.5(c )/ P-76) | 820 | S.ft | 2116.41 | % Sft | Rs: | 17354.562
|  | Total |  |  |  | Rs: | 6680984.0156
|  | Cost of Carriage |  |  |  | Rs: | 380593.7838
|  | Ded: 20% Below on Marble/Tiles. |  |  |  | Rs: | 335922.9439
|  | Add: 10% Above on Fabrication. |  |  |  | Rs: | 77727.3135
|  | Add: (1%) Contingencies |  |  |  | Rs: | 66809.8402
|  | G.Total Part -- A. |  |  |  | Rs: | 6870192.0092
|  | S A Y : - |  |  |  | Rs: | 6870200
SUB-ENGINEER.
Rehbalitation , Improvement / Renovation & provision for Missing Facilities existing primary / Elementary school at GBPS. Saeed Pur Taluka B.S.Karim District Tando Mohammad Khan.
ASSISTANT ENGINEER
EDUCATION WORKS
(SUB-DIVISION) T.M.KHAN
EXECUTIVE ENGINEER
EDUCATION WORKS
(DIVISION) T.M.KHAN

## M-B.
SCHEDULE - B.
| NAME OF WORK:- | Rehbalitation , Improvement / Renovation & provision for Missing Facilities existing primary / Elementary school at GBPS. Saeedpur Taluka B.S.Karim District Tando Mohammad Khan.
S.No | Description |  | Quantity |  | Rate. | Unit | Amount
1 | Dismentling cement concrete reinforced separating refinorcement for cleaning and sarighening the same (S.I.No.20/P-10).
|  |  | 1235 | Cft | 5445 | %.Cft | 67245.75
2 | Dismentling brick work in lime or cement mortor (S.I.No.13/P-10).
|  |  | 4761 | Cft | 1285.63 | %.Cft | 61208.8443
3 | Excavation of foundation of building bridges and other structure i/c dagbelling dressing refilling around structure with excavated lead upto one chain and lift upto 5' feet.(S.I.NO:18(b)P-4).
|  |  | 2062 | Cft | 1376.25 | %.Cft | 2837.8275
4 | Cement Concret brick or stone ballast 1-1/2" to 2"guage Ratio1:4:8(S.I.No:4/B/P-14).
|  |  | 805 | Cft | 12346.65 | %.Cft | 99390.5325
5 | Pacca brick work in foundation or plinth in cement sand morter1:6 (S.I.No.41/E/P-20)
|  |  | 2062 | Cft | 11948.36 | %.Cft | 246375.1832
6 | R.C.C. work i/c all labour and material except the cost of steel reinforcement and its labour for bending binding which will be paid separately. This rate also i/c all kinds of forms moulds lifting shuttering curing rendering washing of shingle surface. (a) R.C.C work in roof slabs, beams, columns, rafts, lintels and other structural members laid in situ or precast laid in position, complete in all respects Ratio 1:2:4 (S.I No 6/p -18).
|  |  | 3165 | Cft | 337 | P.Cft. | 1066605
7 | Filling, watering, and ramming earth under floors with new earth excavated from outside lead upto 1 chain and lift upto 5'ft (s.I.NO:22/P-05).
|  |  | 4153 | Cft | 3630 | %0.Cft | 15075.39
8 | Add: Extra lead 06 (Miles).
|  |  | 4153 | Cft | 771.96 | %.Cft | 32059.4988
9 | Pacca brick work in Ground Floor i/c stricking of joints upto 20 ft: hieght in cement sand mortor ratio 1:6 (S.I. No. 05/P-24)
|  |  | 3869 | Cft | 12674.36 | %.Cft | 490370.9884
10 | Cement Plaster 1:6 upto 20 ft. hight 1/2" thick (S.I.No. 13(b)/P - 57)
|  |  | 9428 | Sft | 2206.6 | % Sft | 208038.248
11 | Cement Plaster 1:4 upto 20 ft. hight 3/8" thick (S.I.No. 11(a)/P - 57)
|  |  | 10131 | Sft | 2197.52 | % Sft | 222630.7512
12 | Providing and laying 2" thick topping cement concrete 1:2:4 I/c surface finishing and dividing into panells.(S.I.No:16/C/P-47).
|  |  | 2845 | Sft | 3275.5 | % Sft | 93187.975
13 | Providing and laying 3" thick topping cement concrete 1:2:4 I/c surface finishing and dividing into panells.(S.I.No:16/C/P-47).
|  |  | 9500 | Sft | 4411.82 | % Sft | 419122.9
14 | First class deodar wood wrought joinery in doors & windows fixed in position with chowkads i/c cleats cords hooks iron tower bolts hinges holds fasts deodar panelled or glazed or fully glazed 1-3/4" thick (S.I.No7/P-64)
|  |  | 410 | Sft | 1276.73 | P.Sft | 523459.3
15 | Primary coat of chalk under distemper (S.I.No.23/P-58)
|  |  | 9428 | Sft | 442.75 | % Sft | 41742.47
16 | Distempering 03 coats . (S.I.No. 24(b )/P-60)
|  |  | 9428 | Sft | 1079.65 | % Sft | 101789.402
17 | Painting new surface preparing surface and door & window any type i/c edges. (S.I.No.5(c )/ P-76)
|  |  | 820 | Sft | 2116.41 | % Sft | 17354.562
[5 empty] | Total:- |  | 3708494.6229
Part................B.
1 | Fabrication of mild steel reinforcement for R.C.C i/c its labour for cutting bending binding and laying in position making joints and fastening i/c the cost of binding wire also removal of rust from bars (S.I.No. 7/ P- 19)
|  |  | 155.4 | Cft | 5001.7 | P.Cwt | 777264.18
2 | S/F iron steel grill of 3/4" and 1/4" size flate iron of approved design i/c painting 3 coats etc. complete( weight not less than 3.7 Lb./ Sq: ft: of finished grill) (S.I.No.26/P-97)
|  |  | 324 | Sft | 194.16 | P.Sft | 62907.84
[5 empty] | Total:- |  | 840172.02
Part................C.
1 | P/L Hala or patterned tiles glazed 8"x8"and 1/4" on floor or walls facing in required pattern of Stile specification jointed in white cement and pigment over a base of 1:2 grey cement mortar 3/4" thick I/c washing and filling of joints with slurry of white cement and pigment in desired shade with finishing, cleaning and wax polish etc complete i/c cutting tile to proper profile (S .I. No 62 /P-54)
|  |  | 1306 | Sft | 34520.31 | % Sft | 450835.2486
2 | Laying floor of approved with glazed tiles 1/4" thick laid in white cement and pigment on a bed of 3/4" thick cement mortor (S.I No 25/P-49)
|  |  | 288 | Sft | 27678.86 | % Sft | 79715.1168
3 | White glazed tiles 1/4" thick dadoo jointed in white cement and laid over 1:2 cement sand mortor 3/4" thick i/c finishing (S.I.No. 37/P-49)
|  |  | 340 | Sft | 28253.61 | % Sft | 96062.274
[5 empty] | Total:- |  | 626612.6394
Part..........D.
1 | Providing & Fixing printed Glazed Proceline tile 18"18" finished in white cement of laid over a bed of 1/2" thick gray cement sand mortar ratio 1"3 using / filling of joints with white cement etc. (R. A ).
|  |  | 5121 | Sft | 350 | P.Sft | 1792350
[5 empty] | Total:- |  | 1792350
[5 empty] | Total Part- A. |  | 3708494.6229
[5 empty] | Total Part- B. |  | 840172.02
[5 empty] | Total Part- C. |  | 626612.6394
[5 empty] | Total Part- D. |  | 1792350
[5 empty] | G. Total :- |  | 6967629.2823