NIT No.XEN(Bldgs:)/TC/G-55/              Dated:

Issued to ________________________________________

Vide D.R. No.			Dated:

C.D No.			Dated

Bank/Branch:

SPPRA BIDDING DOCUMENT

STANDARD FORM OF BIDDING DOCUMENT

FOR

PROCUREMENT OF WORKS

(For Contracts (Small) Amounting between Rs.2.5 million to Rs.50 million)

CONSTRUCTION OF ANNEXE D.C HOUSE THATTA @ MAKLI.

INSTRUCTIONS TO PROCURING AGENCIES

INSTRUCTIONS TO PROCURING AGENCIES

(Not to be included in bidding documents)

- Basis of Documents

These Documents have been prepared as a global document intended to be used by different agencies/users according to their requirements.  This document is envisaged for National Competitive Bidding (NCB), meant for use for Works costing not more than Rs. 25 Million. These  documents  may  be  tailored  according  to  the  scope  of  works  as  well  as  in  case  of contracts on International Competitive Bidding (ICB) basis, funded by international financial institutions/donors, with payments in foreign currencies. Procuring agencies are then to tailor the  relevant  clauses  to  suit  their  requirements  including  appropriate  modifications  in  the relevant  sections  of  the  documents  in  the  light  of  SPPRA  Bidding  Documents  for  Large Works.

The Executive Engineer, Buildings Division Thatta is expected to manage the Contract itself. The role of Engineer may be added by the Executive Engineer, Buildings Division Thatta, if the Executive Engineer, Buildings Division Thatta, wishes to engage a consultant. The role of  the Engineer with specific delegated powers under various clauses of  Instructions  to Bidders such as clarifications of Bid Documents, Amendment of Bid Documents, evaluation of Bids etc. and  to administer  the Contract under various clauses of Conditions of Contract should  have  been  specified.  The  Executive Engineer, Buildings Division Thatta,  will  be  required  to  set  out  in  the specifications and drawings  the full scope of work  including  the extent of design to be done by the Contractor, if any.

B) 	Contents of Documents

As  stated  in  Clause  IB.4  of  Instructions  to  Bidders,  the  complete  Bidding  Documents  in addition to Invitation for Bids shall comprise items listed therein including any addendum to Bidding  Documents  issued  in  accordance  with  IB.6.  The Standard Form of Bidding Documents (for Small Contracts) includes the following:

- Instructions to Bidders & Bidding Data

- Form of Bid & Schedules to Bid

- Conditions of Contract & Contract Data

- Standard Forms

- Specifications

- Drawings, if any

In addition,  Instructions  to procuring agencies are also provided at various  locations of  this document  within  parenthesis  or  as  a  Note(s).  Executive Engineer, Buildings Division Thatta,  are  expected  to  edit  or finalize this document accordingly, by filling in all the relevant blank spaces and forms as per the scope of the work, deleting all notes and instructions intended to help the bidders.

The Executive Engineer, Buildings Division Thatta,  is  required  to  prepare  the  following  for  completion  of  the  Bidding Documents:

- Invitation for Bids

- Bidding Data

- Schedules to Bid (Samples)

- Schedule of Prices (Format)

- Contract Data

- Specifications

- Drawings, if any

The  Executive Engineer, Buildings Division, Thatta,  attention  is  drawn  to  the  following  while  finalizing  the  Bidding Documents.

C)	Notice Inviting Tender/ Invitation for Bids/ Request for Expression of Interest

The  Notice  Inviting  Tender is  meant  for  publication  of  tenders  for  calling  bids  in  the newspapers and SPPRA Website.

The blank spaces wherever shown are required to be filled by the Executive Engineer, Buildings Division Thatta, before issuance of Bidding Documents.

The Procuring Agency may modify para 1 of Notice Inviting Tender as per its requirements. The notice should be published so as to give the interested bidders sufficient working period for preparation and submission of bids – not less than 15 days for National Competitive Bidding and 90 days for International Competitive Bidding (SPPRA Rule 18).

- The  eligible  bidders  are  defined  in  IB.2;  the  text  can  be  amended  by  the Procuring Agency as deemed appropriate.

- The non-refundable fee for the sale of Bidding Documents should be nominal so as to cover  printing/reproduction  and  mailing  costs  and  to  ensure  that  only  bona-fide bidders shall apply (SPP Rule 20).

- The amount of Bid Security should be a lump sum figure or a percentage, but not less than  1%  and more  than  5%  of  bid  price  and  should  be  in  accordance with  IB.13.1 (SPP Rule 37).

- If the venue of receipt of bids and the opening of bids is the same, the times for receipt and  opening  of  bids  are  to  be  entered  in  last  Para  of  the  Notice  Inviting  Tender, otherwise  indicate  the  name,  address  and  exact  location  for  the  opening  of  bids. However the date for the receipt and the opening of bids shall be same (SPP Rule 41).

D)	Instructions to Bidders

These Instructions to Bidders will not be part of Contract and will cease to have effect once the contract is signed along with Bidding Data.

The instructions to Bidders can be used as given.  Executive Engineer, Buildings Division Thatta, may have to make changes under Bidding Data.

The Executive Engineer, Buildings Division Thatta or Engineer‘s Representative,  if  any,  shall  exercise  powers  of  the Engineer/Procuring Agency under  and  in  connection with Clauses  IB.5,  IB.6,  IB.16, etc.  case an Engineer has been appointed by  the Executive Engineer, Buildings Division Thatta, the aforesaid clauses may be modified accordingly to specify the role of the Engineer by the Executive Engineer, Buildings Division Thatta, otherwise the Engineer‘s reference wherever exist, except Sub-Clause 1.1.20 & Clause 15 of Conditions of Contract and Item 1.1.20 of Contract Data, shall be deleted.

E)	 Bidding Data

The  blank  spaces  wherever  shown  in  Bidding  Data  are  required  to  be  filled  by  the Engineer/ Executive Engineer, Buildings Division Thatta, before issuance of Bidding Documents.

- Contents of IB.10.3 may be retained or modified by the Executive Engineer, Buildings Division Thatta.

- Procuring Agency should insert required experience in IB.11.2.

- Referring  to  IB.14.1,  the  period  of  bid  validity  may  range  from  30  to  90  days depending upon the size and nature of the works. Number of days shall be filled in as per Procuring Agency‘s requirements.

- Contents of IB.16.3 to IB.16.8 may be retained or modified by the Procuring Agency in accordance with its requirements.

F)	SCHEDULES TO BID

Specimen  of  Schedules  to Bid  including  format  of  Schedule  of Prices  are  provided in this document. The Executive Engineer, Buildings Division Thatta. May add / delete / modify as per its requirement.

The blank spaces wherever shown are required to be filled by the Engineer/ Executive Engineer, Buildings Division Thatta before  issuance  of  Bidding  Documents  except  those  required  to  be  provided  by  the Contractor.

G)	CONDITIONS OF CONTRACT

The  procuring  agency  while  preparing  Contract  Data,  shall  ensure  that  no  Clause  of Conditions of Contract is deleted and that the changes included in Contract Data shall be such as  not  to  change  the  spirit  of  the  document.  Any  adjustment  or  change  in  clauses  of Conditions  of  Contract  to  meet  specific  project  features  shall  be  made  with  care  and incorporated in Contract Data.

H)	CONTRACT DATA

The blank spaces wherever shown are required to be filled by the Engineer / Executive Engineer, Buildings Division Thatta before issuance of Bidding Documents.

1.  	Referring  to  Sub-Clause  1.1.1  of  Conditions  of  Contract,  the  Engineer/ Executive Engineer, Buildings Division Thatta  may  add,  in  order  of  priority,  such  other  documents  as  to  form  part  of  the Contract, in Sub-Clause 1.3 of the Contract Data.

2.  	The Executive Engineer, Buildings Division Thatta Representative, if any, shall exercise powers of the Executive Engineer, Buildings Division Thatta under and in connection with Sub-Clauses 1.3, 2.3, 4.2, 4.3, 5.1, 7.3, 8.2, 9.1, 9.2, 10.1, 10.2. 10.5, 11.1, 11.5, 12.1, 13.2 and 14.1 of the Conditions of Contract. In case an Engineer has been appointed by the Executive Engineer, Buildings Division Thatta, the aforesaid clauses may be modified accordingly by the Procuring Agency.

3.  	The  sum  insured  for  different  insurances  including minimum  amount  of  third  party insurance  should  be  assessed  by  the  Engineer/ Executive Engineer, Buildings Division Thatta  and  entered  in Contract  Data.  Such insurance cover shall be carried out with Insurance Company having at least AA rating from PACRA / JCR in the favour of the Executive Engineer, Buildings Division Thatta.

4.  	The  time  for  completion  of  the  whole  of  the  works  should  be  assessed  by  the Engineer/ Executive Engineer, Buildings Division Thatta and entered in the Contract Data.

5.  	The Conditions of Contract contain no overall limit on the Contractor‘s liability. The amount  of  liquidated  damages  per  day  of  delay  shall  be  entered  by  the Engineer/ Executive Engineer, Buildings Division Thatta in Contract Data. Usually  the  liquidated damages are set between  0.05  percent  and  0.10  percent  per  day  and  the maximum  limit  as  10 percent of contract price stated in the Letter of Acceptance.

6.  	Any amendment and/or additions to the Conditions of the Contract that are specific to a given Bid/Contract should be included by the Executive Engineer, Buildings Division Thatta. This may include but not be limited to the provisions regarding the following:

- Terms of Payment should be prepared and incorporated in Contract Data by the Engineer/ Executive Engineer, Buildings Division Thatta.

- The Engineer/ Executive Engineer, Buildings Division Thatta to make sure that all taxes and duties are included by the Bidders/Contractors in their prices.

I.  Specifications

To be prepared and incorporated by the Engineer/ Executive Engineer, Buildings Division Thatta.

J.  Drawings

To be prepared and incorporated by the Engineer/ Executive Engineer, Buildings Division Thatta, if required.

SUMMARY OF CONTENTS

Subject  									    Page No

(I)  INVITATION FOR BIDS………………………………………………………. 	02

(II)  INSTRUCTIONS TO BIDDERS & BIDDING DATA………………………… 	04

(III)  FORM OF BID & SCHEDULES TO BID……………………………………… 	19

(IV)  CONDITIONS OF CONTRACT & CONTRACT DATA……………………...   	33

(V)  STANDARD FORMS…………………………………………………………... 	54

(VI)  SPECIFICATIONS………………………………………………………………  	67

(VII)  DRAWINGS…………………………………………………………………….  	68

INVITATION FOR BIDS

INVITATION FOR BIDS

Date:     .      .

Bid Reference No.

The Executive Engineer, Buildings Division Thatta, [Executive Engineer, Buildings Division Thatta], invites sealed bids from interested  firms or persons licensed by the Pakistan Engineering Council in the appropriate category( not required  for works costing Rs 2.5 million or  less) and/or duly pre-qualified(if pre-qualification  is done  for  specific  scheme/project) with  the Executive Engineer, Buildings Division Thatta for the Works, Construction of  CONSTRUCTION OF ANNEXE D.C HOUSE THATTA @ MAKLI [enter title, type and financial volume of work], which will be completed in  24-Months  [enter appropriate time period] days.

- A complete set of Bidding Documents may be purchased by an interested eligible bidder on submission of a written application to the office given below and upon payment of a non-refundable fee of Rupees______________________. Bidders  may acquire  the  Bidding  Documents  from  the  Office  of  the  Executive Engineer, Buildings Division Thatta, at S.E. OFFICE THATTA. (Mailing Address).

- All  bids  must  be  accompanied  by  a  Bid  Security  in  the  amount  of Rs._____________/- (Rupees _____________________________________________) or 2% percentage  of bid price  in the  form of (pay order /demand draft/ bank  guarantee) and must be delivered to Executive Engineer Buildings Division Thatta (Indicate Address and Exact Location) at or before ____ P.M, on ____________. Bids will be opened at ________ P.M on dated _________________ in the presence of bidders’ representatives who choose to attend, at the same address [indicate the address if it differs].

Note:

- Executive Engineer, Buildings Division Thatta, to enter the requisite information in blank spaces.

- The bid shall be opened within one hour   after the deadline for submission of bids.

INSTRUCTIONS

TO BIDDERS

&

BIDDING DATA

Notes on the Instructions to Bidders

This section of the bidding documents should provide the information necessary for bidders to prepare responsive bids, in accordance with the requirements of the Executive Engineer, Buildings Division Thatta. It should also give information on bid submission, opening and evaluation, and on the award of contract.

Matters  governing  the  performance  of  the  Contract  or  payments  under  the  Contract,  or matters  affecting  the  risks,  rights,  and  obligations  of  the parties under  the Contract  are not normally  included  in  this Section, but rather  in  the appropriate sections of  the Conditions of Contract and/or Contract Data.

TABLE OF CONTENTS

INSTRUCTIONS TO BIDDERS

Clause No.  	Description  								Page No.

A)	GENERAL

IB.1  Scope of Bid & Source of Funds………………………………… 		6

IB.2  Eligible Bidders………………………………………………….. 		6

IB.3  Cost of Bidding………………………………………………….. 		7

- BIDDING DOCUMENTS

IB.4  Contents of Bidding Documents………………………………… 		7

IB.5  Clarification of Bidding Documents…………………………….. 		7

IB.6  Amendment of Bidding Documents……………………………..  	8

- PREPARATION OF BID

IB.7  Language of Bid…………………………………………………. 		8

IB.8  Documents Comprising the Bid…………………………………. 		8

IB.9  Sufficiency of Bid………………………………………………..  		8

IB.10  Bid Prices, Currency of Bid & Payment…………………………  	9

IB.11  Documents Establishing Bidder‘s Eligibility and Qualifications... 	9

IB.12  Documents Establishing Works Conformity to

Bidding Documents……………………………………………… 		9

IB.13  Bidding Security…………………………………………………. 		10

IB.14  Validity of Bids, Format, Signing and Submission of Bid………. 	10

D)	SUBMISSION OF BID

IB.15  Deadline for Submission, Modification & Withdrawal of Bids…. 	11

E)	BID OPENING AND EVALUATION

IB.16  Bid Opening, Clarification and  Evaluation……………………… 	12

IB.17  Process to be Confidential………………………………………... 	13

F)	AWARD OF CONTRACT

IB.18  Qualification……………………………………………………... 		13

IB.19  Award Criteria & Procuring Agency‘s Right……………………. 	14

IB.20  Notification of Award & Signing of Contract Agreement………  	14

IB.21  Performance Security……………………………………………. 		14

IB.22  Integrity Pact……………………………………………………..  		15

INSTRUCTIONS TO BIDDERS

Note:  	(These  Instructions  to  Bidders  (IB)  along  with  Bidding  Data  will  not  be  part  of Contract and will cease to have effect once the Contract is signed).

A.  GENERAL

IB.1   Scope of Bid & Source of Funds

1.1  Scope of Bid

The Executive Engineer, Buildings Division Thatta as defined  in  the Bidding Data (hereinafter called ―the Executive Engineer, Buildings Division Thatta)  wishes  to  receive  Bids  for  the  Works  summarized  in  the  Bidding  Data (hereinafter referred to as ―the Works).

Bidders must quote  for  the complete  scope of work. Any Bid covering partial scope of work will be rejected as non-responsive.

1.2  Source of Funds

The Executive Engineer, Buildings Division Thatta has arranged funds from its own sources or Federal/ Provincial /Donor agency or any other source, which may be indicated accordingly in bidding data towards the cost of the project/scheme.

IB.2 	Eligible Bidders

2.1 	Bidding is open to all firms and persons meeting the following requirements:

a)  	Duly  licensed  by  the  Pakistan  Engineering  Council  (PEC)  in  the  appropriate category for value of works.

Provided that the works costing Rs. 2.50 million or less shall not require any registration with PEC.

b)  	Duly pre-qualified with the Procuring Agency. (Where required).

In the event that prequalification of potential bidders has been undertaken, only bids from prequalified bidders will be considered for award of Contract.

c)        	If prequalification has not undertaken, the procuring agency may ask information and documents not limited to following:-

(i)      	Company profile;

(ii)      	Works of similar nature and size for each performed in last 3/5 years;

(iii)    	Construction equipments;

(iv)	Qualification and experience of technical personnel and key site management;

(v)        Financial statement of last 3 years;

(vi)       Information regarding litigations and abandoned works if any.

IB.3  Cost of Bidding

3.1  	The bidder shall bear all costs associated with  the preparation and submission of  its bid and  the  Executive Engineer, Buildings Division Thatta  will  in  no  case  be  responsible  or  liable  for  those  costs, regardless of the conduct or outcome of the bidding process (SPP Rules 24 & 25).

B.  BIDDING DOCUMENTS

IB.4  	Contents of Bidding Documents

4.1  	In  addition  to  Invitation  for Bids,  the Bidding Documents  are  those  stated  below,  and should be read in conjunction with any Addendum issued in accordance with Sub-Clause

IB.6.1.

1.  	Instructions to Bidders & Bidding Data

2.  	Form of Bid, Qualification Information & Schedules to Bid Schedules to Bid comprise the following:

(i)  	Schedule A: Schedule of Prices/ Bill of Quantities (BOQ).

(ii)  	Schedule B: Specific Works Data

(iii)  	Schedule C: Works to be Performed by Subcontractors

(iv)  	Schedule D: Proposed Programme of Works

(v)  	Schedule E: Method of Performing Works

(vi)  	Schedule F: Integrity Pact (works costing Rs.10 million and above)

3.  	Conditions of Contract & Contract Data

4.  	Standard Forms:

(i)  	Form of Bid Security,

(ii) 	Form of Performance Security;

(iii)	Form of Contract Agreement;

(iv)   	Form of Bank Guarantee for Advance Payment.

5.  	Specifications

6.  	Drawings, if any

IB.5 	Clarification of Bidding Documents

5.1  	A prospective bidder requiring any clarification(s) in respect of the Bidding Documents may notify the Engineer/Procuring Agency at the Engineer‘s/ Executive Engineer, Buildings Division Thatta  address indicated in the Bidding Data.

5.2  	An interested bidder, who has obtained bidding documents, may request for clarification  of contents of bidding documents  in writing and Executive Engineer, Buildings Division Thatta  shall respond  to such quarries  in writing within  three  calendar  days,  provided  they  are  received  at  least  five calendar days prior to the date of opening of bid (SPP Rule 23-1).

IB.6  	Amendment of Bidding Documents (SPP Rules 22(2) & 22).

6.1  	At any time prior to the deadline for submission of Bids, the Executive Engineer, Buildings Division Thatta  may, for any  reason, whether at his own  initiative or  in response  to a clarification requested by a interested  bidder, modify the Bidding Documents by issuing addendum.

6.2  	Any  addendum  thus  issued  shall  be  part  of  the  Bidding Documents  pursuant  to  Sub-Clause 6.1 hereof, and shall be communicated in writing to all purchasers of the Bidding Documents. Prospective bidders shall acknowledge receipt of each addendum in writing to the Executive Engineer, Buildings Division Thatta.

6.3  	To afford interested  bidders reasonable time in which to take an addendum into account in preparing their Bids, the Executive Engineer, Buildings Division Thatta may at its discretion extend the deadline for submission of Bids.

C.  PREPARATION OF BIDS

IB.7  	Language of Bid

7.1    	All documents relating to the Bid shall be in the language specified in the Contract Data.

IB.8  	Documents Comprising the Bid

8.1  	The Bid submitted by the bidder shall comprise the following:

(a)  	Offer /Covering Letter

(b)      	Form of Bid duly filled, signed and sealed, in accordance with IB.14.3.

(c)  	Schedules  (A  to  F)  to  Bid  duly  filled  and  initialed,  in  accordance  with  the

Instructions contained therein & in accordance with IB.14.3.

(d)   	Bid Security furnished in accordance with IB.13.

(e)   	Power of Attorney in accordance with IB 14.5.

(f)   	Documentary evidence in accordance with IB.2(c) & IB.11

(g)  	Documentary evidence in accordance with IB.12.

IB.9 	Sufficiency of Bid

9.1  	Each bidder shall satisfy himself before Bidding as  to  the correctness and sufficiency of his Bid and of  the premium on  the rates of CSR  / rates and prices quoted/entered  in  the Schedule  of  Prices,  which  rates  and  prices  shall  except  in  so  far  as  it  is  otherwise expressly  provided  in  the Contract,  cover  all his obligations under  the Contract  and  all matters and things necessary for the proper completion of the works.

9.2  	The  bidder  is  advised  to  obtain  for  himself  at  his  own  cost  and  responsibility  all information  that may be necessary for preparing  the bid and entering  into a Contract for execution of the Works.

IB.10  	Bid Prices, Currency of Bid and Payment

10.1  	The  bidder  shall  fill  up  the  Schedule  of  Prices  (Schedule  A  to  Bid)  indicating  the percentage above or below  the Composite Schedule of Rates/unit rates and prices of  the Works  to  be  performed  under  the  Contract.  Prices  in  the  Schedule  of  Prices/Bill  of Quantities  shall  be  quoted  entirely  in  Pak  Rupees  keeping  in  view  the  instructions contained in the Preamble to Schedule of Prices.

10.2  	Unless  otherwise  stipulated  in  the Conditions  of Contract,  prices  quoted  by  the  bidder shall  remain  fixed  during  the  bidder‘s  performance  of  the Contract  and  not subject  to variation on any account.

10.3   	The unit rates and prices in the Schedule of Prices or percentage above or below on the composite schedule of rates shall be quoted by the bidder in the currency as stipulated in   Bidding Data.

10.4    	Items  for  which  no  rate  or  price  is  entered  by  the  Bidder will  not  be  paid  for  by  the Executive Engineer, Buildings Division Thatta  when  executed  and  shall  be  deemed  covered  by  the  other  rates  and prices in the Bill of Quantities.

IB.11  	Documents Establishing Bidder’s Eligibility and Qualifications

11.1  	Pursuant to Clause IB.8, the bidder shall furnish, as part of its bid, documents establishing the  bidder‘s  eligibility  to  bid  and  its qualifications  to perform  the Contract  if  its  bid  is accepted.

11.2  	Bidder  must  possess  and  provide  evidence  of  its  capability  and  the  experience  as stipulated  in  Bidding  Data  and  the  Qualification  Criteria  mentioned  in  the  Bidding Documents.

IB.12 	Documents Establishing Works’ Conformity to Bidding Documents

12.1  	The documentary evidence of the Works conformity to the Bidding Documents may be in the form of literature, drawings and data and the bidder shall furnish documentation as set out in Bidding Data.

12.2  	The  bidder  shall  note  that  standards  for  workmanship,  material  and  equipment,  and references  to  brand  names  or  catalogue  numbers, if  any,  designated  by  the  Executive Engineer, Buildings Division Thatta in the Technical Provisions are intended to be descriptive only and not restrictive.

IB.13  Bid Security

13.1  	Each bidder shall furnish, as part of his bid, at the option of the bidder, a Bid Security as percentage of bid price/estimated cost or in the amount stipulated in Bidding Data in Pak. Rupees  in  the form of Deposit at Call/ Payee’s Order or a Bank Guarantee  issued by a Scheduled Bank  in Pakistan  in  favour of  the Executive Engineer, Buildings Division Thatta valid  for a period up  to twenty  eight  (28)  days  beyond  the  bid  validity  date  (Bid  security  should  not  be  below  1%.and not exceeding 5% of bid price/estimated cost SPP Rule 37).

13.2  	Any bid not accompanied by an acceptable Bid Security shall be rejected by the Executive Engineer, Buildings Division Thatta as non-responsive.

13.3  	The bid securities of unsuccessful bidders will be returned upon award of contract to the successful bidder or on the expiry of validity of Bid Security whichever is earlier.

13.4  	The Bid Security of the successful bidder will be returned when the bidder has furnished the required Performance Security, and signed the Contract Agreement (SPP Rule 37).

13.5  	The Bid Security may be forfeited:

(a)  	If a bidder withdraws his bid during the period of bid validity; or

(b)  	If a bidder does not accept the correction of his Bid Price, pursuant to Sub-Clause

16.4 	(b) hereof; or

(c)  	In the case of a successful bidder, if he fails within the specified time limit to:

(i)  	Furnish the required Performance Security or

(ii)  	Sign the Contract Agreement.

IB.14  	Validity of Bids, Format, Signing and Submission of Bid

14.1  	Bids shall remain valid for the period stipulated in the Bidding Data after the date of bid opening.

14.2  	In  exceptional  circumstances,  Executive Engineer, Buildings Division Thatta  may  request  the  bidders  to  extend  the period of validity for a additional period but not exceeding 1/3 of the original period. The request and the bidders responses shall be made in writing or by cable.   A Bidder may refuse the request without forfeiting the Bid Security.  A Bidder agreeing  to  the request will  not  be  required  or  permitted  to  otherwise modify  the Bid,  but will  be  required  to extend the validity of Bid Security for the period of the extension, and in compliance with IB.13 in all respects (SPP Rule 38).

14.3  	All Schedules to Bid are to be properly completed and signed.

14.4  	No alteration is to be made in the Form of Bid except in filling up the blanks as directed. If any alteration be made or if these instructions be not fully complied with, the bid may be rejected.

14.5  	Each bidder shall prepare Original and number of copies specified in the Bidding Data of the  documents  comprising  the  bid  as  described  in  IB.8  and  clearly  mark  them -ORIGINAL and -COPY as appropriate. In the event of discrepancy between them, the original shall prevail.

14.6  	The original and all copies of the bid shall be typed or written in indelible ink and shall be signed by a person or persons duly authorized to sign (in the case of copies, Photostats are also acceptable).  This  shall  be  indicated  by  submitting  a  written  Power  of  Attorney authorizing the signatory of the bidder to act for and on behalf of the bidder. All pages of the bid shall be initialed and official seal be affixed by the person or persons signing the bid.

14.7  	The Bid shall be delivered in person or sent by registered mail at the address to Procuring Agency as given in Bidding Data.

D. SUBMISSION OF BID

IB.15  	Deadline for Submission, Modification & Withdrawal of Bids

15.1  	Bids must be received by the Procuring Agency at the address/provided in Bidding Data not later than the time and date stipulated therein.

15.2   	The inner and outer envelopes shall

(a)  	Be addressed to the Executive Engineer, Buildings Division Thatta at the address provided in the Bidding Data;

(b)  	Bear the name and identification number of the Contract as defined in the Bidding and Contract Data; and

(c)  	Provide a warning not to open before the specified time and date for Bid opening as defined in the Bidding Data.

(d)   	In addition to the identification required in 15.2, the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late.

(e)   	If the outer envelope is not sealed and marked as above, the Executive Engineer, Buildings Division Thatta will assume no responsibility for the misplacement or premature opening of the Bid.

15.3  	Bids submitted through telegraph, telex, fax or e-mail shall not be considered.

15.4  	Any bid received by the Executive Engineer, Buildings Division Thatta after the deadline for submission prescribed in Bidding Data will be returned unopened to such bidder.

15.5  	Any  bidder  may  modify  or  withdraw  his  bid  after  bid  submission  provided  that  the modification or written notice of withdrawal is received by the Executive Engineer, Buildings Division Thatta  prior to the deadline for submission of bids.

15.6  	Withdrawal of a bid during the interval between the deadline for submission of bids and the  expiration  of  the  period  of  bid  validity  specified  in  the Form  of Bid may  result  in forfeiture of the Bid Security pursuant to IB.13.5 (a).

E.  BID OPENING AND EVALUATION

IB.16  	Bid Opening, Clarification and Evaluation (SPP Rules 41, 42 & 43)

16.1  	The Executive Engineer, Buildings Division Thatta will open the bids, in the presence of bidders‘representatives who choose to attend, at the time, date and in the place specified in the Bidding Data.

16.2  	The bidder‘s name, Bid Prices, any discount, the presence or absence of Bid Security, and such other details as the Executive Engineer, Buildings Division Thatta  at its discretion may consider appropriate, will be  announced by  the Procuring Agency  at  the bid opening. The Executive Engineer, Buildings Division Thatta will record the minutes of the bid opening.  Representatives of the bidders who choose to attend shall sign the attendance sheet.

Any Bid Price or discount which is not read out and recorded at bid opening will not be taken into account in the evaluation of bid.

16.3 	To assist in the examination, evaluation and comparison of Bids the Engineer/ Executive Engineer, Buildings Division Thatta may, at its discretion, ask the bidder for a clarification of its Bid. The request for clarification and the response shall be in writing and no change in the price or substance of the Bid shall be sought, offered or permitted (SPP Rule 43).

16.4  (a)  Prior  to  the  detailed  evaluation,  pursuant  to  IB.16.7  to  16.9,  the Engineer/ Executive Engineer, Buildings Division Thatta  will determine the substantial responsiveness of each bid  to  the Bidding Documents. For purpose of  these  instructions, a  substantially responsive  bid  is  one  which  conforms  to  all  the  terms  and  conditions  of  the Bidding Documents without material  deviations.  It will include  determining  the requirements listed in Bidding Data.

(b)  Arithmetical errors will be rectified on the following basis:

If there is a discrepancy between the unit price and total price that is obtained by multiplying the unit price and quantity, the unit price shall prevail and the total price shall be corrected.  If there is a discrepancy between the words and figures the amount in words shall prevail. If there is a discrepancy between the Total Bid price entered in Form of Bid and the total shown in Schedule of Prices-Summary, the amount stated in the Form of Bid will be corrected by the Executive Engineer, Buildings Division Thatta in accordance with the Corrected Schedule of Prices.

If the bidder does not accept the corrected amount of Bid, his Bid will be rejected and his Bid Security forfeited.

16.5 	A  Bid  determined  as  substantially  non-responsive  will  be  rejected  and  will  not subsequently be made responsive by the bidder by correction of the non-conformity.

16.6  	Any  minor  informality  or  non-conformity  or  irregularity  in  a  Bid  which  does  not constitute a material deviation  (major deviation) may be waived by Executive Engineer, Buildings Division Thatta,  provided  such  waiver  does  not  prejudice  or  affect  the  relative  ranking  of  any  other bidders.

A)	Major (material) Deviations include:-

- Has been not properly signed;

- Is not accompanied by the bid security of required amount and manner;

- Stipulating price adjustment when fixed price bids were called for;

- Failing to respond to specifications.

- Failing to comply with Mile-stones/Critical dates provided in Bidding documents;

- Sub-contracting contrary to the Conditions of Contract specified in Bidding documents;

- Refusing to bear important responsibilities and liabilities allocated in the Bidding Documents, such as performance guarantees and insurance coverage;

- Taking exception to critical provisions such as applicable law, taxes and duties and dispute resolution procedures;

- A material deviation or reservation is one :

- Which affect in any substantial way the scope, quality or performance of the works;

- Adoption/rectification whereof would affect unfairly the competitive position of other bidders presenting substantially responsive bids.

(B) Minor Deviations

Bids that offer deviations acceptable to the Procuring Agency and which can be assigned a monetary value may be considered substantially responsive at least as to the issue of fairness. This value would however be added as an adjustment for evaluation purposes only during the detailed evaluation process.

16.7.	The Engineer/ Executive Engineer, Buildings Division Thatta will evaluate and compare only the bids previously determined to be substantially responsive pursuant to IB.16.4 to 16.6 as per requirements given hereunder. Bids will be evaluated for complete scope of works. The prices will be compared on the basis of the Evaluated Bid Price pursuant to IB.16.8 herein below.

Technical Evaluation: It will be examined in detail whether the works offered by the bidder complies with the Technical Provisions of the Bidding Documents. For this purpose, the bidder‘s data submitted with the bid in Schedule B to Bid will be compared with technical features/criteria of the works detailed in the Technical Provisions. Other technical information submitted with the bid regarding the Scope of Work will also be reviewed.

16.8.	Evaluated Bid Price

In  evaluating  the  bids,  the  Engineer/ Executive Engineer, Buildings Division Thatta will  determine  for  each  bid  in addition  to  the Bid Price,  the  following  factors  (adjustments)  in  the manner  and  to  the extent indicated below to determine the Evaluated Bid Price:

- Making any correction for arithmetic errors pursuant to IB.16.4 hereof.

- Discount, if any, offered by the bidders as also read out and recorded at the time of bid opening.

- Excluding provisional sums and the provisions for contingencies in the Bill of   Quantities if any, but including Day work, where priced competitively.

IB.17.	Process to be Confidential

17.1.	Subject to IB.16.3 heretofore, no bidder shall contact Engineer/ Executive Engineer, Buildings Division Thatta on any matter relating to its Bid from the time of the Bid opening to the time the bid evaluation result is announced by the Executive Engineer, Buildings Division Thatta. The evaluation result shall be announced at least seven (07) days prior to award of Contract (SPP Rule 45). The announcement to all bidders  will  include  table(s)  comprising  read  out  prices,  discounted  prices,  price adjustments  made,  final  evaluated  prices  and  recommendations  against  all  the  bids evaluated.

17.2  	Any effort by a bidder to influence Engineer/ Executive Engineer, Buildings Division Thatta the Bid evaluation, Bid comparison or Contract Award decisions may result in the rejection of his Bid. Whereas any  bidder  feeling  aggrieved,  may  lodge  a  written  complaint  to  Complaint  Redressal Committee as per terms and conditions mentioned in SPP Rules 31 & 32. However, mere fact of lodging a complaint shall not warrant suspension of procurement process.

17.3  	Bidders may be excluded if involved in “Corrupt and Fraudulent Practices” means either one or any combination of the practices given below SPP Rule 2(q);

- Coercive  Practice means  any  impairing  or  harming,  or  threatening  to  impair  or  harm, directly or indirectly, any party or the property of the party to influence the actions of a party to achieve a wrongful gain or to cause a wrongful loss to another party;

- Collusive  Practice‖  means  any  arrangement  between  two  or  more  parties  to  the procurement process or contract execution, designed to achieve with or without the knowledge of the Executive Engineer, Buildings Division Thatta  to establish prices at artificial, noncompetitive levels for any wrongful gain;

- Corrupt  Practice”  means  the  offering,  giving,  receiving  or  soliciting,  directly or indirectly, of anything of value to influence the acts of another party for wrongful gain;

- Fraudulent  Practice”  means  any  act  or  omission,  including  a  misrepresentation,  that knowingly or  recklessly misleads, or attempts  to mislead, a party  to obtain a  financial or other benefit or to avoid an obligation;

- Obstructive  Practice”  means  harming  or  threatening  to  harm,  directly  or  indirectly, persons or  their property  to  influence  their participation  in a procurement process, or affect  the execution of a contract or deliberately destroying, falsifying, altering or concealing of evidence material to the investigation or making false statements before investigators in order to materially impede an investigation into allegations of a corrupt, fraudulent, coercive or collusive practice;  or  threatening,  harassing  or  intimidating  any  party  to  prevent  it  from  disclosing  its knowledge  of matters  relevant  to  the  investigation  or  from  pursuing  the  investigation,  or  acts intended  to materially  impede  the exercise of  inspection and audit rights provided for under the Rules.

F)	AWARD OF CONTRACT

IB.18.	Post Qualification

18.1.	The Executive Engineer, Buildings Division Thatta , at any stage of the bid evaluation, having credible reasons for or prima facie evidence of any defect in contractor‘s capacities, may require the contractors to  provide  information  concerning  their  professional,  technical,  financial,  legal  or managerial competence whether already  pre-qualified or not:

Provided, that such qualification shall only be laid down after recording reasons therefore in writing. They shall form part of the records of that bid evaluation report.

18.2.	The determination will take into account the bidder‘s financial and technical capabilities. It  will  be  based  upon  an  examination  of  the  documentary  evidence  of  the  bidders‘ qualifications  submitted  under B.11,  as well  as  such  other  information  required  in  the Bidding Documents.

IB.19.	Award Criteria & Executive Engineer, Buildings Division Thatta  Right

19.1.  Subject to IB.19.2, the Executive Engineer, Buildings Division Thatta  will award the Contract to the bidder whose bid has been determined  to be  substantially  responsive  to  the Bidding Documents and who has offered the lowest evaluated Bid Price, provided that such bidder has been determined to be qualified  to satisfactory perform  the Contract  in accordance with  the provisions of the IB.18.

19.2  Notwithstanding IB.19.1, the Executive Engineer, Buildings Division Thatta  reserves the right to accept or reject any bid,  and  to  annul  the bidding process  and  reject  all  bids,  at  any  time prior  to  award of Contract, without thereby incurring any liability to the affected bidders or any obligation to  inform  the  affected bidders of  the grounds  for  the Executive Engineer, Buildings Division Thatta action except that  the grounds for  its rejection of all bids shall upon request be communicated,  to any bidder who submitted a bid, without  justification of  the grounds. Notice of the rejection of all the bids shall be given promptly to all the bidders (SPP Rule 25).

IB.20.	Notification of Award & Signing of Contract Agreement

20.1.  Prior  to expiration of  the period of bid validity prescribed by  the Executive Engineer, Buildings Division Thatta ,  the Procuring Agency will  notify  the  successful  bidder  in writing  (―Letter  of Acceptance) that his bid has been accepted (SPP Rule 49).

20.2.  Within  seven  (07) days  from  the date of  furnishing of acceptable Performance Security under  the Conditions of Contract,  the Executive Engineer, Buildings Division Thatta  will send  the successful bidder the Form of Contract Agreement provided  in  the Bidding Documents,  incorporating all agreements between the parties.

20.3  The  formal  Agreement  between  the  Procuring Agency  and  the  successful  bidder  duly stamped  at  rate  of  0.3%  of  bid  price (updated from time to time)  stated  in  Letter  of Acceptance shall be executed within seven (07) days of  the receipt of Form of Contract Agreement by the successful bidder from the Executive Engineer, Buildings Division Thatta .

IB.21.	Performance Security

21.1.	The successful bidder shall furnish to the Executive Engineer, Buildings Division Thatta a Performance Security in the form and the amount stipulated in the Conditions of Contract within a period of fourteen  (14) days after the receipt of Letter of Acceptance (SPP 39).

21.2. Failure of the successful bidder to comply with the requirements of Sub-Clauses IB.20.2 & 20.3 or 21.1 or Clause IB.22 shall constitute sufficient grounds for the annulment of the award and forfeiture of the Bid Security.

21.3 Publication of Award of Contract: within  seven days of  the  award of  contract,  the procuring shall publish on  the website of  the  authority  and on  its own website,  if  such  a website  exists,  the results  of  the  bidding  process,  identifying  the bid  through procurement  identifying Number  if  any and the following information:

- Evaluation Report;

- Form of Contract and letter of Award;

- Bill of Quantities or Schedule of Requirements. (SPP Rule 50)

IB.22  Integrity Pact The Bidder  shall  sign  and  stamp  the Form of  Integrity Pact  provided at Schedule-F  to Bid  in  the Bidding Document  for  all  Sindh Government  procurement  contracts exceeding Rupees ten (10) million. Failure to provide such Integrity Pact shall make the bid non-responsive (SPP Rule 89).

BIDDING DATA

(This  section  should  be  filled  in  by  the  Engineer/ Executive Engineer, Buildings Division Thatta  before  issuance  of  the Bidding Documents.  The following specific data for the works to be tendered shall complement, amend, or supplement the provisions in the Instructions to Bidders. Wherever there is a conflict, the provisions herein shall prevail over those in the Instructions to Bidders.)

Instructions to Bidders

Clause Reference

1.1  Name of Procuring Agency

Executive Engineer, Buildings Division Thatta

Executive Engineer

(Insert name of the Procuring Agency)

Brief Description of Works

CONSTRUCTION OF ANNEXE D.C HOUSE THATTA @ MAKLI.

5.1  (a)  Procuring Agency‘s address:

OFFICE OF THE EXECUTIVE ENGINEER BUILDINGS DIVISION, GHULAMULLAH, ROAD NEAR D.C OFFICE THATTA.

(Insert address of the Procuring Agency with telex/fax)

(b)  Engineer‘s address:

Residence of Building Colony Bungalow No. D-1/2 at Makli 0298-920170

(Insert name and address of the Engineer, if any, with telex/fax.)

10.3   Bid shall be quoted entirely in Pak. Rupees. The payment shall be made in Pak. Rupees.

11.2     The bidder has the financial, technical and constructional capability necessary to perform the Contract as follows: (Insert required capabilities and documents)

- Financial capacity: (must have turnover of Rs._____________ Million);

- Technical capacity: (mention the appropriate category of registration with PEC and qualification and experience of the staff);

- Construction Capacity: (mention the names and number of equipments required for the work).

12.1.

- A detailed description of the Works, essential technical and performance characteristics.

- Complete set of technical information, description data, literature and drawings as required in accordance with Schedule B to Bid, Specific Works Data. This will include  but  not  be  limited  to  a  sufficient  number  of  drawings,  photographs, catalogues,  illustrations  and  such  other  information  as  is  necessary  to  illustrate clearly the significant characteristics such as general construction dimensions and other relevant information about the works to be performed.

13.1.	Amount of Bid Security

2% of Bid Amount._____________________________________________

(Fill in lump sum amount or in % age of bid amount /estimated cost, but not below 1% and not exceeding 5%)

14.1  Period of Bid Validity

90 Days________________________________________________________

(Fill in “number of days” not exceeding 90)

14.4  Number of Copies of the Bid to be submitted:

One original plus 01 copy.

  - (a)  Executive  Engineer, Buildings Division, Thatta, Address for the Purpose of Bid Submission

OFFICE OF THE EXECUTIVE ENGINEER BUILDINGS DIVISION THATTA GULAMULLAH ROAD NEAR DC OFFICE THATTA.

(insert postal address or location of bid box for delivery by hand)

15.1  Deadline for Submission of Bids

Time:_________ PM on dated _______________.

16.1  Venue, Time, and Date of Bid Opening

Venue:		Executive Engineer, Buildings Division Thatta.

Time:_________PM on dated _____________

16.4  Responsiveness of Bids

- Bid is valid till required period,

- Bid prices are firm during currency of contract/Price adjustment;

- Completion period offered is within specified limits,

- Bidder  is  eligible  to Bid  and  possesses  the  requisite  experience, capability  and  qualification.

- Bid does not deviate from basic technical requirements and

- Bids are generally in order, etc.

*	Executive Engineer, Buildings Division Thatta can adopt either of two options. (Select either of them).

- Fixed  Price  contract:  In  these  contracts  no  escalation  will  be  provided during currency of the contract and normally period of completion of these works is upto 12 months.

(b)      	Price adjustment contract: In  these contracts escalation will be paid only on  those  items  and  in  the  manner  as  notified  by  Finance  Department, Government of Sindh, after bid opening during currency of the contract.

FORM OF BID AND SCHEDULES TO BID

FORM OF BID

(LETTER OF OFFER)

Bid Reference No.

CONSTRUCTION OF ANNEXE D.C HOUSE THATTA @ MAKLI

(Name of Works)

To,

_____________________________,

_____________________________,

_____________________________.

Gentlemen,

- Having  examined  the Bidding Documents  including  Instructions  to Bidders, Bidding  Data,  Conditions  of  Contract,  Contract  Data,  Specifications, Drawings,  if  any,  Schedule  of  Prices  and  Addenda  Nos.______________ for  the execution  of  the  above-named works, we,  the undersigned, being a company doing business under  the name of and address  _______________________________________________________________________ __________________________________________________________ and  being duly  incorporated  under  the  laws  of    Pakistan  hereby  offer  to  execute  and complete  such works  and  remedy  any defects  therein  in  conformity with  the said  Documents  including Addenda thereto for the Total Bid Price of Rs.___________________/-(Rupees ______________________________________ ___________________________________________________________________ only)  or  such  other sum as may be ascertained in accordance with the said Documents.

- We understand that all the Schedules attached hereto form part of this Bid.

- As  security  for  due  performance  of  the  undertakings  and  obligations  of  this Bid,  we  submit  herewith  a  Bid  Security  in  the  amount  of  CD No._____________, Dated ___________________ drawn  in  your  favour or made  payable to you and valid for a period of  twenty eight (28) days beyond  the period of validity of Bid.

- We undertake, if our Bid is accepted, to commence the Works and to deliver and complete the Works comprised in the Contract within the time(s) stated in Contract Data.

- We  agree  to  abide  by  this Bid  for  the  period  of  (____)  days  from  the  date fixed  for  receiving  the same and  it shall  remain binding upon us and may be accepted at any time before the expiration of that period.

- Unless  and  until  a  formal  Agreement  is  prepared  and  executed,  this  Bid, together  with  your  written  acceptance  thereof,  shall  constitute  a  binding contract between us.

- We  undertake,  if  our  Bid  is  accepted,  to  execute  the  Performance  Security  referred to in Conditions of Contract for the due performance of the Contract.

- We understand that you are not bound to accept the lowest or any bid you may receive.

- We do hereby declare that the Bid is made without any collusion, comparison of figures or arrangement with any other person or persons making a bid for the Works.

Dated this __________________ of ________________.

Signature ________________

In  the  capacity  of  ______________________ duly  authorized  to  sign  bid  for  and  on  behalf  of (__________________________________________________________________)

(Name of Bidder in Block Capitals)

(Seal)

Address:

______________________________________________________________________________

WITNESS:

(Signature) _______________________

Name: _____________________________________________________

Address: ____________________________________________________________________

_____________________________________________________________________________

SCHEDULES TO BID INCLUDE THE FOLLOWING:

- Schedule A to Bid: Schedule of  Prices

- Schedule B to Bid: Specific Works Data

- Schedule C to Bid: Works to be Performed by Subcontractors

- Schedule D to Bid: Proposed Program of Works

- Schedule E to Bid: Method of Performing Works

- Schedule F to Bid: Integrity Pact]

SCHEDULE – A TO BID

SCHEDULE OF PRICES

Sr. No.  										Page No.

1.  	Preamble to Schedule of Prices…………..  					24

2.  	Schedule of Prices……………………….   					26

- Summary of Bid Prices

- Detailed Schedule of Prices /Bill of Quantities (BOQ)

* [To be prepared by the Engineer/Procuring Agency]

SCHEDULE - A TO BID

PREAMBLE TO SCHEDULE OF PRICES

1.  General

1.1  	The  Schedule  of  Prices  shall  be  read  in  conjunction  with  the Conditions of Contract, Contract Data together with the Specifications and Drawings, if any.

1.2  	The Contract shall be for the whole of the works as described in these Bidding Documents. Bids must be for the complete scope of works.

2.  Description

2.1  	The general directions and descriptions of works and materials are not necessarily repeated nor summarized in the Schedule of Prices. References  to  the relevant sections of the Bidding Documents shall be made  before  entering  prices  against  each  item  in  the  Schedule  of Prices.

3.  Units & Abbreviations

3.1  	Units  of  measurement,  symbols  and  abbreviations  expressed  in  the Bidding Documents  shall  comply with  the  System  International  d‘ Unites (SI Units).

______________________________

______________________________

(Note:  The  abbreviations  to  be  used  in  the  Schedule  of Prices  to  be defined by the Executive Engineer, Buildings Division Thatta).

4.  Rates and Prices

4.1  	Except  as  otherwise  expressly  provided  under  the  Conditions  of Contract, the rates and amounts entered in the Schedule of Prices shall be  the rates at which  the Contractor shall be paid and shall be  the full inclusive value of the works set forth or implied in the Contract; except for  the  amounts  reimbursable,  if  any  to  the  Contractor  under  the Contract.

4.2  	Unless  otherwise  stipulated  in  the Contract Data,  the  premium,  rates and  prices  entered  by  the  bidder  shall  not  be  subject  to  adjustment during the performance of the Contract.

4.3  	All  duties,  taxes  and  other  levies  payable  by  the Contractor  shall  be included in the rates and prices.

4.4  	The whole cost of complying with the provisions of the Contract shall be included in the items provided in the Schedule of Prices, and where SCHEDULE - A TO BID no  items  are  provided,  the  cost  shall  be  deemed  to  be  distributed among  the  rates and prices entered  for  the  related  items of  the Works and no separate payment will be made for those items.

The rates, prices and amounts shall be entered against each item in the Schedule of Prices. Any  item against which no rate or price is entered by  the  bidder  will  not  be  paid  for  by  the  Executive  Engineer, Buildings Division, Thatta  when executed and shall be deemed covered by the rates and prices for other items in the Schedule of Prices.

4.5

- The bidder shall be deemed to have obtained all information as to and all requirements related thereto which may affect the bid price.

- The Contractor shall be responsible to make complete arrangements for the transportation of the Plant to the Site.

*(Procuring Agency may modify as appropriate)

4.6  	The Contractor shall provide for all parts of the Works to be completed in every respect.  Notwithstanding  that  any  details,  accessories,  etc. required  for  the complete  installation and satisfactory operation of  the Works,  are  not  specifically  mentioned  in  the  Specifications,  such details shall be considered as included in the Contract Price.

5. 	Bid Prices

5.1. 	Break-up of Bid Prices

The various elements of Bid Prices shall be quoted as detailed by the Executive Engineer, Buildings Division, in the format of Schedule of Prices. The bidder shall recognize such elements of the costs which he expects to incur the performance of the Works and shall include all such costs in the rates and amounts entered in the Schedule of Prices.

5.2.	Total Bid Price

The total of bid prices in the Schedule of Prices shall be entered in the Summary of Bid Prices.

6.	Provisional Sums and Day work

6.1.	Provisional Sums included and so designated in the Schedule of Prices if  any,  shall  be  expended  in  whole  or  in  part  at  the  direction  and discretion of the Engineer/ Executive  Engineer, Buildings Division. The Contractor will only receive  payment  in  respect  of  Provisional  Sums,  if  he  has  been instructed by the Engineer/Procuring Agency to utilize such sums.

6.2     Day  work  rates  in  the  contractor‘s  bid  are  to  be  used  for  small additional  amounts  of work  and  only when  the  Engineer  have  given written  instructions  in  advance  for  additional work  to  be  paid  for  in that way.

SCHEDULE - A TO BID

| Bill No. | Description | Total Amount (Rs) |
| --- | --- | --- |
| 1 2 3 4 5 1 2 3 4 1 2 3 4 5 6 | (A) Building Work Civil works Internal sanitary and water supply Water Supply External Development works Miscellaneous Items (B) Road Work. Earthwork Hard Crust and Surface Treatment Culverts and Bridges Miscellaneous Items (C) Public Health Engineering Works. Earthwork Subsurface Drains Pipe Laying and Man holes Tube wells, Pump houses Compound wall Miscellaneous Items |  |
|  | Total Bid Price (The amount to be entered in Paragraph 1 of the Form of Bid) (In words). |  |

SCHEDULE A TO BID

SCHEDULE OF PRICES

| Sr # | Description | Qty | Unit Rate | Total |
| --- | --- | --- | --- | --- |
| 1 2 3 1 2 3 1 2 3 1 2 3 | I. (Civil works) II. Internal sanitary and water supply. III. Electrification. IV. External Development works. V. Miscellaneous It |  |  |  |
|  | Total (to be carried to Summary of Bid Price) Add/ Deduct the percentage quoted above/below on the prices of items based on Composite Schedule of Rat |  |  |  |

SCHEDULE - B TO BID

*SPECIFIC WORKS DATA

(To be prepared and incorporated by the Procuring Agency)

*(Note: The Executive Engineer, Buildings Division, shall spell out the information & data required to be filled out by the bidder and to furnish complementary information).

SCHEDULE – C TO BID

WORKS TO BE PERFORMED BY SUBCONTRACTORS*

The bidder will do the work with his own forces except the work listed below which he intends to sub-contract.

| Items of Works to be Sub-Contracted | Name and address of sub contractors | Statement of similar works previously executed. (attach evidence) |
| --- | --- | --- |

Note:

*  	The Executive Engineer, Buildings Division, should decide whether to allow subcontracting or not. In  case  Procuring  Agency  decides  to  allow  subcontracting  then  following conditions shall be complied with:

1.  	No  change  of  Sub-Contractors  shall  be  made  by  the  bidder  without  prior approval of the Executive  Engineer, Buildings Division.

2.  	The  truthfulness  and  accuracy  of  the  statement  as  to  the  experience  of Sub-Contractors  is  guaranteed  by  the  bidder.  The  Procuring Agency‘s  judgment shall  be  final  as  to  the  evaluation  of  the  experience  of  Sub-Contractors submitted by the bidder.

3.  	Statement  of  similar  works  shall  include  description,  location  &  value  of works, year completed and name & address of the clients.

SCHEDULE – D TO BID

PROPOSED PROGRAMME OF WORKS

Bidder  shall  provide  a  programme  in  a  bar-chart  or  Program  Evaluation  and  Review Technique  (PERT) or Critical Path Method  (CPM)  showing  the  sequence of work  items by which  he  proposes  to  complete  the  works  of  the  entire  Contract.  The  programme  should indicate  the  sequence  of work  items  and  the  period  of  time  during which  he  proposes  to complete the works including the activities like designing, schedule of submittal of drawings, ordering  and  procurement  of  materials,  manufacturing,  delivering,  construction  of  civil works, erection, testing and commissioning of works to be supplied under the Contract.

SCHEDULE – E TO BID

METHOD OF PERFORMING WORKS

- The bidder is required to submit a narrative outlining the method of performing the Works. The narrative should indicate in detail and include but not be limited to:

- The sequence and methods in which he proposes to carry out the Works, including the number of shifts per day and hours per shift, he expects to work.

(______________________________________________)

- A  list  of  all  major  items  of  construction  and  plant  erection,  tools  and  vehicles proposed to be used in delivering/carrying out the works at site.

(List attached)

- The procedure for installation of equipment and transportation of equipment and materials to the site.

(By own Names as per list at above)

- Organization  chart  indicating  head  office  &  field  office  personnel  involved  in management,  supervision  and  engineering  of  the  Works  to  be  done  under  the Contract.

(Supervision attached)

SCHEDULE – F TO BID

(INTEGRITY PACT)

DECLARATION OF FEES, COMMISSION AND BROKERAGE ETC

PAYABLE BY CONTRACTORS

(FOR CONTRACTS WORTH RS. 10.00 MILLION OR MORE)

Contract No. 	 Dated

Contract Value: __________________________

Contract Title: CONSTRUCTION OF THE STAFF FLATS (PAIR) FROUND FLOOR + 2 FLOORS AND IMPROVEMENT/ADDITION OF DC CAMP OFFICE AT OFFICERS COLONY OF WORKS & SERVICES DEPARTMENT THATTA @ MAKLI.

_____________________________ name of Contractor] hereby declares that it has not obtained or  induced  the  procurement  of  any  contract,  right,  interest, privilege or other obligation or benefit from Government of Sindh (GoS) or any administrative subdivision or agency thereof or any other entity owned or controlled by it (GoS) through any corrupt business practice.

Without  limiting  the  generality  of  the  foregoing,  [name  of  Contractor]  represents  and warrants  that  it has  fully declared  the brokerage, commission,  fees etc. paid or payable  to anyone and not given or agreed to give and shall not give or agree to give to anyone within or  outside  Pakistan  either  directly  or  indirectly  through  any  natural  or  juridical  person, including  its  affiliate,  agent,  associate, broker,  consultant, director, promoter,  shareholder, sponsor  or  subsidiary,  any  commission,  gratification,  bribe,  finder‘s  fee  or  kickback, whether described as consultation fee or otherwise, with the object of obtaining or inducing the  procurement  of  a  contract,  right,  interest,  privilege  or  other  obligation  or  benefit  in whatsoever form from, from Executive  Engineer, Buildings Division, (PA)   except that which has been expressly declared pursuant hereto.

__________________________ accepts  full  responsibility and strict  liability  that  it has made and will make  full  disclosure  of  all  agreements  and  arrangements with  all  persons  in  respect  of  or related to the transaction with PA and has not taken any action or will not take any action to circumvent the above declaration, representation or warranty.

__________________________  accepts  full  responsibility  and  strict  liability  for  making  any  false declaration, not making  full disclosure, misrepresenting  facts or  taking any action  likely  to defeat  the  purpose  of  this  declaration,  representation  and  warranty.  It  agrees  that  any contract,  right,  interest,  privilege  or  other  obligation  or  benefit  obtained  or  procured  as aforesaid shall, without prejudice to any other rights and remedies available to PA under any law, contract or other instrument, be voidable at the option of PA.

Notwithstanding  any  rights  and  remedies  exercised  by  PA  in  this  regard,  [name  of Supplier/Contractor/Consultant] agrees  to  indemnify PA for any  loss or damage incurred by it  on  account  of  its  corrupt  business  practices  and  further  pay  compensation  to  PA  in  an amount equivalent to ten time the sum of any commission, gratification, bribe, finder‘s fee or kickback given by ________________________ as aforesaid for the purpose of obtaining or inducing the  procurement  of  any  contract,  right,  interest,  privilege  or  other  obligation  or  benefit  in whatsoever form from PA.

………………………

[Executive Engineer]                                               Contractor

Signature ____________________

Name________________________

CONDITIONS OF CONTRACT

TABLE OF CONTENTS

CONDITIONS OF CONTRACT

Clause No    		Description  						Page No

- General Provisions……………………………………………………...  	35

- The Procuring Agency…………………………………………………  	37

- Engineer‘s/Procuring Agency‘s Representatives……………………  	37

- The Contractor…………………………………………………………  	38

- Design by Contractor…………………………………………….…….  	38

- Procuring Agency‘s Risks………………………………………………  	39

- Time for Completion…………………………………………………... 	40

- Taking Over……………………………………………………………. 	41

- Remedying Defects…………………………………………………….  	41

- Variations and Claims………………….……………………………… 	41

- Contract Price And Payment…………………………………………... 	43

- Default…………………………………………………………………  	44

- Risks and Responsibilities……………………………………….…….. 	46

- Insurance……………………………………………………………….  	46

- Resolution of Disputes………………………………………………… 	47

- Integrity Pact…………………………………………………………… 	48

CONDITIONS OF CONTRACT

1.  GENERAL PROVISIONS

1.1  Definitions

In the Contract as defined below, the words and expressions defined shall have the following meanings assigned to them, except where the context requires otherwise:

The Contract

1.1.1  ―Contract means  the Contract Agreement and  the other documents  listed  in  the contract data.

1.1.2  ―Specifications  means  the  document  as  listed  in  the  Contract  Data,  including

Executive Engineer, Buildings Division Thatta  requirements  in  respect  of  design  to  be  carried  out  by  the Contractor (if any), and any Variation to such document.

1.1.3  ―Drawings means the Executive Engineer, Buildings Division Thatta  drawings of the Works as listed in the Contract Data, and any Variation to such drawings.

Persons

1.1.4  	Executive Engineer, Buildings Division Thatta  means  the person named  in  the Contract Data and  the  legal successors  in  title  to  this  person,  but  not  (except  with  the  consent  of  the Contractor) any assignee.

1.1.5 	Contractor  means  the  person  named  in  the  Contract  Data  and  the  legal successors in title to this person, but not (except with the consent of the Procuring Agency) any assignee.

1.1.6 	Party means either the Executive Engineer, Buildings Division Thatta or the Contractor.

Dates, Times and Periods

1.1.7  	Commencement  Date  means  the  date  fourteen  (14)  days  after  the  date  the Contract comes into effect or any other date named in the Contract Data.

1.1.8  	Day means a calendar day

1.1.9  	Time for Completion means the time for completing the Works as stated in the Contract  Data  (or  as  extended  under  Sub-Clause  7.3),  calculated  from  the Commencement Date.

Money and Payments

1.1.10 Cost  means  all  expenditure  properly  incurred  (or  to  be  incurred)  by  the Contractor, whether on or off the Site, including overheads and similar charges but  does not include any allowance for profit.

Other Definitions

1.1.11  	Contractor‘s  Equipment  means  all  machinery,  apparatus  and  other  things required  for  the  execution of  the Works but does not  include Materials or Plant intended to form part of the Works.

1.1.12  	Country means the Islamic Republic of Pakistan.

1.1.13  	Procuring Agency‘s Risks means those matters listed in Sub-Clause 6.1.

1.1.14  	Force Majeure means an event or circumstance which makes performance of a

Party‘s  obligations  illegal  or  impracticable  and  which  is  beyond  that  Party‘s reasonable control.

1.1.15  	Materials means  things  of  all  kinds  (other  than  Plant)  to  be  supplied  and incorporated in the Works by the Contractor.

1.1.16  	Plant means the machinery and apparatus intended to form or forming part of the Works.

1.1.17  	Site means the places provided by the Executive Engineer, Buildings Division Thatta where the Works are to be executed, and any other places specified in the Contract as forming part of the Site.

1.1.18  	Variation means a change which is instructed by the Engineer/ Executive Engineer, Buildings Division Thatta under Sub-Clause 10.1.

1.1.19  ‗	Works means  any  or  all  the works whether  Supply,  Installation, Construction etc.  and  design  (if  any)  to  be  performed  by  the Contractor  including  temporary works and any variation thereof.

1.1.20  	Engineer means the person notified by the Executive Engineer, Buildings Division Thatta to act as Engineer for the purpose of the Contract and named as such in Contract Data.

1.2.	Interpretation

Words importing persons or parties shall include firms and organizations. Words importing singular or one gender shall include plural or the other gender where the context requires.

1.3 	Priority of Documents

The documents forming the Contract are to be taken as mutually explanatory of one another. If an ambiguity or discrepancy is found in the documents, the priority of the documents shall be in accordance with the order as listed in the Contract Data.

1.4  Law

The law of the Contract is the relevant Law of Islamic Republic of Pakistan.

1.5  Communications

All Communications related to the Contract shall be in English language.

1.6  Statutory Obligations

The Contractor  shall comply with  the Laws of  Islamic Republic of Pakistan and shall give all notices and pay all fees and other charges in respect of the Works.

2.  THE PROCURING AGENCY

2.1  Provision of Site

The Executive Engineer, Buildings Division Thatta shall provide the Site and right of access thereto at the times stated in the Contract Data.  Site Investigation Reports are those that were included in the bidding documents and  are  factual  and  interpretative  reports  about  the  surface  and  subsurface conditions at the Site.

2.2  Permits etc.

The Executive Engineer, Buildings Division Thatta   shall, if requested by the Contractor, assist him in applying for permits, licenses or approvals which are required for the Works.

2.3  Engineer’s/Procuring Agency’s Instructions

The Contractor shall comply with all instructions given by the Procuring Agency or the Engineer, if notified by the Executive Engineer, Buildings Division Thatta , in respect of the Works including the suspension of all or part of the works.

2.4  Approvals

No approval or consent or absence of comment by the Engineer/ Executive Engineer, Buildings Division Thatta shall affect the Contractor‘s obligations.

3.  ENGINEER’S/PROCURING AGENCY’S REPRESENTATIVES

3.1  Authorized Person

The Executive Engineer, Buildings Division Thatta shall appoint a duly authorized person to act for him and on his behalf for the purposes of this Contract. Such authorized person shall be duly identified in the Contract Data or otherwise notified in writing to the Contractor as soon as he is so appointed.  In either case the Procuring Agency shall notify the Contractor, in writing, the precise scope of the authority of such authorized person at the time of his appointment.

3.2	Engineer’s/ Executive Engineer, Buildings Division Thatta  Representative  The name and address of Engineer‘s/ Executive Engineer, Buildings Division Thatta Representative  is given in  Contract  Data.  However  the  Contractor  shall  be  notified  by  the Engineer/ Executive Engineer, Buildings Division Thatta,  the  delegated  duties  and  authority  before  the Commencement of works.

4.  THE CONTRACTOR

  - General Obligations

The  Contractor  shall  carry  out  the  works  properly  and  in  accordance  with  the Contract.  The Contractor shall provide all supervision, labour, Materials, Plant and Contractor‘s Equipment which may be required

4.2  Contractor’s Representative

The Contractor shall appoint a representative at site on full time basis to supervise the execution of work and  to receive  instructions on behalf of  the Contractor but only  after  obtaining  the  consent  of  the  Executive Engineer, Buildings Division Thatta  for  such  appointment which consent shall not be withheld without plausible reason(s) by  the Executive Engineer, Buildings Division Thatta.  Such  authorized  representative  may  be  substituted/  replaced  by  the Contractor  at  any  time  during  the  Contract  Period  but  only  after  obtaining  the consent of the Procuring Agency as aforesaid.

4.3  Subcontracting

The Contractor shall not subcontract the whole of the works. The Contractor shall not  subcontract  any  part  of  the  works  without  the  consent  of  the  Executive Engineer, Buildings Division Thatta.

4.4  Performance Security

The Contractor  shall  furnish  to  the  Procuring Agency within  fourteen  (14)  days after  receipt of Letter of Acceptance a Performance Security at  the option of  the bidder,  in  the  form  of  Payee‘s  order  /Bank  Draft  or  Bank  Guarantee  from scheduled bank for the amount and validity specified in Contract Data.

5.  DESIGN BY CONTRACTOR

5.1  Contractor’s Design

The Contractor shall carry out design to the extent specified, as referred to in the Contract Data.  The Contractor  shall  promptly  submit  to  the Engineer/ Executive Engineer, Buildings Division Thatta  all  designs  prepared  by  him,  within  fourteen  (14)  days  of  receipt  the Engineer/ Executive Engineer, Buildings Division Thatta shall notify any comments or, if the design submitted is  not  in  accordance  with  the  Contract,  shall  reject  it  stating  the  reasons.  The  Contractor  shall not  construct  any element of  the works designed by him within fourteen  (14) days after  the design has been submitted  to  the Engineer/ Executive Engineer, Buildings Division Thatta  or  which  has  been  rejected.  Design that has been rejected shall be promptly amended and re-submitted.  The Contractor shall resubmit all designs commented on taking these comments into account as necessary.

5.2  Responsibility for Design

The Contractor shall remain responsible for his bided design and the design under this Clause,  both  of which  shall  be  fit  for  the  intended  purposes  defined  in  the Contract and he shall also remain responsible for any infringement of any patent or copyright  in  respect  of  the  same.  The Engineer/ Executive Engineer, Buildings Division Thatta shall be responsible for the Specifications and Drawings.

6.  PROCURING AGENCY’S RISKS

6.1  The Executive Engineer, Buildings Division Thatta  Risks

The Executive Engineer, Buildings Division Thatta   Risks are:-

- War,  hostilities  (whether  war  be  declared  or  not),  invasion,  act  of  foreign enemies, within the Country;

- Rebellion, terrorism, revolution, insurrection, military or usurped power or civil war, within the Country;

- Riot, commotion or disorder by persons other than the Contractor‘s personnel and other employees including the personnel and employees of Sub-Contractors, affecting the Site and/or the Works;

- Ionizing  radiations, or contamination by radio-activity from any nuclear fuel, or from any nuclear waste from the combustion of nuclear fuel, radio-active toxic explosive,  or  other  hazardous  properties  of  any  explosive  nuclear assembly or nuclear component of such an assembly, except to the extent to which the Contractor/Sub-Contractors may be responsible for the use of any radio-active material;

- Pressure waves caused by aircraft or other aerial devices traveling at sonic or supersonic speeds;

- Use or occupation by the Executive Engineer, Buildings Division Thatta  of any part of the Works, except as may be specified in the Contract;

- Late  handing  over  of  sites,  anomalies  in  drawings,  late  delivery  of  designs and drawings of any part of the Works by the Procuring Agency‘s personnel or by others for whom the Procuring Agency is responsible;

- A  suspension  under  Sub-Clause  2.3  unless  it  is  attributable  to  the Contractor‘s failure; and  Physical  obstructions or physical  conditions other  than  climatic  conditions, encountered on the Site during the performance of the Works, for which the Contractor  immediately  notified  to  the  Executive Engineer, Buildings Division Thatta  and  accepted  by the Procuring Agency.

7.	TIME FOR COMPLETION

7.1	Execution of the Works

The Contractor shall commence the Works on the Commencement Date and shall proceed expeditiously and without delay and shall complete the Works, subject to Sub-Clause 7.3 below, within the Time for Completion.

7.2  Programme

Within  the  time  stated  in  the Contract Data,  the Contractor  shall  submit  to  the Engineer/ Executive Engineer, Buildings Division Thatta  a programme for  the Works  in  the form stated  in  the Contract Data.

7.3  Extension of Time

The  Contractor  shall,  within  such  time  as  may  be  reasonable  under  the circumstances,  notify  the  Executive Engineer, Buildings Division Thatta/Engineer  of  any  event(s)  falling within  the  scope of Sub-Clause 6.1 or 10.3 of  these Conditions of Contract  and request  the Executive Engineer, Buildings Division Thatta/Engineer for a reasonable extension  in  the time for the completion of works. Subject to the aforesaid, the Executive Engineer, Buildings Division Thatta/Engineer shall determine such reasonable extension in the time for the completion of works as may be justified in the light of the details/particulars supplied by the Contractor in  connection  with  the such determination  by  the  Executive Engineer, Buildings Division Thatta/Engineer within such period as may be prescribed by the Executive Engineer, Buildings Division Thatta /Engineer for the same; and  the  Procuring  Agency  may  extend  the  time  for  completion  as determined.

7.4  Late Completion

If the Contractor fails to complete the Works within the Time for Completion, the Contractor‘s only liability to the Executive Engineer, Buildings Division Thatta  for such failure shall be to pay the  amount  as  liquidity  damages  stated  in  the  Contract Data  for  each  day  for which he fails to complete the Works.

8.  TAKING-OVER

8.1  Completion

The Contractor may notify the Engineer/ Executive Engineer, Buildings Division Thatta  when he considers that the Works are complete.

8.2  Taking-Over Notice

Within fourteen (14) days of the receipt of the said notice of completion from the Contractor  the  Executive Engineer, Buildings Division Thatta/Engineer  shall  either  takeover  the  completed works  and  issue  a  Certificate  of  Completion  to  that  effect  or  shall  notify  the Contractor his reasons for not taking-over the works. While issuing the Certificate of  Completion  as  aforesaid,  the  Executive Engineer, Buildings Division Thatta/Engineer  may  identify  any outstanding  items  of  work  which  the  Contractor  shall  undertake  during  the Maintenances Period.

9.  REMEDYING DEFECTS

9.1  Remedying Defects

The Contractor shall for a period stated in the Contract Data from the date of issue of  the Certificate  of Completion  carry  out,  at  no  cost  to  the  Executive Engineer, Buildings Division Thatta, repair and rectification work which is necessitated by the earlier execution of poor quality of work or use of below specifications material in the execution of Works and which is so identified by the Executive Engineer, Buildings Division Thatta/Engineer in writing within the said  period.  Upon  expiry  of  the  said  period,  and  subject  to  the  Contractor‘s faithfully  performing  his  aforesaid  obligations,  the  Executive Engineer, Buildings Division Thatta/Engineer shall  issue a Maintenance Certificate whereupon all obligations of  the Contractor under this Contract shall come to an end.

Failure  to  remedy  any  such  defects  or  complete  outstanding  work  within  a reasonable time shall entitle the Executive Engineer, Buildings Division Thatta  to carry out all necessary works at the Contractor‘s cost. However, the cost of remedying defects not attributable to the Contractor shall be valued as a Variation.

9.2  Uncovering and Testing

The Engineer/ Executive Engineer, Buildings Division Thatta may give instruction as to the uncovering and/or testing of any work.  Unless  as  a  result  of  an  uncovering  and/or  testing  it  is established  that  the Contractor‘s design, materials, plant or workmanship are not in accordance with the Contract, the Contractor shall be paid for such uncovering and/or testing as a Variation in accordance with Sub-Clause 10.2.

10.  VARIATIONS AND CLAIMS

10.1  Right to Vary

The Procuring Agency/Engineer may issue Variation Order(s) in writing. Where for any reason it has not been possible for the Executive Engineer, Buildings Division Thatta/Engineer to issue such Variations Order(s),  the Contractor may confirm any verbal orders given by the Executive Engineer, Buildings Division Thatta/Engineer  in writing and  if  the same are not  refuted/denied by  the  Executive Engineer, Buildings Division Thatta/Engineer  within  ten  (10)  days  of  the  receipt  of  such confirmation  the same shall be deemed to be a Variation Orders for  the purposes of this Sub-Clause.

10.2.  Valuation of Variations

Variations shall be valued as follows:

- At a lump sum price agreed between the Parties, or

- Where appropriate, at rates in the Contract, or

- In the absence of appropriate rates, the rates in the Contract shall be used as the basis for valuation, or failing which at  appropriate  new  rates,  as  may  be  agreed  or  which  the Engineer/ Executive Engineer, Buildings Division Thatta  considers appropriate, or.

- If  the Engineer/ Executive Engineer, Buildings Division Thatta  so  instructs, at day work rates set out in the Contract Data for which the Contractor shall keep records of hours of labour and Contractor‘s Equipment, and of Materials, used.

10.3   	Changes in the Quantities.

- If  the final quantity of  the work done differs from  the quantity  in  the Bill of  Quantities for the particular item by more than 25 percent, provided the change  exceeds  1  percent  of  the  Initial  Contract  Price,  the  Executive Engineer, Buildings Division Thatta/Engineer shall adjust  the rate  to allow for  the change and will be valued as per  sub clause 10.2.

- The Engineer  shall  not  adjust  rates  from  changes  in  quantities  if  thereby the Initial Contract Price is exceeded by more than 15 percent, except with the prior approval of the Procuring Agency.

- If requested by the Engineer, the contractor shall provide the Engineer with a detailed cost breakdown of any rate in the Bill of Quantities.

10.4  Early Warning

The Contractor shall notify the Engineer/ Executive Engineer, Buildings Division Thatta in writing as soon as he is aware of any circumstance which may delay or disrupt the Works, or which may give rise to a claim for additional payment.

To  the  extent  of  the  Contractor‘s  failure  to  notify,  which  results  to  the Engineer/ Executive Engineer, Buildings Division Thatta  being unable to keep all relevant records or not taking steps to minimize any delay, disruption, or Cost, or the value of any Variation, the Contractor‘s  entitlement  to  extension  of  the  Time  for Completion  or  additional payment shall be reduced/rejected.

10.5  Valuation of Claims

If the Contractor incurs Cost as a result of any of the Executive Engineer, Buildings Division Thatta   Risks, the Contractor shall be entitled to the amount of such Cost.  If as a result of any Procuring Agency‘s Risk, it is necessary to change the Works, this shall be dealt with as a Variation subject to Contractor‘s notification for intention of claim to the Engineer/ Executive Engineer, Buildings Division Thatta within fourteen (14) days of the occurrence of cause.

10.6  Variation and Claim Procedure

The  Contractor  shall  submit  to  the  Engineer/ Executive Engineer, Buildings Division Thatta  an  itemized detailed breakdown of the value of variations and claims within twenty eight (28) days  of  the  instruction  or  of  the  event  giving  rise  to  the  claim.  The Engineer/Procuring Agency shall check and if possible agree the value. In the absence of agreement, the Procuring Agency shall determine the value.

11.  CONTRACT PRICE AND PAYMENT

11.1  (a)  Terms of Payments

The amount due to the Contractor under any Interim Payment Certificate issued by  the Engineer pursuant  to  this Clause, or  to any other  terms of the Contract,  shall  ,  subject    to Clause  11.3,  be  paid  by  the  Executive Engineer, Buildings Division Thatta  to  the  Contractor within  30  days  after  such  Interim  Payment Certificate has been jointly verified by Executive Engineer, Buildings Division Thatta  and Contractor, or,  in  the  case  of  the  Final Certificate  referred  to  in  Sub Clause  11.5, within  60days  after  such  Final  Payment  Certificate  has  been  jointly verified by Procuring Agency and Contractor;

Provided that the Interim Payment shall be caused in thirty (30) days and Final Payment in 60 days in case of foreign funded project.  In the event of  the failure of  the Procuring Agency  to make payment within 90 days then Executive Engineer, Buildings Division Thatta  shall pay  to  the Contractor compensation at  the 28 days rate of KIBOR+2% per annum in local currency and LIBOR+1% for  foreign  currency, upon  all  sums unpaid  from  the date by which  the

same should have been paid.

(b)  Valuation of the Works

The Works shall be valued as provided for in the Contract Data, subject to Clause 10.

11.2  Monthly Statements

The Contractor shall be entitled to be paid at monthly intervals:

a)  	the  value  of  the Works  executed  less  to  the  cumulative  amount  paid   previously; and

b)  	Value of secured advance on the materials and valuation of variations (if any).

The Contractor shall submit each month to the Engineer/ Executive Engineer, Buildings Division Thatta  a statement showing the amounts to which he considers himself entitled.

11.3  Interim Payments

Within a period not exceeding  seven  (07) days  from  the date of submission of a statement  for  interim  payment  by  the  Contractor,  the  Engineer  shall  verify  the same and within a period not exceeding  thirty (30/60) days from  the said date of submission  by  the Contractor,  the Executive Engineer, Buildings Division Thatta  shall pay  to  the Contractor the sum subject to adjustment for deduction of the advance payments and retention money.

11.4  Retention

Retention money shall be paid by  the Executive Engineer, Buildings Division Thatta  to  the Contractor within fourteen (14) days after either the expiry of the period stated in the Contract Data, or the remedying of notified defects, or the completion of outstanding work, all as referred to in Sub-Clause 9.1, whichever is the later.

11.5  Final Payment

Within  twenty  one  (21)  days  from  the  date  of  issuance  of  the  Maintenance Certificate the Contractor shall submit a final account to the Engineer to verify and the  Engineer  shall  verify  the  same  within  fourteen  (14)  days  from  the  date  of submission  and  forward  the  same  to  the  Executive Engineer, Buildings Division Thatta  together  with  any documentation  reasonably  required  to  enable  the  Executive Engineer, Buildings Division Thatta  to  ascertain the final contract value.

Within sixty (60) days from the date of receipt of the verified final account from the Engineer, the Executive Engineer, Buildings Division Thatta shall pay to the Contractor any amount due to the Contractor.  While making such payment the Executive Engineer, Buildings Division Thatta may, for reasons to be given to the Contractor in writing, withhold any part or parts of the verified amount.

11.6  Currency

Payment shall be in the currency stated in the Contract Data.

12.  DEFAULT

12.1  Defaults by Contractor

If  the  Contractor  abandons  the Works,  refuses  or  fails  to  comply  with  a  valid instruction of the Engineer/ Executive Engineer, Buildings Division Thatta  or fails to proceed expeditiously and without  delay,  or  is,  despite  a written  complaint,  in  breach  of  the Contract,  the Procuring Agency may  give  notice  referring  to  this  Sub-Clause  and  stating  the default.

If  the Contractor has not  taken all practicable  steps  to  remedy  the default within fourteen  (14)  days  after  receipt  of  the Executive Engineer, Buildings Division Thatta  notice,  the Executive Engineer, Buildings Division Thatta  may  by  a  second  notice  given  within  a  further  twenty  one  (21)  days, terminate the Contract. The Contractor shall then demobilize from the Site leaving behind any Contractor‘s Equipment which the Executive Engineer, Buildings Division Thatta instructs, in the second notice, to be used for the completion of the Works at the risk and cost of the Contractor.

12.2.  Defaults by Executive Engineer, Buildings Division Thatta

If the Executive Engineer, Buildings Division Thatta  fails to pay in accordance with the Contract, or is, despite a written  complaint,  in  breach  of  the  Contract,  the  Contractor may  give  notice referring  to  this Sub-Clause and stating  the default. If the default is not remedied within fourteen (14) days after the Executive Engineer, Buildings Division Thatta receipt of this notice, the Contractor may suspend the execution of all or parts of the Works.

If  the  default  is  not  remedied within  twenty  eight  (28)  days  after  the  Executive Engineer, Buildings Division Thatta  receipt  of  the  Contractor‘s  notice,  the  Contractor  may  by  a  second  notice  given within  a  further  twenty  one  (21)  days,  terminate  the Contract. The Contractor shall then demobilize from the Site.

12.3  Insolvency

If a Party  is declared  insolvent under any applicable  law,  the other Party may by notice  terminate  the Contract  immediately. The Contractor  shall  then demobilize from  the  site  leaving  behind,  in  the  case  of  the  Contractor‘s  insolvency,  any Contractor‘s Equipment which  the Executive Engineer, Buildings Division Thatta  instructs  in  the notice  is  to be used for the completion of the Works.

12.4  Payment upon Termination

After  termination,  the  Contractor  shall  be  entitled  to  payment  of  the  unpaid balance  of  the  value  of  the  works  executed  and  of  the  Materials  and  Plant reasonably delivered to the site, adjusted by the following:

a)  	Any sums to which the Contractor is entitled under Sub-Clause 10.4,

b)  	Any sums to which the Executive Engineer, Buildings Division Thatta is entitled,

c)  	If the Executive Engineer, Buildings Division Thatta  has terminated under Sub-Clause 12.1 or 12.3, the Executive Engineer, Buildings Division Thatta  shall be entitled  to a  sum equivalent  to  twenty percent (20%) of  the value of parts of  the Works not  executed at  the date of  the termination, and

d)  	If  the  Contractor  has  terminated  under  Sub-Clause  12.2  or  12.3,  the  Contractor shall be entitled to the cost of his demobilization  together with a  sum  equivalent  to  ten percent  (10%) of  the value of parts of  the works not executed at the date of termination.

The net balance due shall be paid or repaid within twenty eight (28) days of the notice of termination.

13.  RISKS AND RESPONSIBILITIES

13.1  Contractor’s Care of the Works

Subject to Sub-Clause 9.1, the Contractor shall take full responsibility for the care  of  the  Works  from  the  Commencement  Date  until  the  date  of  the  Executive Engineer, Buildings Division Thatta /Engineer‘s issuance of Certificate of Completion under Sub-Clause 8.2. Responsibility shall then pass to the Procuring Agency.  If  any  loss  or  damage happens  to  the Works during  the  above period,  the Contractor  shall  rectify  such loss or damage so that the Works conform with the Contract.

Unless the loss or damage happens as a result of any of the Executive Engineer, Buildings Division Thatta Risks, the Contractor shall indemnify the Executive Engineer, Buildings Division Thatta, or his agents against all claims loss, damage and expense arising out of the Works.

13.2  Force Majeure

If  Force  Majeure  occurs,  the  Contractor  shall  notify  the  Engineer/ Executive Engineer, Buildings Division Thatta  immediately.  If  necessary,  the Contractor may  suspend  the  execution of the Works  and,  to  the  extent  agreed with  the  Procuring Agency  demobilize  the Contractor‘s Equipment.

If the event continues for a period of eighty four (84) days, either Party may then give notice of termination which shall take effect twenty eight (28) days after the giving of the notice.

After  termination,  the  Contractor  shall  be  entitled  to  payment  of  the  unpaid balance  of  the  value  of  the  Works  executed  and  of  the  Materials  and  Plant reasonably delivered to the Site, adjusted by the following:

a)  	Any sums to which the Contractor is entitled under Sub-Clause 10.4,

b)  	The cost of his demobilization, and

c)  	Less any sums to which the Procuring Agency is entitled.

The  net  balance  due  shall  be  paid  or  repaid within  thirty  five  (35)  days  of  the notice of termination.

14.  INSURANCE

14.1  Arrangements

The  Contractor  shall,  prior  to  commencing  the Works,  effect  insurances  of  the types, in the amounts and naming as insured the persons stipulated in the Contract Data except for items (a) to (e) and (i) of the Executive Engineer, Buildings Division Thatta  Risks under Sub-Clause 6.1. The policies shall be issued by insurers and in terms approved by the Procuring Agency. The Contractor shall provide the Engineer/ Executive Engineer, Buildings Division Thatta with evidence that any required policy is in force and that the premiums have been paid.

14.2  Default

If the Contractor fails to effect or keep in force any of the insurances referred to in the  previous  Sub-Clause,  or  fails  to  provide  satisfactory  evidence,  policies  or receipts,  the  Procuring  Agency  may,  without  prejudice  to  any  other  right  or  remedy,  effect  insurance  for  the  cover  relevant  to  such  as  a  default  and  pay  the premiums due and recover the same plus a sum in percentage given in Contractor Data from any other amounts due to the Contractor.

15.  RESOLUTION OF DISPUTES

15.1  Engineer’s Decision

If a dispute of any kind whatsoever arises between  the Executive Engineer, Buildings Division Thatta  and the Contractor  in  connection with  the works,  the matter  in dispute  shall,  in  the  first place, be referred  in writing  to  the Engineer, with a copy to the other party. Such reference  shall  state  that  it  is  made  pursuant  to  this  Clause.  No  later  than  the twenty  eight  (28)  days  after  the  day  on  which  he  received  such  reference,  the Engineer  shall  give  notice  of  his  decision  to  the  Executive Engineer, Buildings Division Thatta  (Superintending Engineer) and the Contractor. Unless  the  Contract  has  already  been  repudiated  or  terminated,  the  Contractor shall, in every case, continue to proceed with the work with all due diligence, and the  Contractor  and  the  Executive Engineer, Buildings Division Thatta  (Superintending  Engineer)shall  give effect  forthwith  to every such decision of  the Engineer unless and until  the same shall be revised, as hereinafter provided in an arbitral award.

15.2  Notice of Dissatisfaction

If  a Party  is dissatisfied with  the decision of  the Engineer of consultant or  if no decision is given within the time set out in Sub-Clause 15.1 here above, the Party may give notice of dissatisfaction referring to this Sub-Clause within fourteen (14) days  of  receipt  of  the  decision  or  the  expiry  of  the  time  for  the  decision.  If  no notice  of  dissatisfaction  is given within  the  specified  time,  the decision  shall be final  and  binding  on  the  Parties.  If  notice  of  dissatisfaction  is  given within  the specified time, the decision shall be binding on the Parties who shall give effect to it without  delay  unless  and  until  the  decision  of  the  Engineer  is  revised  by  an arbitrator.

If a contractor  is dissatisfied with  the decision of  the Engineer of  the department or  decision  is  not  given  in  time  then  he  can  approach  Superintending Engineer within 14 days, in case of dissatisfaction with decision of Superintending Engineer or not decided within 28 days,  then arbitration process would be  adopted as per clause 15.3.

15.3  Arbitration

A dispute which has been the subject of a notice of dissatisfaction shall be finally settled as per provisions of Arbitration Act 1940 (Act No. X of 1940) and Rules made  there  under  and  any  statutory modifications  thereto. Any  hearing  shall  be held at  the place specified in  the Contract Data and in the language referred to in Sub-Clause 1.5.

16  INTEGRITY PACT

16.1   	If the Contractor or any of his Sub-Contractors, agents or servants is found to have violated or involved in violation of the Integrity Pact signed by the Contractor as Schedule-F to his Bid, then the Procuring Agency shall be entitled to:

(a)   	Recover  from  the Contractor  an  amount  equivalent  to  ten  times  the  sum of any  commission,  gratification,  bribe,  finder‘s  fee  or  kickback  given  by  the Contractor or any of his Sub-Contractors, agents or servants;

(b)   	Terminate the Contract; and

(c)      	Recover from the Contractor any loss or damage to the Executive Engineer, Buildings Division Thatta   as a result of such termination or of any other corrupt business practices of the Contractor or any of his Sub-Contractors, agents or servants.

On  termination  of  the  Contract  under  Sub-Para  (b)  of  this  Sub-Clause,  the Contractor shall demobilize from  the site  leaving behind Contractor‘s Equipment which the Procuring Agency instructs, in the termination notice, to be used for the completion of the works at the risk and cost of the Contractor. Payment upon such termination shall be made under Sub-Clause 12.4, in accordance with Sub-Para (c) thereof,  after  having  deducted  the  amounts  due  to  the  Executive Engineer, Buildings Division Thatta  under Sub-Para (a) and (c) of this Sub-Clause.

CONTRACT DATA

(Note:  Except  where  otherwise  indicated,  all  Contract  Data  should  be  filled  in  by  the Executive Engineer, Buildings Division Thatta  prior to issuance of the Bidding Documents.)

Sub-Clauses of

Conditions of Contract

1.1.3  Executive Engineer, Buildings Division Thatta   Drawings, if any

(To be listed by the Executive Engineer, Buildings Division Thatta)

1.1.4  The Procuring Agency means

Executive Engineer, Buildings Division Thatta

1.1.5  The Contractor means

_________________________

1.1.7  Commencement Date means  the  date  of  issue  of Engineer‘s Notice  to Commence which  shall  be  issued  within  fourteen  (14)  days  of  the  signing  of  the  Contract Agreement.

1.1.9  Time for Completion  24 - Months.

(The  time  for  completion  of  the  whole  of  the  Works  should  be  assessed  by  the

Executive Engineer, Buildings Division Thatta)

1.1.20  Engineer (mention the name along with the designation including whether he

belongs to department or consultant) and other details

Executive Engineer, Buildings Division Thatta.

1.3  Documents forming the Contract listed in the order of priority:

(a)  The Contract Agreement

(b)  Letter of Acceptance

(c)  The completed Form of Bid

(d)  Contract Data

(e)  Conditions of Contract

(f)  The completed Schedules to Bid including Schedule of Prices

(g)  The Drawings, if any

(h)  The Specifications

(i)  ___________________

(j)  ___________________

(The Executive Engineer, Buildings Division Thatta may add,  in order of priority, such other documents as  form part of  the Contract. Delete the document, if not applicable)

2.1   Provision of Site: On the Commencement Date

3.1   Authorized person: Assistant Engineer Building Sub-Division Thatta.

3.2   Name and address of Engineer’s/ Executive Engineer, Buildings Division Thatta representative Mr. _________________________________________________________ Assistant Engineer Building Sub-Division Thatta.

4.4   Performance Security:

Amount: Security Deposit 4%

Validity_________________

(Form: As provided under Standard Forms of these Documents)

5.1   Requirements for Contractor’s design (if any):

Specification Clause No‘s__________________

7.2   Programme:

Time for submission: Within fourteen (14) days* of the Commencement Date.

Form of Programme: attached (Bar Chart/CPM/PERT or other)

7.4- 	Amount payable due to failure to complete shall be 1% per day up to a maximum of (10%)  of sum stated in the Letter of Acceptance (Usually  the  liquidated  damages  are  set  between  0.05 percent  and  0.10  percent  per day).

7.5      Early Completion

In case of earlier completion of the Work, the Contractor is entitled to be paid bonus up-to limit and at a rate equivalent to 50% of the relevant limit and rate of liquidated damages stated in the contract data.

9.1   Period for remedying defects

15 Days as per under of defects.

10.2  (e)  Variation procedures:

Day work rates______________

__________________________ (details)

11.1    Terms of Payments

a)  Mobilization Advance

(1)  Mobilization Advance up to 10 % of the Contract Price stated in the Letter of Acceptance  shall  be  paid  by  the  Executive Engineer, Buildings Division Thatta  to  the Contractor  on  the works costing Rs.2.5 million or above on following conditions:

- On submission by the Contractor of a Mobilization Advance Guarantee for  the  full  amount  of  the  Advance  in  the  specified  form  from  a Scheduled Bank in Pakistan to the Executive Engineer, Buildings Division Thatta;

- Contractor will pay interest on the mobilization advance at the rate of 10% per annum on the advance; and

- This  Advance  including  the  interest  shall  be  recovered  in  5  equal installments from the five (05) R.A bills and in case the number of bills is less than five (05) then 1/5th of the advance inclusive of the interest thereon shall be recovered from each bill and the balance together with interest be recovered from the final bill. It may be insured that there is sufficient  amount  in  the  final  bill  to  enable  recovery  of  the Mobilization Advance.

OR

Secured Advance on Materials

(a)  	The Contractor shall be entitled to receive from the Executive Engineer, Buildings Division Thatta  Secured Advance against an INDENTURE BOND  in P W Account Form No. 31(Fin. R.  Form No.  2  acceptable  to  the  Procuring  Agency  of  such  sum  as  the Engineer may consider proper in respect of non-perishable materials brought at the Site but not yet incorporated in the Permanent Works provided that:

(i)  	The  materials  are  in  accordance  with  the  Specifications  for  the Permanent Works;

(ii)  	Such materials have been delivered  to  the Site and are properly stored and protected against loss or damage or deterioration to the satisfaction and  verification  of  the  Engineer  but  at  the  risk  and  cost  of  the Contractor;

(iii)  	The Contractor‘s  records of  the  requirements, orders, receipts and use of materials  are  kept  in  a  form  approved  by  the  Engineer,  and  such records shall be available for inspection by the Engineer;

(iv)  	The Contractor shall submit with his monthly statement  the estimated value of the materials on Site together with such documents as may be required by  the Engineer for  the purpose of valuation of materials and providing evidence of ownership and payment therefore;

(v)  	Ownership of such materials shall be deemed  to vest  in  the Procuring Agency  and  these  materials  shall  not  be  removed  from  the  Site  or otherwise  disposed  of  without  written  permission  of  the  Procuring Agency;

(vi)  	The  sum  payable  for  such  materials  on  Site  shall  not  exceed  75 % of  the  (i)  landed  cost  of  imported  materials,  or  (ii)  ex-factory  / ex-warehouse price of  locally manufactured or produced materials, or (iii) market price of stands other materials;

(vii)  	Secured Advance should not be allowed unless &until the previous advance, if an, fully recovered;

(viii)   	Detailed account of advances must be kept in part II of running account bill; and

(ix)     	Secured Advance may be permitted only against materials/quantities anticipated to be consumed / utilized on the work within a period of 3 months from the date of issue of secured advance and definitely not for full quantities of materials for the entire work/contract

(b)  	Recovery of Secured Advance:

- Secured Advance  paid  to  the  Contractor  under  the  above  provisions shall  be  effected  from  the monthly  payments  on  actual  consumption basis,  but  not  later  than  period  specified  in  the  rules  not more  than three months (even if unutilized); other conditions.

- As  recoveries  are  made  the  outstanding  accounts  of  the  items concerned  in Part  II  should be  reduced b making deduction entries  in the column; ―deduct quantity utilized in work measured since previous bill, equivalent to the quantities of materials used by the contractor on items of work shown as executed in part I of the bill.

(c)    	Interim  payments:  The  Contractor  shall  submit  to  the  Engineer  monthly  statements of  the estimated value of  the work completed  less  the cumulative amount certified previously.

- The value of work completed comprises the value of the quantities of the items in the Bill of Quantities completed.

- Value of secured advance on the materials and valuation of variations (if any).

- Engineer may exclude any item certified in a previous certificate or reduce the proportion of any item previously certified in any certificate in the light of later information.

- Retention money and other advances are to be recovered   from the bill submitted by contractor.

11.2  *(a)  Valuation of the Works:

i)  	Lump sum price_____________(details), or

ii)  	Lump sum price with schedules of rates ____________ (details), or

iii) 	Lump sum price with bill of quantities____________(details), or

iv) 	Re-measurement with  estimated/bid  quantities  in  the  Schedule  of Prices  or  on  premium  above  or  below  quoted  on  the  rates mentioned in CSR ______________(details), or/and

v)  	Cost reimbursable___________(details)

11.3  	Percentage of retention*:     five (5%)

11.6  	Currency of payment: Pak. Rupees

14.1  	Insurances: (Procuring Agency may decide, keeping in view the nature and the scope of the work)

Type of cover

The Works

Amount of cover

The sum stated in the Letter of Acceptance plus fifteen percent (15%)

Type of cover

Contractor‘s Equipment:

Amount of cover

Full replacement cost

Type of cover

Third Party-injury to persons and damage to property

_________________________

(The  minimum  amount  of  third  party  insurance  should  be  assessed  by  the

Procuring Agency and entered).

Workers:

_________________________

_________________________

Other cover*:

_________________________

(In each case name of insured is Contractor and Procuring Agency)

14.2  	Amount to be recovered

Premium plus _________________________ percent (____%).

15.3  	Arbitration**

Place of Arbitration:___________

* (Procuring Agency to specify as appropriate)

** (It has to be in the Province of Sindh)

STANDARD FORMS

(Note: Standard Forms provided in this document for securities are to be issued by a bank. In case the bidder chooses to issue a bond for accompanying his bid or performance of contract or receipt of advance, the relevant format shall be tailored accordingly without changing the spirit of the Forms of securities).