## sum
SUMMARY OF COST
NAME OF WORK:- | Maintenance & Repair of Educational Institutes @ GBLES Sabo Khan Chang Taluka & District Badin.
S # | Item of Work | Total Amount
Part-A Civil Work
1 | Cost of Schedule Items | 1067161.2513
| Add 10 % Above | 106716.1251
| Add Cartage Amount | 120375.6025
| Total | 1294252.9789
2 | Part-B (W/S & S/F)
| Cost of Schedule Items | 77041.19
| Add 10 % above | 7704.119
| Total | 84745.309
3 | Cost of Non-Schedule Item | 14417.7
| Total | 14417.7
| Total (1+2+3) | 1393415.9879
| Add 0.50% Contigency | 6967.0799
| G.Total:- | 1400383.0679
| Say Rs: in Million | 1.4004 | 1.4 | -0.00038307
SUB-ENGINEER |  | ASSISTANT ENGINEER
EDUCATION WORKS SUB DIVISION
BADIN

## Meterial
M A T E R I A L S T A T E M E N T
| NAME OF WORK:- | Maintenance & Repair of Educational Institutes @ GBLES Sabo Khan Chang Taluka & District Badin.
S.No | Description | Quantity | Cement | Sand | Shingle | Stone Ballast | Steel | Bricks
1 | CC 1:5:10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Brick Masonary 1:6 | 859 | 25.77 | 237.943 | 0 | 0 | 0 | 11596.5
3 | RCC 1:2:4 | 351 | 61.776 | 154.44 | 308.88 | 0 | 0 | 0
4 | Fabrication (Tor) | 14.88 | 0 | 0 | 0 | 0 | 14.88 | 0
5 | Cement Plaster 1/2" Thick 1:6 | 4701 | 22.5648 | 169.236 | 0 | 0 | 0 | 0
6 | Cement Plaster 3/8" Thick 1:4 | 3743 | 18.715 | 93.2007 | 0 | 0 | 0 | 0
7 | Cement Plaster 3/4" Thick 1:4 | 1141 | 11.41 | 68.46 | 0 | 0 | 0 | 0
8 | CC Topping 2" thick(1:2:4) | 2777 | 83.31 | 208.275 | 416.55
9 | CC Topping 3" thick(1:2:4) | 1776 | 79.92 | 213.12 | 426.24
10 | Cement Pointing 1:2 | 2050 | 14.76 | 36.9 | 0 | 0 | 0 | 0
|  | Total | 318.2258 | 1181.5747 | 1151.67 | 0 | 14.88 | 11596.5
|  | Rate | 52.53 | 3734.92 | 4190.76 | 3637.24 | 3213.96 | 930.14
|  | Amount | 16716.4013 | 44130.8698 | 48263.7257 | 0 | 478.2372 | 10786.3685
|  | G.Total | 120375.6025
|  |  | SUB-ENGINEER |  |  |  | ASSISTANT ENGINEER
EDUCATION WORKS SUB-DIVISION
BADIN

## LC
| NAME OF WORK :- | Maintenance & Repair of Educational Institutes @ GBLES Sabo Khan Chang Taluka & District Badin.
S.# | DESCRIPTION | S.BAJRI | S.METAL | H.SAND | S.# | DESCRIPTION | CEMENT | STEEL | S.# | DESCRIPTION | BRICKS
1 | From quarry to main road | 14 | 13 | 3 | 1 | From Zeal Pak Factory to Badin | 59 | 63 | 1 | From Badin to Seerani | 12
2 | From mile 110/4 to 122/0 | 11.4 | 0 | 9 | 2 | From Badin to Seerani | 12 | 12 | 2 | From Seerani to Site | 6
3 | From mile 122/0 to Ring road | 4.4 | 0 | 4.4 | 3 | From Seerani to Site | 6 | 6
4 | From Ring road to Badin | 63 | 63 | 63 |  | Total | 77 | 81 |  | Total | 18
5 | From Badin to Seerani | 12 | 12 | 12 |  | Say | 77 | 81
6 | From Seerani to Site | 6 | 6 | 6 | [5 empty] | Rate for 1st 6 miles | 617.54
| Total | 110.8 | 94 | 97.4 | 1 | Rate for 1st three miles | 8.13 | 771.96
| Say | 111 | 94 | 97 | [5 empty] | Rate for subsequent miles
[5 empty] | 2 | Rate for Subsequent miles | (74x0.60). | (75x32.56) |  | ( 12 x 26.05 ) | 312.6
1 | Rate for 1st 6 mile | 771.96 | 771.96 | 771.96 |  |  | 44.4 | 2442 |  | Total | 930.14
|  | (105 x32.56) | (88 x32.56) | (91 x32.56) |  | Total | 52.53 | 3213.96
2 | Rate for subsequent mile | 3418.8 | 2865.28 | 2962.96
| Total | 4190.76 | 3637.24 | 3734.92
|  | SUB ENGINEER |  |  |  |  | ASSISTANT ENGINEER
EDUCATION WORKS SUB-DIVISION
BADIN

## Estimate
ESTIMATE.
Name of Work:- |  | Maintenance & Repair of Educational Institutes @ GBLES Sabo Khan Chang Taluka & District Badin.
S # | Descripition. |  | Qty. | Rate. | Unit. | Amount.
a) Civil Work (i)
1 | Dismentling CC reinforced seperating reainforcement from
concrate cleaning and straightning the same(S.I.No.20/P-10)
| Lav: Roof | 1x12.25x7.50x0.42 | 66
| " Lintal | 1x10.25x0.75x1.0 | 8
| C/Wall Gate Col: | 1x2x1.50x1.50x6.0 | 27
|  |  | 101 | 5445 | %Cft | Rs: | 5499.45 | /-
2 | Dismentling brick work in cement or lime morter(S.No.13/P-10)
| C/Wall | 1x1x202.50x0.37x4.0 | 300
| " Piller | 1x1x34x0.75x0.37x4.0 | 38
|  |  | 338 | 1285.63 | %Cft | Rs: | 4345.4294 | /-
3 | Removing Cement or lime plaster (S.No.53/P-13)
a) | C/R I/Side | 1x3x2x(20.0+14.0)x(2.50+1.50) | 816
| C/R D/W | 1x1x62.25x(2.50+1.50) | 249
| Ver: + Office | 1x2x28.13x(2.50+1.50) | 225
| Ver: S/Wall | 1x2x6.50x(2.0+1.50) | 42
| Offices | 1x2x2x(12.0+10.0)x(2.50+1.50 | 352
| Store | 1x2x1x(13.25+7.0)x(2.0+1.50) | 142
| Offset | 1x2x22.39x(2.0+1.50) | 157
| Office F/Side | 1x34.0x3.0 | 102
| " Sides | 1x2x13.13x3.0 | 79
| Offset | 1x2x2.0x3.0 | 12
| Store Side | 1x2x1x7.13x3.0 | 43
2219
b) | G.Lav: | 1x2x2x(4.0+4.0)x7.25 | 232
| Passage | 1x2x10.25x6.0 | 123
| Passage S/Wall | 1x2x3.0x6.0 | 36
391
2610
Deduction
| Ent: Door | 1x5.0x7.0 | 35
| Window | 1x4x6.0x4.0 | 96
| Lav: Door | 1x2x2.50x7.0 | 35
166
| Net Qty: | 2610.0 ( - ) 166.0 | 2444
c) | C/R | 1x2x20.0x14.0 | 640
| Ver: | 1x62.25x1-1/2x6.25 | 195
| Off: Ver: | 1x18.33x6.0 | 110
945
|  | Total ( a + b + c ) = | 3389 | 121 | %Sft | Rs: | 4100.69 | /-
4 | Dismentling cement concrate Plain 1:2:4 (S.I.No. 19 (c)/P-10).
| C/R | 1x3x20.0x14.0x0.25 | 210
| Ver: | 1x1x62.25x6.50x0.25 | 101
| Offices | 1x2x10.0x12.0x0.25 | 60
| Store | 1x1x13.25x7.0x0.25 | 23
| Att: Lav: | 1x1x6.50x7.0x0.25 | 11
| C/R O/Roof | 1x1x67.0x26.50x0.17 | 302
| Office Block | 1x1x37.0x18.75x0.17 | 108
|  |  | 815 | 3327.5 | %Cft | Rs: | 27119.125 | /-
5 | Pacca brick work in foundation & plinth in cement sand
martor 1:6 (S.I.NO: 4 ie/P-19).
| S.Tank Raise | 1x2x(7.50+5.0)x0.75x3.50 | 88
|  |  | 88 | 11948.36 | %Cft | Rs: | 10514.5568 | /-
6 | R.C.C. work I/c all labour and material execpt the cost of steel reinforcement and its
labour for bending and binding which will be paid sperately. This rate also I/c all kinds
of moulds lifting shuttering curing rendering and finishing the exposedsurface (I/c screening
and washing of shingle)(a) R.C.work in roof slab,beams columns rafts lintels and other
structural members laid in situe or precast laid in position complete in all respect(I) Ratio
1:2:4 90 lbs cement 2 Cft sand 4 Cft shingle 1/8" to 1/4" gauge.(S.I.No.6ai/P-15).
| Qty: same item No: 1 |  | 101
| C/Wall P.Beam | 1x202.50x1.13x0.50 | 114
| C/Wall Col: | 1x23x0.75x1.13x6.0 | 117
| S.Tank Slab | 1x1x7.50x7.50x0.33 | 19
|  |  | 351 | 337 | P/Cft | Rs: | 118287 | /-
7 | Fabrication of mild steel reinforcement for cement concrete i/c cutting bending laying
in position making joints and fastening i/c cost of binding wire (also i/c removal of
rust from bars) (S.I.No:7-A/P-20).
a) Tor Steel
| Qty same as RCC | 351.0 x 4.75/112 | 14.88 | 5001.7 | P/Cwt | Rs: | 74425.296 | /-
8 | Applying floating coat 1/32" thick (S.I.No. 14/P-52)
a) | Same Qty: item No: 3 (a) |  | 2444
b) | Same Qty: item No: 3 (b) |  | 945
|  |  | 3389 | 660 | %Sft | Rs: | 22367.4 | /-
9 | Pacca brick work in other than building I/c stricking of joints in cement sand
ratio 1:6.(S.I.No. 7/P-21).
| C/Wall | 1x202.50x0.75x5.0 | 771
|  |  | 771 | 12346.65 | %Cft | Rs: | 95192.6715 | /-
10 | Cement plaster 1:6 upto 12 ft height 1/2" thick. (S.I.No.13-c/P-51)
a) | C/R I/Side | 1x3x2x(20.0+14.0)x(2.50+1.50) | 816
| C/R D/W | 1x1x62.25x(2.50+1.50) | 249
| Ver: + Office | 1x2x28.13x(2.50+1.50) | 225
| Ver: S/Wall | 1x2x6.50x(2.0+1.50) | 42
| Offices | 1x2x2x(12.0+10.0)x(2.50+1.50 | 352
| Store | 1x2x1x(13.25+70)x(2.0+1.50) | 142
| Offset | 1x2x22.39x(2.0+1.50) | 157
| Office F/Side | 1x34.0x3.0 | 102
| " Sides | 1x2x13.13x3.0 | 79
| Offset | 1x2x2.0x3.0 | 12
| Store Side | 1x2x1x7.13x3.0 | 43
| Lav: I/Side | 1x2x2x(4.0+4.0)x7.0 | 224
| " F/Side | 1x1x9.50x3.0 | 76
| Passage | 1x1x(9.50+3.0)x6.0 | 75
| O/Side | 1x1x(4.50+9.50)x6.0 | 84
| Lav: Plinth | 1x2x(10.63+9.63)x1.50 | 61
| C/Wall I/Side | 1x1x202.50x(6.0+0.75) | 1367
| " Plinth | 1x2x202.50x1.0 | 405
4511
Deduction
| Lav: | 1x2x2.50x7.0 | 35
35
| Net Qty: | 4511.0 ( - ) 35.0 = | 4476
b) | S.Tank I/Side | 1x2x(6.0+6.0)x5.0 | 120
| " O/Side | 1x2x(7.50+7.50)x1.50 | 45
| C/R Steps | 1x3x7.0x(1.25+0.50) | 37
| Lav: Steps | 1x3x5.0(1.0+0.50 | 23
225
|  | Total (a + b) = | 4701 | 2206.6 | %Sft | Rs: | 103732.266 | /-
11 | Cement plaster 1:4 upto 12 ft height 3/8" thick. (S.I.No.11-a/P-51)
| Qty same Item No. 10 |  | 4701
Deduction
| Lav: I/Side | 1x2x2x(4.0+4.0)x2.75 | 880
| " | 1x1x8.75x2.0 | 18
| Steps | 1x3x7.0x(1.25+0.50) | 37
| Lav: Steps | 1x3x5.0x(1.0+0.50) | 23
958
|  |  | 3743 | 2197.52 | % Sft | Rs: | 82253.1736 | /-
12 | Cement plaster 1:4 upto 12' height 3/4" thick.(S.I.No:11-c/51)
a) | Same Qty: item No: 8 (b) |  | 945
b) | Pattas C/R B/Side | 1x64.50x0.50 | 32
| " Sides | 1x2x15.13x0.50 | 15
| Corner | 1x2x2x0.50x10.50 | 21
| Lav: B/Side | 1x10.25x0.50 | 5
| " Sides | 1x2x5.50x0.50 | 6
| Corner | 1x2x2x0.50x7.75 | 16
| C/Wall | 1x202.50x0.50 | 101
196
|  | Total ( a + b ) = | 1141 | 3015.76 | %Sft | Rs: | 34409.8216 | /-
13 | Extra labour rate for making cement plaster pattas/bend width not less
then 6" wide with fine finishing as directed by Engineer Incharge.
| Qty: same as item No.12 (b) / 0.50 = 196.0/0.50 = |  | 392 | 19.36 | P.Rft | Rs: | 7589.12 | /-
14 | S/F in position iron/steel grill of 3/4"x1/4" size flat iron of approved design i/c
painting 3 coats etc complete (weight not to be less than 3.7 lbs sq. foot of
finished grill (S.I.No. 26/P-92)
| Ver: Opp: | 1x4.0x6.0 | 24 | 180.5 | P.Sft | Rs: | 4332 | /-
15 | Providing fixing G.I. frame chowkats of size 7"x2" or 4-1/2"x3" for door using 20 gauge G.I.
sheet i/c welded hinges and fixing at site with necessary holds fasts filling with cement sand
slury of ratio 1:6 & repairing the jambs the cost also i/c all carriage tools and plants used
making and fixing etc complete.(S.I.No. 29/P-92).
| M. Ent: Door | 1x(7.0+5.0+7.0) | 19
| Lav: Door | 1x2x(7.0+2.50+7.0) | 33
|  |  | 52 | 228.9 | P/Rft | Rs: | 11902.8 | /-
16 | M/F steel grated door with 1/16" thick sheeting I/c angle iron frame 2"x2"x3/8"&3/4"
square bars 4" centre to centre with locking arrangement.(S.I.No. 24/P-91).
| C/Wall M/Gate. | 1x10.0x6.0 | 60 | 726.72 | P.Sft. | Rs: | 43603.2 | /-
17 | Laying floor of approved coloured glazed tiles 1/4" thick laid in white cement and
pigment on a bed of 3/4" thick CM 1:2(S.I.No. 25/P-42)
| Att: Lav: " | 1x6.50x7.0 | 46
| Door Jambs | 1x2x2.50x1.0 | 5
|  |  | 51 | 27747.06 | % Sft | Rs: | 14151.0006 | /-
18 | First class deodar wood wrought joinery in doors and windows etc fixed in
position I/c chawkhats, holdfasts hinges, iron tower bolts, handles and cords
with hooks etc deodar panelled or panelled and glazed or fully glazed
1-3/4" thick. (S.I.No.7b/P-57) Shutter Only
| C/R Window | 1x1x4.0x4.0 | 16
| Lav: Door | 1x2x2.50x7.0 | 35
|  |  | 51 | 902.93 | P.Sft | Rs: | 46049.43 | /-
19 | Cement pointing struck joints on walls 1:2 (S.I.No.19/P-52)
| C/R B/Side | 1x64.25x10.50 | 675
| " Sides | 1x2x15.13x10.50 | 318
| Lav: B/Side | 1x10.025x7.75 | 79
| " Sides | 1x2x5.07x7.75 | 85
| C/Wall | 1x202.50x5.50 | 1114
2271
Deduction.
| C/R Window | 1x3x2x5.0x4.0 | 120
| Lav: Vent: | 1x2x2.0x1.50 | 6
| C/Wall Col: | 1x23x0.75x5.50 | 95
221
| Net Qty: | 2271.0 ( - ) 221.0 = | 2050 | 1287.44 | % Sft | Rs: | 26392.52 | /-
20 | P/L CC 1:2:4 topping I/c surface finishing and dividing into
panells (S.I.No.16/P-41)
(a) | 2" thick
| C/R O/Roof | 1x67.52x26.88 | 1815
| Off: " | 1x37.0x12.63 | 467
| Offset | 1x39.0x7.75 | 302
| Lav: | 1x12.25x7.50 | 92
| " | 1x8.25x5.50 | 43
| G.Lav: Floor | 1x2x4.0x4.0 | 32
| Passage | 1x1x8.75x3.0 | 26
|  |  | 2777 | 3275.5 | %Sft | Rs: | 90960.635 | /-
(b) | 3" thick
| C/Room | 1x3x2.0x14.0 | 840
| Ver: | 1x62.25x6.50 | 405
| D/Jambs | 1x3x4.0x1.13 | 14
| Office | 1x2x10.0x12.0 | 224
| Store | 1x13.25x7.0 | 93
| Kitt: | 1x6.0x7.0 | 42
| D/Jambs | 1x3x3.50x1.13 | 12
| Office Ver: | 1x22.39x6.50 | 146
|  |  | 1776 | 4411.82 | %Sft | Rs: | 78353.9232 | /-
21 | Making notice board made with cement (S.I.No.1/P-94)
| C/R | 1x3x8.0x4.0 | 96 | 58.11 | P.Sft. | Rs: | 5578.56 | /-
22 | White washing two coats.(S.I.No:26/P-53).
| C/R Ceiling | 1x3x20.0x14.0 | 840
| T.Beam | 1x3x2x14.0x1.50 | 126
| Ver: Ceiling | 1x62.25x6.50 | 405
| Office | 1x2x10.0x12.0 | 240
| Store | 1x13.25x7.0 | 93
| Kitt: | 1x6.0x7.0 | 42
| Bath | 1x6.50x7.0 | 46
| Office Ver: | 1x22.39x6.50 | 146
| G: Lav: | 1x2x4.0x4.0 | 32
| G.Lav: Ceiling | 1x1x5.0x4.0 | 20
|  |  | 1990 | 829.95 | % Sft | Rs: | 16516.005 | /-
23 | Primary coat of chalk under distemper (S.I.No.23/P-53)
| Qty: same asitem No.11 |  | 3743
| Qty: same asitem No.12 (b) |  | 196
|  |  | 3939 | 442.75 | % Sft | Rs: | 17439.9225 | /-
24 | Distempering three coats.(S.I.No:24/P-53).
| Qty: same asitem No.23 |  | 3939 | 1079.65 | %Sft | Rs: | 42527.4135 | /-
25 | Distempering two coats (S.I.No.24-b/P-53)
| C/R I/Side | 1x3x2x(20.0+14.0)x(11.50+11.0)2 | 2295
| Ver: | 1x2x(62.25+6.25)x(11.50+11.0)/2 | 1541
| Ver: + Office | 1x2x18.33x(11.50+11.0)/2 | 412
| Offices | 1x2x2x(12.0+10.0)x(11.50+11.0)/2 | 990
| Store | 1x2x1x(13.25+7.0)x(11.50+11.0)/2 | 456
| Office F/Side | 1x34.0x11.50 | 191
| " Sides | 1x2x13.13x11.50 | 302
| Offset | 1x2x2.0x11.50 | 46
| Store Side | 1x2x1x7.13x11.50 | 164
6397
Deduction
| Qty same item No 3 (a) = |  | 2219
| C/R Door | 1x3x4.0x7.0 | 84
| Office " | 1x3x3.50x7.0 | 74
| Att: Lav: Door | 1x2.50x7.0 | 18
| Office Window | 1x2x2x4.0x4.0 | 64
| Ver: Opp: | 1x2x4.0x6.0 | 48
| Side " | 1x2x4.25x6.0 | 51
2558
| Net Qty: | 6397.0 (- ) 2558.0 = | 3839 | 1043.9 | %Sft | Rs: | 40075.321 | /-
26 | Colour wash two coats.(S.I.No.25/P-53)
| Qty: same asitem No.19 |  | 2050 | 859.9 | % Sft | Rs: | 17627.95 | /-
27 | Painting new surface ( c) painting door and windows any type three coats.
(S.I.No.4-c/P-67).
| Qty: same asitem No. 18 = 51.0 x 2 = |  | 102 | 2116.41 | %Sft | Rs: | 2158.7382 | /-
28 | Painting old surface ( c) painting door and windows any type three coats.
(S.I.No.4-c/P-66).
| C/R Door | 1x2x2x4.0x7.0 | 112
| " Window | 1x8x2x6.0x4.0 | 384
| Main Ent: Door | 1x2x5.0x7.0 | 70
| Office Door | 1x3x2x3.50x7.0 | 147
| Store " | 1x2x3.0x7.0 | 42
| Lav: Att: Door | 1x2x2.50x7.0 | 35
| Office Window | 1x2x2x3.0x4.0 | 48
| " " | 1x4x2x4.0x4.0 | 128
| Lav: Vent: | 1x3x2x2.0x1.50 | 18
|  |  | 984 | 1662.26 | %Sft | Rs. | 16356.6384 | /-
29 | Painting new surface ( c) painting guard bars, gates iron bars gratings, railings I/c
standard bracess (etc) and similar open work three coats.(S.I.No.4d/P-68).
| C/Wall M/Gate | 1x2x10.0x6.0 | 120 | 1270.83 | %Sft |  | 1524.996 | /-
30 | Painting old surface ( c) painting guard bars, gates iron bars gratings, railings I/c
standard bracess (etc) and similar open work two coats.(S.I.No.4d/P-68).
| Ver: Opp: Grill | 1x3x4.0x6.0 | 72
| C/R Window | 1x9x3x1.33x3.50 | 126
| " " | 1x2x2.50x3.50 | 18
| " " | 1x4x2x1.67x3.50 | 47
|  |  | 263 | 674.6 | %Sft | Rs. | 1774.198 | /-
|  |  |  | G.Total:- |  | Rs: | 1067161.2513 | /-
PART- B (W/S & S/F)
1 | P/F squating type white glazsed earthen ware W.C. pan with I/c cost of flushing cistern
with internal fitting and flush pipe with bend and making requisite number of holes in
walls plinth & floor for pipe connections & making good in cement concrete 1:2:4.
(a) W.C. pan of not less than 23" clear opening between flushing rims and 3 gallons
flushing tank (i) with 4@ dia C.I. trape.(S.I.No.1(b-i)/P-1).
| Att: Lav: | 1x1 | 1
| G.Lav: | 1x2 | 2
|  |  | 3 | 4802.6 | P/No. | Rs. | 14407.8 | /-
2 | P/F 6"x2" or 6"x3" C.I floor trap of the approved self cleaning designe with a C.I screwed
down gratting with or without a vent arm complete with & I/c making requisite number
of holes in walls plinth & floor for pipe connection & making good in cement concrete
1:2:4 (S.I.No. 20/P-6).
| Att: Lav: | 1x1 No: | 1 | 2042.43 | P.No | Rs. | 2042.43 | /-
3 | S/F Consealed tee-stop cock of superior quality with cp head 1/2" dia (S.I. No.12-b/P-18).
| G. Lav: | 1x1 | 1 | 889.46 | P.No | Rs. | 889.46 | /-
4 | Cancealed C.P fitting or superior quality for tiles Bath room (a) S.F concealed bib cock
of superior quality with C.P head 1/2" dia (S.I.No.13-a/ P-19).
| Att: Lav: | 1x1 | 1
| G Lav: | 1x2 | 2
|  |  | 3 | 1109.46 | P.No | Rs. | 3328.38 | /-
5 | Supplying & fixing fiber glass tank of approved quality and desing and wall thickness as specified I/c
cost of nuts, bolts and fixing in plateform of cement concrete 1:3:6 and making connections for in let
out let & over flow inlet outlet flow pipes etc. complete (500 Gallons) (S.I.No.3(c)/P-21)
| Fiber Glass Tank | 1x1 Nos: | 1 | 37505.42 | P.Each | Rs. | 37505.42 | /-
6 | P/F handle valves (China) (S.I.No.5-i/P-17).
1/2" dia
| Lav: O/S | 1x2 | 2 | 200.42 | Each | Rs. | 400.84 | /-
7 | Providing R.C.C pipes with collars class "B" and digging the trenches to required depth
and fixing in position I/c cutting fitting and jointing with maphalt composition & cement
mortar 1:1 and testing with water pressure to a head of 4 feet above the top of the
highest pipe & refilling with excavted staff 4" dia R.C.C pipes class "B" (S.I.No.2/P-23)
4" Dia
| Lav: to O/S | 1x3x6.0 | 18 | 146.57 | P.Rft | Rs. | 2638.26 | /-
8 | Providing G.I. Pipes specials and clamps etc I/c fixing cutting & fitting I/c cost of
breaking through walls and floor making good etc painting two coats after cleaning
the pipe etc with white zink paint with pigment to match the colour of the building &
testing with water to a pressure head of 200 ft: and handling .(S.I.No.1-ii/P-14).
a) 3/4" Dia.
| O/S to Lav: | 1x100.0 | 100 | 86.36 | P.Rft | Rs. | 8636 | /-
b) 1/2" Dia.
| Lav: I/S | 1x60.0 | 60 | 73.21 | P.Rft | Rs. | 4392.6 | /-
Providing PVC Pipes of Class "D" (equivalent) in trenches I/c cutting fitting
9 | Providing PVC Pipes of Class "D" (equivalent) in trenches I/c cutting fitting
and jointing with "Z" joints with one rubber ring I/c testing with water to a head
of 122 meters or 400 feet (25 mm) 1" dia (S.I.No.3/P-23). (PHE)
| Bore to Motor | 1x100.0 | 100 | 28 | P.Rft | Rs: | 2800 | /-
|  |  |  | TOTAL:- |  | RS: | 77041.19 | /-
Non-Schedule Item
1 | P&F water pimping set 1/2 H.P Mono Block single phase 220 volts with1"x1" -1/4"
suction and delivery 50 ft head i/c making C.C 1:3:6 plate form of required size and fixing
with nuts and bolts (local made) (R.A).
| Water Pump. | 1x1 | 1 | 14417.7 | Each. | Rs: | 14417.7 | /-
|  |  |  | TOTAL:- |  | Rs: | 14417.7 | /-
CERTIFICATE
Certified that I have prepared this estimate under the supervision of Assistan Engineer
Education works Sub-Division Badin on the basis of drawing & design supplied to me
for items identified by the Assistant Engineer. The rate provided in this estimate are from
composite schedule of Rates & sanctioned rate analysis.
SUB-ENGINEER
Certified that this estimate has been prepared by the Sub-Engineer under my supervision
for the items identified by me which are prepared for the execution. Further certified that
the quantities provided in this estimate are correct.
ASSISTANT ENGINEER
EDUCATION WORKS SUB-DIVISION
BADIN

## Face Sheet
F A C E S H E E T
| FUND HEAD. |  |  | -:- | M&R Programme
| MAJOR HEAD. |  |  | -:- | 09 Education Affairs & Services
| MINOR HEAD |  |  | -:- | DEVELOPMENT
| SERVICE HEAD |  |  | -:- | SCHEME NO.
| DEPARTMENTAL HEAD |  |  | -:- | The Detailed working estimate for the
work Maintenance & Repair of Educational Institutes
@ GBLES Sabo Khan Chang Taluka &
District Badin.
Certified that this estimate has been prepared in the office of
the Assistant Engineer, Education Works Sub-Division Badin. The expenditure
incurred on the above said work shall be chargeable against the Head
of Account 09 Education Affairs & Services.
[5 empty] | Estimated Cost | Rs: 1.400 (Million)
GENERAL DESCRIPTION
| HISTORY. | Government of Sindh have approved the ADP Scheme during the year
for District Badin, which are to be executed by Education & Litreracy Department
within years. The above said work is one of the approved schemes hance its
estimate has been prepared.
| SCOPE. | The work will be completed in current financial years subject to availbility of funds.
| LAND. | The Education Department Government of Sindh shall provide the plot for
the purpose of construction of the above said building.
| METERIAL. | No lead weather small or long for carraige of meterial for which finished
items are applicable is to be paid seperately. However the construction meterial
as detailed below shall have to be brought by the contractor from the following
pre-determined quaries / approved source of supply. The estimate is based on
the rates provided by the Composite Schedule of Rates (Recent Edition).
| 1- | Crush |  |  | Thano Bola Khan
| 2- | Stone Ballast |  |  | Ongar
| 3- | Hill Sand |  |  | Bholari
| 4- | Steel |  |  | Hyderabad
| 5- | Cement |  |  | Zeal-Pak
| 6- | Tiles |  |  | Hyderabad
| 7- | Bricks |  |  | Badin
|  | SUB-ENGINEER |  |  |  | ASSISTANT ENGINEER
EDUCATION WORKS SUB-DIVISION
BADIN

## Schedule
SCHEDULE "B"
Name of Work:- |  | Maintenance & Repair of Educational Institutes @ GBLES Sabo Khan Chang Taluka & District Badin.
S.No. | Descripition. |  | Qty. | Rate. | Unit. | Amount.
a) Civil Work (i)
1 | Dismentling CC reinforced seperating reainforcement from
concrate cleaning and straightning the same(S.I.No.20/P-10)
|  |  | 74 | 5445 | %Cft | Rs: | 5029 | /-
(Rs: five thousand four hundred forty five only)
2 | Dismentling brick work in cement or lime morter(S.No.13/P-10)
|  |  | 338 | 1285.63 | %Cft | Rs: | 4345.4294 | /-
(Rs: one thousand two hundred eighty five & Ps: sixty three only)
3 | Removing Cement or lime plaster (S.No.53/P-13)
|  |  | 3393 | 121 | %Sft | Rs: | 4105.53 | /-
(Rs: one hundred twenty one only)
4 | Dismentling CC 1:2:4 plain (S.I.No.19-c/P-10)
|  |  | 815 | 3327.5 | %Cft | Rs: | 27119.125 | /-
(Rs: three thousand three hundred twenty seven and paisa fifty only)
5 | Pacca brick work in foundation & plinth in cement sand martor .
ratio 1:6 ( S.I.NO: 4-ie/P-19 )
|  |  | 66 | 11948.36 | %Cft | Rs: | 7885.9176 | /-
(Rs: eleven thousand nine hundred forty eight and Paisa thirty six only)
6 | R.C.C. work I/c all labour and material execpt the cost of steel reinforcement and its
labour for bending and binding which will be paid sperately. This rate also I/c all kinds
of moulds lifting shuttering curing rendering and finishing the exposedsurface (I/c screening
and washing of shingle)(a) R.C.work in roof slab,beams columns rafts lintels and other
structural members laid in situe or precast laid in position complete in all respect(I) Ratio
1:2:4 90 lbs cement 2 Cft sand 4 Cft shingle 1/8" to 1/4" gauge.(S.I.No.6ai/P-19).
|  |  | 351 | 337 | P.Cft | Rs: | 118287 | /-
(Rs: three hundred thirty seven only)
7 | Fabrication of mild steel reinforcement for cement concrete i/c cutting bending
laying in position making joints and fastening i/c cost of binding wire (also i/c removal
of rust from bars) (S.I.No:8/P-16).
| a) Tor Steel |  | 14.88 | 5001.7 | P. Cwt | Rs: | 74425.296 | /-
(Rs: five thousand one & Paisa seventy only)
8 | Applying floating coat of cement 1/32" thick (S.I.No.14/P-52)
|  |  | 3393 | 660 | %Sft | Rs: | 22393.8 | /-
(Rs: six hundred sixty only)
9 | Pacca brick work in other then building in cement sand morter
ratio 1:6 (S.I.No.7(I-e)/P-21)
|  |  | 759 | 12346.65 | %Cft | Rs: | 93711.0735 | /-
(Rs: twelve thousand three hundred forty six & Paisa sixty five only)
10 | Cement plaster 1:6 upto 12 ft height 1/2" thick. (S.I.No.13-c/P-51)
|  |  | 4658 | 2206.6 | % Sft | Rs: | 102783.428 | /-
(Rs: two thousand two hundred six and paisa sixty only)
11 | Cement plaster 1:4 upto 12 ft height 3/8" thick. (S.I.No.11-a/P-51)
|  |  | 3700 | 2197.52 | %Sft | Rs: | 81308.24 | /-
(Rs: two thousand one hundred ninty seven and paisa fifty two only)
12 | Cement plaster 1:4 upto 12 ft height 3/4" thick. (S.I.No.11-c/P-51)
|  |  | 1141 | 3015.76 | %Sft | Rs: | 34409.8216 | /-
(Rs: three thousand fifteen and paisa seventy six only)
13 | Extra labour rate for making cement plaster pattas/bend width not less
then 6" wide with fine finishing as directed by Engineer Incharge.
|  |  | 392 | 19.36 | P.Sft | Rs: | 7589.12 | /-
(Rs: ninteen & Paisa thirty six only)
14 | S/F in position iron/steel grill of 3/4"x1/4" size flat iron of approved design i/c
painting 3 coats etc complete (weight not to be less than 3.7 lbs sq. foot of
finished grill (S.I.No. 26/P-92)
|  |  | 24 | 180.5 | P.Sft. | Rs: | 4332 | /-
(Rs: one hundred eighty and paisa fifty only)
15 | Providing fixing G.I. frame chowkats of size 7"x2" or 4-1/2"x3" for door using 20 gauge G.I.
sheet i/c welded hinges and fixing at site with necessary holds fasts filling with cement sand
slury of ratio 1:6 & repairing the jambs the cost also i/c all carriage tools and plants used
making and fixing etc complete.(S.I.No. 29/P-92).
|  |  | 52 | 228.9 | P.Sft. | Rs: | 11902.8 | /-
(Rs: two hundred twenty eight and paisa ninety only)
16 | M/F steel grated door with 1/16" thick sheeting I/c angle iron frame 2"x2"x3/8"&3/4"
square bars 4" centre to centre with locking arrangement.(S.I.No. 24/P-91).
|  |  | 60 | 726.72 | P.Sft. | Rs: | 43603.2 | /-
17 | Laying floor of approved coloured glazed tiles 1/4" thick laid in white cement and
pigment on a bed of 3/4" thick CM 1:2(S.I.No. 25/P-42)
|  |  | 51 | 27747.06 | % Sft | Rs: | 14151.0006 | /-
(Rs: twenty seven thousand seven hundred forty seven & Ps: six only)
18 | First class deodar wood wrought joinery in doors and windows etc fixed in
position I/c chawkhats, holdfasts hinges, iron tower bolts, handles and cords
with hooks etc deodar panelled or panelled and glazed or fully glazed
1-3/4" thick. (S.I.No.7b/P-57) (Shutters).
|  |  | 51 | 902.93 | P.Sft | Rs: | 46049.43 | /-
(Rs: nine hundred two and paisa ninty three only)
19 | Cement pointing struck joints on walls 1:2 (S.I.No.19/P-52)
|  |  | 2050 | 1287.44 | % Sft | Rs: | 26392.52 | /-
(Rs: one thousand two hundred eighty seven & Paisa forty four only )
20 | P/L CC 1:2:4 topping I/c surface finishing and dividing into
panells (S.I.No.16/P-41)
| a) 2" thick |  | 2779 | 3275.5 | %Sft | Rs: | 91026.145 | /-
(Rs: three thousand two hundred seventy five & Paisa fifty only)
| b) 3" thick. |  | 1776 | 4411.82 | %Sft | Rs: | 78353.9232 | /-
(Rs: four thousand four hundred eleven & Paisa eighty two only)
21 | Making notice board made with cement (S.I.No.1/P-94)
|  |  | 96 | 58.11 | P.Sft | Rs: | 5578.56 | /-
(Rs: fifty eight and paisa eleven only)
22 | White washing three coats ( S.I.No26/P-53)
|  |  | 1990 | 829.95 | % Sft | Rs: | 16516.005 | /-
(Rs: eight hundred twenty nine and paisa ninty five only)
23 | Primary coat of chalk under distemper (S.I.No.23/P-53)
|  |  | 3896 | 442.75 | %Sft | Rs: | 17249.54 | /-
(Rs: four hundred forty two and paisa seventy five only)
24 | Distempering three coats (S.I.No.24/P-53 )
|  |  | 3896 | 1079.65 | %Sft | Rs: | 42063.164 | /-
(Rs: one thousand seventy nine and Ps: sixty five only)
25 | Distempering two coats (S.I.No.24/P-53 )
|  |  | 4035 | 1043.9 | % Sft | Rs: | 42121.365 | /-
(Rs: one thousand forty three and Ps: ninety only)
26 | Colour Wash two coats (S.I.No.25/P-53)
|  |  | 2050 | 859.9 | % Sft | Rs: | 17627.95 | /-
(Rs: eight hundred fifty nine and paisa ninty only)
27 | Painting new surface painting to doors and windows any type i/c edges 3 coats
( S.I.No.4-c/P-67)
|  |  | 102 | 2116.41 | %Sft | Rs: | 2158.7382 | /-
(Rs: two thousand one hundred sixteen and paisa forty one only)
28 | Painting old surface ( c) painting door and windows any type three coats.
(S.I.No.4-c/P-66).
|  |  | 984 | 1662.25 | %Sft | Rs: | 16356.54 | /-
(Rs: one thousand six hundred sixty two and paisa twenty five only)
29 | Painting new surface ( c) painting guard bars, gates iron bars gratings, railings I/c
standard bracess (etc) and similar open work three coats.(S.I.No.4d/P-68).
|  |  | 120 | 1270.83 | %Sft | Rs: | 1524.996 | /-
(Rs: one thousand two hundred seventy and paisa eighty three only)
30 | Painting old surface ( c) painting guard bars, gates iron bars gratings, railings I/c
standard bracess (etc) and similar open work two coats.(S.I.No.4d/P-68).
|  |  | 263 | 674.6 | %Sft | Rs: | 1774.198 | /-
(Rs: six hundred seventy four and paisa sixty only)
[5 empty] | Total | Rs: | 1062174.8561 | /-
PART- B (W/S & S/F)
1 | P/F squating type white glazsed earthen ware W.C. pan with I/c cost of flushing cistern
with internal fitting and flush pipe with bend and making requisite number of holes in
walls plinth & floor for pipe connections & making good in cement concrete 1:2:4.
(a) W.C. pan of not less than 19" clear opening between flushing rims and 3 gallons
flushing tank (i) with 4@ dia C.I. trape.(S.I.No.1(b-i)/P-1).
|  |  | 3 | 4802.6 | P/No. | Rs. | 14407.8 | /-
(Rs: four thousand eight hundred two and paisa sixty only)
2 | P/F 6"x2" or 6"x3" C.I floor trap of the approved self cleaning designe with a C.I screwed
down gratting with or without a vent arm complete with & I/c making requisite number
of holes in walls plinth & floor for pipe connection & making good in cement concrete
1:2:4 (S.I.No. 20/P-6).
|  |  | 1 | 2042.43 | P/No. | Rs. | 2042.43 | /-
(Rs: two thousand twenty four and paisa forty three only)
3 | S/F Consealed tee-stop cock of superior quality with cp head 1/2" dia (S.I.No.12-b/P-8)
|  |  | 1 | 889.46 | P.No | Rs. | 889.46 | /-
(Rs: eight hundred eighty nine and paisa forty six only)
4 | S/Fixing long bib cock of superior quality with C.P head 1/2" dia
(S.I.No.13-a/ P-19).
|  |  | 3 | 1109.46 | P.No | Rs. | 3328.38 | /-
(Rs: one thousand one hundred nine and paisa forty six only)
5 | Supplying & fixing fiber glass tank of approved quality and desing and wall thickness as
specified I/c cost of nuts, bolts and fixing in plateform of cement concrete 1:3:6 and
making connections for in let out let & over flow inlet outlet flow pipes etc. complete
(S.I.No.3(c)/P-21)
| 500 Gallons |  | 1 | 37505.42 | Each | Rs. | 37505.42 | /-
(Rs: thirty seven thousand five hundred five and paisa forty two only)
6 | P/F handle valves (China) (S.I.No.5-i/P-17).
| 1/2" dia |  | 2 | 200.42 | Each | Rs. | 400.84 | /-
(Rs: two hundred & Pasia forty two only)
7 | Providing R.C.C pipes with collars class "B" and digging the trenches to required depth
and fixing in position I/c cutting fitting and jointing with maphalt composition & cement
mortar 1:1 and testing with water pressure to a head of 4 feet above the top of the
highest pipe & refilling with excavted staff 6" dia R.C.C pipes class "B" (S.I.No.2-b/P-23)
| 4" Dia |  | 18 | 146.57 | P.Rft | Rs. | 2638.26 | /-
(Rs: one hundred forty six & Pasia fifty seven only)
8 | Providing G.I. Pipes specials and clamps etc I/c fixing cutting & fitting I/c cost of
breaking through walls and floor making good etc painting two coats after cleaning
the pipe etc with white zink paint with pigment to match the colour of the building &
testing with water to a pressure head of 200 ft: and handling (External).
(S.I.No.1-ii/P-14).
| a) 3/4" Dia. |  | 100 | 86.36 | P.Rft | Rs. | 8636 | /-
(Rs: eighty six & Pasia thirty six only)
| b) 1/2" Dia. |  | 60 | 73.21 | P.Rft | Rs. | 4392.6 | /-
(Rs: seventy three & Pasia twenty one only)
9 | Providing PVC Pipes of Class "D" (equivalent) in trenches I/c cutting fitting
and jointing with "Z" joints with one rubber ring I/c testing with water to a head
of 122 meters or 400 feet (25 mm) 1" dia (S.I.No.3/P-23). (PHE)
|  |  | 100 | 28 | P.Rft | Rs: | 2800 | /-
(Rs: twenty eight only)
|  |  |  | TOTAL:- |  | Rs: | 77040 | /-
Non-Schedule Item
1 | P&F water pimping set 1/2 H.P Motor Block single phase 220 volts with 1" x 1 1/4"
suction and delivery 50 ft head i/c making C.C 1:3:6 plate form of required size and fixing
with nuts and bolts (local made) (R.A).
|  |  | 1 | 14417.7 | Each. | Rs: | 14417.7 | /-
(Rs: forteen thousand four hundred seventeen & Pasia seventy only)
|  |  |  | TOTAL:- |  | RS: | 14417.7 | /-