## FACE SHEET
FACE SHEET.
FUND HEAD:- |  |  | PROVINCIAL
MAJOR HEAD:- |  |  | 6-314 .(BUILDING AND STRUCTURE).
MINOR HEAD:- |  |  | DEVELOPMENT.
SERVICE HEAD:- |  |  | SCHEME NO._____________
DEPARTMENTAL HEAD:- |  |  | MAINTENANCE & REPAIR PROGRAMME 2016-17 OF EDUCATIONAL INSTITUTES (COLLEGE EDUCATION) IN DISTRICT BADIN @ GOVERNMENT BOYS DIGREE COLLEGE MATLI TALUKA MATLI. (B.Sc BLOCK FIRST FLOOR)
The estimate has been prepared in the office of the Assistant Enginner
Education works Sub-Division Matli. The probable expenditure incurred on the
above said work, shall be chargeable against the head of account. 6-314
(Buildings & structure) (Dev:).
Estimated cost Rs: _____5000000/=_____
GENERAL DISCRIPTION.
1. HISTORY:- |  | The Government of Sindh have approved the ADP- scheme during
the year 200 -- for District Badin which are to be executed by
works & services Departement in (02) financial years.
2. SCOPE. |  | This work is to be completed in current financial year subjected to
available of funds.
3. LAND. |  | The Education Department Government of Sindh shall provided plot for
Construction of the proposed scheme/work.
4. MATERIAL. |  | No lead weather small or long for carriage of material of items for which
finished items are applicable is to be paid separately. However the
construction material as detailed below shall have to be brought by the
contractor from the following predetermined quarried/approved source
of supply. The estimate is mainly based on rates provided by the
composite schedule of rates.(Recent Edition).
1. Bajri from. |  |  |  |  | Thana Bola Khan.
2.Stone ballast from. |  |  |  |  | Onger.
3.Hill sand from. |  |  |  |  | Bholari.
4.Stone from.
5.Steel & cement from. |  |  |  |  | Hyderabad.
6.Brick from. |  |  |  |  | Tando Ghulam Ali
7.Tiles from. |  |  |  |  | Hyderabad.
| Sub-Engineer. |  |  |  |  | ASSISTANT ENGINEER
EDUCATION WORKS SUB-DIVISION
MATLI

## Summary of cost
SUMMARY OF COST
NAME OF WORK:- |  | MAINTENANCE & REPAIR PROGRAMME 2016-17 OF EDUCATIONAL INSTITUTES (COLLEGE EDUCATION) IN DISTRICT BADIN @ GOVERNMENT BOYS DIGREE COLLEGE MATLI TALUKA MATLI. (B.Sc BLOCK FIRST FLOOR)
PART - A
1 | COST OF SCHEDULE ITEMS |  | Rs: | 4352032
2 | COST OF NON-SCHEDULE ITEMS |  | Rs: | --
3 | ADD 10.0 % ABOVE ON SCHEDULE ITEMS |  | Rs: | 435203
4 | COST OF CARRIAGE |  | Rs: | 161979
5 | TOTAL |  |  | 4949214
6 | ADD: 1.02 % CONTIGENCY |  | Rs: | 50482
7 | G. TOTAL |  | Rs: | 4999696
8 | Say Rs:- |  |  | 5000000
SUB ENGINEER
ASSISTANT ENGINEER
EDUCATION WORKS SUB DIVISION MATLI
EXECUTIVE ENGINEER,
EDUCATION WORKS DIVISION,
BADIN.
ASSISTANT ENGINEER,
EDUCATION WORKS SUB-DIV:
MATLI
SUB-ENGINEER EDUCATION WORKS SUB-DIV: MATLI..

## estimates
ESTIMATE.
Name of Work:- |  | MAINTENANCE & REPAIR PROGRAMME 2016-17 OF EDUCATIONAL INSTITUTES (COLLEGE EDUCATION) IN DISTRICT BADIN @ GOVERNMENT BOYS DIGREE COLLEGE MATLI TALUKA MATLI. (B.Sc BLOCK FIRST FLOOR)
S.No. | Descripition. |  | Qty. | Rate. | Unit. | Amount.
PART - A CIVIL WORK.
1 | Dismentling brick work in lime or cement mortor (S.I.No. 13/P-11).
(A) | F-Floor
| O/Roof Parapit Wall B/S | 1x188.50x0.75x2.0 | 283
| " F/S | 1x97.83x0.75x2.0 | 147
| " " | 1x57.0x0.75x2.0 | 86
| Ent: Hall L/Wall | 1x18.0x0.75x2.0 | 27
| " S/Wall | 1x7.67x0.75x2.0 | 12
| C/R S/Wall | 1x2x32.0x0.75x2.0 | 96
| Tover O/Roof L/Wall | 1x2x18.67x0.75x2.0 | 56
| " S/Wall | 1x2x24.0x0.75x2.0 | 72
|  | TOTAL | 779 | 1285.63 | %Cft | Rs: | 10015.0577 | /-
2 | Dismentling cement concrete plain 1:2:4 (S.I.No. 19/C P-11).
(A) | F-Floor
| Tover O/Roof | 1x18.67x26.0x0.17 | 83
| Stair Hall | 1x18.67x10.92x0.17 | 35
| Ent: Hall | 1x18.0x7.75x0.17 | 24
| C/R O/Roof | 1x188.50x33.50x0.17 | 1074
|  | TOTAL | 1216 | 3327.5 | %Cft | Rs: | 40462.4 | /-
3 | Dismentling cement concrete reinforced seprating reinforcement from concrete
cleaning and straighting the same (S.I.No. 20/P-11).
A= | C/R B/S Window Chajja G.Floor | 1x188.50x2.50x0.38 | 179
(B) | Stair Hall | 1x18.67x10.92x0.5 | 102
| Ent Hall | 1x18.0x7.75x0.5 | 70
| C/R Ver;Slab | 1x188.50x33.50x0.5 | 3157
| C/R C/Beam | 1x8x26.0x1.0x2.0 | 416
| C/R B/S Window Chajja F.Floor | 1x188.50x2.50x0.38 | 179
(C) | Tower Slab | 1x18.67x26.0x0.46 | 223
| Tower Col: | 1x3x1.0x1.0x6.33 | 19
| " Beam L/Wall | 1x2x18.67x0.75x1.50 | 42
| " Beam S/Wall | 1x2x26.0x0.75x1.50 | 59
(D) | O/H Tower Cover | 1x15.0x15.0x0.38 | 86
| " L/Wall | 1x2x15.0x0.75x5.0 | 113
| " S/Wall | 1x2x13.50x0.75x5.0 | 101
| " B/Slabl | 1x15.0x15.0x0.5 | 113
| " Beam L/Wall | 1x2x15.0x0.75x1.0 | 23
| " S/Wall | 1x2x13.50x0.75x1.0 | 20
|  | TOTAL | 4902 | 5445 | %Cft | Rs. | 266913.9 | /-
4 | Removing cement or lime plaster (S.I. No. 53/P-14).
First Floor
| C/R I/S | 1x2x(36.0+24.0)x(2.0+1.50) | 420
| C/R I/S Wall | 1x2x2x(33.0+24.0)x(2.0+1.50) | 798
| " " " | 1x2x(34.33+24.0)x(2.0+1.50) | 408
| " " " | 1x2x(33.17x24.0)x(2.0+1.50) | 400
| Ver: I/S " | 1x2x(186.50+6.71)x(2.0+1.50) | 1352
| Stair Hall I/S | 1x(24.0+17.0+24.0)x10.0 | 650
| " O/S | 1x(26.0+19.0+26.0)10.0 | 710
| Ent: Hall | 1x(14.0+17.0+14.0)10.0 | 450
| Lav: I/S | 1x2x(10.42+24.0)x(5.0+1.50) | 447
| Lav: I/S | 1x3x2x(5.0+4.17)x5.0 | 275
| C/R F/S B/S | 1x2x188.0x3.0 | 1131
| Ent: O/S | 1x(19.0+15.0)x10.0 | 340
| C/R S/Wall O/S | 1x2x33.50x5.0 | 335
|  | TOTAL | 7716 | 121 | %Sft | Rs: | 9336.36 | /-
5 | Scrapping ordinary distemper oil bond distempring or paint on walls.
First Floor
| C/R I/S Wall | 1x2x(36.0+24.0)x8.50 | 1020
| " " " | 1x2x2x(33.0+24.0)x8.50 | 1938
| C/R I/S Walls | 1x2x(34.33+24.0)x8.50 | 992
| " " " | 1x2x(33.17+24.0)x8.50 | 972
| Ver: I/S | 1x2x(186.50+6.71)8.50 | 3285
| Com: Lav: I/S | 1x3x2x(5.0+4.17)2.75 | 151
| Lav: Halls I/S | 1x2x(10.42+24.0)x7.0 | 482
| C/R B/S | 1x188.50x9.50 | 1791
| Ver: F/S | 1x(95.83+56.0)x9.50 | 1442
| C/R S/Wall O/S | 1x2x33.50x7.50 | 503
|  | TOTAL | 12576
Deduction:-
First Floor
| C/R Door | 1x5x4.0x7.0 | 140
| " Window | 1x35x4.0x4.0 | 560
| Ver: Opp: F/S | 1x17x4.58x5.0 | 389
| " S/Wall | 1x2x6.58x5.0 | 66
|  | TOTAL | 1155
| Net Qty: | 12576.0 ( - ) 1155.0
|  | TOTAL | 11421 | 226.88 | % Sft. | Rs: | 25911.9648 | /-
6 | Pacca brick work in ground floor I/c stricking of joints in cement sand mortar
ratio 1:6.(S.I.No:5/P-25).
2nd Floor
| Qty: Same as item No.1= A |  | 779
|  | TOTAL | 779 | 13687.74 | P/Cwt | Rs: | 106627.4946 | /-
7 | R.C.C. work I/c all labour and material execpt the cost of steel reinforcement and its
labour for bending and binding which will be paid sperately. This rate also I/c all kinds
of moulds lifting shuttering curing rendering and finishing the exposedsurface (I/c screening
and washing of shingle)(a) R.C.work in roof slab,beams columns rafts lintels and other
structural members laid in situe or precast laid in position complete in all respect(I) Ratio
1:2:4 90 lbs cement 2 Cft sand 4 Cft shingle 1/8" to 1/4" gauge.(S.I.No.6ai/P-19).
(A) | Fist Floor
| Qty: Same as Item No.3B |  | 3924
|  | TOTAL | 3924 | 349.1 | P/Sft | Rs: | 1369868.4 | /-
(B) | 2nd Floor
| Qty: Same as Item No.3C |  | 343
|  | TOTAL | 343 | 361.2 | P/Sft | Rs: | 123891.6 | /-
8 | Fabrication of mild steel reinforcement for cement concrete i/c cutting bending laying
in position making joints and fastening i/c cost of binding wire (also i/c removal of
rust from bars) (S.I.No:7-A/P-20).
a) Tor Steel
| Qty:Same as item No.7 (A+B) = 4267.0x5.50/112 |  | 210
|  | TOTAL | 210 | 5001.7 | P/Cwt | Rs: | 1050357 | /-
9 | P/F G.I. frames/chowkats size of 7"x2" or 4-1/2" x3" for door using 20 guage
GI sheet I/c welded hings and fixing at site with necessary holds fasts filling with
cement sand slurry of ratio 1:6 and repairing the jambs.The cost also I/c all carriage,
tools and plants used in making and fixing. ( S.I.No.29/P-98 )
| Lav: Door | 1x3x(7.0+2.50+7.0) | 50
| Lav: Passage | 1x(7.0+4.0+7.0) | 18
|  | TOTAL | 68 | 228.9 | P/Rft | Rs: | 15565.2 | /-
10 | P/F G.I. frames/chowkats size of 7"x2" or 4-1/2" x3" for door using 20 guage
GI sheet I/c welded hings and fixing at site with necessary holds fasts filling with
cement sand slurry of ratio 1:6 and repairing the jambs.The cost also I/c all carriage,
tools and plants used in making and fixing. ( S.I.No.29/P-98 )
| Lav: Vent | 1x4x2x(2.50+1.50) | 32
|  | TOTAL | 32 | 240.5 | P/Rft | Rs: | 7696 | /-
11 | P/F iron steel grill of 3/4"x1/4" and flat iron frame of 1/2 with approved design and
I/s painting 3coats (S.I.No.26/P-97
| C/R Window | 1x8x3x1.08x3.58 | 93
|  | TOTAL | 93 | 180.5 | P/Sft | Rs: | 16786.5 | /-
12 | Cement plaster 1:6 upto 20 ft height 1/2" thick. (S.I.No.11/P-58)
(A) | 1st Floor
| O/Roof P/P Wall I/O | 1x10.100.0x2.38 | 2380
| " " " | 1x47.33x2.38 | 113
| Qty: Same as item No.4 |  | 7716
|  | TOTAL | 10209 | 2347.57 | P/Cwt | Rs: | 239663.4213 | /-
13 | Cement plaster 1:4 upto 20 ft height 3/8" thick. (S.I.No.11/P-58)
(A) | First Floor
| Qty: Same as item No.12 |  | 10209
|  | TOTAL | 10209 | 2338.49 | P/Cwt | Rs: | 238736.4441 | /-
14 | Notice board made with cement.(S.I.No.1/P-100).
| C/Room. I/S | 1x5x16.0x4.50 | 360
|  | TOTAL | 360 | 58.11 | P/Sft. | Rs: | 20919.6 | /-
15 | P/L 2" thick topping cement concrete 1:2:4 I/c surface finishing and dividing into panells.
2"thick (S.I.No.16/P-47).
2nd Floor
| Qty: Same as item No. 2 | 1216.0/0.17 | 7153
|  | TOTAL | 7153 | 3729.26 | %Sft | Rs: | 266753.9678 | /-
16 | Tow coast of bitumen laid 3/4 Ibs over hot uding over roof and blinded with sand at one
cft per %Sft (S.I.No.13/P-41).
| Qty same as item No.15 |  | 7153
|  | TOTAL | 7153 | 1887.4 | %Sft | Rs: | 135005.722 | /-
17 | R.C.C Spout I/c fixing in position 2-1/2"x6"x5(S.I.No.13/P-21).
| O/Roof | 1x18 | 18
|  | TOTAL | 18 | 261.25 | Each | Rs: | 4702.5 | /-
18 | First class deodar wood wrought joinery in doors and windows etc fixed in
position I/c chawkhats, holdfasts hinges, iron tower bolts, handles and cords
with hooks etc deodar panelled or panelled and glazed or fully glazed
1-3/4" thick. (S.I.No.7b/P-65) (Shutters).
| Lav: Door | 1x3x2.50x7.0 | 53
| C/R Door | 1x2x4.0x7.0 | 56
| Lav: Window | 1x2x3.0x4.0 | 24
|  | TOTAL | 133 | 902.93 | P/Sft | Rs: | 120089.69 | /-
19 | Applying chemical poishing on existing mosaic/marble mflooring/dado I/c cleaning grinding with
carborandum stone/sand paper and applying chemical polish as per requirment.(S.I.No70/P-55)
(A) | Fisrt Floor
| C/R Floor | 1x34.33x24.0 | 824
| " " | 1x32.17x24.0 | 772
| " " | 1x2x33.0x24.0 | 1584
| " " | 1x36.0x24.0 | 864
| Ver: Floor | 1x186.50x6.71 | 1251
| Ent: | 1x17.38x8.75 | 152
| Stair F/S | 1x17.63x11.0 | 194
| C/R I/S Skarting | 1x2x(34.33+24.0)x0.68 | 79
| " " | 1x2x(32.17+24.0)x0.68 | 76
| " " | 1x2x2x(33.0+24.0)x.0.68 | 155
| " " | 1x2x(36.0+24.0)x0.68 | 82
| Ver: " | 1x2x(186.50+6.71)x0.68 | 263
| Ent: S/Wall | 1x2x8.75x0.68 | 12
| Stair Hall F/S | 1x2x11.0x0.68 | 15
| Stair Steps | 1x50x4.50x1.50 | 338
| " Landing | 1x4x5.13x4.87 | 100
| Stair Side | 1x2x70.52x0.68 | 96
|  | TOTAL | 6857 | 36.6 | P/Sft | Rs: | 250966 | /-
20 | Extra labour for lifting of steel above first floor for every additional floor (S.I.No28/P-23)
| Qty: Same as item No.7 A+B = 4267.0 x 5.50 /112 |  | 210
|  | TOTAL | 210 | 151.25 | P/Cwt | Rs: | 31762.5 | /-
|  |  |  | TOTAL Rs:- |  |  | 4352032
CERTIFICATE
Certified that I have prepared this estimate under the supervision of Assistan Engineer Education works sub-Division on the basis of drawing & design supplied to me for items identified by the Assistant Engineer. The rate provided in this estimate are from composite schedule of Rates & sanctioned rate analysis.
SUB-ENGINEER
Certified that this estimate has been prepared by the Sub-Engineer under my supervision for the items identified by me which are prepared for the execution. Further certified that the quantities provided in this estimate are correct.
ASSISTANT ENGINEER
EDUCATION WORKS SUB-DIVISION
MATLI
MORBLE AREA FLOOR (SHEET).
01 | Laying white marble flooring fine dressed on the surface without winding set in line
mortar 1:2 I/c rubbing & polish of the joints (a) 3/4" thick flooring (S.I.No.28(a)/P-43)
INTERMEDIATE BLOCK
| C/R Floor | 1x2x33.75x24.75 | 1671
| N.C.C Floor | 1x2x11.75x11.75 | 276
| Store Floor | 1x8.75x17.87 | 156
| C/R Floor | 1x3x24.75x19.75 | 1466
| Principle Office Floor | 1x18.0x14.0 | 252
| Staff Room | 1x13.0x19.75 | 257
| Store | 1x10.75x19.75 | 212
| Lobby | 1x23.75x23.75 | 564
| Clerk Office | 1x25.0x19.75 | 494
| '' '' | 1x11.75x15.75 | 185
| Store | 1x12.13x11.75 | 143
| Ver;Floor | 1x171.25x6.75 | 1156
| '' '' | 1x33.25x6.75 | 224
| '' '' | 1x27.0x6.75 | 182
| '' '' | 1x90.63x6.75 | 612
| '' '' | 1x28.38x6.75 | 192
| Botony;Lab | 1x2x28.83x30.0 | 1730
| Physics Lab; | 1x38.83x30.0 | 1165
| Chemistry Lab; | 1x48.75x30.0 | 1463
| Store | 1x8.83x9.83 | 1050
| Office | 1x8.83x9.83 | 87
| '' | 1x13.50x10.50 | 142
| Ver; | 1x168.63x6.75 | 1138
| Lib; + C/R | 1x2x34.83x24.83 | 1730
| '' Ver; | 1x73.0x6.75 | 493
| Store | 1x3x12.38x11.75 | 436
| C/Room | 1x34.0x24.0 | 816
| Bot;Lab | 1x24.58x24.0 | 590
| Zoology Lab | 1x24.58x24.0 | 590
| Physics Lab; | 1x25.75x24.0 | 618
| Chemistry Lab; | 1x33.75x24.0 | 810
| Office + Store | 1x8x10.25x11.68 | 957
| Ver;Floor | 1x188.50x6.71 | 1265
| Ent;F/S | 1x17.42x7.0 | 122
| Stair Hall | 1x16.67x17.0 | 283
| F/S P/F | 1x2x25.x15.0 | 750
|  | TOTAL | 24277
ASSISTANT ENGINEER
| SUB-ENGINEER |  | EDUCATION WORKS SUB-DIVISION
MATLI

## M.Statement
MATERIAL STATEMENT
NAME OF WORK:- |  | MAINTENANCE & REPAIR PROGRAMME 2016-17 OF EDUCATIONAL INSTITUTES (COLLEGE EDUCATION) IN DISTRICT BADIN @ GOVERNMENT BOYS DIGREE COLLEGE MATLI TALUKA MATLI. (B.Sc BLOCK FIRST FLOOR)
S.NO | Description |  | Qty: | Cement | Sand | Shingle | Stone Ballast | Steel | Bricks | Earth Filling
01 | CC 1:5:10 |  | --- | --- | --- | --- | --- | --- | 10517 | ---
02 | Brick Masonry 1:6 |  | 779 | 23 | 216 | --- | --- | --- | --- | ---
03 | Cement Plaster 1/2"Thick 1:6 |  | 10209 | 49 | 368 | --- | --- | --- | --- | ---
04 | Cement Plaster 3/8"Thick 1:4 |  | 10209 | 51 | 254 | --- | --- | --- | --- | ---
05 | Cement Plaster 3/4"Thick 1:4 |  | --- | --- | --- | --- | --- | --- | --- | ---
06 | Glazed tiles 8"x8"x3/4x1:2 |  | --- | --- | --- | --- | --- | --- | --- | ---
07 | Cement Pointing 1:2 |  | --- | --- | --- | --- | --- | --- | --- | ---
08 | CC Topping 2"Thick (1:2:4) |  | 7153 | 215 | 536 | 1073 | --- | --- | --- | ---
09 | RCC 1:2:4 |  | 4267 | 751 | 1877 | 3755 | --- | --- | --- | ---
10 | CC Topping 3"Thick (1:2:4) |  | --- | --- | --- | --- | --- | --- | --- | ---
11 | Fabrication (Tor+Mild) |  | 210 | --- | --- | --- | --- | 210 | --- | ---
|  |  | --- | 1089 | 3251 | 4828 | --- | 210 | 10517 | ---
|  |  | --- | 60.93 | 2106.92 | 2562.76 | --- | 1585.96 | 1086.44 | ---
|  |  | --- | 66352.77 | 68495.9692 | 123730.0528 | --- | 3330.516 | 114260.8948 | ---
|  |  |  | TOTAL Rs: | 161979
ASSISTANT ENGINEER
EDUCATION WORKS SUB DIVISION MATLI
SUB ENGINEER

## Rate Analysis
RATE ANALYSIS
| NAME OF WORK :- | MAINTENANCE & REPAIR PROGRAMME 2016-17 OF EDUCATIONAL INSTITUTES (COLLEGE EDUCATION) IN DISTRICT BADIN @ GOVERNMENT BOYS DIGREE COLLEGE MATLI TALUKA MATLI. (B.Sc BLOCK FIRST FLOOR)
S. NO | DESCRIPTION. | S.BAJRI. | S.METAL. | H.SAND | S. NO | DESCRIPTION. | CEMENT. | S. NO | DESCRIPTION. | BRICK.
01 | From quarry to Main Road. | 14 | 13 | 3 | 01 | From Lucky Star Factory | 60 | 01 | From Killin to T.G.Ali . | 8
02 | From mile 110/4 to 122/0 | 11.4 | -- | 9 |  | to Hyderabad |  | 02 | From T.G.Ali to Matli. | 16
03 | From mile 122/0 to Ring Road. | 4.4 | 4.4 | 4.4 | 02 | From Hyderabad to Matli. | 31
04 | From Ring Road to Matli. | 31 | 31 | 31
[6 empty] | Total | 91 |  | Total | 24
[6 empty] | Say:- | 91 |  | Say:- | 24
| TOTAL:- | 60.8 | 48.4 | 47.4
[5 empty] | 01 | Rate for 1st 02 miles. | 7.53 | 01 | Rate for 1st 06 miles. | 617.54
| Say:- | 61 | 48 | 47 | 02 | Rate for subsquent. |  | 02 | Rate for subsquent.
[6 empty] | miles ( 89 x 0.60 ). | 53.4 |  | miles ( 18.0 x 26.05 ). | 468.9
01 | Rate for 1st 06 miles. | 771.96 | 771.96 | 771.96 |  | TOTAL:- | 60.93 |  | TOTAL:- | 1086.44
|  | (55 x32.56) | (42 x32.56) | (41 x32.56)
02 | Rate for subsquent miles. | 1790.8 | 1367.52 | 1334.96
| TOTAL:- | 2562.76 | 2139.48 | 2106.92
ASSISTANT ENGINEER
| SUB-ENGINEER | [6 empty] | EDUCATION WORKS SUB-DIVISION
MATLI

## SCHEDULE B..
SCHEDULE - B.
Name of Work:- |  | MAINTENANCE & REPAIR PROGRAMME 2016-17 OF EDUCATIONAL INSTITUTES (COLLEGE EDUCATION) IN DISTRICT BADIN @ GOVERNMENT BOYS DIGREE COLLEGE MATLI TALUKA MATLI. (B.Sc BLOCK FIRST FLOOR)
S.No. | Descripition. |  | Qty. | Rate. | Unit. | Amount.
PART - A CIVIL WORK (i).
1 | Dismantling brick work in lime or cement mortor.(S.I.No.13.P.10)
|  |  | 779 | 1285.63 | %Cft | Rs: | 10015.0577 | /-
(Rs.One thousand two hundred Eighty five & ps sixty three only).
2 | Dismentling cement concrete plain 1.2.4(S.I.No. 19C/P-10).
|  |  | 1216 | 3327.5 | %Cft | Rs: | 40462.4 | /-
(Rs.Three thousand three hundred twenty seven & ps fifty only).
3 | Dismentling cement concrete reinforced separating reinfor cement from concrete
cleaning and straightening the same.(S.I.No. 20/P-11).
|  |  | 4603 | 5445 | %Cft | Rs: | 250633.35 | /-
(Rs.Five thousand four hundred fourty five & ps zero only).
4 | Removing cement or lime plaster.(S.I.No. 53 P-13).
|  |  | 7321 | 121 | %Sft | Rs: | 8858.41 | /-
(Rs.One hundred twenty one & ps zero only).
5 | Scraping ordinary oil bound distempering or paint on Wall.(S.I.No. 54 b -P-13).
|  |  | 6853 | 226.88 | %Sft | Rs: | 15548.0864 | /-
(Rs.Two hundred twenty six & ps Eighty eight only).
6 | Pacca brick work in ground floor I/c stricking of joints in cement sand mortar
ratio 1:6.(S.I.No:5/P-25).
|  |  | 779 | 13687.74 | %Cft | Rs: | 106627.4946 | /-
(Rs.Thirteen thousand six hundred eighty seven & ps seventy four only).
7 | R.C.C. work I/c all labour and material execpt the cost of steel reinforcement and its
labour for bending and binding which will be paid sperately. This rate also I/c all kinds
of moulds lifting shuttering curing rendering and finishing the exposedsurface (I/c screening
and washing of shingle)(a) R.C.work in roof slab,beams columns rafts lintels and other
structural members laid in situe or precast laid in position complete in all respect(I) Ratio
1:2:4 90 lbs cement 2 Cft sand 4 Cft shingle 1/8" to 1/4" gauge.(S.I.No.6ai/P-19).
(A) | Fist Floor
|  |  | 3577 | 349.1 | P/Sft | Rs: | 1248730.7 | /-
(Rs.Three hundred fourty nine & ps ten only).
(B) | 2nd Floor
|  |  | 324 | 361.2 | P/Sft | Rs: | 117028.8 | /-
(Rs.Three hundred sixty one & ps twenty only).
8 | Fabrication of mild steel reinforcement for cement concrete i/c cutting bending laying
in position making joints and fastening i/c cost of binding wire (also i/c removal of
rust from bars) (S.I.No:7-A/P-20).
| a) Tor steel | TOTAL | 191.56 | 5001.7 | P/Cwt | Rs: | 958125.652 | /-
(Rs.Five Thousand one & ps seventy only).
9 | P/F G.I. frames/chowkats size of 7"x2" or 4-1/2" x3" for door using 20 guage
GI sheet I/c welded hings and fixing at site with necessary holds fasts filling with
cement sand slurry of ratio 1:6 and repairing the jambs.The cost also I/c all carriage,
tools and plants used in making and fixing. ( S.I.No.29/P-98 )
|  | TOTAL | 68 | 228.9 | P/Cwt | Rs: | 15565.2 | /-
(Rs.Two hundred twenty eight & ps ninty only).
10 | P/F G.I. frames/chowkats size of 7"x2" or 4-1/2" x3" for window using 20 guage
GI sheet I/c welded hings and fixing at site with necessary holds fasts filling with
cement sand slurry of ratio 1:6 and repairing the jambs.The cost also I/c all carriage,
tools and plants used in making and fixing. ( S.I.No.29/P-98 )
|  | TOTAL | 32 | 240.5 | P/Cwt | Rs: | 7696 | /-
(Rs.Two hundred fourty & ps fifty only).
11 | P/F iron steel grill of 3/4"x1/4" and flat iron frame of 1/2 with approved design and
I/s painting 3coats (S.I.No.26/P-97
|  | TOTAL | 93 | 180.5 | P/Cwt | Rs: | 16786.5 | /-
(Rs.one hundred eighty & ps fifty only).
12 | Cement plaster 1:6 upto 20 ft height 1/2" thick. (S.I.No.11/P-58)
(A) | 1st Floor | TOTAL | 9814 | 2347.57 | %0Sft | Rs: | 23039.052 | /-
(Rs two thousand.three hundred fourty seven & ps fifty seven only).
13 | Cement plaster 1:4 upto 20 ft height 3/8" thick. (S.I.No.11/P-58)
(A) | First Floor | TOTAL | 9814 | 2338.49 | %Sft | Rs: | 229499.4086 | /-
(Rs. Two thousand three hundred thirty eight & ps fourty nine only).
14 | Notice board made with cement.(S.I.No.1/P-100).
|  | TOTAL | 360 | 58.11 | P/Sft | Rs: | 20919.6 | /-
(Rs. Fifty eight & ps eleven only).
15 | P/L 2" thick topping cement concrete 1:2:4 I/c surface finishing and dividing into panells.
2"thick (S.I.No.16/P-47).
|  | TOTAL | 7153 | 3729.26 | %Sft | Rs: | 266753.9678 | /-
(Rs.Three Thousand seven hundred twenty nine & ps twenty six only).
16 | Tow coast of bitumen laid 3/4 Ibs over hot uding over roof and blinded with sand at one
cft per %Sft (S.I.No.13/P-41).
|  | TOTAL | 7153 | 1887.4 | %Sft | Rs: | 135005.722 | /-
(Rs.One thousand eight hundred eighty seven & ps fourty only).
17 | Reinforced cement concrete spout including fixing in position 2 1/2"x6"x5"
(i/c edges).two coats.(S.I.No.14 /P-18).
|  | TOTAL | 18 | 261.25 | P.E | Rs: | 4702.5 | /-
(Rs.One thousand eight hundred eighty seven & ps fourty only).
18 | First class deodar wood wrought joinery in doors and windows etc fixed in
position I/c chawkhats, holdfasts hinges, iron tower bolts, handles and cords
with hooks etc deodar panelled or panelled and glazed or fully glazed
1-3/4" thick. (S.I.No.7b/P-65) (Shutters).
|  | TOTAL | 124 | 902.93 | P.Sft | Rs: | 111963.32 | /-
(Rs.Nine hundred fifty zero two & ps Ninty three only).
19 | Applying chemical poishing on existing mosaic/marble mflooring/dado I/c cleaning grinding with
carborandum stone/sand paper and applying chemical polish as per requirment.(S.I.No70/P-55)
(A) | Fisrt Floor
|  | TOTAL | 6857 | 36.6 | P.Sft | Rs: | 250966.2 | /-
(Rs.Thirty six & ps sixty only).
20 | Extra labour for lifting of steel above first floor for every additional floor (S.I.No28/P-23)
|  | TOTAL | 191.56 | 151.25 | P.Cwt | Rs: | 28973.45 | /-
(Rs. One hundred fifty one & ps twenty five only).
21 | White washing three coats.(S.I.No:26/P-60).
|  | TOTAL | 6857 | 829.95 | %Sft | Rs: | 56909.6715 | /-
(Rs. eight hundred twenty nine & ps ninty five only).
22 | Distempering two coats (S.I.No.24/P-54 )
|  |  | 14174 | 1043.9 | %Sft | Rs: | 147962.386 | /-
(Rs.One Thousand Eighty six & ps ninty only).
23 | Painting new surface ( c) painting door and windows any type two coats.(S.I.No.5/P-76).
|  | TOTAL | 295 | 2116.41 | %Sft | Rs: | 6243.4095 | /-
(Rs. Two thousand one hundred sixteen & ps fourty one only).
24 | Painting old surface ( c ) painting doors and window any type two coats. (S.I.No.4(c ) i,ii /P-68).
|  | TOTAL | 1456 | 1106.06 | %Sft | Rs: | 16104.2336 | /-
(Rs.One Thousand one hundred six & ps zero six only).
|  |  |  | TOTAL Rs:- |  |  | 4302471 | /-

## r.a
RATE ANALYSIS
| NAME OF WORK :- | ADP.NO.276 CONSTRUCTION / REPAIR / RAISING OF COMPOUND WALL OF COLLEGES IN SINDH (SECURITY THREATENED COLLEGES) @GOVERNMENT BOYS DEGREE COLLEGE MATLI TALUKA MATLI DISTRICT BADIN (2015-2016 PROGRAMME).
S. NO | DESCRIPTION. | S.BAJRI. | S.METAL. | H.SAND | S. NO | DESCRIPTION. | CEMENT | S. NO | DESCRIPTION. | BRICK.
01 | From quarry to Main Road. | 14 | 13 | 3 | 01 | From Zeal Pak Factory | 27 | 01 | From killin to Phalkara | 5
02 | From mile 110/4 to 122/0 | 11.4 | -- | 9 |  | to Site. |  | 02 | From Phalkara to site. | 7
03 | From mile 122/0 to Ring Road. | 4.4 | -- | 4.4
04 | From Ring Road to Site | 29 | 29 | 29
[6 empty] | Total | 27 |  | Total | 12
[6 empty] | Say:- | 27 |  | Say:- | 12
| TOTAL:- | 58.8 | 42 | 45.4
[5 empty] | 01 | Rate for 1st 02 miles. | 7.53 | 01 | Rate for 1st 06 miles. | 617.54
| Say:- | 59 | 42 | 45 | 02 | Rate for subsquent. |  | 02 | Rate for subsquent.
[6 empty] | miles ( 25 x 0.60 ). | 15 |  | miles ( 6 x 26.05 ). | 156.3
01 | Rate for 1st 06 miles. | 771.96 | 771.96 | 771.96 |  | TOTAL:- | 22.53 |  | TOTAL:- | 773.84
|  | ( 53x32.56) | (36 x32.56) | (39 x32.56)
02 | Rate for subsquent miles. | 1725.68 | 1172.16 | 1269.84
| TOTAL:- | 2497.64 | 1944.12 | 2041.8
ASSISTANT ENGINEER
| SUB-ENGINEER | [6 empty] | EDUCATION WORKS SUB-DIVISION
MATLI