## L.P
ADP-477 (ILMI) INFRASTRUCTURE DEVELOPMENT HYDERABAD DIVISION @ GPS CHAK NO: 14 TALUKA S.F.RAHU.
80
4x4
4x4
|  |  | C/R |  |  | C/R
|  |  | 14.0 x 16.0 |  |  | 14.0 x 16.0
70
Ver: 6.0 wide
M.Gate
| SUB-ENGINEER | [7 empty] | ASSISTANT ENGINEER
EDUCATION WORKS SUB-DIVISION
S.F.RAHU

## sum
SUMMARY OF COST
NAME OF WORK:- | ADP-477 (ILMI) INFRASTRUCTURE DEVELOPMENT HYDERABAD DIVISION @ GPS CHAK NO: 14 TALUKA S.F.RAHU.
S # | Item of Work | Total Amount
Part-A Civil Work
1 | Cost of Schedule Items | 1262427.3318
| Add 10 % Above | 126242.7332
| Add Cartage Amount | 81740.1719
| Total | 1470410.2369
2 | Part-B (W/S & S/F)
| Cost of Schedule Items | 47793.57
| Add 10 % above | 4779.357
| Total | 52572.927
3 | Cost of Non-Schedule Item | 14417.7
| Total | 14417.7
| Total:- | 1537400.8639
133140
| Ad: 0.50% Contigency | 7687.0043 | 19971
| G.Total:- | 1545087.8682 | 153111
1698000
1544889
|  |  | 1.5449 | -0.00019887
| Say Rs: in Million | 1.5451
SUB-ENGINEER |  | ASSISTANT ENGINEER
EDUCATION WORKS SUB DIVISION
S.F.RAHU

## Meterial
M A T E R I A L S T A T E M E N T
| NAME OF WORK:- | ADP-477 (ILMI) INFRASTRUCTURE DEVELOPMENT HYDERABAD DIVISION @ GPS CHAK NO: 14 TALUKA S.F.RAHU.
S.No | Description | Quantity | Cement | Sand | Shingle | Stone Ballast | Steel | Bricks
1 | RCC 1:2:4 | 639 | 112.464 | 281.16 | 562.32 | 0 | 0 | 0
2 | Fabrication (Tor + Mild) | 31.37 | 0 | 0 | 0 | 0 | 31.37 | 0
3 | Brick Masonary 1:6 | 583 | 17.49 | 161.491 | 0 | 0 | 0 | 7870.5
4 | Cement Plaster 1/2" Thick 1:6 | 4074 | 19.5552 | 146.664 | 0 | 0 | 0 | 0
5 | Cement Plaster 3/8" Thick 1:4 | 4074 | 20.37 | 101.4426 | 0 | 0 | 0 | 0
6 | Cement Plaster 3/4" Thick 1:4 | 564 | 5.64 | 33.84 | 0 | 0 | 0 | 0
7 | Cement Pointing 1:2 | 1984 | 14.2848 | 35.712 | 0 | 0 | 0 | 0
8 | CC Topping 2" thick(1:2:4) | 1067 | 32.01 | 80.025 | 160.05 | 0 | 0 | 0
9 | CC Topping 3" thick | 37 | 1.665 | 4.44 | 8.88 | 0 | 0 | 0
|  | Total | 223.479 | 844.7746 | 731.25 | 0 | 31.37 | 7870.5
|  | Rate | 57.93 | 4027.96 | 3376.76 | 3930.28 | 2895.72 | 1164.59
|  | Amount | 12946.1385 | 34027.183 | 24692.5575 | 0 | 908.3874 | 9165.9056
|  | G.Total | 81740.1719
| SUB-ENGINEER |  |  |  |  | ASSISTANT ENGINEER
EDUCATION WORKS SUB-DIVISION
S.F.RAHU

## Schedule
SCHEDULE "B"
Name of Work:- |  | ADP-477 (ILMI) INFRASTRUCTURE DEVELOPMENT HYDERABAD DIVISION @ GPS CHAK NO: 14 TALUKA S.F.RAHU.
S.No. | Descripition. |  | Qty. | Rate. | Unit. | Amount.
a) Civil Work (i)
1 | Dismentling CC reinforced seperating reainforcement from
concrate cleaning and straightning the same(S.I.No.20/P-10)
|  |  | 639 | 5445 | %Cft | Rs: | 34793.55 | /-
(Rs: five thousand four hundred forty five only)
2 | Dismentling CC 1:2:4 plain (S.I.No.19-c/P-10)
|  |  | 170 | 3327.5 | %Cft | Rs: | 5656.75 | /-
(Rs: three thousand thee hundred twenty seven and paisa fifty only)
3 | Dismentling brick work in cement or lime morter(S.No.13/P-10)
|  |  | 519 | 1285.63 | %Cft | Rs: | 6672.4197 | /-
(Rs: one thousand two hundred eighty five & Ps: sixty three only)
4 | Removing Cement or lime plaster (S.No.53/P-13)
|  |  | 2499 | 121 | %Sft | Rs: | 3023.79 | /-
(Rupees one thousand twenty one only)
5 | R.C.C. work I/c all labour and material execpt the cost of steel reinforcement and its
labour for bending and binding which will be paid sperately. This rate also I/c all kinds
of moulds lifting shuttering curing rendering and finishing the exposedsurface (I/c screening
and washing of shingle)(a) R.C.work in roof slab,beams columns rafts lintels and other
structural members laid in situe or precast laid in position complete in all respect(I) Ratio
1:2:4 90 lbs cement 2 Cft sand 4 Cft shingle 1/8" to 1/4" gauge.(S.I.No.6/P-15).
|  |  | 639 | 337 | P.Cft | Rs: | 215343 | /-
(Rs: three hundred thirty seven only)
6 | Fabrication of mild steel reinforcement for cement concrete i/c cutting bending
laying in position making joints and fastening i/c cost of binding wire (also i/c removal
of rust from bars) (S.I.No:8/P-16).
| a) Tor Steel |  | 28.52 | 5001.7 | P. Cwt | Rs: | 142648.484 | /-
(Rs: five thousand one & Paisa seventy only)
| b) Mild Steel |  | 2.85 | 4820.2 | P. Cwt | Rs: | 13737.57 | /-
(Rs: five thousand one & Paisa seventy only)
7 | Pacca brick work in other then building in cement sand morter
ratio 1:6 (S.I.No.7(I-e)/P-21)
|  |  | 583 | 12346.65 | %Cft | Rs: | 71980.9695 | /-
(Rs: twelve thousand three hundred forty six & Paisa sixty five only)
8 | M/F steel grated door with 1/16" thick sheeting I/c angle iron frame 2"x2"x3/8"&3/4"
square bars 4" centre to centre with locking arrangement.(S.I.No. 24/P-91).
|  |  | 50 | 726.72 | P.Sft. | Rs: | 36336 | /-
(Rs: seven hundred twenty six and paisa seventy two only)
9 | Cement plaster 1:6 upto 12 ft height 1/2" thick. (S.I.No.13-c/P-51)
|  |  | 4074 | 2206.6 | % Sft | Rs: | 89896.884 | /-
(Rs: two thousand two hundred six and paisa sixty only)
10 | Cement plaster 1:4 upto 12 ft height 3/8" thick. (S.I.No.11-a/P-51)
|  |  | 4074 | 2197.52 | %Sft | Rs: | 89526.9648 | /-
(Rs: two thousand one hundred ninty seven and paisa fifty two only)
11 | Cement plaster 1:4 upto 12 ft height 3/4" thick. (S.I.No.11-c/P-51)
|  |  | 565 | 3015.76 | %Sft | Rs: | 17039.044 | /-
(Rs: three thousand fifteen and paisa seventy six only)
12 | Extra labour rate for making cement plaster pattas/bend width not less
then 6" wide with fine finishing as directed by Engineer Incharge.
|  |  | 846 | 19.36 | P.Sft | Rs: | 16378.56 | /-
(Rs: ninteen & Paisa thirty six only)
13 | First class deodar wood wrought joinery in doors and windows etc fixed in
position I/c chawkhats, holdfasts hinges, iron tower bolts, handles and cords
with hooks etc deodar panelled or panelled and glazed or fully glazed
1-3/4" thick. (S.I.No.7b/P-57) (Shutters).
|  |  | 138 | 1273.76 | P.Sft | Rs: | 175778.88 | /-
(Rs: one thousand two hundred seventy three and paisa seventy three only)
14 | Making notice board made with cement (S.I.No.1/P-94)
|  |  | 64 | 58.11 | P.Sft | Rs: | 3719.04 | /-
(Rs: fifty eight and paisa eleven only)
15 | Cement pointing struck joints on walls 1:2 (S.I.No.19/P-52)
|  |  | 1970 | 1287.44 | %Sft | Rs: | 25362.568 | /-
(Rs: one thousand two hundredeighty seven & Paisa forty four only )
16 | P/L CC 1:2:4 topping I/c surface finishing and dividing into
panells (S.I.No.16/P-41)
| a) 2" thick |  | 1067 | 3275.5 | %Sft | Rs: | 34949.585 | /-
(Rs: three thousand two hundred seventy five & Paisa fifty only)
| b) 3" thick. |  | 37 | 4482.11 | %Sft | Rs: | 1658.3807 | /-
(Rs: four thousand four hundred eleven & Paisa eighty two only)
17 | Cement tiles 8"x8"x3/4" laid flat in 1:2 cement morter over a bed
of 3/4" thick cement morter 1:2 (S.I.No. 13/P-40)
|  |  | 644 | 10916.65 | %sft | Rs: | 70303.226 | /-
(Rs: ten thousand nine hundred sixteen & Paisa sixty five only)
18 | Tow coast of bitumen laid 34 Lbs over hot using over roof and blinded with sand at one
cft per %Sft (S.I.No.13/P-41).
|  |  | 1067 | 1887.4 | % Sft | Rs: | 20138.558 | /-
(Rs: one thousand eight hundred eighty seven & Paisa forty only)
19 | White washing three coats ( S.I.No26/P-53)
|  |  | 966 | 829.95 | % Sft | Rs: | 8017.317 | /-
(Rs: eight hundred twenty nine and paisa ninty five only)
20 | Primary coat of chalk under distemper (S.I.No.23/P-53)
|  |  | 4397 | 442.75 | %Sft | Rs: | 19467.7175 | /-
(Rs: four hundred forty two and paisa seventy five only)
21 | Distempering three coats (S.I.No.24/P-53 )
|  |  | 4397 | 1079.65 | %Sft | Rs: | 47472.2105 | /-
(Rs: one thousand seventy nine and Ps: sixty five only)
22 | Colour Wash two coats (S.I.No.25/P-53)
|  |  | 1970 | 859.9 | % Sft | Rs: | 16940.03 | /-
(Rs: eight hundred fifty nine and paisa ninty only)
23 | Painting new surface painting to doors and windows any type i/c edges 3 coats
( S.I.No.4-c/P-67)
|  |  | 276 | 2116.41 | %Sft | Rs: | 5841.2916 | /-
(Rs: two thousand one hundred sixteen and paisa forty one only)
24 | Painting new surface ( c) painting guard bars, gates iron bars gratings, railings I/c
standard bracess (etc) and similar open work three coats.(S.I.No.4d/P-68).
|  |  | 100 | 1270.83 | %Sft | Rs: | 1270.83 | /-
(Rs: one thousand two hundred seventy and paisa eighty three only)
25 | Painting new surface painting to doors and windows any type i/c edges 2 coats
( S.I.No.5-c/P-67)
|  |  | 48 | 1160.06 | %sft | Rs: | 556.8288 | /-
(Rs: one thousand one hundred sixty & paisa six only)
[5 empty] | Total | Rs: | 1174486 | /-
PART- B (W/S & S/F)
1 | P/F squating type white glazsed earthen ware W.C. pan with I/c cost of flushing cistern
with internal fitting and flush pipe with bend and making requisite number of holes in
walls plinth & floor for pipe connections & making good in cement concrete 1:2:4.
(a) W.C. pan of not less than 19" clear opening between flushing rims and 3 gallons
flushing tank (i) with 4@ dia C.I. trape.(S.I.No.1(b-i)/P-1).
|  |  | 2 | 4802.6 | P/No. | Rs. | 9605.2 | /-
(Rs: four thousand eight hundred two and paisa sixty only)
2 | P/F handle valves (China) (S.I.No.5-i/P-17).
| 1/2" dia |  | 1 | 200.42 | Each | Rs. | 200.42 | /-
(Rs: two hundred & Pasia forty two only)
3 | Supplying & fixing fiber glass tank of approved quality and desing and wall thickness as
specified I/c cost of nuts, bolts and fixing in plateform of cement concrete 1:3:6 and
making connections for in let out let & over flow inlet outlet flow pipes etc. complete
(S.I.No.3(c)/P-21)
| 250 Gallons |  | 1 | 21989.61 | Each | Rs. | 21989.61 | /-
(Rs: twenty one thousand nine hundred eighty nine and paisa sixty one only)
4 | Providing R.C.C pipes with collars class "B" and digging the trenches to required depth
and fixing in position I/c cutting fitting and jointing with maphalt composition & cement
mortar 1:1 and testing with water pressure to a head of 4 feet above the top of the
highest pipe & refilling with excavted staff 6" dia R.C.C pipes class "B" (S.I.No.2-b/P-23)
| 1/4" Dia |  | 12 | 146.57 | P.Rft | Rs. | 1758.84 | /-
(Rs: one hundred forty six & Pasia fifty seven only)
5 | Providing G.I. Pipes specials and clamps etc I/c fixing cutting & fitting I/c cost of
breaking through walls and floor making good etc painting two coats after cleaning
the pipe etc with white zink paint with pigment to match the colour of the building &
testing with water to a pressure head of 200 ft: and handling (External).
(S.I.No.1-ii/P-14).
| a) 3/4" Dia. |  | 120 | 86.36 | P.Rft | Rs. | 10363.2 | /-
(Rs: eighty six & Pasia thirty six only)
| b) 1/2" Dia. |  | 30 | 73.21 | P.Rft | Rs. | 2196.3 | /-
(Rs: seventy three & Pasia twenty one only)
6 | Providing PVC Pipes of Class "D" (equivalent) in trenches I/c cutting fitting
and jointing with "Z" joints with one rubber ring I/c testing with water to a head
of 122 meters or 400 feet (25 mm) 1" dia (S.I.No.3/P-23). (PHE)
|  |  | 60 | 28 | P.Rft | Rs: | 1680 | /-
(Rs: twenty eight only)
|  |  |  | TOTAL:- |  | Rs: | 47793 | /-
Non-Schedule Item
1 | P&F water pimping set 1/2 H.P Motor Block single phase 220 volts with 1" x 1 1/4"
suction and delivery 50 ft head i/c making C.C 1:3:6 plate form of required size and fixing
with nuts and bolts (local made) (R.A).
|  |  | 1 | 14417.7 | Each. | Rs: | 14417.7 | /-
(Rs: forteen thousand four hundred seventeen & Pasia seventy only)
|  |  |  | TOTAL:- |  | RS: | 14417.7 | /-

## LC
| NAME OF WORK :- | ADP-477 (ILMI) INFRASTRUCTURE DEVELOPMENT HYDERABAD DIVISION @ GPS CHAK NO: 14 TALUKA S.F.RAHU.
S# | DESCRIPTION | CRUSH | S.METAL | H.SAND | S# | DESCRIPTION | CEMENT | STEEL | S# | DESCRIPTION | BRICKS
1 | From quarry to main road | 3.875 | 3 | 3 | 1 | From Zeal Pak Factory to Badin | 59 | 63 | 1 | From Badin to SFR | 19
2 | From mile 110/4 to 122/0 | 15.125 | 7 | 9 | 2 | From Badin to S.F.Rahu | 19 | 19 | 2 | From S.F.Rahu to Site | 8
3 | From mile 122/0 to Ring road |  | 16.625 | 4.4 | 3 | From S.F.Rahu to Site | 8 | 8
4 | From Ring road to Badin | 48.875 | 48.875 | 63 |  | Total | 86 | 90 |  | Total | 27
5 | From Badin S.F.Rahu | 19 | 19 | 19 |  | Say | 86 | 90
6 | From S.F.Rahu to Site | 8 | 8 | 8 | [5 empty] | Rate for 1st 6 miles | 617.54
| Total | 94.875 | 102.5 | 106.4 | 1 | Rate for 1st three miles | 8.13 | 63 |  | Rate for subsequent miles
| Say | 95 | 103 | 106 | [5 empty] | ( 21 x 26.05 ) | 547.05
[5 empty] | 2 | Rate for Subsequent miles | (83x0.60). | (87x32.56) |  | Total | 1164.59
1 | Rate for 1st 6 miles | 771.96 | 771.96 | 771.96 |  |  | 49.8 | 2832.72
|  | (89x32.56) | (97 x32.56) | (100x32.56) |  | Total | 57.93 | 2895.72
2 | Rate for subsequent miles | 2604.8 | 3158.32 | 3256
| Total | 3376.76 | 3930.28 | 4027.96
|  |  |  | SUB ENGINEER |  |  | ASSIATANT ENGINEER
EDUCATION WORKS SUB-DIVISION
S.F.RAHU

## Estimate
ESTIMATE.
Name of Work:-
ADP-477 (ILMI) INFRASTRUCTURE DEVELOPMENT HYDERABAD DIVISION @ GPS CHAK NO: 14 TALUKA S.F.RAHU.
S.No: | Discription |  | Qty |  | Rate | Unit |  | Amount
a) Civil Work (i)
1 | Dismentling CC reinforced seperating reainforcement from
concrate cleaning and straightning the same(S.I.No.20/P-10)
a) | CR + Main Slab | 1x34.37x29.87x0.42 | 431
| CR T.Beam | 1x2x15.67x0.75x1.50 | 35
| B.Plate | 1x302.50x1.13x0.50 | 4
b) | CR L/W Lint: | 1x2x31.37x1.13x0.75 | 53
| Ver: L/Wall Lintal | 1x31.37x1.13x1.0 | 35
| " S/W " | 1x2x6.0x1.13x1.0 | 14
| Lav: L/W | 1x10.25x0.75x0.75 | 6
| " R/Slab | 1x12.25x7.50x0.37 | 34
| M.Gate Col: | 1x2x1.50x1.50x6.0 | 27
|  |  | 639 | Cft | 5445 | %Cft | Rs: | 34793.55 | /-
2 | Dismentling C.C Plain 1:2:4 (S.No.19/P-10)
a) | CR Floor | 1x2x14.0x16.0x0.25 | 112
| Ver: " | 1x29.13x6.0x0.25 | 44
| Door Sill | 1x2x3.50x1.25x0.25 | 2
| Ver: Opp: | 1x7.75x1.33x0.25 | 3
161
b) | Lav: Floor | 1x2x4.0x4.0x0.25 | 8
| " D/Sill | 1x2x2.50x1.0x0.25 | 1
9
|  | Total (a + b) = | 170 | Cft | 3327.5 | %Cft | Rs: | 5656.75 | /-
3 | Dismentling brick work in cement or lime morter(S.No.13/P-10)
| C/Wall | 1x(50.0+65.0+85.0)x0.37x5.0 | 370
| " | 1x(25.0+13.0+12.0)x0.37x5.0 | 93
| Piller | 1x41x0.75x0.37x5.0 | 56
|  |  | 519 | 1285.63 | 1285.63 | %Cft | Rs: | 6672.4197 | /-
4 | Removing cement or lime platser(S.I.No.53/P-13)
| CR I/Side | 1x2x2x(14.0+16.0)x(11.0+11.33)/2 | 1339
| Ver: " | 1x2x(29.13+6.0)x(11.33+11.50)/2 | 802
| " O/S F/S | 1x31.37x11.50 | 361
| " " Side | 1x2x8.13x(11.33+11.50)/2 | 186
| Lav: O/S F/S | 1x10.25x8.0 | 82
| " " Side | 1x5.50x(8.0+7.75)/2 | 43
| S/Tank I/S | 1x2x(5.0+4.50)x4.0 | 76
| Ver: Step | 1x7.75x3.0 | 23
2912
Deduction
| Door | 1x2x3.50x7.0 | 49
| Wind's | 1x6x3.0x4.0 | 72
| Ver: F/S Opp: | 1x3x7.75x8.0 | 186
| " Side " | 1x2x4.50x8.0 | 72
| Lav: Door | 1x2x2.50x7.0 | 35
414
| Net Qty: | 2912.0 ( - ) 414.0 = | 2498 | Sft | 121 | %Sft | Rs: | 3022.58 | /-
5 | R.C.C. work I/c all labour and material execpt the cost of steel reinforcement and its
labour for bending and binding which will be paid sperately. This rate also I/c all kinds
of moulds lifting shuttering curing rendering and finishing the exposedsurface (I/c screening
and washing of shingle)(a) R.C.work in roof slab,beams columns rafts lintels and other
structural members laid in situe or precast laid in position complete in all respect(I) Ratio
1:2:4 90 lbs cement 2 Cft sand 4 Cft shingle 1/8" to 1/4" gauge.(S.I.No.6ai/P-19).
| CR + Main Slab | 1x34.37x29.87x0.42 | 431
| CR T.Beam | 1x2x15.67x0.75x1.50 | 35
| B.Plate | 1x302.50x1.13x0.50 | 4
| CR L/W Lint: | 1x2x31.37x1.13x0.75 | 53
| Ver: L/Wall Lintal | 1x31.37x1.13x1.0 | 35
| " S/W " | 1x2x6.0x1.13x1.0 | 14
| Lav: L/W | 1x10.25x0.75x0.75 | 6
| " R/Slab | 1x12.25x7.50x0.37 | 34
| M.Gate Cols: | 1x2x1.50x1.50x6.0 | 27
|  |  | 639 | Cwt | 337 | P. Cwt | Rs: | 215343 | /-
6 | Fabrication of mild steel reinforcement for cement concrete i/c cutting bending
laying in position making joints and fastening i/c cost of binding wire (also i/c removal
of rust from bars) (S.I.No:8/P-16).
| a) Tor Steel | R.C.C x 5.0 = 639.0 x 5.0 | 28.52 | Cwt | 5001.7 | P. Cwt | Rs: | 142648.484 | /-
112 112
| b) Mild Steel | R.C.C x 0.50 = 639.0 x 0.50 | 2.85 | Cwt | 4820.2 | P. Cwt | Rs: | 13737.57 | /-
112 112
7 | Pacca brick work in other than building I/c stricking of joints in cement sand
ratio 1:6.(S.I.No. 7/P-21).
| C/Wall | 1x284.0x0.37x5.0 | 525
| Piller | 1x42x0.75x0.37x5.0 | 58
|  |  | 583 |  | 12346.65 | %Cft | Rs: | 71980.9695 | /-
8 | M/F steel grated door with 1/16" thick sheeting I/c angle iron frame 2"x2"x3/8"&3/4"
square bars 4" centre to centre with locking arrangement.(S.I.No. 24/P-91).
| C/Wall M/Gate. | 1x10.0x5.0 | 50 | 726.72 | 726.72 | P.Sft. | Rs: | 36336 | /-
9 | Cement plaster 1:6 upto 12 ft height 1/2" thick. (S.I.No.13-c/P-51)
| CR I/S | 1x2x2x(14.0+16.0)x(11.33+11.0)/2 | 1340
| Ver: I/S | 1x2x(29.13+6.0)x(11.33+11.50)/2 | 802
| Ver: FS | 1x1x31.37x11.50 | 361
| " O/Side | 1x2x8.13x(11.33+11.50)/2 | 186
| Lav: O/Side | 1x10.25x8.0 | 82
| " Side | 1x5.50x(8.0+7.75)/2 | 43
| C/Wall | 1x284.0x5.0 | 1420
| Piller side | 1x2x42x0.37x5.0 | 155
4389
Deducation
| CR Door | 1x2x3.5x7.0 | 49
| " Window | 1x6x3.0x4.0 | 72
| V/R Opp: | 1x3x7.75x8.0 | 186
| Sides | 1x2x4.50x8.0 | 72
| Lav: Door | 1x2x2.50x7.0 | 35
414
| Net Qty | a) 4389.0 ( - ) 414 = | 3975 |  | 2206.6 | % Sft | Rs: | 87712.35 | /-
(b) | S/Tank I/Side | 1x2x(5.0+4.50)x4.0 | 76
| Ver: Step | 1x7.75x3.0 | 23
99
|  | Total (a + b) = | 4074 | 2206.6 | 2206.6 | % Sft | Rs: | 89896.884 | /-
10 | Cement plaster 1:4 upto 12 ft height 3/8" thick. (S.I.No.11-a/P-51)
a) | Qty: same as item No.9-a |  | 3975
b) | Qty: same as item No.9-b |  | 99
|  |  | 4074 |  | 2197.52 | % Sft | Rs: | 89526.9648 | /-
11 | Cement plaster 1:4 upto 12 ft height 3/4" thick. (S.I.No.11-c/P-51)
a) | C/R B/Side | 1x31.37x0.50 | 16
| " Sides | 1x2x17.13x0.50 | 17
| " Corner | 1x2x2x0.50x10.50 | 21
| " Window | 1x4x2x0.50x4.50 | 18
| " " | 1x4x3.0x0.50 | 6
| Lav: B/Side | 1x10.25x0.50 | 5
| " Sides | 1x2x0.50x7.75 | 8
| C/Wall O/S | 1x284.0x0.50 | 142
| Sides | 1x2x42x4.50x0.50 | 189
422
b) | C/R Plinth | 1x2x(25.62+31.62)x1.25 | 142
142
|  | Total (a+b) = | 564 |  | 3015.76 | % Sft. | Rs: | 17008.8864 | /-
12 | Extra labour rate for making cement plaster pattas/bend width not less
then 6" wide with fine finishing as directed by Engineer Incharge.
| Qty: same as item No.11 (a) / 0.50 = 422/0.50 = |  | 844 |  | 19.36 | P.Rft | Rs: | 16339.84 | /-
13 | First class deodar wood wrought joinery in doors and windows etc fixed in
position I/c chawkhats, holdfasts hinges, iron tower bolts, handles and cords
with hooks etc deodar panelled or panelled and glazed or fully glazed
1-3/4" thick. (S.I.No.7b/P-57)
(Shutters Only)
| C/R Door | 1x2x3.50x7.0 | 49
| " Window | 1x4x3.0x4.0 | 48
| Lav: Door | 1x2x2.50x7.0 | 35
| " Vent: | 1x2x2.0x1.50 | 6
|  |  | 138 |  | 1273.76 | P.Sft | Rs: | 175778.88 | /-
14 | Making notice board made with cement (S.I.No.1/P-94)
| C/Room. I/S. | 1x2x8.0x4.0 | 64 |  | 58.11 | P.Sft. | Rs: | 3719.04 | /-
15 | Cement pointing struck joints on walls 1:2 (S.I.No.19/P-52)
| CR B/Side | 1x30.37x10.50 | 319
| CR Sides | 1x2x16.63x(10.50+10.33)/2 | 360
| Lav: L/Wall B/S | 1x9.25x7.25 | 67
| " Sides | 1x5.0x(7.25+7.50)/2 | 37
| C/Wall O/S | 1x284.0x4.50 | 1278
2061
Deduction.
| C/R Windows | 1x4x3.0x4.0 | 48
| C/R Lintal | 1x30.37x0.75 | 23
| Lav: Vent: | 1x2x2.0x1.50 | 6
77
| Net Qty: | 2061.0 ( - ) 77.0 = | 1984 |  | 1287.44 | % Sft | Rs: | 25542.8096 | /-
16 | P/L CC 1:2:4 topping I/c surface finishing and dividing into
panells (S.I.No.16/P-41)
a) | 2" thick
| CR O/R | 1x34.37xx28.37 | 975
| Lav: O/Roof | 1x12.25x7.50 | 92
|  |  | 1067 |  | 3275.5 | %Sft | Rs: | 34949.585 | /-
b) | 3" thick
| Lav: Floor | 1x2x4.0x4.0 | 32
| D/Sill | 1x2x2.50x1.0 | 5
|  |  | 37 |  | 4411.82 | %Sft | Rs: | 1632.3734 | /-
17 | Cement tiles 8"x8"x3/4" laid flat in 1:2 cement morter over a bed of
3/4" thick cement morter 1:2 (S.I 58/P-53)
| Qty: same item No: 2 (a) = 161.0 / 0.25 = |  | 644 |  | 10916.65 | %Sft | Rs: | 70303.226 | /-
18 | Tow coast of bitumen laid 34 Lbs over hot using over roof and blinded with sand at one
cft per %Sft (S.I.No.13/P-41).
| Qty: same item No: 16 (a) = |  | 1067 |  | 1887.4 | % Sft | Rs: | 20138.558 | /-
19 | White washing three coats ( S.I.No26/P-53)
| C/R Ceiling | 1x2x14.0x16.0 | 448
| Ver: " | 1x29.13x6.0 | 175
| Beam Sides | 1x2x2x16.0x1.50 | 96
| Lav: Ceiling | 1x2x4.0x4.0 | 32
| Lav: Chajja | 1x2x(12.25+5.50)x1.0 | 36
| C/R " | 1x2x(34.037+25.37)x1.50 | 179
|  |  | 966 |  | 829.95 | % Sft | Rs: | 8017.317 | /-
20 | Primary coat of chalk under distemper (S.I.No.23/P-53)
| Qty: same as item No.10 (a) |  | 3975
| Qty: same as item No.11 (a) |  | 422
|  |  | 4397 |  | 442.75 | % Sft | Rs: | 19467.7175 | /-
21 | Distempering three coats (S.I.No.24/P-53 )
| Qty: same asitem No.20 |  | 4397 |  | 1079.65 | % Sft | Rs: | 47472.2105 | /-
22 | Colour wah two coats.(S.I.No.25/P-53)
| Qty: same asitem No.15 |  | 1984 |  | 859.9 | % Sft | Rs: | 17060.416 | /-
23 | Painting new surface ( c) painting door and windows any type three coats.
(S.I.No.5-c/P-67).
| Qty: same as item No.12. = 2x 138.0 = |  | 276 | 2116.41 | 2116.41 | %Sft | Rs. | 5841.2916 | /-
24 | Painting new surface ( c) painting guard bars, gates iron bars gratings, railings I/c
standard bracess (etc) and similar open work three coats.(S.I.No.4d/P-68).
| C/Wall M/Gate | 1x2x10.0x5.0 | 100 | 1270.83 | 1270.83 | %Sft |  | 1270.83 | /-
25 | Painting old surface ( c) painting door and windows any type two coats.
(S.I.No.4-c/P-66).
| CR Windows | 1x2x2x3.0x4.0 | 48
|  |  | 48 |  | 1160.06 | %Sft | Rs. | 556.8288 | /-
[5 empty] | G.Total:- |  | Rs: | 1262427.3318 | /-
PART- B.(W/S & S/F)
1 | P/F squating type white glazsed earthen ware W.C. pan with I/c cost of flushing cistern
with internal fitting and flush pipe with bend and making requisite number of holes in
walls plinth & floor for pipe connections & making good in cement concrete 1:2:4.
(a) W.C. pan of not less than 23" clear opening between flushing rims and 3 gallons
flushing tank (i) with 4@ dia C.I. trape.(S.I.No.1(b-i)/P-1).
| Comm: Lav | 1x2 | 2 | No: | 4802.6 | P/No. | Rs. | 9605.2 | /-
2 | P/F handle valves (China) (S.I.No.5-i/P-17).
1/2" dia
| Lav: O/S | 1x1 | 1 | Each | 200.42 | Each | Rs. | 200.42 | /-
3 | Supplying & fixing fiber glass tank of approved quality and desing and wall thickness as specified I/c
cost of nuts, bolts and fixing in plateform of cement concrete 1:3:6 and making connections for in let
out let & over flow inlet outlet flow pipes etc. complete .(S.I.No.3(a)/P-21) (250 Gallons)
| O/H Tank | 1x1 | 1 | Each | 21989.61 | P.Each | Rs. | 21989.61 | /-
4 | Providing R.C.C pipes with collars class "B" and digging the trenches to required depth
and fixing in position I/c cutting fitting and jointing with maphalt composition & cement
mortar 1:1 and testing with water pressure to a head of 4 feet above the top of the
highest pipe & refilling with excavted staff 6" dia R.C.C pipes class "B" (S.I.No.2-b/P-23)
| Lav: to O/S | 1x2x6.0 | 12 | Rft | 146.57 | P.Rft | Rs. | 1758.84 | /-
5 | Providing G.I. Pipes specials and clamps etc I/c fixing cutting & fitting I/c cost of
breaking through walls and floor making good etc painting two coats after cleaning
the pipe etc with white zink paint with pigment to match the colour of the building &
testing with water to a pressure head of 200 ft: and handling .(S.I.No.1-ii/P-14).
(a) | 3/4" Dia.
| O/S to Lav: | 1x120.0 | 120 | Rft | 86.36 | P.Rft | Rs. | 10363.2 | /-
(b) | 1/2" Dia.
| Lav: I/S | 1x30.0 | 30 | Rft | 73.21 | P.Rft | Rs. | 2196.3 | /-
6 | Providing PVC Pipes of Class "D" (equivalent) in trenches I/c cutting fitting
and jointing with "Z" joints with one rubber ring I/c testing with water to a head
of 122 meters or 400 feet (25 mm) 1" dia (S.I.No.3/P-23).
| Bore to Motor | 1x60.0 | 60 |  | 28 | P.Rft | Rs: | 1680 | /-
[5 empty] | TOTAL:- |  | Rs: | 47793.57 | /-
Non-Schedule Item
1 | P&F water pimping set 1/2 H.P Mono Block single phase 220 volts with1"x1" -1/4"
suction and delivery 50 ft head i/c making C.C 1:3:6 plate form of required size and fixing
with nuts and bolts (local made) (R.A).
Rft
| Water Pump. | 1x1 | 1 |  | 14417.7 | Each | Rs: | 14417.7 | /-
[5 empty] | TOTAL:- |  | Rs: | 14417.7 | /-
CERTIFICATE
Certified that I have prepared this estimate under the supervision of Assistan Engineer
Education works Sub-Division S.F.Rahu on the basis of drawing & design supplied to me
for items identified by the Assistant Engineer. The rate provided in this estimate are from composite
schedule of Rates & sanctioned rate analysis.
SUB-ENGINEER
Certified that this estimate has been prepared by the Sub-Engineer under my supervision
for the items identified by me which are prepared for the execution. Further certified that
the quantities provided in this estimate are correct.
ASSISTANT ENGINEER
EDUCATION WORKS SUB-DIVISION
S.F.RAHU

## Face Sheet
F A C E S H E E T
| FUND HEAD. |  |  | -:- | PROVINCIAL ADP
| MAJOR HEAD. |  |  | -:- | 09 Education Affairs & Services
| MINOR HEAD |  |  | -:- | DEVELOPMENT
| SERVICE HEAD |  |  | -:- | SCHEME NO. ADP-477
| DEPARTMENTAL HEAD |  |  | -:- | The Detailed working estimate for the
work " (ILMI) INFRASTRUCTURE DEVELOPMENT
HYDERABAD DIVISION @ GPS CHAK NO: 14
TALUKA S.F.RAHU .
Certified that this estimate has been prepared in the office of
the Assistant Engineer, Education Works Sub-Division S.F.Rahu. The expenditure
incurred on the above said work shall be chargeable against the Head
of Account 09 Education Affairs & Services.
[5 empty] | Estimated Cost | Rs: 1.545 (Million)
GENERAL DESCRIPTION
| HISTORY. | Government of Sindh have approved the ADP Scheme during the year
for District Badin, which are to be executed by Education & Literacy Department
within years. The above said work is one of the approved schemes hance its
estimate has been prepared.
| SCOPE. | The work will be completed in current financial years subject to availbility of funds.
| LAND. | The Education Department Government of Sindh shall provide the plot for
the purpose of construction of the above said building.
| METERIAL. | No lead weather small or long for carraige of meterial for which finished
items are applicable is to be paid seperately. However the construction meterial
as detailed below shall have to be brought by the contractor from the following
pre-determined quaries / approved source of supply. The estimate is based on
the rates provided by the Composite Schedule of Rates (Recent Edition).
| 1- | Crush |  |  | Thano Bula Khan
| 2- | Stone Ballast |  |  | Chillya
| 3- | Hill Sand |  |  | Bholari
| 4- | Steel |  |  | Hyderabad
| 5- | Cement |  |  | Zeal-Pak
| 6- | Bricks |  |  | Badin
|  | SUB-ENGINEER |  |  |  | ASSISTANT ENGINEER
EDUCATION WORKS SUB-DIVISION
S.F.RAHU

## Abstract
S # | Descripition. |  | Qty. | Rate. | Unit. | Amount.
PART- C.
1 | P&F water pimping set 1/2 H.P Mono Block single phase 220 volts with1"x1" -1/4"
suction and delivery 50 ft head i/c making C.C 1:3:6 plate form of required size and fixing
with nuts and bolts (local made) (R.A).
| Water Pump. | 1x1 | 1 | 14417.7 | Each | Rs: | 14417.7 | #REF! | /-
|  |  | TOTAL:- | TOTAL:- |  | RS: | 14417.7 | #REF! | /-
CERTIFICATE
Certified that I have prepared this estimate under the supervision of Assistan Engineer
Education works Sub-Division S.F.Rahu on the basis of drawing & design supplied to me for items
identified by the Assistant Engineer. The rate provided in this estimate are from composite schedule
of Rates & sanctioned rate analysis.
SUB-ENGINEER
Certified that this estimate has been prepared by the Sub-Engineer under my supervision
for the items identified by me which are prepared for the execution. Further certified that
the quantities provided in this estimate are correct.
ASSISTANT ENGINEER
EDUCATION WORKS SUB-DIVISION
S.F.RAHU