## FACE SHEET
FACE SHEET.
FUND HEAD:- |  |  | PROVINCIAL
MAJOR HEAD:- |  |  | 6-314 .(BUILDING AND STRUCTURE).
MINOR HEAD:- |  |  | DEVELOPMENT.
SERVICE HEAD:- |  |  | SCHEME NO._____________
DEPARTMENTAL HEAD:- |  |  | ADP NO 477 ILMI' (INFRASTRUCTURE DEVELOPMENT) HYDERABAD DIVISION DISTRICT BADIN (CASE NO 13780), @GBPS MUHAMMAD HASHIM JARWAR U/C BUDHO QAMBRANI TALUKA MATLI , SEMIS CODE 401030404.
The estimate has been prepared in the office of the Assistant Enginner
Education works Sub-Division Matli. The probable expenditure incurred on the
above said work, shall be chargeable against the head of account. 6-314
(Buildings & structure) (Dev:).
Estimated cost Rs: _____1223000/=_____
GENERAL DISCRIPTION.
1. HISTORY:- |  | The Government of Sindh have approved the ADP- scheme during
the year 200 -- for District Badin which are to be executed by
works & services Departement in (02) financial years.
2. SCOPE. |  | This work is to be completed in current financial year subjected to
available of funds.
3. LAND. |  | The Education Department Government of Sindh shall provided plot for
Construction of the proposed scheme/work.
4. MATERIAL. |  | No lead weather small or long for carriage of material of items for which
finished items are applicable is to be paid separately. However the
construction material as detailed below shall have to be brought by the
contractor from the following predetermined quarried/approved source
of supply. The estimate is mainly based on rates provided by the
composite schedule of rates.(Recent Edition).
1. Bajri from. |  |  |  |  | Thana Bola Khan.
2.Stone ballast from. |  |  |  |  | Onger.
3.Hill sand from. |  |  |  |  | Bholari.
4.Stone from.
5.Steel & cement from. |  |  |  |  | Hyderabad.
6.Brick from. |  |  |  |  | Tando Ghulam Ali
7.Tiles from. |  |  |  |  | Hyderabad.
| Sub-Engineer. |  |  |  |  | ASSISTANT ENGINEER
EDUCATION WORKS SUB-DIVISION
MATLI

## Summary of cost
SUMMARY OF COST
NAME OF WORK:- |  | ADP NO 477 ILMI' (INFRASTRUCTURE DEVELOPMENT) HYDERABAD DIVISION DISTRICT BADIN (CASE NO 13780), @GBPS MUHAMMAD HASHIM JARWAR U/C BUDHO QAMBRANI TALUKA MATLI , SEMIS CODE 401030404.
|  |  |  | PART - A | PART - B
1 | COST OF SCHEDULE ITEM |  | Rs: | 880660 | 105549
2 | COST OF NON-SCHEDULE ITEMS |  | Rs: | -- | 14418
3 | ADD 10 % ABOVE OVER SCHEDULE ITEM |  | Rs: | 88066 | 10555
4 | COST OF CARRIAGE |  | Rs: | 111750 | ---
5 | TOTAL |  |  | 1080476 | 130522
6 | TOTAL ( A + B ) |  | Rs: | 1210998
7 | ADD: 1.0 % CONTIGENCY |  | Rs: | 12110
8 | G. TOTAL |  | Rs: | 1223108
9 | Say Rs:- |  |  | 1223000
SUB ENGINEER
EXECUTIVE ENGINEER,
EDUCATION WORKS DIVISION,
BADIN.
ASSISTANT ENGINEER,
EDUCATION WORKS SUB-DIV:
MATLI
SUB-ENGINEER EDUCATION WORKS SUB-DIV: MATLI..

## estimate
E S T I M A T E
Name of Work:- |  | ADP NO 477 ILMI' (INFRASTRUCTURE DEVELOPMENT) HYDERABAD DIVISION DISTRICT BADIN (CASE NO 13780), @GBPS MUHAMMAD HASHIM JARWAR U/C BUDHO QAMBRANI TALUKA MATLI , SEMIS CODE 401030404.
S.No. | Descripition. |  | Qty. | Rate. | Unit. | Amount.
PART - A CIVIL WORK
1 | Dismentling cement concrete plain 1:2:4 (S.I.No. 19/C P-10).
| O/Roof C/R Room | 1x46.50x28.50x0.17 | 225
| Lav: O/Roof | 1x12.25x7.50x0.17 | 16
| C/R Floor | 1x2x20.0x16.0x0.25 | 160
| Ver: '' | 1x41.13x6.0x0.25 | 62
| Door Side | 1x2x4.0x1.25x0.25 | 3
| Ver: Opp: F/S | 1x2x6.0x1.50x0.25 | 5
|  | TOTAL | 471 | 3327.5 | %Cft | Rs: | 15672.525 | /-
2 | Removing cement or lime plaster.(S.I.No. 53 P-13).
| C/R I/S Walls | 1x2x2x(20.0+16.0)x2.50 | 360
| Ver: I/S | 1x2x(41.13+6.0)x2.50 | 236
| Ver: F/S L/Wall | 1x43.38x2.50 | 108
| Plinth O/S | 1x2x(43.75+25.75)x2.0 | 278
| Lav: Plinth | 1x2x(10.63+5.63)x2.0 | 65
|  | TOTAL | 1047 | 121 | %Sft | Rs: | 1266.87 | /-
3 | Excavation in foundation of building briges and other structure I/c dagbelling
dreesing,refilling around the structure with excavated earth watering and
ramming lead upto 5 feet, (b) In ordinary soil. (S.I.No.18.b/P-4).
| C/Wall Col: footing. | 1x40x2.0x2.0x2.0 | 320
| " Gate Col: | 1x2x2.0x2.0x2.0 | 16
| Plinth Parot | 1x150.0x1.0x1.0 | 150
| M/Hool | 1x6.0x6.0x4.0 | 144
|  | TOTAL | 630 | 3176.25 | %0Cft | Rs. | 2001.0375 | /-
4 | Cement concrete brick or stone ballast 1-1/2" to 2" gauge ratio 1:5:10. (S.I.No:- 4.C/P-15).
| C/Wall Col: footing. | 1x40x2.0x2.0x0.5 | 80
| " Gate Col: | 1x2x2.0x2.0x0.75 | 6
| Plinth Parot | 1x150.0x1.0x0.38 | 57
| '' U/Bed | 1x150.0x2.25x0.38 | 128
| M/Hool | 1x6.0x6.0x0.5 | 18
|  | TOTAL | 289 | 8694.95 | %Cft | Rs: | 25128.4055 | /-
5 | Pacca brick work in foundation & plinth in cement sand martor ratio 1:6 ( S.I.No: 4,(I)(e) /P-20.21 ).
| Plinth Parot | 1x150.0x0.75x2.0 | 225
| M/Hool L/Wall | 1x2x6.0x0.75x6.0 | 54
| '' S/Wall | 1x2x4.50x0.75x6.0 | 41
|  | TOTAL | 320 | 11948.36 | %Cft | Rs: | 38234.752 | /-
6 | Suplying & filling Sand under floor and plugging in walls.(S.I.No:29 /P-26).
| Plinth Parot U/Bed | 1x150.0x2.25x1.0 | 338
|  |  | 338 | 1141.25 | %Cft | Rs: | 3857.425 | /-
7 | R.C.C. work I/c all labour and material execpt the cost of steel reinforcement and its
labour for bending and binding which will be paid sperately. This rate also I/c all kinds
of forms moulds lifting shuttering curing rendering and finishing the exposedsurface (I/c screening
and washing of shingle)(a) R.C.work in roof slab,beams columns rafts lintels and other
structural members laid in situ or precast laid in position complete in all respect(I) Ratio
(1:2:4) 90 lbs cement 2 Cft sand 4 Cft shingle 1/8" to 1/4" gauge.(S.I.No.6(a),i/P-16).
| C/Wall Col: Footing | 1x40x1.50x1.50x1.0 | 90
| " " Pedistal | 1x40x0.75x0.75x2.0 | 45
| " Plinth Beam | 1x3x100.0x0.75x0.75 | 169
| " Above Plinth | 1x40x0.75x0.75x5.0 | 113
| C/Wall Gate Col: | 1x2x2.0x2.0x3.50 | 28
| " " | 1x2x1.50x1.50x7.0 | 32
| M/Hool Cover | 1x6.0x6.0x0.42 | 15
|  | TOTAL | 492 | 337 | P/Cft | Rs: | 165804 | /-
8 | (a)Fabrication of mild steel reinforcement for cement concrete i/c cutting bending laying
in position, making joints and fastening i/c cost of binding wire (also i/c removal of
(b) using Tor Bars) (S.I.No:8-(a)+(b)/P-17).
a) Using Tor Bar
| Qty Same Item No.07 | 492.0 x 5.50/112 | 24.1607
|  | TOTAL | 24.1607 | 5001.7 | P/Cwt | Rs: | 120841 | /-
9 | Pacca brick work other than building i/c striking of joints upto 20 feet height in cement sand mortar ratio 1:6 ( S.I.No: 7,(I)(e) /P-22 ).
| C/Wall | 1x3x100.0x0.38x5.0 | 570
|  | TOTAL | 570
Deduction :
| C/Wall Col: . | 1x13.0x0.38x5.0 | 25
| " Gate | 1x40x0.75x0.38x5.0 | 57
|  | TOTAL | 82
| Net Qty: | 570.0 ( - ) 82.0 | 488
|  | TOTAL | 488 | 12346.65 | %Cft | Rs: | 60251.652
10 | Cement plaster 1:6 upto 12' ft height 1/2" thick. (S.I.No.13(b) /P-52)
| C/Wall | 1x3x100.0x5.38 | 1614
| Plinth Parot | 1x150.0x1.38 | 207
| M/Hool I/S | 1x2x(4.50+4.50) x6.0 | 108
| '' O/S | 1x2x(6.0+6.0) x3.25 | 78
| Qty Same Item No.02 |  | 1047
|  | TOTAL | 3054
Deduction
| C/Wall Col: . | 1x40x0.75x5.38 | 161
| " Gate | 1x13.0x5.38 | 70
|  | TOTAL | 231
| Net Qty: | 3054.0 ( - ) 231.0 | 2823
|  | TOTAL | 2823 | 2206.6 | %Sft | Rs: | 62292.318
11 | Cement plaster 1:4 upto 12' ft height 3/8" thick. (S.I.No.11(a) /P-52)
| Qty:Same as item No.10 |  | 2823
|  | TOTAL | 2823 | 2197.52 | %Sft | Rs: | 62035.9896 | /-
12 | Cement plaster 1:4 upto 12' ft height 3/4" thick. (S.I.No.11(c) /P-52)
| C/Wall O/S Patta | 1x3x100.0x0.5 | 150
|  | TOTAL | 150 | 3015.76 | %Sft | Rs: | 4523.64
13 | Extra labour rate for making cement plaster pattas/band around straight or carved openings and around the edges of roof slabs, the width not less than 6" with fine finishing as directed by Engineer Incharge.(S.I.No.35/P-55)
| Qty:Same as item No.12 150.0 / 0.5 |  | 300
|  | TOTAL | 300 | 19.36 | P/Rft | Rs. | 5808
14 | Cement pointing struck joints on walls ratio 1:2 (S.I.No.19(a)/P-53).
| C/R L/Wall B/S | 1x43.38x11.50 | 499
| C/R S/Wall | 1x2x17.13x11.50 | 394
| C/Wall O/S | 1x3x100.0x4.50 | 1350
|  | TOTAL | 2243
Deduction
| C/Wall Col: | 1x40x0.75x4.50 | 135
| C/Wall Gate | 1x13.0x4.50 | 59
| C/R Window | 1x4x4.0x4.0 | 64
|  | TOTAL | 258
| Net Qty: | 2243.0 ( - ) 258.0 | 1985
|  | TOTAL | 1985 | 1287.44 | %Sft | Rs: | 25555.684
15 | P/L 2" thick topping cement concrete 1:2:4 I/c surface finishing and dividing
into panells. (S.I.No. 16(c) /P-42)
| O/Roof C/R | 1x46.50x28.50 | 1325
| Lav;O/Roof | 1x12.25x7.50 | 92
| M/Hool | 1x4.50x4.50 | 20
|  | TOTAL | 1437 | 3275.5 | %Sft |  | 47068.935 | /-
16 | P/L 3" thick topping cement concrete 1:2:4 I/c surface finishing and dividing into panells.
2"thick (S.I.No.16/P-47).
| C/R Floor | 1x2x20.0x16.0 | 640
| Ver; '' | 1x41.13x6.0 | 247
| Door Side | 1x2x4.0x1.25 | 10
| Ver; Opp;F/S | 1x2x6.0x1.50 | 18
| Plinth Parot | 1x150.0x3.0 | 450
| Lav;Floor | 1x2x4.0x4.0 | 32
| '' Door Side | 1x2x2.50x1.0 | 5
|  | TOTAL | 1402 | 4411.82 | %Sft | Rs: | 61853.7164 | 61853.7164
17 | Two coats of bitumen laid 34 lbs over hot using over roof and blinded with sand at
one Cft per % Sft.(S.I.No.13 /P-41).
| C/R O/Roof | 1x46.50x28.50 | 1325
|  | TOTAL | 1325 | 1887.4 | %Sft | Rs: | 25008.05 | /-
18 | Making & fixing steel grated door with 1/16" thick sheeting I/c angle iron frame 2"x2"and 3/4" square bars 4" center to center with locking arrangmant (S.I.No.24/P-92) .
| C/Wall M/Gate | 1x10.0x6.0 | 60
|  | TOTAL | 60 | 726.72 | P/Sft | Rs: | 43603.2
19 | White washing two coats.(S.I.No:26/P-60).
| C/R Celling | 1x2x20.0x16.0 | 640
| '' C/Beam | 1x2x2x16.0x1.50 | 96
| Ver; Celling | 1x41.13x6.0 | 247
| O/S Chhajja | 1x2x(46.50+25.50)x2.08 | 300
| Lav; Celling | 1x2x4.0x4.0 | 32
| O/S Chhajja | 1x2x(12.25+5.50)x1.50 | 53
|  | TOTAL | 1368 | 425.84 | %Sft | Rs: | 5825.4912 | /-
20 | Distempering two coats (S.I.No.24/P-60 )
| C/R I/S Walls | 1x2x2x(20.0+16.0)x9.0 | 1296
| Ver; I/S '' | 1x2x(24.13+6.0)x9.0 | 848
| Ver; F/S O/S | 1x43.38x9.0 | 390
| '' S/Wall O/S | 1x2x8.25x11.50 | 190
| Com;Lav;I/S | 1x2x2x(4.0+4.0)x8.0 | 256
| O/S | 1x2x(10.25+5.5)x8.0 | 252
|  | TOTAL | 3232
Deduction
| C/R Door | 1x2x4.0x7.0 | 56
| ''' Window | 1x2x4.0x4.0 | 32
| Ver;Opp;F/S | 1x2x6.0x8.0 | 96
| '' '' | 1x4x5.50x5.50 | 121
|  | TOTAL | 305
| Net Qty: | 3232.0 ( - ) 305.0 | 2927
|  | TOTAL | 2927 | 1043.9 | %Sft | Rs: | 30554.953 | /-
21 | Primary coat of chalk under distemper (S.I.No.23/P-58).
| Qty: same as item No. 10 |  | 2823
| Qty: same as item No. 12 |  | 150
|  | TOTAL | 2973
Deduction
| M/Hool I/S | 1x2x(4.50+4.50)x6.0 | 108
|  | TOTAL | 108
| Net Qty: | 2973.0 ( - ) 108.0 | 2865 | 442.75 | %Sft | Rs: | 12684.7875 | /-
22 | Distempering three coats (S.I.No.24/P-60 )
| Qty: same as item No.21 |  | 2865
|  | TOTAL | 2865 | 1079.65 | %Sft | Rs: | 30931.9725 | /-
23 | Colour washing two coats.(S.I.No.25/P-60)
| C/Wall Col: O/S | 1x40x0.75x5.0 | 150
| " Gate Col: | 1x2x2x(1.50+1.50)x7.0 | 84
| C/W Plinth Beam | 1x3x100.0x1.50 | 450
| Qty:Same as item No.14 |  | 1985
|  | TOTAL | 2669 | 859.9 | %Sft | Rs: | 22950.731 | /-
24 | Painting old surface ( c ) painting doors and window any type two coats. (S.I.No.4(c ) i,ii /P-68).
| C/R Door | 1x2x2x4.0x7.0 | 112
| Lav: Door | 1x2x2x2.50x7.0 | 70
| C/R Window | 1x6x2x4.0x4.0 | 192
|  | TOTAL | 374 | 1160.06 | %Sft |  | 4338.6244 | /-
25 | Painting old surface ( c ) painting guard bars, gate iron bars gratings, railing i/c
standard braces (etc) and similar open work.(S.I.No.4(d ) i,ii /P-69).
| C/R Window | 1x12x2x1.75x3.67 | 154
|  | TOTAL | 154 | 674.6 | %Sft |  | 1038.884 | /-
26 | Painting new surface ( d ) preparing surface and painting guard bars, gates of iron bars,
gratings, railings (i/c standards braces, etc.)and similar open work.(S.I.No.5(d ) i,ii /P-70).
| C/Wall Main Gate | 1x2x10.0x6.0 | 120
|  | TOTAL | 120 | 1270.83 | %Sft | Rs. | 1524.996
|  |  |  | TOTAL:- |  | RS: | 880660 | /-
PART - B WATER SUPPLY & SAINATRY WORK
1 | P/F squating type white glazsed earthen ware W.C. pan with I/c cost of flushing cistern with internal fitting and flush pipe with bend and making requisite number of holes in walls plinth & floor for pipe connections & making good in cement concrete 1:2:4.(a) W.C. pan of not less than 23" clear opening between flushing rims and 3 gallons flushing tank (i) with 4@ dia C.I. trape.(S.I.No.1b/P-1).
| Com:Lav: | 1x2 | 2
|  | TOTAL | 2 | 4802.6 | P/No. | Rs. | 9605.2
2 | Providing & fixing 4" dia C.I soil & vent pipes i/c cutting and fitting and extra painting to match the colour of the building (S.I.No.1/P-08)
| Com:Lav: O/S | 1x2x6.0 | 12
|  | TOTAL | 12 | 333.29 | P.Rft | Rs. | 3999.48
3 | Providing & fixing 4" dia C.I terminal guard I/c extra painting to match the colour of the building (S.I.No.11/P-09)
| Lav: O/S | 1x2 | 2
|  | TOTAL | 2 | 389.7 | Each | Rs. | 779.4
4 | Providing & fixing 4"x4x4x dia C.I brach of the required degree with access door Rubber washer 3/8" thick and builts & nuts and extra painting to match the colour of the building (S.I.No.5/P-08)
| Lav: O/S | 1x2 | 2
|  | TOTAL | 2 | 702 | Each | Rs. | 1404
5 | S/F Conceled tee-stop cock of superior quality single C.P head 1/2" dia (S.I.No.12(b)/P-18).
| Com: Lav: I/S | 1x2 | 2
|  | TOTAL | 2 | 889.46 | P.No | Rs. | 1778.92
6 | (a) S.F long bib cock of superior quality with C.P head 1/2" dia (S.I.No.13(a)/P-19).
| Lav: I/S | 1x2 | 2
| Lav:OI/S | 1x1 | 1
|  | TOTAL | 3 | 1109.46 | P.No | Rs. | 3328.38
7 | P/F handle valves (China) (S.I.No.5(i&ii)/P-17).
(i) 1/2" dia
| Lav: O/S | 1x2 | 2
|  | TOTAL | 2 | 200.42 | P/Rft. | Rs. | 400.84
8 | S/F Fiber glass tank of approved quality anddesign and well thickness as specified i/c
cost of nuts , builts and fixing in platform of c.c.plain 1:3:6 and making connection
for in let out let & over flow inlet flow pipes etc complete ( S.I.No:3(a)/P-21).
| O/H Tank | 1x1 | 1
|  | TOTAL | 1 | 21989.61 | P.No | Rs. | 21989.61
9 | Providing R.C.C pipes with collars class "B" and digging the trenches to required depth
and fixing in position I/c cutting fitting and jointing with maphalt composition & cement
mortar 1:1 and testing with water pressure to a head of 4 feet above the top of the
highest pipe & refilling with excavated staff 6" dia R.C.C pipes class "B" (S.I.No.2(b)/P-23)
| Lav: to O/S | 1x2x6.0 | 12
| O/S to Tank | 1x2x12.0 | 24
|  | TOTAL | 36 | 146.57 | P.Rft | Rs. | 5276.52
10 | Providing G.I. Pipes, specials and clamps etc I/c fixing cutting & fitting complete with and I/c
the cost of breaking through walls and roof making good etc painting two coats after cleaning
the pipe etc with white zink paint with pigment to match the colour of the building &
testing with water to a pressure head of 200 ft: and handling .(S.I.No.1ii /P-14).
(a) 3/4" dia.
| O/S to Lav: | 1x30.0 | 30
|  | TOTAL | 30 | 86.36 | P.Rft | Rs. | 2590.8
(a) 1/2" dia.
| Lav: to I/S | 1x30.0 | 30
|  | TOTAL | 30 | 73.21 | P/Rft. | Rs. | 2196.3
(PHE Schedule.
1 | Providing P.V.C pipes of class "D" (equivalent) in touch i/c cutting fitting and jointing
with one rubbing Ring i/c testing with water to hand of 122 meter or 400' ft
( 25 mm 1" dia). (S.I.No.3/P-21 P.H.E)
| Bore to Motor | 1x10.0x100.0 | 1000
|  | TOTAL | 1000 | 28 | P.Rft | Rs: | 28000
2 | Boaring for utbe well in all water bearing soils from ground level upto 100 ft or 30,5 meter depth i/c sinking and with drawing of casting pipe. (S.I.No. 1(a) /P-41) ( Chapter PHE)
| 4" dia. | 1x 100.0 = | 100.0 Rft | 242 | P.Rft | Rs: | 24200 | 48400
|  |  |  | TOTAL Rs:- |  |  | 105549.45
Non-schedule items
1 | P/Fixing Water Pumping Set 1 H.P Mono-Block Single-Phase 220 Volts with 1-1/4" suction & delivery 50 ft: head i/c making C.C.1:3:6 plate form of required size & fixing with nuts & boklts ( Local Made) (R.A).
| Pistam Pump | 1x1 = | 1.0 Nos: @ | 14417.7 | Each | Rs: | 14418 | 28835
|  |  |  | TOTAL Rs:- |  |  | 14418
CERTIFICATE
Certified that I have prepared this estimate under the supervision of Assistan Engineer Education works sub-Division on the basis of drawing & design supplied to me for items identified by the Assistant Engineer. The rate provided in this estimate are from composite schedule of Rates & sanctioned rate analysis.
SUB-ENGINEER
Certified that this estimate has been prepared by the Sub-Engineer under my supervision for the items identified by me which are prepared for the execution. Further certified that the quantities provided in this estimate are correct.
ASSISTANT ENGINEER
EDUCATION WORKS SUB-DIVISION
MATLI
PART - A CIVIL WORK (ii).
|  |  |  | TOTAL Rs:- |  |  | 120841 | /-
GENRAL ABSTRACT
|  | PART - A CIVIL WORK (i). |  |  |  | RS: | 880660
|  | PART - A CIVIL WORK (ii). |  |  |  | RS: | 120841
|  |  |  | G.TOTAL:- |  | RS: | 1001500
CERTIFICATE
Certified that I have prepared this estimate under the supervision of Assistan Engineer Education works sub-Division on the basis of drawing & design supplied to me for items identified by the Assistant Engineer. The rate provided in this estimate are from composite schedule of Rates & sanctioned rate analysis.
SUB-ENGINEER
Certified that this estimate has been prepared by the Sub-Engineer under my supervision for the items identified by me which are prepared for the execution. Further certified that the quantities provided in this estimate are correct.
ASSISTANT ENGINEER
EDUCATION WORKS SUB-DIVISION
MATLI

## M.Statement
MATERIAL STATEMENT
NAME OF WORK:- |  | ADP NO 477 ILMI' (INFRASTRUCTURE DEVELOPMENT) HYDERABAD DIVISION DISTRICT BADIN (CASE NO 13780), @GBPS MUHAMMAD HASHIM JARWAR U/C BUDHO QAMBRANI TALUKA MATLI , SEMIS CODE 401030404.
S.NO | Description |  | Qty: | Cement | Sand | Shingle | Stone Ballast | Steel | Bricks
01 | CC 1:5:10 |  | 289 | 22 | 139 | 0 | 277 | 0 | 0
02 | Brick Masonry 1:6 |  | 808 | 24 | 218 | 0 | 0 | 0 | 10908
03 | Cement Plaster 1/2"Thick 1:6 |  | 2823 | 14 | 104 | 0 | 0 | 0 | 0
04 | Cement Plaster 3/8"Thick 1:4 |  | 2823 | 14 | 70 | 0 | 0 | 0 | 0
05 | Cement Plaster 3/4"Thick 1:4 |  | 150 | 2 | 8 | 0 | 0 | 0 | 0
06 | Cement Pointing 1:2 |  | 1985 | 14 | 36 | 0 | 0 | 0 | 0
07 | RCC (1:2:4) |  | 792 | 87 | 216 | 433 | 0 | 0 | 0
08 | C.C.Topping 2'' thick (1:2:4) |  | 1437 | 43 | 101 | 201 | 0 | 0 | 0
09 | C.C.Topping 3'' thick (1:2:4) |  | 1402 | 63 | 168 | 336 | 0 | 0 | 0
10 | Fabrication (Tor+Mild) |  | 24.16 | 0 | 0 | 0 | 0 | 24.16 | 0
|  |  | TOTAL | 283 | 1060 | 970 | 277 | 24.16 | 10908
|  |  | RATE | 80.13 | 3148.84 | 3604.68 | 3181.4 | 2627.88 | 1034.34
|  |  | AMOUNT | 22676.79 | 33377.704 | 34965.396 | 8812.478 | 634.8958 | 11282.5807
|  |  |  | TOTAL Rs: | 111749.8445
ASSISTANT ENGINEER
EDUCATION WORKS SUB DIVISION MATLI
SUB ENGINEER

## SCHEDULE-B
SCHEDULE - B.
Name of Work:- |  | ADP NO 477 ILMI' (INFRASTRUCTURE DEVELOPMENT) HYDERABAD DIVISION DISTRICT BADIN (CASE NO 13780), @GBPS MUHAMMAD HASHIM JARWAR U/C BUDHO QAMBRANI TALUKA MATLI , SEMIS CODE 401030404.
S.No. | Descripition. |  | Qty. | Rate. | Unit. | Amount.
PART - A CIVIL WORK (i).
1 | Dismentling cement concrete plain 1:2:4 (S.I.No. 19/C P-10).
|  |  | 471 | 3327.5 | %Cft | Rs. | 15672.525 | /-
(Rs.Three thousand three hundred twenty seven & ps fifty only).
2 | Removing cement or lime plaster.(S.I.No. 53 P-13).
|  |  | 1047 | 121 | %Cft | Rs: | 1266.87 | /-
(Rs.One hundred twenty one & ps zero only).
3 | Excavation in foundation of building briges and other structure I/c dagbelling
dreesing,refilling around the structure with excavated earth watering and
ramming lead upto 5 feet, (b) In ordinary soil. (S.I.No.18.b/P-4).
|  |  | 630 | 3176.25 | %0Cft | Rs. | 2001.0375 | /-
(Rs.Three thousand one hundred seventy six & ps twenty five only).
4 | Cement concrete brick or stone ballast 1-1/2" to 2" gauge ratio 1:5:10. (S.I.No:- 4.C/P-15).
|  |  | 289 | 8694.95 | %Cft | Rs: | 25128.4055 | /-
(Rs.Eight thousand six hundred ninty four & ps ninty five only).
5 | Pacca brick work in foundation & plinth in cement sand martor ratio 1:6 ( S.I.No: 4,(I)(e) /P-20.21 ).
|  |  | 320 | 11948.36 | %Cft | Rs: | 38234.752 | /-
(Rs.Eleven thousand nine hundred fourty eight & ps thirty six only).
6 | Supplying and filling sand under floor and ploughnig in walls( S.No 29 P-26.)
|  |  | 338 | 1141.25 | %Cft | Rs: | 3857.425 | /-
(Rs.One Thousand one hundred fourty one & ps twenty five only).
7 | R.C.C. work I/c all labour and material execpt the cost of steel reinforcement and its
labour for bending and binding which will be paid sperately. This rate also I/c all kinds
of forms moulds lifting shuttering curing rendering and finishing the exposedsurface (I/c screening
and washing of shingle)(a) R.C.work in roof slab,beams columns rafts lintels and other
structural members laid in situ or precast laid in position complete in all respect(I) Ratio
(1:2:4) 90 lbs cement 2 Cft sand 4 Cft shingle 1/8" to 1/4" gauge.(S.I.No.6(a),i/P-16).
|  |  | 492 | 337 | P/Sft | Rs: | 165804 | /-
(Rs.Three hundred thirty seven & ps zero only).
8 | (a)Fabrication of mild steel reinforcement for cement concrete i/c cutting bending laying
in position, making joints and fastening i/c cost of binding wire (also i/c removal of
(b) using Tor Bars) (S.I.No:8-(a)+(b)/P-17).
a) Tor Steel
|  |  | 24.16 | 5001.7 | P/Cwt | Rs: | 120841.072 | /-
(Rs.Five Thousand one & ps seventy only).
9 | Pacca brick work other than building i/c striking of joints upto 20 feet height in cement sand mortar
ratio 1:6 ( S.I.No: 7,(I)(e) /P-22 ).
|  |  | 488 | 12346.65 | %Cft | Rs: | 60251.652 | /-
(Rs.Twelth thousand three hundred fourty six & ps sixty five only).
10 | Cement plaster 1:6 upto 12' ft height 1/2" thick. (S.I.No.13(b) /P-52)
|  |  | 2823 | 2206.6 | %Sft | Rs: | 62292.318 | /-
(Rs.Two Thousand two hundred six & ps sixty only).
11 | Cement plaster 1:4 upto 12' ft height 3/8" thick. (S.I.No.11(a) /P-52)
|  |  | 2823 | 2197.52 | %Sft | Rs: | 62035.9896 | /-
(Rs.Two Thousand one hundred ninty seven & ps fifty two only).
12 | Cement plaster 1:4 upto 12' ft height 3/4" thick. (S.I.No.11(c) /P-52)
|  |  | 150 | 3015.76 | %Sft | Rs: | 4523.64 | /-
(Rs.Three Thousand fifteen & ps seventy six only).
13 | Extra labour rate for making cement plaster pattas/band around straight or carved openings and around
the edges of roof slabs, the width not less than 6" with fine finishing as directed by
Engineer Incharge.(S.I.No.35/P-55)
|  |  | 300 | 19.36 | P/Rft | Rs. | 5808 | /-
(Rs.Ninteen & ps thirty six only).
14 | Cement pointing struck joints on walls ratio 1:2 (S.I.No.19(a)/P-53).
|  |  | 1985 | 1287.44 | %Sft | Rs: | 25555.684 | /-
(Rs.One Thousand two hundred eighty seven & ps fourty four only).
15 | P/L 2" thick topping cement concrete 1:2:4 I/c surface finishing and dividing
into panells. (S.I.No. 16(c) /P-42)
|  |  | 1437 | 3275.5 | %Sft |  | 47068.935 | /-
(Rs.Three Thousand two hundred seventy five & ps fifty only).
16 | P/L 3" thick topping cement concrete 1:2:4 I/c surface finishing and dividing
into panells. (S.I.No. 16(c) /P-42)
|  |  | 1402 | 4411.82 | %Sft | Rs: | 61853.7164 | /-
(Rs.Four Thousand four hundred eleven & ps eighty tow only).
17 | Two coats of bitumen laid 34 lbs over hot using over roof and blinded with sand at
one Cft per % Sft.(S.I.No.13 /P-41).
|  |  | 1325 | 1887.4 | %Sft | Rs. | 25008.05 | /-
(Rs.One thousand eight hundred eighty seve & ps fourty only).
18 | Making & fixing steel grated door with 1/16" thick sheeting I/c angle iron frame 2"x2"and 3/4" square bars 4" center to center with locking arrangmant (S.I.No.24/P-92) .
|  |  | 60 | 726.72 | P/Sft | Rs: | 43603.2
(Rs.Seven hundred twenty six & ps seventy two only).
19 | White washing three coats (S.I.No:29 /P-55 ).
|  |  | 1368 | 425.84 | %Sft | Rs: | 5825.4912
(Rs.Four hundred twenty five & ps eighty four only).
20 | Distemper two coats.(S.I.No.24(b) /P-54).
|  |  | 2927 | 1043.9 | %Sft | Rs: | 30554.953 | /-
(Rs.One thousand fourty three & ps ninty only).
21 | Primary coat of chalk under distemper (S.I.No.23/P-54).
|  |  | 2865 | 442.75 | %Sft | Rs: | 12684.7875 | /-
(Rs.Four hundred fourty two & ps seventy five only).
22 | Distemper three coats.(S.I.No.24(c) /P-54).
|  |  | 2865 | 1079.65 | %Sft | Rs: | 30931.9725 | /-
(Rs.One thousand seventy nine & ps sixty five only).
23 | Colour washig two coats.(S.I.No.25(b)/P-54)
|  |  | 2669 | 859.9 | %Sft | Rs: | 22950.731 | /-
(Rs.Eight hundred fifty nine & ps ninty only).
24 | Painting old surface ( c ) painting doors and window any type two coats. (S.I.No.4(c ) i,ii /P-68).
|  |  | 374 | 1160.06 | %Sft | Rs. | 4338.6244 | /-
(Rs.One Thousand one hundred sixty & ps zero six only).
25 | Painting old surface ( c ) painting guard bars, gate iron bars gratings, railing i/c
standard braces (etc) and similar open work.(S.I.No.4(d ) i,ii /P-69).
|  |  | 154 | 674.6 | %Sft | Rs. | 1038.884 | /-
(Rs. Six hundred seventy four & ps sixty only).
26 | Painting new surface ( d ) preparing surface and painting guard bars, gates of iron bars,
gratings, railings (i/c standards braces, etc.)and similar open work.(S.I.No.5(d ) i,ii /P-70).
|  |  | 120 | 1270.83 | %Sft | Rs. | 1524.996 | /-
(Rs.One Thousand two hundred seventy & ps eighty three only).
|  |  |  | TOTAL Rs:- |  |  | 880660 | /-
PART- "B" Water supply & Santary work
1 | P/F squating type white glazsed earthen ware W.C. pan with I/c cost of flushing cistern with internal fitting and flush pipe with bend and making requisite number of holes in walls plinth & floor for pipe connections & making good in cement concrete 1:2:4.(a) W.C. pan of not less than 23" clear opening between flushing rims and 3 gallons flushing tank (i) with 4@ dia C.I. trape.(S.I.No.1b/P-1).
|  | TOTAL | 2 | 4802.6 | P/No. | Rs. | 9605.2 | /-
(Rs.Four Thousand eight hundred zero two & ps sixty only).
2 | Providing & fixing 4" dia C.I soil & vent pipes i/c cutting and fitting and extra painting to match the colour of the building (S.I.No.1/P-08)
|  | TOTAL | 12 | 333.29 | P.Rft | Rs. | 3999.48 | /-
(Rs.Three hundred thirty three & ps twenty nine only).
3 | Providing & fixing 4" dia C.I terminal guard I/c extra painting to match the colour of the building (S.I.No.11/P-09)
|  | TOTAL | 2 | 389.7 | Each | Rs. | 779.4 | /-
(Rs.Three hundred eighty nine & ps seventy only).
4 | Providing & fixing 4"x4x4x dia C.I brach of the required degree with access door Rubber washer 3/8" thick and builts & nuts and extra painting to match the colour of the building (S.I.No.5/P-08)
|  | TOTAL | 2 | 702 | Each | Rs. | 1404 | /-
(Rs.seven hundred zero two & ps zero only).
5 | S/F Conceled tee-stop cock of superior quality single C.P head 1/2" dia (S.I.No.12(b)/P-18).
|  | TOTAL | 2 | 889.46 | P.No | Rs. | 1778.92 | /-
(Rs.eight hundred eighty nine & ps fourty six only).
6 | (a) S.F long bib cock of superior quality with C.P head 1/2" dia (S.I.No.13(a)/P-19).
|  | TOTAL | 3 | 1109.46 | P.No | Rs. | 3328.38 | /-
(Rs. One thousand one hundred zero nine & ps fourty six only).
7 | P/F handle valves (China) (S.I.No.5(i&ii)/P-17).
(i) 1/2" dia
|  | TOTAL | 2 | 200.42 | P/Rft. | Rs. | 400.84 | /-
(Rs. Two hundred & ps fourty two only).
8 | S/F Fiber glass tank of approved quality anddesign and well thickness as specified i/c
cost of nuts , builts and fixing in platform of c.c.plain 1:3:6 and making connection
for in let out let & over flow inlet flow pipes etc complete ( S.I.No:3(a)/P-21).
|  | TOTAL | 1 | 21989.61 | P.No | Rs. | 21989.61 | /-
(Rs. Twenty one thousand nine hundred eighty nine & ps sixty one only).
9 | Providing R.C.C pipes with collars class "B" and digging the trenches to required depth
and fixing in position I/c cutting fitting and jointing with maphalt composition & cement
mortar 1:1 and testing with water pressure to a head of 4 feet above the top of the
highest pipe & refilling with excavated staff 6" dia R.C.C pipes class "B" (S.I.No.2(b)/P-23)
|  | TOTAL | 36 | 146.57 | P.Rft | Rs. | 5276.52 | /-
(Rs. One hundred fourty six & ps fifty seven only).
10 | Providing G.I. Pipes, specials and clamps etc I/c fixing cutting & fitting complete with and I/c
the cost of breaking through walls and roof making good etc painting two coats after cleaning
the pipe etc with white zink paint with pigment to match the colour of the building &
testing with water to a pressure head of 200 ft: and handling .(S.I.No.1ii /P-14).
(a) 3/4" dia.
|  | TOTAL | 30 | 86.36 | P.Rft | Rs. | 2590.8 | /-
(Rs. Eighty six & ps thirty six only).
(a) 1/2" dia.
|  | TOTAL | 30 | 73.21 | P/Rft. | Rs. | 2196.3 | /-
(Rs. Thirty seven & ps twenty one only).
(PHE-Schedule)
11 | Providing P.V.C pipes of class "D" (equivalent) in touch i/c cutting and jointing with one rubbing ring i/c testing with water to hand of 122 meter or 400' ft (25 mm 1" dia) (S.I.No. 3/P-21 P.H.E)
|  | TOTAL | 300 | 28 | P/Rft. | Rs. | 8400 | /-
(Rs. Twenty eight only).
11 | Boaring for utbe well in all water bearing soils from ground level upto 100 ft or 30,5 meter depth i/c sinking and with drawing of casting pipe. (S.I.No. 1(a) /P-41) ( Chapter PHE)
|  | TOTAL | 100 | 242 | P/Rft. | Rs. | 24200 | /-
(Rs. Two hundred & ps fourty two only).
|  |  |  | TOTAL:- |  | RS: | 85949.45 | /-
Non Schedule Item
1 | P/Fixing Water Pumping Set 1 H.P Mono-Block Single-Phase 220 Volts with 1-1/4" suction & delivery 50 ft: head i/c making C.C.1:3:6 plate form of required size & fixing with nuts & boklts ( Local Made) (R.A).
|  | TOTAL | 1 | 14417.7 | Each | Rs. | 14417.7 | /-
(Rs. Fourteen thousand four hundred seventeen & Ps seventy only).
|  |  |  | TOTAL:- |  | RS: | 14417.7 | /-

## Rate Analysis (2)
RATE ANALYSIS
| NAME OF WORK :- | ADP NO 477 ILMI' (INFRASTRUCTURE DEVELOPMENT) HYDERABAD DIVISION DISTRICT BADIN (CASE NO 13780), @GBPS MUHAMMAD HASHIM JARWAR U/C BUDHO QAMBRANI TALUKA MATLI , SEMIS CODE 401030404.
S. NO | DESCRIPTION. | S.BAJRI. | S.METAL. | H.SAND | S. NO | DESCRIPTION. | CEMENT. | S. NO | DESCRIPTION. | BRICK.
01 | From quarry to Main Road. | 14 | 13 | 3 | 01 | From Lucky Star Factory | 60 | 01 | From Killin to Digree | 10
02 | From mile 110/4 to 122/0 | 11.4 | -- | 9 |  | to Hyderabad |  | 02 | From T.G.A to Digree | 12
03 | From mile 122/0 to Ring Road. | 4.4 | 4.4 | 4.4 | 02 | From Hyderabad to T.G.A | 35
04 | From Ring Road to T,G Ali | 35 | 35 | 35 | 03 | From T.G.A to Digree | 16
05 | From T.G.Ali to Digree | 16 | 16 | 16 | 04 | From Digree to Site | 12
06 | From Digree to site | 12 | 12 | 12
[6 empty] | Total | 123 |  | Total | 22
[6 empty] | Say:- | 123 |  | Say:- | 22
| TOTAL:- | 92.8 | 80.4 | 79.4
[5 empty] | 01 | Rate for 1st 02 miles. | 7.53 | 01 | Rate for 1st 06 miles. | 617.54
| Say:- | 93 | 80 | 79 | 02 | Rate for subsquent. |  | 02 | Rate for subsquent.
[6 empty] | miles ( 121 x 0.60 ). | 72.6 |  | miles ( 16.0 x 26.05 ). | 416.8
01 | Rate for 1st 06 miles. | 771.96 | 771.96 | 771.96 |  | TOTAL:- | 80.13 |  | TOTAL:- | 1034.34
|  | ( 87x32.56) | (74 x32.56) | (73 x32.56)
02 | Rate for subsquent miles. | 2832.72 | 2409.44 | 2376.88
| TOTAL:- | 3604.68 | 3181.4 | 3148.84
ASSISTANT ENGINEER
| SUB-ENGINEER | [6 empty] | EDUCATION WORKS SUB-DIVISION
MATLI