## ANNUAL PROC PLAN 2015-16
ANNUAL PROCUREMENT PLAN 2015-16 PROVINCIAL BUILDINGS DIVISION HYDERABAD
Sr. No. | Tilte of Procurement | Estimated in Million Rs. | Method | Tentative Actual Date of NIT | Tentative Actual Date Closing Date of NIT |  | Tentative Actual Date of Award of Contract | Tentative Dead Line/Actual Date of Execution | Remarks
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9
1 | Re-Construction of Jamia Mosque Abul Fazal at Mola Ali Qadam Gah Hyderabad (ADP No. 33) | 45 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
2 | Construction of underground Car Parking and Auditorium Hall at High Court Circuit Hyderabad (ADP 917) | 45 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
3 | Construction of Officers Residential accommodation offices of the Deputy Director Industries Hyderabad (Main Office Building Remaining Work Internal Road, C.C Platform, C/ Wall & Ext: Development (ADP No. 537) | 18.5 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
4 | Construction of Officers Residential accommodation offices of the Deputy Director Industries Hyderabad (Construction of Flats Grade 11 to 14 (06 Nos.) Remaining work (ADP No. 537) | 12 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
5 | Rehabilitation/Renovation of Jail in Sindh at Central Prison Hyderabad (Additional Verandah Circle-II) (ADP No. 515) | 4 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
6 | Rehabilitation/Renovation of Jail in Sindh at Central Prison Hyderabad (Circle-I Barrack) (ADP No. 515) | 4 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
7 | Rehabilitation/Renovation of Jail in Sindh at Central Prison Hyderabad (Circle-I Division-II Cell) (ADP No. 515) | 5 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
8 | Rehabilitation/Renovation of Jail in Sindh at Central Prison Hyderabad (Main Compound Wall inside) (ADP No. 515) | 5 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
9 | Rehabilitation/Renovation of Existing Godown in Sindh Hyderabad and Sukkur Region (at Hali Road Hyderabad (Grain Godown Size 50 x 50) 4 Nos. (ADP No. 341) | 16 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
10 | Rehabilitation/Renovation of Existing Godown in Sindh Hyderabad and Sukkur Region (at Hali Road Hyderabad (Platform No. 11 50 x 50) 01 No. (ADP No. 341) | 1.9 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9
11 | Construction of Office and Residence Enquiry Anti Corruption Establishment at Matiari Construction of Catg: Vth Flats (10 Nos.) ADP No. 1581 | 1.9 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
12 | Rehabilitation/Renovation of Existing Godown in Sindh Hyderabad and Sukkur Region District Jamshoro D.F.C Office at Kotri (ADP No. 341) | 1.9 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
13 | Rehabilitation/Renovation of Existing Godown in Sindh Hyderabad and Sukkur Region District Jamshoro Damage Portion of Compound Wall (ADP No. 341) | 17.5 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
14 | Rehabilitation/Renovation of Existing Godown in Sindh Hyderabad and Sukkur Region at Sehwan Sharif Remaining work existing Godowns (ADP No. 341) | 3 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
15 | Rehabilitation/Renovation of Existing Godown in Sindh Hyderabad and Sukkur Region in Arazi (Colouring & Roof treatment) (ADP No. 341) | 3 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
16 | Rehabilitation/Renovation of Existing Godown in Sindh Hyderabad and Sukkur Region at Bhan Saeedabad Roof treatment/flooring of Godowns (ADP No. 341) | 3 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
17 | Establishment of Agriculture Complex at Tando Jam (Auditorium Hall) Balance Work. | 3 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
18 | Construction of Official Residence for Assistant Commissioner & Mulhtiarkar Taluka K.N Shah Dadu (ADP # 1587) | 3 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
19 | Renovation / Repair of Accountability Court i/c Re-Const: of Compound Wall at Hyderabad- Left Wing | 12.5 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
20 | Renovation / Repair of Accountability Court Hyderabad Right Wing | 12.5 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
21 | Rehabilitation/Renovation of Existing Godown in Sindh Hyderabad and Sukkur Region (at Hali Road Hyderabad Platform No. 12 (size 50 x 50) 01 No. (ADP No. 341) | 5 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
22 | Rehabilitation/Renovation of Existing Godown in Sindh Hyderabad and Sukkur Region at Hali Road Hyderabad (Platform No. 13 (size 50 x 50) 01 No. ADP No. 341) | 4 | Single Stage One Envelope Bidding Procedure | 08.10.2015 | 04.11.2015 |  | November'15 | November'15
EXECUTIVE ENGINEER PROVINCIAL BUILDINGS DIVISION HYDERABAD

## M&R to B'low D-1
ANNUAL PROCUREMENT PLAN 2015-16 PROVINCIAL BUILDINGS DIVISION HYDERABAD
Sr. No. | Tilte of Procurement | Estimated in Million Rs. | Method | Tentative Actual Date of NIT | Tentative Actual Date Closing Date of NIT |  | Tentative Actual Date of Award of Contract | Tentative Dead Line/Actual Date of Execution | Remarks
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9
1 | M & R to Bungalow No. D-1, G.O.R Colony Hyderabad. | 5 | Single Stage One Envelope Bidding Procedure | 17.02.2016 | 07.03.2016 |  | March' 2016 | March' 2016
EXECUTIVE ENGINEER PROVINCIAL BUILDINGS DIVISION HYDERABAD

## M&R to Session Court Bldg. (2)
ANNUAL PROCUREMENT PLAN 2015-16 PROVINCIAL BUILDINGS DIVISION HYDERABAD
Sr. No. | Tilte of Procurement | Estimated in Million Rs. | Method | Tentative Actual Date of NIT | Tentative Actual Date Closing Date of NIT |  | Tentative Actual Date of Award of Contract | Tentative Dead Line/Actual Date of Execution | Remarks
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9
1 | M & R to Session Court Building Hyderabad, (Sitting Benches Waiting Area & Lawn). | 5 | Single Stage One Envelope Bidding Procedure | 18.03.2016 | 08.04.2016 |  | April' 2016 | May' 2016
EXECUTIVE ENGINEER PROVINCIAL BUILDINGS DIVISION HYDERABAD
ANNUAL PROCUREMENT PLAN 2015-16 PROVINCIAL BUILDINGS DIVISION HYDERABAD
Sr. No. | Tilte of Procurement | Estimated in Million | Method | Tentative Actual Date of NIT | Tentative Actual Date Closing Date of NIT |  | Tentative Actual Date of Award of Contract | Tentative Dead Line/Actual Date of Execution | Remarks
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9
1 | M & R to Session Court Building Hyderabad, (Judicial Lock-up). | 0.5 | Single Stage One Envelope Bidding Procedure | 18.03.2016 | 08.04.2016 |  | April' 2016 | May' 2016
EXECUTIVE ENGINEER PROVINCIAL BUILDINGS DIVISION HYDERABAD

## M&R to B'low D-1 (3)
ANNUAL PROCUREMENT PLAN 2015-16 PROVINCIAL BUILDINGS DIVISION HYDERABAD
Sr. No. | Tilte of Procurement | Estimated in Million Rs. | Method | Tentative Actual Date of NIT | Tentative Actual Date Closing Date of NIT |  | Tentative Actual Date of Award of Contract | Tentative Dead Line/Actual Date of Execution | Remarks
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9
1 | M & R to Bungalow No. D-1, G.O.R Colony Hyderabad. | 5 | Single Stage One Envelope Bidding Procedure | 17.02.2016 | 07.03.2016 |  | March' 2016 | March' 2016
EXECUTIVE ENGINEER PROVINCIAL BUILDINGS DIVISION HYDERABAD
ANNUAL PROCUREMENT PLAN 2015-16 PROVINCIAL BUILDINGS DIVISION HYDERABAD
Sr. No. | Tilte of Procurement | Estimated in Million Rs. | Method | Tentative Actual Date of NIT | Tentative Actual Date Closing Date of NIT |  | Tentative Actual Date of Award of Contract | Tentative Dead Line/Actual Date of Execution | Remarks
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9
1 | M & R to Session Court Building Hyderabad, (Sitting Benches Waiting Area & Lawn). | 5 | Single Stage One Envelope Bidding Procedure | 18.03.2016 | 08.04.2016 |  | April' 2016 | May' 2016
EXECUTIVE ENGINEER PROVINCIAL BUILDINGS DIVISION HYDERABAD
ANNUAL PROCUREMENT PLAN 2015-16 PROVINCIAL BUILDINGS DIVISION HYDERABAD
Sr. No. | Tilte of Procurement | Estimated in Million Rs. | Method | Tentative Actual Date of NIT | Tentative Actual Date Closing Date of NIT |  | Tentative Actual Date of Award of Contract | Tentative Dead Line/Actual Date of Execution | Remarks
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9
1 | M & R to Session Court Building Hyderabad, (Judicial Lock-up). | 0.5 | Single Stage One Envelope Bidding Procedure | 18.03.2016 | 08.04.2016 |  | April' 2016 | May' 2016
EXECUTIVE ENGINEER PROVINCIAL BUILDINGS DIVISION HYDERABAD

## ESTAB; DISTT; ARCHIVES HYD.
ANNUAL PROCUREMENT PLAN 2015-16 PROVINCIAL BUILDINGS DIVISION HYDERABAD
Sr. No. | Tilte of Procurement | Estimated in Million Rs. | Method | Tentative Actual Date of NIT | Tentative Actual Date Closing Date of NIT |  | Tentative Actual Date of Award of Contract | Tentative Dead Line/Actual Date of Execution | Remarks
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9
1 | M & R to Bungalow No. D-1, G.O.R Colony Hyderabad. | 5 | Single Stage One Envelope Bidding Procedure | 17.02.2016 | 07.03.2016 |  | March' 2016 | March' 2016
EXECUTIVE ENGINEER PROVINCIAL BUILDINGS DIVISION HYDERABAD
ANNUAL PROCUREMENT PLAN 2015-16 PROVINCIAL BUILDINGS DIVISION HYDERABAD
Sr. No. | Tilte of Procurement | Estimated in Million Rs. | Method | Tentative Actual Date of NIT | Tentative Actual Date Closing Date of NIT |  | Tentative Actual Date of Award of Contract | Tentative Dead Line/Actual Date of Execution | Remarks
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9
1 | M & R to Session Court Building Hyderabad, (Sitting Benches Waiting Area & Lawn). | 5 | Single Stage One Envelope Bidding Procedure | 18.03.2016 | 08.04.2016 |  | April' 2016 | May' 2016
EXECUTIVE ENGINEER PROVINCIAL BUILDINGS DIVISION HYDERABAD
ANNUAL PROCUREMENT PLAN 2015-16 PROVINCIAL BUILDINGS DIVISION HYDERABAD
Sr. No. | Tilte of Procurement | Estimated in Million Rs. | Method | Tentative Actual Date of NIT | Tentative Actual Date Closing Date of NIT |  | Tentative Actual Date of Award of Contract | Tentative Dead Line/Actual Date of Execution | Remarks
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9
1 | Establishment of District Archives Hyderabad (Main Building)-ADP No. 546. | 25 | Single Stage One Envelope Bidding Procedure | 21.03.2016 | 11.04.2016 |  | April' 2016 | April' 2016
EXECUTIVE ENGINEER PROVINCIAL BUILDINGS DIVISION HYDERABAD

## NIT # LARGE (02-wrks)
ANNUAL PROCUREMENT PLAN 2016-17 PROVINCIAL BUILDINGS DIVISION HYDERABAD
Sr. No. | Tilte of Procurement | Estimated in Million Rs. | Method | Tentative Actual Date of NIT | Tentative Actual Date Closing Date of NIT | Tentative Actual Date of Award of Contract | Tentative Dead Line/Actual Date of Execution | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
1 | Construction of Additional Building in the Premises of Sindh Prison Staff Training Institute Nara Hyderabad (Location at Central Jail) | 100 | Single Stage One Envelope Bidding Procedure | 03.04.2017 | 24.04.2017 | May' 2017 | May' 2017
2 | Establishment of Cardiology Unit at Sindh Govt. Hospital Qasimabad Hyderabad. | 100 | Single Stage One Envelope Bidding Procedure | 03.04.2017 | 24.04.2017 | May' 2017 | May' 2017
EXECUTIVE ENGINEER PROVINCIAL BUILDINGS DIVISION HYDERABAD