## Sheet1
PROCUREMENT PLAN 2016-17
IN RESPECT OF BUILDINGS DIVISION SUKKUR
S.No | ADP No. |  | Name of Scheme | Estimated Cost | Source of Funds ADP / Non ADP | Proposed procurement method | Cost of New works | Funds for New works |  | Nature of procurement | Timing of procurement
[11 empty] | 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11 | 12 | 13
|  |  | 3: NEW ADP 2016-17 |  | NEW ADP 2016-17
1 |  |  | 3: Construction Of Boundary Wall Sangi Grave Yard Taluka Pano Akil |  | Construction Of Boundary Wall Sangi Grave Yard Taluka Pano Akil
|  | i) | Civil Work | 8 | District ADP | N.CB | 8 | 8 | i) | Civil Work | 2 | 2 | 2 | 2
2 |  |  | 3: Construction of Dispensary Village Mohammad Bachal. |  | Construction of Dispensary Village Mohammad Bachal.
|  | i) | Civil Work | 3.8 | District ADP | N.CB | 3.8 | 3.8 | i) | Civil Work | 0.95 | 0.95 | 0.95 | 0.95
|  | ii) | Electric Work | 0.2 | District ADP | N.CB | 0.2 | 0.2 | ii) | Electric Work | 0.05 | 0.05 | 0.05 | 0.05
3 |  |  | 3: Renovation / Rehabilitation of Eid Gah Loung Bhatti. |  | Renovation / Rehabilitation of Eid Gah Loung Bhatti.
|  | i) | Civil Work | 4 | District ADP | N.CB | 4 | 4 | i) | Civil Work | 1 | 1 | 1 | 1
4 |  |  | 3: Construction of Eid Gah @ Village Mohammad Bux Soomro @ Rohri. |  | Construction of Eid Gah @ Village Mohammad Bux Soomro @ Rohri.
|  | i) | Civil Work | 4 | District ADP | N.CB | 4 | 4 | i) | Civil Work | 1 | 1 | 1 | 1
5 |  |  | 3: Remaining Work Of Community Hall @ Village Pedaish Ali Shah Taluka Rohri |  | Remaining Work Of Community Hall @ Village Pedaish Ali Shah Taluka Rohri
|  | i) | Civil Work | 1.85 | District ADP | N.CB | 1.85 | 1.85 | i) | Civil Work | 0.4625 | 0.4625 | 0.4625 | 0.4625
|  | ii) | Electric Work | 0.15 | District ADP | N.CB | 0.15 | 0.15 | ii) | Electric Work | 0.0375 | 0.0375 | 0.0375 | 0.0375
6 |  |  | 3: Construction of Boundary Wall of Graveyard Dargah Noor Shah UC-Arore Taluka Rohri. |  | Construction of Boundary Wall of Graveyard Dargah Noor Shah UC-Arore Taluka Rohri.
|  | i) | Civil Work | 4 | District ADP | N.CB | 4 | 4 | i) | Civil Work | 1 | 1 | 1 | 1
7 |  |  | 3: Construction of Dispensary @ Village Manzoor Metlo Taluka Pano Akil. |  | Construction of Dispensary @ Village Manzoor Metlo Taluka Pano Akil.
|  | i) | Civil Work | 3.8 | District ADP | N.CB | 3.8 | 3.8 | i) | Civil Work | 0.95 | 0.95 | 0.95 | 0.95
|  | ii) | Electric Work | 0.2 | District ADP | N.CB | 0.2 | 0.2 | ii) | Electric Work | 0.05 | 0.05 | 0.05 | 0.05
8 |  |  | 3: Construction of Dispensary @ Village Moule Dino Mirbahar Taluka Pano Akil. |  | Construction of Dispensary @ Village Moule Dino Mirbahar Taluka Pano Akil.
|  | i) | Civil Work | 3.8 | District ADP | N.CB | 3.8 | 3.8 | i) | Civil Work | 0.95 | 0.95 | 0.95 | 0.95
|  | ii) | Electric Work | 0.2 | District ADP | N.CB | 0.2 | 0.2 | ii) | Electric Work | 0.05 | 0.05 | 0.05 | 0.05
9 |  |  | 3: Construction of Govt. Dispensary @ Village Salhani Taluka Pano Akil. |  | Construction of Govt. Dispensary @ Village Salhani Taluka Pano Akil.
|  | i) | Civil Work | 3.8 | District ADP | N.CB | 3.8 | 3.8 | i) | Civil Work | 0.95 | 0.95 | 0.95 | 0.95
|  | ii) | Electric Work | 0.2 | District ADP | N.CB | 0.2 | 0.2 | ii) | Electric Work | 0.05 | 0.05 | 0.05 | 0.05
10 |  |  | 3: Construction of Govt. Dispensary @ Village Waheed Kalhoro Taluka Pano Akil. |  | Construction of Govt. Dispensary @ Village Waheed Kalhoro Taluka Pano Akil.
|  | i) | Civil Work | 3.8 | District ADP | N.CB | 3.8 | 3.8 | i) | Civil Work | 0.95 | 0.95 | 0.95 | 0.95
|  | ii) | Electric Work | 0.2 | District ADP | N.CB | 0.2 | 0.2 | ii) | Electric Work | 0.05 | 0.05 | 0.05 | 0.05
11 |  |  | 3: Construction of Govt. Dispensary @ Village Mubarakpur Taluka Pano Akil. |  | Construction of Govt. Dispensary @ Village Mubarakpur Taluka Pano Akil.
|  | i) | Civil Work | 3.8 | District ADP | N.CB | 3.8 | 3.8 | i) | Civil Work | 0.95 | 0.95 | 0.95 | 0.95
|  | ii) | Electric Work | 0.2 | District ADP | N.CB | 0.2 | 0.2 | ii) | Electric Work | 0.05 | 0.05 | 0.05 | 0.05
12 |  |  | 3: Construction & Rehabilitation of Masjid / Imam Bargah i/c Renovation of Mohammadi Masjid Adam Shah Colony, Bilal Masjid UC-02 Ward-1 & Jamia Masjid Village Umeed Ali Khoso of NA-198 Sukkur. |  | Construction & Rehabilitation of Masjid / Imam Bargah i/c Renovation of Mohammadi Masjid Adam Shah Colony, Bilal Masjid UC-02 Ward-1 & Jamia Masjid Village Umeed Ali Khoso of NA-198 Sukkur.
|  | i) | Civil Work | 4.125 | District ADP | N.CB | 4.1.25 | 4.125 | i) | Civil Work | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | ii) | Electric Work (Mohammadi Masjid) | 0.375 | District ADP | N.CB | 0.375 | 0.375 | ii) | Electric Work (Mohammadi Masjid) | 0.09375 | 0.09375 | 0.09375 | 0.09375
13 |  |  | 3: Construction & Rehabilitation of Masjid / Imam Bargah i/c Renovation of (Gol Masjid Barrage Colony Sukkur) of NA-198 Sukkur. |  | Construction & Rehabilitation of Masjid / Imam Bargah i/c Renovation of (Gol Masjid Barrage Colony Sukkur) of NA-198 Sukkur.
|  | i) | Civil Work | 4.5 | District ADP | N.CB | 4.5 | 4.5 | i) | Civil Work | 1.125 | 1.125 | 1.125 | 1.125
14 |  |  | 3: Construction of Auditorium / Internal Paths of IBA Public School Sukkur. |  | Construction of Auditorium / Internal Paths of IBA Public School Sukkur.
|  | i) | Civil Work | 9 | District ADP | N.CB | 9 | 9 | i) | Civil Work | 2.25 | 2.25 | 2.25 | 2.25
|  | ii) | Electric Work | 1 | District ADP | N.CB | 1 | 1 | ii) | Electric Work | 0.25 | 0.25 | 0.25 | 0.25
15 |  |  | 3: Renovation of Various Rounds Abouts at Sukkur City. |  | Renovation of Various Rounds Abouts at Sukkur City.
|  | i) | Civil Work | 9.9 | District ADP | N.CB | 9.9 | 9.9 | i) | Civil Work | 2.475 | 2.475 | 2.475 | 2.475
|  | ii) | Electric Work | 0.1 | District ADP | N.CB | 0.1 | 0.1 | ii) | Electric Work | 0.025 | 0.025 | 0.025 | 0.025
16 |  |  | 3: Rehabilitation of Nauman Park at UC-1 Near SSP Office Indus Apppartment Sukkur. |  | Rehabilitation of Nauman Park at UC-1 Near SSP Office Indus Apppartment Sukkur.
|  | i) | Civil Work | 2 | District ADP | N.CB | 2 | 2 | i) | Civil Work | 0.5 | 0.5 | 0.5 | 0.5
17 |  |  | 3: Rehabilitation & Construction Naugaz Pir Ward-1 UC-02 Sukkur. |  | Rehabilitation & Construction Naugaz Pir Ward-1 UC-02 Sukkur.
|  | i) | Civil Work | 1.9 | District ADP | N.CB | 1.9 | 1.9 | i) | Civil Work | 0.475 | 0.475 | 0.475 | 0.475
|  | ii) | Electric Work | 0.1 | District ADP | N.CB | 0.1 | 0.1 | ii) | Electric Work | 0.025 | 0.025 | 0.025 | 0.025
18 |  |  | 3: Rehabilitation & Construction Ghaznavi Park at Sukkur. |  | Rehabilitation & Construction Ghaznavi Park at Sukkur.
|  | i) | Civil Work | 2.5 | District ADP | N.CB | 2.5 | 2.5 | i) | Civil Work | 0.625 | 0.625 | 0.625 | 0.625
19 |  |  | 3: Construction & Rehabilitation / Renovation of Chiistain Community Hall at Ayoub Gate UC-13 Sukkur. |  | Construction & Rehabilitation / Renovation of Chiistain Community Hall at Ayoub Gate UC-13 Sukkur.
|  | i) | Civil Work | 2.6 | District ADP | N.CB | 2.6 | 2.6 | i) | Civil Work | 0.65 | 0.65 | 0.65 | 0.65
|  | ii) | Electric Work | 0.4 | District ADP | N.CB | 0.4 | 0.4 | ii) | Electric Work | 0.1 | 0.1 | 0.1 | 0.1
20 |  |  | 3: Construction of Boundary Wall Pir Gul Shah Near Dharejo Mohalla and Construction of Internal Paths and Shade Graveyard Mughal UC-15 Old Sukkur. |  | Construction of Boundary Wall Pir Gul Shah Near Dharejo Mohalla and Construction of Internal Paths and Shade Graveyard Mughal UC-15 Old Sukkur.
|  | i) | Civil Work | 1.95 | District ADP | N.CB | 1.95 | 1.95 | i) | Civil Work | 0.4875 | 0.4875 | 0.4875 | 0.4875
|  | ii) | Electric Work | 0.05 | District ADP | N.CB | 0.05 | 0.05 | ii) | Electric Work | 0.0125 | 0.0125 | 0.0125 | 0.0125
21 |  |  | 3: Maintenance & Rehabilitation of Dargah and Graveyard Pir Bahawal Shah Bukhari UC-20 Small Industries Sukkur. |  | Maintenance & Rehabilitation of Dargah and Graveyard Pir Bahawal Shah Bukhari UC-20 Small Industries Sukkur.
|  | i) | Civil Work | 2.15 | District ADP | N.CB | 2.15 | 2.15 | i) | Civil Work | 0.5375 | 0.5375 | 0.5375 | 0.5375
|  | ii) | Electric Work | 0.35 | District ADP | N.CB | 0.35 | 0.35 | ii) | Electric Work | 0.0875 | 0.0875 | 0.0875 | 0.0875
22 |  |  | 3: Construction of Boundary Wall and Internal Path of Graveyard Near Golimar Road at UC-20 Small Industries Sukkur. |  | Construction of Boundary Wall and Internal Path of Graveyard Near Golimar Road at UC-20 Small Industries Sukkur.
|  | i) | Civil Work | 2.5 | District ADP | N.CB | 2.5 | 2.5 | i) | Civil Work | 0.625 | 0.625 | 0.625 | 0.625
23 |  |  | 3: Construction of Imam Bargah Military Road Sukkur. |  | Construction of Imam Bargah Military Road Sukkur.
|  | i) | Civil Work | 3.2 | District ADP | N.CB | 3.2 | 3.2 | i) | Civil Work | 0.8 | 0.8 | 0.8 | 0.8
|  | ii) | Electric Work | 0.3 | District ADP | N.CB | 0.3 | 0.3 | ii) | Electric Work | 0.075 | 0.075 | 0.075 | 0.075
24 |  |  | 3: Construction of Paver Block Flooring & Drain at Nusrat Colony No.1 & 5 Oliya Masjid to Rajput Office UC-14 Old Sukkur. |  | Construction of Paver Block Flooring & Drain at Nusrat Colony No.1 & 5 Oliya Masjid to Rajput Office UC-14 Old Sukkur.
|  | i) | Civil Work | 3 | District ADP | N.CB | 3 | 3 | i) | Civil Work | 0.75 | 0.75 | 0.75 | 0.75
25 |  |  | 3: Construction of CC Block Flooring at Outer Signal and Adjacent Streets of UC-14 Old Sukkur. |  | Construction of CC Block Flooring at Outer Signal and Adjacent Streets of UC-14 Old Sukkur.
|  | i) | Civil Work | 2 | District ADP | N.CB | 2 | 2 | i) | Civil Work | 0.5 | 0.5 | 0.5 | 0.5
26 |  |  | 3: Construction of Paver Block Flooring & Drain at Village Laique Maka UC-20 Sukkur. |  | Construction of Paver Block Flooring & Drain at Village Laique Maka UC-20 Sukkur.
|  | i) | Civil Work | 3 | District ADP | N.CB | 3 | 3 | i) | Civil Work | 0.75 | 0.75 | 0.75 | 0.75
27 |  |  | 3: Construction of Paver Block Town Cmmittee Bagerji. |  | Construction of Paver Block Town Cmmittee Bagerji.
|  | i) | Civil Work | 2.2 | District ADP | N.CB | 2.2 | 2.2 | i) | Civil Work | 0.55 | 0.55 | 0.55 | 0.55
28 |  |  | 3: Construction of New Yard Park Near Primary School New Yard Rohri (Ghazi Baba Park). |  | Construction of New Yard Park Near Primary School New Yard Rohri (Ghazi Baba Park).
|  | i) | Civil Work | 5 | District ADP | N.CB | 5 | 5 | i) | Civil Work | 1.25 | 1.25 | 1.25 | 1.25
29 |  |  | 3: Construction of Park & Mosque at Village Ameen-u-Din Shah UC-Hingoro Taluka Pano Akil. |  | Construction of Park & Mosque at Village Ameen-u-Din Shah UC-Hingoro Taluka Pano Akil.
|  | i) | Civil Work | 1.9 | District ADP | N.CB | 1.9 | 1.9 | i) | Civil Work | 0.475 | 0.475 | 0.475 | 0.475
|  | ii) | Electric Work | 0.1 | District ADP | N.CB | 0.1 | 0.1 | ii) | Electric Work | 0.025 | 0.025 | 0.025 | 0.025
30 |  |  | 3: Construction of Community Hall at UC-New Nauraja Taluka Pano Akil. |  | Construction of Community Hall at UC-New Nauraja Taluka Pano Akil.
|  | i) | Civil Work | 1.9 | District ADP | N.CB | 1.9 | 1.9 | i) | Civil Work | 0.475 | 0.475 | 0.475 | 0.475
|  | ii) | Electric Work | 0.1 | District ADP | N.CB | 0.1 | 0.1 | ii) | Electric Work | 0.025 | 0.025 | 0.025 | 0.025
31 |  |  | 3: Renovation of Dargah Makki Shah Sukkur. |  | Renovation of Dargah Makki Shah Sukkur.
|  | i) | Civil Work | 1.8 | District ADP | N.CB | 1.8 | 1.8 | i) | Civil Work | 0.45 | 0.45 | 0.45 | 0.45
|  | ii) | Electric Work | 0.2 | District ADP | N.CB | 0.2 | 0.2 | ii) | Electric Work | 0.05 | 0.05 | 0.05 | 0.05
32 |  |  | 3: Pir Fazul Shah Paver Block & Side Drain UC-20 Tamachani. |  | Pir Fazul Shah Paver Block & Side Drain UC-20 Tamachani.
|  | i) | Civil Work | 2 | District ADP | N.CB | 2 | 2 | i) | Civil Work | 0.5 | 0.5 | 0.5 | 0.5
33 |  |  | 3: Jamali Goth Paver Block & Drain UC-20 Tamachani. |  | Jamali Goth Paver Block & Drain UC-20 Tamachani.
|  | i) | Civil Work | 3 | District ADP | N.CB | 3 | 3 | i) | Civil Work | 0.75 | 0.75 | 0.75 | 0.75
34 |  |  | 3: Village Ismail Labano Paver Block & Side Drain UC-20 Tamachani. |  | Village Ismail Labano Paver Block & Side Drain UC-20 Tamachani.
|  | i) | Civil Work | 2 | District ADP | N.CB | 2 | 2 | i) | Civil Work | 0.5 | 0.5 | 0.5 | 0.5
35 |  |  | 3: Pir Hashim Shah Boundary Wall UC-20 Tamachani. |  | Pir Hashim Shah Boundary Wall UC-20 Tamachani.
|  | i) | Civil Work | 1.5 | District ADP | N.CB | 1.5 | 1.5 | i) | Civil Work | 0.375 | 0.375 | 0.375 | 0.375
36 |  |  | 3: Renovation of Masjid Mahar Mohalla Village Gosarji UC-20 Tamachani. |  | Renovation of Masjid Mahar Mohalla Village Gosarji UC-20 Tamachani.
|  | i) | Civil Work | 1.4 | District ADP | N.CB | 1.4 | 1.4 | i) | Civil Work | 0.35 | 0.35 | 0.35 | 0.35
|  | ii) | Electric Work | 0.1 | District ADP | N.CB | 0.1 | 0.1 | ii) | Electric Work | 0.025 | 0.025 | 0.025 | 0.025
37 |  |  | 3: Construction of Drainage Scheme of Nusrat Colony Shamsabad Ghorra Ghatti UC-10 Nusrat Colony Sukkur. |  | Construction of Drainage Scheme of Nusrat Colony Shamsabad Ghorra Ghatti UC-10 Nusrat Colony Sukkur.
|  | i) | Civil Work | 5 | District ADP | N.CB | 5 | 5 | i) | Civil Work | 1.25 | 1.25 | 1.25 | 1.25
38 |  |  | 3: Remaining Work Camp Office Commissioner House Sukkur |  | Remaining Work Camp Office Commissioner House Sukkur
|  | i) | Civil Work | 6.34 | District ADP | N.CB | 6.34 | 6.34 | i) | Civil Work | 1.585 | 1.585 | 1.585 | 1.585
39 |  |  | 3: Remaining Work of District Bar Sukkur i/c Renovation Old Bar. |  | Remaining Work of District Bar Sukkur i/c Renovation Old Bar.
|  | i) | Civil Work | 4.5 | District ADP | N.CB | 4.5 | 4.5 | i) | Civil Work | 1.125 | 1.125 | 1.125 | 1.125
|  | ii) | Electric Work | 0.5 | District ADP | N.CB | 0.5 | 0.5 | ii) | Electric Work | 0.125 | 0.125 | 0.125 | 0.125
40 |  |  | 3: Renovation of SSP Office Sukkur (External Development work). |  | Renovation of SSP Office Sukkur (External Development work).
|  | i) | Civil Work | 4.95 | District ADP | N.CB | 4.95 | 4.95 | i) | Civil Work | 1.2375 | 1.2375 | 1.2375 | 1.2375
|  | ii) | Electric Work | 0.05 | District ADP | N.CB | 0.05 | 0.05 | ii) | Electric Work | 0.0125 | 0.0125 | 0.0125 | 0.0125
41 |  |  | 3: Construction of Staff Office of Deputy Commissioner Office Sukkur |  | Construction of Staff Office of Deputy Commissioner Office Sukkur
|  | i) | Civil Work | 28 | District ADP | N.CB | 28 | 28 | i) | Civil Work | 7 | 7 | 7 | 7
42 |  |  | 3: Construction of Compound Wall Cancer Hospital (SUIT) Sukkur |  | Construction of Compound Wall Cancer Hospital (SUIT) Sukkur
|  | i) | Civil Work | 29.971 | District ADP | N.CB | 29.971 | 29.971 | i) | Civil Work | 7.4928 | 7.4928 | 7.4928 | 7.4928
43 |  |  | 3: Construction of Naz Ground Walking Track i/c Earth Filling & Solar Light Ward No-9 New Yard Rohri |  | Construction of Naz Ground Walking Track i/c Earth Filling & Solar Light Ward No-9 New Yard Rohri
|  | i) | Civil Work | 2.7 | District ADP | N.CB | 2.7 | 2.7 | i) | Civil Work | 0.675 | 0.675 | 0.675 | 0.675
44 |  |  | 3: Procurement of Blood Campaign for Sukkur Blood Bank Sukkur. |  | Procurement of Blood Campaign for Sukkur Blood Bank Sukkur.
|  | i) | Civil Work | 6.93 | MPA Funds | N.CB | 6.93 | 6.93 | i) | Civil Work | 1.7325 | 1.7325 | 1.7325 | 1.7325
45 |  |  | 3: Construction of Masjid Ali Lal @ Lal Jo Makan Old Sukkur |  | Construction of Masjid Ali Lal @ Lal Jo Makan Old Sukkur
|  | i) | Civil Work | 1.9 | MPA Funds | N.CB | 1.9 | 1.9 | i) | Civil Work | 0.475 | 0.475 | 0.475 | 0.475
|  | ii) | Electric Work | 0.1 | MPA Funds | N.CB | 0.1 | 0.1 | ii) | Electric Work | 0.025 | 0.025 | 0.025 | 0.025
46 |  |  | 3: Renovation / Beautification of 3 Nos. Under Passes @ Rohri |  | Renovation / Beautification of 3 Nos. Under Passes @ Rohri
|  | i) | Civil Work | 5.814 | MPA Funds | N.CB | 5.814 | 5.814 | i) | Civil Work | 1.4535 | 1.4535 | 1.4535 | 1.4535
|  | ii) | Electric Work | 0.186 | MPA Funds | N.CB | 0.186 | 0.186 | ii) | Electric Work | 0.0465 | 0.0465 | 0.0465 | 0.0465
47 |  |  | 3: Eid Gah to Girls College Paver Block Pipe Line Cross Sukkur. |  | Eid Gah to Girls College Paver Block Pipe Line Cross Sukkur.
|  | i) | Civil Work | 1 | District ADP | N.CB | 1 | 1 | i) | Civil Work | 0.25 | 0.25 | 0.25 | 0.25
48 |  |  | 3: Renovation Beautification of Lance Down Bridge & Illumination of Ayoub Bridge, Satiyan Jo Astan Sukkur. |  | Renovation Beautification of Lance Down Bridge & Illumination of Ayoub Bridge, Satiyan Jo Astan Sukkur.
|  | i) | Civil Work | 10 | MPA Funds | N.CB | 10 | 10 | i) | Civil Work | 2.5 | 2.5 | 2.5 | 2.5
|  | ii) | Electric Work | 10 | MPA Funds | N.CB | 10 | 10 | ii) | Electric Work | 2.5 | 2.5 | 2.5 | 2.5
49 |  |  | 3: Installation of CC Tv Cameras for Security Purpose @ Important Places and Sensitive of Sukkur City (Control Room). (Required Specialized in code (EE-02) (Security, Safety Surveillance System). |  | Installation of CC Tv Cameras for Security Purpose @ Important Places and Sensitive of Sukkur City (Control Room). (Required Specialized in code (EE-02) (Security, Safety Surveillance System).
|  | i) | Work | 40 | District ADP | N.CB | 39.6 | 39.6 | i) | Work | 9.9 | 9.9 | 9.9 | 9.9
|  |  | 3: M&R 2016-17 |  | M&R 2016-17
50 |  |  | 3: M&R Office of the Executive Engineer Buildings Division Sukkur. |  | M&R Office of the Executive Engineer Buildings Division Sukkur.
|  | i) | Civil Work | 0.527 | M&R Funds | N.CB | 0.527 | 0.527 | i) | Civil Work | 0.13175 | 0.13175 | 0.13175 | 0.13175
51 |  |  | 3: M&R Office of the Assistant Engineer Highways Sukkur. |  | M&R Office of the Assistant Engineer Highways Sukkur.
|  | i) | Civil Work | 0.5 | M&R Funds | N.CB | 0.5 | 0.5 | i) | Civil Work | 0.125 | 0.125 | 0.125 | 0.125
52 |  |  | 3: M&R Office of the Assistant Engineer Building Division Sukkur. |  | M&R Office of the Assistant Engineer Building Division Sukkur.
|  | i) | Civil Work | 0.25 | M&R Funds | N.CB | 0.45 | 0.45 | i) | Civil Work | 0.1125 | 0.1125 | 0.1125 | 0.1125
|  | ii) | Electric Work | 0.25 | M&R Funds | N.CB | 0.05 | 0.05 | ii) | Electric Work | 0.0125 | 0.0125 | 0.0125 | 0.0125
53 |  |  | 3: M&R Office of the Superintending Engineer Works & Services Sukkur. |  | M&R Office of the Superintending Engineer Works & Services Sukkur.
|  | i) | Civil Work | 0.4 | M&R Funds | N.CB | 0.4 | 0.4 | i) | Civil Work | 0.1 | 0.1 | 0.1 | 0.1
54 |  |  | 3: M&R Office of the Assistant Engineer Building Pano Akil. |  | M&R Office of the Assistant Engineer Building Pano Akil.
|  | i) | Civil Work | 0.3 | M&R Funds | N.CB | 0.3 | 0.3 | i) | Civil Work | 0.075 | 0.075 | 0.075 | 0.075
55 |  |  | 3: M&R to Staff Quarter Revenue Colony Sukkur. (___________________). |  | M&R to Staff Quarter Revenue Colony Sukkur. (___________________).
|  | i) | Civil Work | 2 | M&R Funds | N.CB | 0.4 | 0.4 | i) | Civil Work | 0.1 | 0.1 | 0.1 | 0.1
56 |  |  | 3: M&R to Various Staff Quarters Revenue Colony Sukkur. |  | M&R to Various Staff Quarters Revenue Colony Sukkur.
|  | i) | Electric Work | 0.234 | M&R Funds | N.CB | 0.234 | 0.234 | i) | Electric Work | 0.0585 | 0.0585 | 0.0585 | 0.0585
57 |  |  | 3: M&R to RHC Bachal Shah Miani Sukkur |  | M&R to RHC Bachal Shah Miani Sukkur
|  | i) | Civil Work | 1 | M&R Funds | N.CB | 1 | 1 | i) | Civil Work | 0.25 | 0.25 | 0.25 | 0.25
|  | ii) | Electric Work | 0.2 | M&R Funds | N.CB | 0.2 | 0.2 | ii) | Electric Work | 0.05 | 0.05 | 0.05 | 0.05
EXECUTIVE ENGINEER
BUILDINGS DIVISION
SUKKUR
EXECUTIVE ENGINEER
BUILDINGS DIVISION
SUKKUR