## Procurement Plan
OFFICE OF THE EXECUTIVE ENGINEER BUILDINGS WORKS & SERVICES DEPARTMENT KHAIRPUR
PROCUREMENT PLAN FOR THE YEAR 2016-17
SR. NO. | ADP | NAME OF WORK | TENDER COST | ALLOCATION 2016-17 | RELEASE 2016-17 | UTILIZATION / PROCUREMENT PROGRESS PLAN |  |  |  | REMARKS
[6 empty] | JULY TO DECEMBER 2016 | MAY TO JUNE 2017 | JULY TO SEPT: 2017 | OCTOBER TO DECEMBER 2017
1 | 729 | Rehabilitation of I.T Training Center Kumb Taluka Kotdiji. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
2 | 731 | Construction of Mukhtiarkar House at Gambat Taluka Gambat. | 500000 | 500000 | 500000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
3 | 732 | Construction of Assistant Commissioner /Mukhtiarkar Office Sobhodero Taluka Sobhodero. | 850000 | 850000 | 850000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
4 | 733 | Construction of Assistant Commissioner House Sobhodero @ Ranipur Taluka Sobhodero. | 500000 | 500000 | 500000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
5 | 734 | Rehabilitation / Construction of Revenue Complex at Taluka Faiz Ganj. | 900000 | 900000 | 900000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
6 | 735 | Rehabilitation / Construction of Revenue Complex at Taluka Nara. | 900000 | 900000 | 900000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
7 | 736 | Rehabilitation/ Construction of Mukhtiarkar Office /House Taluka Kotdiji. | 600000 | 600000 | 600000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
8 | 739 | Renovation and Rehabilitation of Ghulstan-e-Manzil (DDMA Cell) near Vegetable Fruit Market Mall Road Taluka & District Khairpur. | 300000 | 300000 | 300000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
9 | 741 | Construction of Union Council Office Ali Muhammad Machi @ Nangerja UC Ali Muhammad Machi Taluka Kotdiji. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
10 | 742 | Construction of Union Council Office Atta Muhammad Hami @ Narodhoro UC Atta Muhammad Hami Taluka Kotdiji. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
11 | 743 | Construction of Union Council Office Goondariro @ Rajpari UC Goondariro Taluka Kotdiji. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
12 | 744 | Construction of Union Council Office Talpur Wada UC Talpur Wada Taluka Kotdiji. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
13 | 745 | Construction of Union Council Office UC Ripri Taluka Gambat. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
14 | 748 | Construction of Compound wall, Earth Filling and Lavatory Block etc for Eidgah Deh Daraza Sharief Taluka Gambat. | 50000 | 50000 | 50000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
15 | 750 | Construction of Compound wall for Graveyard Derwaish Jee Masjid at Mir Ali Bazar Taluka Khairpur. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
16 | 752 | Rehabilitation/Renovation of Bungalow No.A-1/15 at Scarp Colony Taluka Khairpur. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
17 | 754 | Construction of /Remaining work of Dargah Sachal Shah Jillani UC Drib Mehar Shah Taluka Kingri. | 300000 | 300000 | 300000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
18 | 755 | Construction of Hujra of Bibi Pak Daman & Openyard UC Drib Mehar Shah Taluka Kingri. | 300000 | 300000 | 300000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
19 | 765 | Construction of Compound wall for Graveyard at Village Baghyal Khan Chandio UC Bapho Taluka Kotdiji. | 75000 | 75000 | 75000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
20 | 766 | Construction of Compound wall Imam Bargah at Village Ghous Bux Gaho Muhalla Sanwal Gaho UC Ali Muhammad Machi Taluka Kotdiji. | 75000 | 75000 | 75000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
21 | 768 | Construction of Compound wall of Imam Bargah Mohalla Bukhari (Syed Gayoor Abbas Shah) UC Deh Sohu Taluka Kotdiji. | 75000 | 75000 | 75000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
22 | 769 | Construction of Compound wall of Imam Bargah Mohalla Hayat Shaikh UC Shadi Shaheed Taluka Kotdiji. | 75000 | 75000 | 75000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
23 | 771 | Construction of Remaining work of Compound wall of Imam Bargah at Village Mureed Hussain Mahar UC Atta Muhammad Hami Taluka Kotdiji. | 100000 | 100000 | 100000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
24 | 777 | Construction of Compound wall i/c Gate Imam Bargah Mir Ali Bazar near Wassan House Taluka & District Khairpur. | 180000 | 180000 | 180000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
25 | 779 | Construction /Remaining work of Dargah Shah Hussain UC Muhbat wah Taluka Kotdiji. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
26 | 784 | Additional work of Imam Bargah Ali Raza Shah Thallo UC Khairpur Taluka Khairpur. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
27 | 785 | Construction of Dargah Syed Bhoral Shah near Sanhro wah Taluka Khairpur. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
28 | 793 | Construction of Compound wall Imam Bargah Babar Wada UC Ahdi Rajper Taluka Kotdiji. | 100000 | 100000 | 100000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
29 | 794 | Construction of Compound wall for Masjid Sharief at Village Sadoro Janwari Goth near Police Training Center Taluka & District Khairpur. | 150000 | 150000 | 150000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
30 | 795 | Construction of Compound wall of Imam Bargah Bab-Ul-Hawaij Maitla Mohalla at Luqman Khairpur. | 100000 | 100000 | 100000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
31 | 796 | Re-Construction of Imam Bargah Imam Hussain (AS) at Village Sajjan Khan Rind Deh Bugro Taluka & District Khairpur. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
32 | 797 | Construction of Compound wall of Imam Bargah at Village Baloch Abad UC Mahesar Wada Taluka Kingri. | 150000 | 150000 | 150000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
33 | 799 | Construction of Compound wall of Imam Bargah Mohalla Bukhari Taluka & District Khairpur. | 250000 | 250000 | 250000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
34 | 800 | Construction of Compound wall of Imam Bargah Shaheed Abad Mohalla Bukhari Taluka & District Khairpur. | 120000 | 120000 | 120000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
35 | 802 | Construction of Compound wall of Eidgah at Jinnah Colony Ward No.23 Taluka Khairpur. | 100000 | 100000 | 100000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
36 | 804 | Construction of Compound wall of Eidgah Ali-Un-Murtaza Bhutta Mohalla Taluka Kotdiji. | 100000 | 100000 | 100000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
37 | 805 | Construction of Compound wall of Imam Bargah Hyderi at Old Mohalla Kolab Jeal Taluka Kingri. | 100000 | 100000 | 100000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
38 | 806 | Construction of Tomb of Dargah Jam Fakir at Village Kouro Khan Phulpoto Taluka & District Khairpur. | 100000 | 100000 | 100000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
39 | 807 | Construction of Dargah Shaheed Syed Sajjad Hussain Shah Muhalla Syed Bachal Shah Bukhari Taluka Khairpur. | 250000 | 250000 | 250000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
40 | 808 | Construction of Dargah Syed Gareeb Shah City Khairpur Taluka & District Khairpur. | 170000 | 170000 | 170000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
41 | 809 | Construction of Dargah, Musafir Khana Syed Waryal Shah UC Bukhari Taluka & District Khairpur. | 250000 | 250000 | 250000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
42 | 810 | Remaining Boundary wall and widening of Dargah Pir Shah Hussain Badshah Uc Khanpur Taluka & District Khairpur. | 100000 | 100000 | 100000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
43 | 812 | Providing of Paver Block for Sindhi Karballa near Old National Highway Taluka Khairpur. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
44 | 813 | Rehabilitation Compound wall Imam Bargah Abdul Fazal Abbas and Graveyard of Dargah Mehar Ali Shah Abra Muhalla Luqman Khairpur. | 100000 | 100000 | 100000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
45 | 814 | Remaining work Construction of Compound wall Dargah Koral Shah near Mumtaz College Taluka & District Khairpur. | 100000 | 100000 | 100000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
46 | 815 | Construction of Compound wall & Hall i/c Repair of Musafir & C.C Block of Imam Bargah at Dilshad Colony near Naz High School Khairpur. | 150000 | 150000 | 150000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
47 | 816 | Remaining work of Dargah Khanan Shah Taluka & District Khairpur. | 150000 | 150000 | 150000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
48 | 822 | Construction of Boundary wall, Musafir Khana & Paving Block at Dargah Pir Syed Inayat Shah Bukhari Taluka & District Khairpur. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
49 | 826 | Rehabilitation of Dargah Syed Jind Wado near Railway Station Taluka Khairpur. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
50 | 421 | Construction of Markazi Imam Bargah Al-Hussaini Kolab Jail UC Kolab Jail Taluka Kingri. (Electrification). | 120000 | 120000 | 120000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
51 | 398 | Rehabilitation of Shaheed Benazir Bhutto Open Air Theater (Additional work of Electrification). | 400000 | 400000 | 400000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
52 | 827 | Rehabilitation of Basic Health Unit Zafar Abad UC Kandiyari Taluka Faiz Ganj. | 300000 | 300000 | 300000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
53 | 830 | Rehabilitation of Government Dispensary at Rafique Mahesar Taluka Kingri. | 150000 | 150000 | 150000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
54 | 831 | Rehabilitation of Basic Health Unit Sami Taluka Sobhodero. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
55 | 832 | Construction of Government Dispensary at Kot Jubo Taluka Nara. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
56 | 833 | Construction of Government Dispensary at Village Ghulam Rasool Sangi UC Akri Taluka Faiz Ganj. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
57 | 834 | Construction of Government Dispensary at Village Naseer Fakir Jalalani Taluka Kotdiji. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
58 | 835 | Construction of Government Dispensary at Village Qutubuddin Phulpoto Taluka Khairpur. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
59 | 836 | Construction of Government Dispensary at Village Jhango Wassan Muhalla Karam Hussain Wassan Taluka Kotdiji. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
60 | 837 | Construction of Government Dispensary at Village Fateh Ali Lashari Taluka Kotdiji. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
61 | 838 | Construction of Government Dispensary at Village Khair Muhammad Burdi Taluka Kotdiji. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
62 | 839 | Construction of Government Dispensary at Village Badai Solangi UC Machyoon Taluka Khairpur. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
63 | 840 | Construction of Government Dispensary at Village Rind Hajana UC Mithri Taluka Kotdiji. | 200000 | 200000 | 200000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
64 | 1608 | Rehabilitation and Construction / Reconstructions of Veterinary Hospital / Dispensaries and centres in District Khairpur. |  |  |  | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
CONSTRUCTION / RECONSTRUCTION OF VETERINARY DISPENSARIES
| 1 | Bindi Motayo Taluka Sobhodero. | 100000 | 100000 | 100000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
| 2 | Belharo Taluka Gambat. | 100000 | 100000 | 100000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
| 3 | Mangho Fakir Shar Taluka Thair Mirwah. | 100000 | 100000 | 100000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
| 4 | Bozdar Wada Taluka Thair Mirwah. | 100000 | 100000 | 100000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
| 5 | Nawab Khan Wassan Taluka Kotdiji. | 100000 | 100000 | 100000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
| 6 | Jiskani at Atta Muhammad Ujjan Taluka Kotdiji. | 100000 | 100000 | 100000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
| 7 | Abdul Karim Kharal Taluka Sobhodero. | 100000 | 100000 | 100000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
| 8 | Layari Taluka Kotdiji. | 100000 | 100000 | 100000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
| 9 | Kharal Abad Taluka Gambat | 100000 | 100000 | 100000 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
EXECUTIVE ENGINEER (BUILDINGS) WORKS & SERVICES DEPARTMENT KHAIRPUR