## Procurement Plan
OFFICE OF THE EXECUTIVE ENGINEER BUILDINGS WORKS & SERVICES DEPARTMENT KHAIRPUR
PROCUREMENT PLAN FOR THE YEAR 2016-17
SR. NO. | ADP | NAME OF WORK | ESTIMATE/ TENDER COST | ALLOCATION 2016-17 | RELEASE 2016-17 | UTILIZATION / PROCUREMENT PROGRESS PLAN |  |  |  | REMARKS
[6 empty] | JULY TO DECEMBER 2016 | JANUARY TO APRIL 2017 | MAY TO JUNE 2017 | JULY TO JUNE 2018
1 | GR 684 | Providing for the Play Ground of / Cricket Stadium at Drib Mehar Shah Taluka Kingri District Khairpur.
| A) | Construction of New OPD Center i/c Water Supply & Sanitary Fittings. | 21.3 | 25 | 12.5 | -- | Tendering process | 0.5 | 0.5 | The utilization is subject to receipt of budget
| B) | Construction of Mortuary i/c Compound wall & Steel Gate | 1.95
| C) | Electrification | 1.3
| D) | Construction of 3rd Type Bungalow 03 Nos. and 5th Type Quarters 02 Nos. | 16
2 | 671 | Construction of Diagnostic Center with OPD/Reffered Services at Village Adur Narejo U/c Jado Wahan Taluka Gambat District Khairpur.
| A) | Construction of Main Building, Compound wall i/c Water Supply & Sanitary Fittings | 20.5 | 12.5 | 6.25 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
| B) | Electrification | 0.9
EXECUTIVE ENGINEER (BUILDINGS) WORKS & SERVICES DEPARTMENT KHAIRPUR