## sum
SUMMARY OF COST
NAME OF WORK:- | Proposed Restoration/Provision of Wash Room & Boundary Wall Facility in Selected 50 Schools of District Badin @ GBLSS Ibrahim Shoro, Taluka Badin.
S # | Item of Work | Total Amount
Part-A Civil Work
1 | Cost of Schedule Items | 697754.5243
| Add 10 % Above | 69775.4524
| Add Cartage Amount | 81246.806
| Total | 848776.7827
2 | Part-B (W/S & S/F)
| Cost of Schedule Items | 54648.47
| Add 10 % above | 5464.847
| Total | 60113.317
3 | Cost of Non-Schedule Item | 14417.7
| Total | 14417.7
| Total:- | 923307.7997
| Add 0.50% Contigency | 4616.539
| G.Total:- | 927924.3387
| Say Rs: in Million | 0.92792
SUB-ENGINEER |  | ASSISTANT ENGINEER
EDUCATION WORKS SUB DIVISION
BADIN

## Meterial
M A T E R I A L S T A T E M E N T
| NAME OF WORK:- | Proposed Restoration/Provision of Wash Room & Boundary Wall Facility in Selected 50 Schools of District Badin @ GBLSS Ibrahim Shoro, Taluka Badin.
S.No | Description | Quantity | Cement | Sand | Shingle | Stone Ballast | Steel | Bricks
1 | CC 1:5:10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Brick Masonary 1:6 | 2054 | 61.62 | 568.958 | 0 | 0 | 0 | 27729
3 | RCC 1:2:4 | 304 | 53.504 | 133.76 | 267.52 | 0 | 0 | 0
4 | Fabrication (Tor ) | 13.57 | 0 | 0 | 0 | 0 | 13.57 | 0
5 | Cement Plaster 1/2" Thick 1:6 | 2670 | 12.816 | 96.12 | 0 | 0 | 0 | 0
6 | Cement Plaster 3/8" Thick 1:4 | 2670 | 13.35 | 66.483 | 0 | 0 | 0 | 0
7 | Cement Plaster 3/4" Thick 1:4 | 155 | 1.55 | 9.3 | 0 | 0 | 0 | 0
8 | CC Topping 2" thick(1:2:4) | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | CC Topping 3" thick(1:2:4) | 0 | 0 | 0 | 0
|  | Total | 142.84 | 874.621 | 267.52 | 0 | 13.57 | 27729
|  | Rate | 51.33 | 3865.16 | 3572.12 | 3800.04 | 3148.84 | 1086.44
|  | Amount | 7331.9772 | 33805.501 | 9556.1354 | 0 | 427.2976 | 30125.8948
|  | Total | 81246.806
| SUB-ENGINEER |  |  |  |  | ASSISTANT ENGINEER
EDUCATION WORKS SUB-DIVISION
BADIN

## Schedule
SCHEDULE "B"
Name of Work:- |  | Proposed Restoration/Provision of Wash Room & Boundary Wall Facility in Selected 50 Schools of District Badin @ GBLSS Ibrahim Shoro, Taluka Badin.
S.No. | Descripition. |  | Qty. | Rate. | Unit. | Amount.
Civil Work
1 | Dismentling CC reinforced seperating reainforcement from
concrate cleaning and straightning the same(S.I.No.20/P-10)
|  |  | 32 | 5445 | %Cft | Rs: | 1742.4 | /-
(Rs: five thousand four hundred forty five only)
2 | Dismentling brick work in cement or lime morter(S.No.13/P-10)
|  |  | 522 | 1285.63 | %Cft | Rs: | 6710.9886 | /-
(Rs: one thousand two hundred eighty five & Ps: sixty three only)
3 | Pacca brick work in foundation & plinth in cement sand martor .
ratio 1:6 ( S.I.NO: 4-ie/P-19 )
|  |  | 543 | 11948.36 | %Cft | Rs: | 64879.5948 | /-
(Rs: eleven thousand nine hundred forty eight and Paisa thirty six only)
4 | R.C.C. work I/c all labour and material execpt the cost of steel reinforcement and its
labour for bending and binding which will be paid sperately. This rate also I/c all kinds
of moulds lifting shuttering curing rendering and finishing the exposedsurface (I/c screening
and washing of shingle)(a) R.C.work in roof slab,beams columns rafts lintels and other
structural members laid in situe or precast laid in position complete in all respect(I) Ratio
1:2:4 90 lbs cement 2 Cft sand 4 Cft shingle 1/8" to 1/4" gauge.(S.I.No.6/P-15).
|  |  | 304 | 337 | P.Cft | Rs: | 102448 | /-
(Rs: three hundred thirty seven only)
5 | Fabrication of mild steel reinforcement for cement concrete i/c cutting bending
laying in position making joints and fastening i/c cost of binding wire (also i/c removal
of rust from bars) (S.I.No:8/P-16).
| Tor Steel |  | 13.57 | 5001.7 | P. Cwt | Rs: | 67873.069 | /-
(Rs: five thousand one & Paisa seventy only)
6 | Pacca brick work in other then building in cement sand morter
ratio 1:6 (S.I.No.7(I-e)/P-21)
|  |  | 1511 | 12346.65 | %Cft | Rs: | 186557.8815 | /-
(Rs: twelve thousand three hundred forty six & Paisa sixty five only)
7 | Cement plaster 1:6 upto 12 ft height 1/2" thick. (S.I.No.13-c/P-51)
|  |  | 2670 | 2206.6 | % Sft | Rs: | 58916.22 | /-
(Rs: two thousand two hundred six and paisa sixty only)
8 | Cement plaster 1:4 upto 12 ft height 3/8" thick. (S.I.No.11-a/P-51)
|  |  | 2670 | 2197.52 | %Sft | Rs: | 58673.784 | /-
(Rs: two thousand one hundred ninty seven and paisa fifty two only)
9 | Cement plaster 1:4 upto 12 ft height 3/4" thick. (S.I.No.11-c/P-51)
|  |  | 155 | 3015.76 | %Sft | Rs: | 4674.428 | /-
(Rs: three thousand fifteen and paisa seventy six only)
10 | Extra labour rate for making cement plaster pattas/bend width not less
then 6" wide with fine finishing as directed by Engineer Incharge.
|  |  | 78 | 19.36 | P.Sft | Rs: | 1510.08 | /-
(Rs: ninteen & Paisa thirty six only)
11 | M/F steel grated door with 1/16" thick sheeting I/c angle iron frame 2"x2"x3/8"&3/4"
square bars 4" centre to centre with locking arrangement.(S.I.No. 24/P-91).
|  |  | 84 | 726.72 | P.Sft. | Rs: | 61044.48 | /-
(Rs: seven hundred twenty six and paisa seventy two only)
12 | Cement pointing struck joints on walls 1:2 (S.I.No.19/P-52)
|  |  | 1860 | 1287.44 | %Sft | Rs: | 23946.384 | /-
(Rs: one thousand two hundredeighty seven & Paisa forty four only )
13 | Primary coat of chalk under distemper (S.I.No.23/P-53)
|  |  | 2670 | 442.75 | %Sft | Rs: | 11821.425 | /-
(Rs: four hundred forty two and paisa seventy five only)
14 | Distempering three coats (S.I.No.24/P-53 )
|  |  | 2670 | 1079.65 | %Sft | Rs: | 28826.655 | /-
(Rs: one thousand seventy nine and Ps: sixty five only)
15 | Colour Wash two coats (S.I.No.25/P-53)
|  |  | 1860 | 859.9 | % Sft | Rs: | 15994.14 | /-
(Rs: eight hundred fifty nine and paisa ninty only)
16 | Painting new surface ( c) painting guard bars, gates iron bars gratings, railings I/c
standard bracess (etc) and similar open work three coats.(S.I.No.4d/P-68).
|  |  | 168 | 1270.83 | %Sft | Rs: | 2134.9944 | /-
(Rs: one thousand two hundred seventy and paisa eighty three only)
[5 empty] | Total | Rs: | 697754.5243 | /-
PART- B (W/S & S/F)
1 | P/F squating type white glazsed earthen ware W.C. pan with I/c cost of flushing cistern
with internal fitting and flush pipe with bend and making requisite number of holes in
walls plinth & floor for pipe connections & making good in cement concrete 1:2:4.
(a) W.C. pan of not less than 19" clear opening between flushing rims and 3 gallons
flushing tank (i) with 4@ dia C.I. trape.(S.I.No.1(b-i)/P-1).
|  |  | 2 | 4802.6 | P/No. | Rs. | 9605.2 | /-
(Rs: four thousand eight hundred two and paisa sixty only)
2 | S/F Consealed tee-stop cock of superior quality with cp head 1/2" dia (S.I.No.12-b/P-8)
|  |  | 2 | 889.46 | P.No | Rs. | 1778.92 | /-
(Rs: eight hundred eighty nine and paisa forty six only)
3 | S/Fixing long bib cock of superior quality with C.P head 1/2" dia
(S.I.No.13-a/ P-19).
|  |  | 3 | 1109.46 | P.No | Rs. | 3328.38 | /-
(Rs: one thousand one hundred nine and paisa forty six only)
4 | Supplying & fixing fiber glass tank of approved quality and desing and wall thickness as
specified I/c cost of nuts, bolts and fixing in plateform of cement concrete 1:3:6 and
making connections for in let out let & over flow inlet outlet flow pipes etc. complete
(S.I.No.3(c)/P-21)
| 250 Gallan |  | 1 | 21989.61 | Each | Rs. | 21989.61 | /-
(Rs: twenty one thousand nine hundred eighty nine and paisa sixty one only)
5 | P/F handle valves (China) (S.I.No.5-i/P-17).
| 1/2" dia |  | 1 | 200.42 | Each | Rs. | 200.42 | /-
(Rs: two hundred & Pasia forty two only)
6 | Providing R.C.C pipes with collars class "B" and digging the trenches to required depth
and fixing in position I/c cutting fitting and jointing with maphalt composition & cement
mortar 1:1 and testing with water pressure to a head of 4 feet above the top of the
highest pipe & refilling with excavted staff 6" dia R.C.C pipes class "B" (S.I.No.2-b/P-23)
| 4" Dia |  | 12 | 146.57 | P.Rft | Rs. | 1758.84 | /-
(Rs: one hundred forty six & Pasia fifty seven only)
7 | Providing G.I. Pipes specials and clamps etc I/c fixing cutting & fitting I/c cost of
breaking through walls and floor making good etc painting two coats after cleaning
the pipe etc with white zink paint with pigment to match the colour of the building &
testing with water to a pressure head of 200 ft: and handling (External).
(S.I.No.1-ii/P-14).
| a) 3/4" Dia. |  | 30 | 86.36 | P.Rft | Rs. | 2590.8 | /-
(Rs: eighty six & Pasia thirty six only)
| b) 1/2" Dia. |  | 30 | 73.21 | P.Rft | Rs. | 2196.3 | /-
(Rs: seventy three & Pasia twenty one only)
8 | Providing PVC Pipes of Class "D" (equivalent) in trenches I/c cutting fitting
and jointing with "Z" joints with one rubber ring I/c testing with water to a head
of 122 meters or 400 feet (25 mm) 1" dia (S.I.No.3/P-23). (PHE)
|  |  | 400 | 28 | P.Rft | Rs: | 11200 | /-
(Rs: twenty eight only)
|  |  |  | TOTAL:- |  | Rs: | 54648.47 | /-
Non-Schedule Item
1 | P&F water pimping set 1/2 H.P Motor Block single phase 220 volts with 1" x 1 1/4"
suction and delivery 50 ft head i/c making C.C 1:3:6 plate form of required size and fixing
with nuts and bolts (local made) (R.A).
|  |  | 1 | 14417.7 | Each. | Rs: | 14417.7 | /-
(Rs: forteen thousand four hundred seventeen & Pasia seventy only)
|  |  |  | TOTAL:- |  | RS: | 14417.7 | /-

## LC
| NAME OF WORK :- | Proposed Restoration/Provision of Wash Room & Boundary Wall Facility in Selected 50 Schools of District Badin @ GBLSS Ibrahim Shoro, Taluka Badin.
S.# | DESCRIPTION | S.BAJRI | S.METAL | H.SAND | S.# | DESCRIPTION | CEMENT | STEEL | S.# | DESCRIPTION | BRICKS
1 | From quarry to main road | 3.875 | 3 | 3 | 1 | From Zeal Pak Factory to Badin | 59 | 63 | 1 | From Badin to Kadhan | 16
2 | From mile 110/4 to 122/0 | 15.125 | 7 | 9 | 2 | From Badin to Kadhan | 16 | 16 | 2 | From Kadhan to Site | 8
3 | From mile 122/0 to Ring road |  | 16.625 | 4.4
4 | From Ring road to Badin | 48.875 | 48.875 | 61 |  | Total | 75 | 79 |  | Total | 24
5 | From Badin to Kadhan | 16 | 16 | 16 |  | Say | 75 | 79
6 | From Kadhan to Site | 8 | 8 | 8 | [5 empty] | Rate for 1st 6 miles | 617.54
| Total | 91.875 | 99.5 | 101.4 | 1 | Rate for 1st three miles | 8.13 | 771.96 |  | Rate for subsequent miles
| Say | 92 | 99 | 101 | [5 empty] | ( 18 x 26.05 ) | 468.9
[5 empty] | 2 | Rate for Subsequent miles | (72x0.60). | (73x32.56) |  | Total | 1086.44
1 | Rate for 1st 6 mile | 771.96 | 771.96 | 771.96 |  |  | 43.2 | 2376.88
|  | (86x32.56) | (93 x32.56) | (95x32.56) |  | Total | 51.33 | 3148.84
2 | Rate for subsequent mile | 2800.16 | 3028.08 | 3093.2
| Total | 3572.12 | 3800.04 | 3865.16
|  |  | SUB ENGINEER |  |  |  | ASSISTANT ENGINEER
EDUCATION WORKS SUB-DIVISION
BADIN

## Estimate
ESTIMATE.
Name of Work:- |  | Proposed Restoration/Provision of Wash Room & Boundary Wall Facility in Selected 50 Schools of District Badin @ GBLSS Ibrahim Shoro, Taluka Badin.
S # | Descripition. |  | Qty. | Rate. | Unit. | Amount.
a) Civil Work (i)
1 | Dismentling CC reinforced seperating reainforcement from
concrate cleaning and straightning the same(S.I.No.20/P-10)
| M.Gate Col: | 1x2x1.50x1.50x7.0 | 32 | 5445 | %Cft | Rs: | 1742.4 | /-
2 | Dismentling brick work in cement or lime morter(S.No.13/P-10)
| C/Wall | 1x310.0x0.33x4.50 | 460
| Pillers | 1x50x0.75x0.37x4.50 | 62
|  |  | 522 | 1285.63 | %Cft | Rs: | 6710.9886 | /-
3 | Pacca brick work in foundation & plinth in cement sand martor .
ratio 1:6 (S.I.No: 4 ie/P-19)
| C/Wall Raise | 1x310.0x1.13x1.50 | 525
| M.Gate Sill | 1x10.50x1.13x1.50 | 18
|  |  | 543 | 11948.36 | %Cft | Rs: | 64879.5948 | /-
4 | R.C.C. work I/c all labour and material execpt the cost of steel reinforcement and its
labour for bending and binding which will be paid sperately. This rate also I/c all kinds
of moulds lifting shuttering curing rendering and finishing the exposedsurface (I/c screening
and washing of shingle)(a) R.C.work in roof slab,beams columns rafts lintels and other
structural members laid in situe or precast laid in position complete in all respect(I) Ratio
1:2:4 90 lbs cement 2 Cft sand 4 Cft shingle 1/8" to 1/4" gauge.(S.I.No.6ai/P-19).
| Qty same item No: 1 |  | 32
| P.Beam C/Wall | 1x310.0x1.13x0.75 | 263
| M.Gate Sill | 1x10.50x1.13x0.75 | 9
|  |  | 304 | 337 | P. Cwt | Rs: | 102448 | /-
5 | Fabrication of mild steel reinforcement for cement concrete i/c cutting bending laying
in position making joints and fastening i/c cost of binding wire (also i/c removal of
rust from bars) (S.I.No:7-A/P-20).
Tor Steel
| Qty same as RCC | 304.0 x 5.0/112 | 13.57 | 5001.7 | P/Cwt | Rs: | 67873.069 | /-
6 | Pacca brick work in other than building I/c stricking of joints in cement sand
ratio 1:6.(S.I.No. 7/P-21).
| C/Wall | 1x310.0x0.75x6.50 | 1511 | 12346.65 | %Cft | Rs: | 186557.8815 | /-
7 | Cement plaster 1:6 upto 12 ft height 1/2" thick. (S.I.No.13-c/P-51)
| C/Wall I/Side | 1x1x310.0x(6.50+0.75) | 2248
| Plinth | 1x2x310.0x1.50 | 390
| M.Gate Sill | 1x2x10.50x1.50 | 32
|  |  | 2670 | 2206.6 | % Sft | Rs: | 58916.22 | /-
8 | Cement plaster 1:4 upto 12 ft height 3/8" thick. (S.I.No.11-a/P-51)
| Qty: same as item No.7 |  | 2670 | 2197.52 | % Sft | Rs: | 58673.784 | /-
9 | Cement plaster 1:4 upto 12 ft height 3/4" thick. (S.I.No.11-c/P-51)
Pattas
| C/Wall | 1x310.0x0.50 | 155 | 3015.76 | % Sft. | Rs: | 4674.428 | /-
10 | Extra labour rate for making cement plaster pattas/bend width not less
then 6" wide with fine finishing as directed by Engineer Incharge.
| Qty: same as item No.9 = 155.0 / 0.50 = |  | 78 | 19.36 | P.Rft | Rs: | 1510.08 | /-
11 | M/F steel grated door with 1/16" thick sheeting I/c angle iron frame 2"x2"x3/8"&3/4"
square bars 4" centre to centre with locking arrangement.(S.I.No. 24/P-91).
| C/Wall M/Gate. | 1x12.0x7.0 | 84 | 726.72 | P.Sft. | Rs: | 61044.48 | /-
12 | Cement pointing struck joints on walls 1:2 (S.I.No.19/P-52)
| C/Wall O/Side | 1x310.0x6.0 | 1860 | 1287.44 | % Sft | Rs: | 23946.384 | /-
13 | Primary coat of chalk under distemper (S.I.No.23/P-53)
| Qty: same as item No: 8 |  | 2670 | 442.75 | % Sft | Rs: | 11821.425 | /-
14 | Distempering three coats (S.I.No.24/P-53 )
| Qty: same asitem No.13 |  | 2670 | 1079.65 | % Sft | Rs: | 28826.655 | /-
15 | Colour wah two coats.(S.I.No.25/P-53)
| Qty: same asitem No.12 |  | 1860 | 859.9 | % Sft | Rs: | 15994.14 | /-
16 | Painting new surface ( c) painting guard bars, gates iron bars gratings, railings I/c
standard bracess (etc) and similar open work three coats.(S.I.No.4d/P-68).
| C/Wall M/Gate | 1x2x12.0x7.0 | 168 | 1270.83 | %Sft |  | 2134.9944 | /-
|  |  |  | G.Total:- |  | Rs: | 697754.5243 | /-
PART- B.( S/W & S/F)
1 | P/F squating type white glazsed earthen ware W.C. pan with I/c cost of flushing cistern
with internal fitting and flush pipe with bend and making requisite number of holes in
walls plinth & floor for pipe connections & making good in cement concrete 1:2:4.
(a) W.C. pan of not less than 23" clear opening between flushing rims and 3 gallons
flushing tank (i) with 4@ dia C.I. trape.(S.I.No.1(b-i)/P-1).
| Comm: Lav | 1x2 | 2 | 4802.6 | P/No. | Rs. | 9605.2 | /-
2 | S/F Consealed tee-stop cock of superior quality with cp head 1/2" dia (S.I. No.12-b/P-18).
| Com: Lav: I/S | 1x2 | 2 | 889.46 | P.No | Rs. | 1778.92 | /-
3 | Cancealed C.P fitting or superior quality for tiles Bath room (a) S.F concealed bib cock
of superior quality with C.P head 1/2" dia (S.I.No.13-a/ P-19).
| Lav: I/S | 1x2 | 2
| Lav: O/S | 1x1 | 1
|  |  | 3 | 1109.46 | P.No | Rs. | 3328.38 | /-
4 | Supplying & fixing fiber glass tank of approved quality and desing and wall thickness as specified I/c
cost of nuts, bolts and fixing in plateform of cement concrete 1:3:6 and making connections for in let
out let & over flow inlet outlet flow pipes etc. complete .(S.I.No.3(a)/P-21)
| O/H Tank | 1x1 | 1 | 21989.61 | P.Each | Rs. | 21989.61 | /-
5 | P/F handle valves (China) (S.I.No.5-i/P-17).
1/2" dia
| Lav: O/S | 1x1 | 1 | 200.42 | Each | Rs. | 200.42 | /-
6 | Providing R.C.C pipes with collars class "B" and digging the trenches to required depth
and fixing in position I/c cutting fitting and jointing with maphalt composition & cement
mortar 1:1 and testing with water pressure to a head of 4 feet above the top of the
highest pipe & refilling with excavted staff 6" dia R.C.C pipes class "B" (S.I.No.2-b/P-23)
| Lav: to O/S | 1x2x6.0 | 12 | 146.57 | P.Rft | Rs. | 1758.84 | /-
7 | Providing G.I. Pipes specials and clamps etc I/c fixing cutting & fitting I/c cost of
breaking through walls and floor making good etc painting two coats after cleaning
the pipe etc with white zink paint with pigment to match the colour of the building &
testing with water to a pressure head of 200 ft: and handling .(S.I.No.1-ii/P-14).
(a) | 3/4" Dia.
| O/S to Lav: | 1x30.0 | 30 | 86.36 | P.Rft | Rs. | 2590.8 | /-
(b) | 1/2" Dia.
| Lav: I/S | 1x30.0 | 30 | 73.21 | P.Rft | Rs. | 2196.3 | /-
8 | Providing PVC Pipes of Class "D" (equivalent) in trenches I/c cutting fitting
and jointing with "Z" joints with one rubber ring I/c testing with water to a head
of 122 meters or 400 feet (25 mm) 1" dia (S.I.No.3/P-23).
| Bore to Motor | 1x400.0 | 400 | 28 | P.Rft | Rs: | 11200 | /-
|  |  |  | TOTAL:- |  | RS: | 54648.47 | /-
Non-Schedule Item
1 | P&F water pimping set 1/2 H.P Mono Block single phase 220 volts with1"x1" -1/4"
suction and delivery 50 ft head i/c making C.C 1:3:6 plate form of required size and fixing
with nuts and bolts (local made) (R.A).
| Water Pump. | 1x1 | 1 | 14417.7 | Each | Rs: | 14417.7 | /-
|  |  |  | TOTAL:- |  | Rs: | 14417.7 | /-
CERTIFICATE
Certified that I have prepared this estimate under the supervision of Assistan Engineer
Education works Sub-Division Badin on the basis of drawing & design supplied to me
for items identified by the Assistant Engineer. The rate provided in this estimate are from
composite schedule of Rates & sanctioned rate analysis.
SUB-ENGINEER
Certified that this estimate has been prepared by the Sub-Engineer under my supervision
for the items identified by me which are prepared for the execution. Further certified that
the quantities provided in this estimate are correct.
ASSISTANT ENGINEER
EDUCATION WORKS SUB-DIVISION
BADIN

## Face Sheet
F A C E S H E E T
| FUND HEAD. |  |  | -:- | DISTRICT GOVERNMENT
| MAJOR HEAD. |  |  | -:- | 09 Education Affairs & Services
| MINOR HEAD |  |  | -:- | NON-DEVELOPMENT
| SERVICE HEAD |  |  | -:- | SCHEME NO.
| DEPARTMENTAL HEAD |  |  | -:- | The Detailed working estimate for the
work " Proposed Restoration/Provision of
Wash Room & Boundary Wall Facility in Selected
50 Schools of District Badin @ GBLSS Ibrahim Shoro,
Taluka Badin.
Certified that this estimate has been prepared in the office of
the Assistant Engineer, Education Works Sub-Division Badin. The expenditure
incurred on the above said work shall be chargeable against the Head
of Account 09 Education Affairs & Services.
[5 empty] | Estimated Cost | Rs: 0.928 (Million)
GENERAL DESCRIPTION
| HISTORY. | Government of Sindh have approved the ADP Scheme during the year
for District Badin, which are to be executed by Education & Literacy Department
within years. The above said work is one of the approved schemes hance its
estimate has been prepared.
| SCOPE. | The work will be completed in current financial years subject to availbility of funds.
| LAND. | The Education Department Government of Sindh shall provide the plot for
the purpose of construction of the above said building.
| METERIAL. | No lead weather small or long for carraige of meterial for which finished
items are applicable is to be paid seperately. However the construction meterial
as detailed below shall have to be brought by the contractor from the following
pre-determined quaries / approved source of supply. The estimate is based on
the rates provided by the Composite Schedule of Rates (Recent Edition).
| 1- | Crush |  |  | Thatta
| 2- | Stone Ballast |  |  | Chillya
| 3- | Hill Sand |  |  | Bholari
| 4- | Steel |  |  | Hyderabad
| 5- | Cement |  |  | Zeal-Pak
| 6- | Bricks |  |  | Badin
ASSISTANT ENGINEER
| SUB-ENGINEER |  |  |  |  | EDUCATION WORKS SUB-DIVISION
BADIN