## Cover
OFFICE OF THE EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION DADU
DISTRICT A.D.P 2008-09
DETAILED WORKING ESTIMATE CONSTRUCTION OF R CC CROSS SLABS AT VARIOUS STREETS TOWN COMMITTEE, BHAN SAYEDABAD.
| Estimated cost | Rs | #REF!

## FACE SHEET
OFFICE OF THE EXECUTIVE ENGINEER PUBLIC HEALTH ENGG:DIVISION DADU
OFFICE OF THE ASSISTANT ENGINEER PUBLIC HEALTH ENGG: SUB - DIV DADU
| FUND HEAD: - |  | DISTRICT A.D.P
| MAJOR HEAD: - |  | CONSTT: OF C.C BLOK & DRAINS AT VARIOUS
LOCATION OF U.C PIPRI,KHUDABAD,SIYAL,MURADABAD & YAR MUHAMMAD KALHORO TALUKA DADU (2008-09)
| SERVICE HEAD: - |  | Constt: of C.C Block & Drains at Village Meenho Khan Bhand U.C Pipri WORK No. 01
| DEPTT: HEAD: - |  | Detailed working Estimate for Constt: of C.C Block & Drains at Village Meenho Khan Bhand U.C Pipri WORK No. 01
The Estimate framed in the office of the executive Engineer Public Health
Department Division Dadu for the probable expenditure that will be incurred on
Detailed working Estimate for Constt: of C.C Block & Drains at Village Meenho Khan Bhand U.C Pipri WORK No. 01
|  |  |  | ESTIMATED COST | Rs: | #REF!
The Scheme was administrativly approved by the district coordination officer
Dadu wide his letter No. DCO/PA/04 Dated:15-12-2008 Rs: 20 Million and there in above schemes
approved 0.500 Million
The rates provided in the estimate are from general schedule, public health
and approved rates analysis of rates
The expenditure involved shall be debited to the head of account 05 envoirment protection
capital 052 waste water management and 0521 waste water management
The work will be carried out as per standard specificationof P.W.D .
ASSISTANT ENGINEER
PUBLIC HEALTH ENGG: SUB-DIV:
DADU

## abstract
DETAILED WORKING ESTIMATE CONSTRUCTION OF R CC CROSS SLABS AT VARIOUS STREETS TOWN COMMITTEE, BHAN SAYEDABAD.
A B S T R A C T
| GROUP--A |  | RS: | 1304000
| GROUP--B |  | RS: | 696000
|  | Total | RS: | 2000000
|  | SAY | Rs | 2000000 | #REF! | x | 100 | / | 1304000 | = | #REF!
#REF!

## Estimate
DETAILED WORKING ESTIMATE CONSTRUCTION OF R CC CROSS SLABS AT VARIOUS STREETS TOWN COMMITTEE, BHAN SAYEDABAD.
S:No |  | Item QTY: | [8 empty] | Rate | Unit | Rs | Amount
1 | Dismantling cement concret reinforced separating Reinforcement
from concrete cleaning (G.S.I.NO.13 P/10)
|  | 14 | x | 8 | x | 2.5 | x | 0.33 | = | 92.4
|  | 20 | x | 12 | x | 3 | x | 0.5 | = | 360
|  | 20 | x | 10 | x | 3 | x | 0.5 | = | 300
752.4
| 752.4 | [8 empty] | @Rs | 5445 | p%cft | Rs: | 40968.18
2 | Dismantling cement concret plain (1:2:4)(GSI No:13 P/10
|  | 12 | x | 12 | x | 0.75 | x | 0.75 | = | 81
|  | 8 | x | 11 | x | 0.75 | x | 1 | = | 66
|  | 4 | x | 10 | x | 0.75 | x | 0.83 | = | 24.9
171.9
| 171.9 | [8 empty] | @Rs | 3327.5 | p%cft | Rs: | 5719.9725
3 | Dismetling mettled road removing road metaling (GSI No 51 P/13)
|  | 6 | x | 12 | x | 3 | x | 0.75 | = | 162
|  | 2 | x | 10.5 | x | 3 | x | 0.75 | = | 47.25
209.25
| 209.25 | [8 empty] | @Rs | 605 | p%cft | Rs: | 1265.9625
4 | Dismatling brick work in lime or cement mortor (GSI No 13 P/10)
|  | 4 | x | 10 | x | 0.75 | x | 0.75 | = | 22.5
|  | 2 | x | 12 | x | 0.75 | x | 1 | = | 18
40.5
| 40.5 | [8 empty] | @Rs | 1285.63 | p%cft | Rs: | 520.6802
5 | Earth Work Excavation in ashes sand soft soil or silt
clearance undressed lead up to 50ft (GSINO2P/1)
|  | 10 | x | 8 | x | 1 | x | 1.5 | = | 120
|  | 20 | x | 12 | x | 1 | x | 1.5 | = | 360
480
| 480 | [8 empty] | @Rs | 1663.75 | p%0cft | Rs: | 798.6
6 | Earth for slush or daldal incuding dewatering (GSI NO16P/4)
|  | 10 | x | 8 | x | 1 | x | 1.5 | = | 120
|  | 20 | x | 12 | x | 1 | x | 1.5 | = | 360
480
| 480 | [8 empty] | @Rs | 2420 | p%0cft | Rs: | 1161.6
7 | Excavation in foundation of building bridges and other structures
i/c dig billing dressing refilling around the structures with excavated
Earth watering ramming up to 5ft (b) in ordinary soil (G.S.I-18/ P/4)
|  | 8 | x | 10 | x | 3 | x | 1 | = | 240
240
| 240 | [8 empty] | @Rs | 3176.25 | P%0Cft | Rs | 762.3
8 | Extra for every 50ft additional lead or part therof(a) forearth
work soft ordinary hard and very hard (GSI NO 8P/3)
| Lead |  |  | 2500 | (-) | 100 | = | 2400
|  |  |  | 2400 | (/) | 50 | = | 48
| Rate | 48 |  | x |  | 100.78 | = | 4837.44
Qty item No: 1,2,3,4,5
| 1654.05 | [8 empty] | @Rs | 4837.44 | p%0cft | Rs: | 8001.3676
9 | Cement concrete plain i/c placing compacting, finishing
and curing complete i/c s/w of stone aggregate without
shuttering (Ratio 1:4:8) (G.S.I No. 5 p/ 15)
|  | 10 | x | 8 | x | 2.5 | x | 0.25 | = | 50
|  | 20 | x | 12 | x | 3 | x | 0.25 | = | 180
230
| 230 | Cft | [7 empty] | @Rs | 11288.75 | P%cft | Rs | 25964.125
10 | Pacca brick work in foundation and plinth in (1:6) (GSI No 4 P/19)
|  | 4 | x | 10 | x | 0.75 | x | 1 | = | 30
|  | 4 | x | 12 | x | 0.75 | x | 1 | = | 36
66
| 66 | Cft | [7 empty] | @Rs | 11948.34 | P%cft | Rs | 7885.9044
11 | Cement concrete plain i/c placing compacting, finishing
and curing complete i/c s/w of stone aggregate without
shuttering (Ratio 1:2:4) (G.S.I No. 5 p/ 15)
| Inside drain | 10 | x | 8 | x | 0.92 | x | 0.33 | = | 24.288
|  | 20 | x | 12 | x | 1.5 | x | 0.33 | = | 118.8
143.088
| 143.088 | Cft | [7 empty] | @Rs | 14429.25 | P%cft | Rs | 20646.5252
12 | Cement palaster (1:4) up to 12ft height (GSI No 11 P/51)
|  | 2 | x | 2 | x | 10 | x | 1.75 | = | 70
|  | 2 | x | 2 | x | 12 | x | 1.75 | = | 84
154
| 154 | Cft | [7 empty] | @Rs | 2283.93 | P%sft | Rs | 3517.2522
13 | R.C.C work i/c all labour and material except the cost of steel
reinforcement and its labour for bending and binding which will
be paid separately. This rate also includes all kinds of forms moulds
lifting shuttering curing rendering and finishing the exposed surface
i/c screening and washing of shingle (a) R.C work in roof slab members
laid in situ or prrecast laid in position complete in a respect. (i)
Ratio 1;2;4 90 lbs cement 2 cft sand 4 cft shingle 1/8” to ¼” gauge.
(G.S.I-6 P/17)
|  | 10 | x | 8 | x | 2.5 | x | 0.33 | = | 66
|  | 20 | x | 12 | x | 3 | x | 0.75 | = | 540
|  | 18 | x | 10 | x | 3 | x | 0.75 | = | 405
1011
| 1011 | [8 empty] | @Rs | 337 | p/cft | Rs: | 340707
14 | Fabrication of mild steel reinforcement for cement concrete i/c
cutting bending laying in position making joints and fastening i/c
cost of binding wire also includes removal of rust from bars.
(G.S.I-8 (a) P/16)
| 1011 | x | 4 |  |  | 36.1071
112
| 36.1071 | Cwt | [7 empty] | @Rs | 4820.2 | P-Cwt | Rs | 174043.65
[13 empty] | RS | 631963.1196
DETAILED WORKING ESTIMATE CONSTRUCTION OF R CC CROSS SLABS AT VARIOUS STREETS TOWN COMMITTEE, BHAN SAYEDABAD.
S:No |  | Item QTY: | [8 empty] | Rate | Unit | Rs | Amount
1 | Cement concrete plain i/c placing compacting, finishing
and curing complete i/c s/w of stone aggregate without
shuttering (Ratio 1:4:8) (G.S.I No. 5 p/ 15)
| Ramps | 10 | x | 8 | x | 11 | x | 0.33 | = | 290.4
|  | 14 | x | 8 | x | 10 | x | 0.33 | = | 369.6
|  | 20 | x | 12 | x | 13 | x | 0.33 | = | 1029.6
|  | 20 | x | 12 | x | 14 | x | 0.33 | = | 1108.8
|  | 18 | x | 10 | x | 8 | x | 0.33 | = | 475.2
|  | 18 | x | 10 | x | 9 | x | 0.33 | = | 534.6
3808.2
| 3808.2 | Cft | [7 empty] | @Rs | 11288.75 | P%cft | Rs | 429898.1775
2 | Cement concrete plain i/c placing compacting, finishing
and curing complete i/c s/w of stone aggregate without
shuttering (Ratio 1:2:4) (G.S.I No. 5 p/ 18)
| Ramps | 10 | x | 8 | x | 11 | x | 0.33 | = | 290.4
|  | 14 | x | 8 | x | 10 | x | 0.33 | = | 369.6
|  | 20 | x | 12 | x | 13 | x | 0.33 | = | 1029.6
|  | 20 | x | 12 | x | 14 | x | 0.33 | = | 1108.8
|  | 18 | x | 10 | x | 8 | x | 0.33 | = | 475.2
|  | 18 | x | 10 | x | 9 | x | 0.33 | = | 534.6
3808.2
| 3808.2 | Cft | [7 empty] | @Rs | 14429.25 | P%cft | Rs | 549494.6985
[13 empty] | RS | 979392.876
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG:DIVISION
DADU

## Cartage
Cartage of Material
1 | Bajri from Laki (lead | 28 | Miles)
| 7007.088 |  |  |  | @Rs | 1488.28 | P%Cft | Rs | 104285.0893
2 | Stone from Amri (lead | 46 | Miles
| 0 |  |  |  | @Rs | 2074.36 | P%Cft | Rs | 0
3 | Hill sand from Bolhari (Lead |  | 110 | Miles
| 3503.544 |  |  |  | @Rs | 4158.2 | P%Cft | Rs | 145684.3666
4 | Cement from Zeel Pak Hyd (lead |  |  | 109 | Miles
| 1035.8304 |  |  |  | @Rs | 71.73 | P-Bags | Rs | 74300.1146
5 | Brick from Makhdoom Bilawal (Lead |  |  | 15 | Miles)
| 0 |  |  |  | @Rs | 851.99 | P%Onos: | Rs | 0
6 | Cartage of Earth Lead | 3 | Mile)
| 0 |  |  |  | @Rs | 579.41 | P%Cft | Rs | 0
7 | Cartage of Steel lead | 120 | Mile
| 0 |  |  |  | @Rs | 39.954 | p/cwt | Rs | 0
[7 empty] | Total: | Rs | 324269.5705
[5 empty] | Schedule B |  |  | Rs | 979392.876
[7 empty] | Total: | Rs | 1303662.4465
[8 empty] | RS | 1303662.4465
[7 empty] | Total: |  | 1304000
Cartage of Material
1 | Bajri from Laki (lead | 28 | Miles)
| 1236.3974 |  |  |  | @Rs | 1488.28 | P%Cft | Rs | 18401.0558
2 | Stone from Amri (lead | 46 | Miles
| 0 |  |  |  | @Rs | 2074.36 | P%Cft | Rs | 0
3 | Hill sand from Bolhari (Lead |  | 110 | Miles
| 640.7047 |  |  |  | @Rs | 4158.2 | P%Cft | Rs | 26641.7837
4 | Cement from Zeel Pak Hyd (lead |  |  | 109 | Miles
| 228.5941 |  |  |  | @Rs | 71.73 | P-Bags | Rs | 16397.0539
5 | Brick from Makhdoom Bilawal (Lead |  |  | 15 | Miles)
| 891 |  |  |  | @Rs | 851.99 | P%Onos: | Rs | 759.1231
6 | Cartage of Earth Lead | 3 | Mile)
| 0 |  |  |  | @Rs | 579.41 | P%Cft | Rs | 0
7 | Cartage of Steel lead | 120 | Mile
| 36.1071 |  |  |  | @Rs | 39.954 | p/cwt | Rs | 1442.6248
[7 empty] | Total: | Rs | 63641.6413
[5 empty] | Schedule B |  |  | Rs | 631963.1196
[7 empty] | Total: | Rs | 695604.7609
[7 empty] | Total: |  | 695604.7609
[7 empty] | G.Total | Rs | 696000

## Material
Material Statement GROUP --A
S.No: | Item |  |  |  | Qty: | Bajri | Stone | Hill sand | Cement | Bricks | Steel
1 | C.C Plain 1:4:8 |  |  |  | 3808.2 | 3655.872 |  | 1827.936 | 365.5872
2 | Pacca brick work (1:6) |  |  |  | 0 |  |  | 0 | 0 | 0
3 | Type A Drain | #REF! | x | 0.35 | 0 | 0 |  | 0 | 0
| Type B Drain | #REF! | x | 0.74 | 0 | 0 |  | 0 | 0
| Type C Drain |  | x | 1.378
| C.C Plain 1:2:4 |  |  |  | 3808.2 | 3351.216 |  | 1675.608 | 670.2432
3 | C.C. Stone 1:5:10 |  |  |  | 0 |  | 0 | 0 | 0
4 | R.C.C work (1:2:4) |  |  |  | 0 | 0 |  | 0 | 0
5 | Pit Sand
6 | Cement Plaster (1:4) 1/2" |  |  |  | 0 |  |  | 0 | 0
7 | Barrow Pit |  |  |  | 0
8 | DRY Brick
9 | STEEL |  |  |  | 0 | [5 empty] | 0
| Total |  |  |  |  | 7007.088 | 0 | 3503.544 | 1035.8304 | 0 | 0
Material Statement
S.No: | Item |  |  |  | Qty: | Bajri | Stone | Hill sand | Cement | Bricks | Steel
1 | C.C Plain 1:4:8 |  |  |  | 230 | 220.8 |  | 110.4 | 22.08
2 | Pacca brick work (1:6) |  |  |  | 66 |  |  | 16.962 | 2.2704 | 891
3 | Type A Drain | #REF! | x | 0.35 | 0 | 0 |  | 0 | 0
| Type B Drain | #REF! | x | 0.74 | 0 | 0 |  | 0 | 0
| Type C Drain |  | x | 1.378
| C.C Plain 1:2:4 |  |  |  | 143.088 | 125.9174 |  | 62.9587 | 25.1835
3 | C.C. Stone 1:5:10 |  |  |  | 0 |  | 0 | 0 | 0
4 | R.C.C work (1:2:4) |  |  |  | 1011 | 889.68 |  | 444.84 | 177.936
5 | Pit Sand
6 | Cement Plaster (1:4) 1/2" |  |  |  | 154 |  |  | 5.544 | 1.1242
7 | Barrow Pit |  |  |  | 0
8 | DRY Brick
9 | STEEL |  |  |  | 36.1071 | [5 empty] | 36.1071
| Total |  |  |  |  | 1236.3974 | 0 | 640.7047 | 228.5941 | 891 | 36.1071

## lead chart...............
RATE ANALYSIS CARRAIGE
SCHEDULE OF CARRAGE RATE VALUME-III PART-IV
NAME OF WORK |  |  | DETAILED WORKING ESTIMATE CONSTRUCTION OF R CC CROSS SLABS AT VARIOUS STREETS TOWN COMMITTEE, BHAN SAYEDABAD.
Carriage of 100 cft / 5 tons of all material like stone aggregate spqwl, coal lime struck etc: B.G rails fastening points and crossing bridges, girds pipes sheets rails M.S bars etc: or 1000 Nos. bricks 10”x5”x3” or 150 of timer or 100 mounds of fuel wood
a) | Hill Sand From Bolhari ( |  |  | 110 | Miles )
| 1st to 6th mile | [6 empty] | Rs: | 771.96
| Remaining | 104 |  | @Rs: | 32.56 |  | P/ Mile | Rs: | 3386.24
[8 empty] | Total | 4158.2
b) | Bajri Shingle from Laki ( |  |  | 28 | Miles )
| 1st to 6th mile | [6 empty] | Rs: | 771.96
| Remaining | 22 |  | @Rs: | 32.56 |  | P/ Mile | Rs: | 716.32
[8 empty] | Total | 1488.28
c) | Stone From Amri ( |  | 46 | Miles )
| 1st to 6th mile | [6 empty] | Rs: | 771.96
| Remaining | 40 |  | @Rs: | 32.56 |  | P/ Mile | Rs: | 1302.4
[8 empty] | Total | 2074.36
d) | Bricks 1000 No. Lead( |  | 15 | Miles )
| 1st to 6th mile | [6 empty] | Rs: | 617.54
| Remaining | 9 |  | @Rs: | 26.05 |  | P/ Mile | Rs: | 234.45
[8 empty] | Total | 851.99
e) | Cement From Zeel Pak Hyderabad ( |  |  |  | 109 | Miles )
| 1st to 2nd mile | [6 empty] | Rs: | 7.53
| Remaining | 107 |  | @Rs: | 0.6 |  | P/ Mile | Rs: | 64.2
[8 empty] | Total | 71.73
F | Steel of Hyderbad |  |  | ( | 105 | Mile )
| Ist to 6th mile | [6 empty] | Rs: | 771.96
| Remaning | 99 |  | @Rs: | 32.56 |  | P/Mile | Rs: | 3223.44
[8 empty] | Total | 3995.4
[5 empty] | 3995.4 | ( / ) | 100 | ( = ) | 39.954

## schedule -B
SCHEDULE-B
Name of work: - |  |  |  | DETAILED WORKING ESTIMATE CONSTRUCTION OF R CC CROSS SLABS AT VARIOUS STREETS TOWN COMMITTEE, BHAN SAYEDABAD.
S.No: | Item | Qty: | [8 empty] | Rate | Unit | Rs | Amount
1 | Dismantling cement concret reinforced separating Reinforcement
from concrete cleaning (G.S.I.NO.13 P/10)
| 752.4 | [8 empty] | @Rs | 5445 | p%cft | Rs: | 40968.18
2 | Dismantling cement concret plain (1:2:4)(GSI No:13 P/10
|  | 6 | x | 12 | x | 0.75 | x | 0.75 | = | 40.5
| 171.9 | [8 empty] | @Rs | 3327.5 | p%cft | Rs: | 5719.9725
3 | Dismetling mettled road removing road metaling (GSI No 51 P/13)
| 209.25 | [8 empty] | @Rs | 605 | p%cft | Rs: | 1265.9625
4 | Dismatling brick work in lime or cement mortor (GSI No 13 P/10)
| 40.5 | [9 empty] | 1285.63 | p%cft | Rs: | 520.6802
5 | Earth Work Excavation in ashes sand soft soil or silt
clearance undressed lead up to 50ft (GSINO2P/1)
| 480 | [8 empty] | @Rs | 1663.75 | p%0cft | Rs: | 798.6
6 | Earth for slush or daldal incuding dewatering (GSI NO16P/4)
| 480 | [8 empty] | @Rs | 2420 | p%0cft | Rs: | 1161.6
7 | Excavation in foundation of building bridges and other structures
i/c dig billing dressing refilling around the structures with excavated
Earth watering ramming up to 5ft (b) in ordinary soil (G.S.I-18/ P/4)
| 240 | [8 empty] | @Rs | 3176.25 | P%0Cft | Rs | 762.3
8 | Extra for every 50ft additional lead or part therof(a) forearth
work soft ordinary hard and very hard (GSI NO 8P/3)
| Lead |  |  | 2500 | (-) | 100 | = | 2400
|  |  |  | 2400 | (/) | 50 | = | 48
| Rate | 48 |  | x |  | 100.78 | = | 4837.44
Qty item No: 1,2,3,4,5
| 1654.05 | [8 empty] | @Rs | 4837.44 | p%0cft | Rs: | 8001.3676
9 | Cement concrete plain i/c placing compacting, finishing
and curing complete i/c s/w of stone aggregate without
shuttering (Ratio 1:4:8) (G.S.I No. 5 p/ 15)
| 230 | Cft | [7 empty] | @Rs | 11288.75 | P%cft | Rs | 25964.125
10 | Pacca brick work in foundation and plinth in (1:6) (GSI No 4 P/19)
| 66 | Cft | [7 empty] | @Rs | 11948.34 | P%cft | Rs | 7885.9044
11 | Cement concrete plain i/c placing compacting, finishing
and curing complete i/c s/w of stone aggregate without
shuttering (Ratio 1:2:4) (G.S.I No. 5 p/ 15)
| 143.088 | Cft | [7 empty] | @Rs | 14429.25 | P%cft | Rs | 20646.5252
12 | Cement palaster (1:4) up to 12ft height (GSI No 11 P/51)
| 154 | Cft | [7 empty] | @Rs | 2283.93 | P%sft | Rs | 3517.2522
13 | R.C.C work i/c all labour and material except the cost of steel
reinforcement and its labour for bending and binding which will
be paid separately. This rate also includes all kinds of forms moulds
lifting shuttering curing rendering and finishing the exposed surface
i/c screening and washing of shingle (a) R.C work in roof slab members
laid in situ or prrecast laid in position complete in a respect. (i)
Ratio 1;2;4 90 lbs cement 2 cft sand 4 cft shingle 1/8” to ¼” gauge.
(G.S.I-6 P/17)
| 1011 | [8 empty] | @Rs | 337 | p/cft | Rs: | 340707
14 | Fabrication of mild steel reinforcement for cement concrete i/c
cutting bending laying in position making joints and fastening i/c
cost of binding wire also includes removal of rust from bars.
(G.S.I-8 (a) P/16)
| 36.1071 | Cwt | [7 empty] | @Rs | 4820.2 | P-Cwt | Rs | 174043.65
[13 empty] | RS | 631963.1196
SCHEDULE-B
DETAILED WORKING ESTIMATE CONSTRUCTION OF R CC CROSS SLABS AT VARIOUS STREETS TOWN COMMITTEE, BHAN SAYEDABAD.
S:No |  | Item QTY: | [8 empty] | Rate | Unit | Rs | Amount
1 | Cement concrete plain i/c placing compacting, finishing
and curing complete i/c s/w of stone aggregate without
shuttering (Ratio 1:4:8) (G.S.I No. 5 p/ 15)
| 3808.2 | Cft | [7 empty] | @Rs | 11288.75 | P%cft | Rs | 429898.1775
2 | Cement concrete plain i/c placing compacting, finishing
and curing complete i/c s/w of stone aggregate without
shuttering (Ratio 1:2:4) (G.S.I No. 5 p/ 18)
| 3808.2 | Cft | [7 empty] | @Rs | 14429.25 | P%cft | Rs | 549494.6985
[13 empty] | RS | 979392.876