## Procurement Plan
OFFICE OF THE EXECUTIVE ENGINEER BUILDINGS WORKS & SERVICES DEPARTMENT KHAIRPUR
PROCUREMENT PLAN FOR THE YEAR 2017-18
SR. NO. | ADP | NAME OF WORK | ESTIMATE/ TENDER COST | ALLOCATION 2017-18 | RELEASE 2017-18 | UTILIZATION / PROCUREMENT PROGRESS PLAN |  |  |  | REMARKS
[6 empty] | JULY TO AUGUST 2017 | AUGUST TO SEPTEMBER 2017 | OCTOBER TO DECEMBER 2017 | JANUARY TO JUNE 2018
1 | 671 | Construction of Diagnostic Center with OPD/Referred Services at Village Adur Narejo U/c Jado Wahan Taluka Gambat District Khairpur.
| A) | 3rd Type Bungalow 01 Nos. 4th Type Quarters 02 Nos. Garrages, Pump Room, Under Water Tank, Over Head Water Tank & External Development i/c Paths. | 14 | 3.5 | 1.75 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
| B) | Installation of Electrification | 0.55 | 0.1375 | 0.06875
2 |  | Rehabilitation of R.H.C Ranipur & Construction of New OPD at R.H.C Ranipur Taluka Sobhodero District Khairpur.
| A) | Renovation / Rehabilitation of Main Building i/c Masjid | 12.6 | 3.15 | 1.575 | -- | Tendering process | 50% | 50% | The utilization is subject to receipt of budget
| B) | Construction of Category IV th Type Staff Quarters 04 Nos. | 9 | 2.25 | 1.125 | -- |  | 50% | 50%
| C) | External Development Over Head Water Tank & Under Ground Water Tank | 5.2 | 1.3 | 0.65 | -- |  | 50% | 50%
| D) | Internal & External Electrification | 2 | 0.5 | 0.25 | -- |  | 50% | 50%
EXECUTIVE ENGINEER (BUILDINGS) WORKS & SERVICES DEPARTMENT KHAIRPUR