## Massonary
G.B.H.S SINDH UNIVERSITY MEASUREMENT SHEET
S. No. | DESCRIPTION | UNIT | NO | L | B | H | TOTAL
1 | EXCAVATION
Excavation in foundation in ordinary soil of Building Bridges and other structures including dagbelling dressing, refilling around structure with excavated earth watering and ramming lead upto 5 ft. (Page No. 4, Item No. 18-b)
Toilet
| Footing F1 | CFT | 4 | 5 | 4 | 5.5 | 440
| Footing Situ Horizontal | CFT | 2 | 10 | 2.5 | 2.5 | 125
| Vertical | CFT | 2 | 12 | 2.5 | 2.5 | 150
| B/Wall F1 | CFT | 90 | 4 | 4 | 4 | 5760
| B/W Situ | CFT | 1 | 440 | 2.5 | 2.5 | 2750
External Development out side of
| Class Room for K.Stone | CFT | 2 | 25 | 1 | 1 | 50
| F.2 | CFT | 2 | 145 | 1 | 1 | 290
| F.3 | CFT | 2 | 125 | 1 | 1 | 250
| F.4 | CFT | 6 | 30 | 1 | 1 | 180
| F.5 | CFT | 2 | 40 | 1 | 1 | 80
| TOTAL | [5 empty] | 10075
2 | SAND UNDER FLOOR
CLASS ROOM (A)
| TOILET | CFT | 1 | 11.75 | 12.25 | 3 | 431.8125
| EXTERNAL DAY | CFT | 1 | 100 | 30 | 1 | 3000
| Out Side of Building | CFT | 1 | 30 | 30 | 1 | 900
| Shownon | CFT | 1 | 35 | 30 | 1 | 1050
| Main Gate Area Drawing | CFT | 1 | 150 | 40 | 1 | 6000
| Main Gate Area | CFT | 1 | 120 | 70 | 1 | 8400
| TOTAL | [5 empty] | 19781.8125
2a | Extra Lead | CFT |  |  |  |  | 19781.81
3 | BAILING OUT WATER
| Full hire charge of the pumping set per day inclusive of wage driver and assistant fuel or electric energy plate forms required for placing pumps etc. At lower depth with suction and delivery pipes for pumping out water found at various depths from trenches i/e the cost of erection and dismantling after completion of the job. (Page No. 76, Item No. 23(1) | P/DAY | 6 |  |  |  | 6 DAYS
4 | STONE SOLING
Dry rammed block or stone ballast 1 ½" to 2" guage 6" thick. (S.I.No: 2 (d) P/16).
Under Soiling
| FOOTING F1,F2 | CFT | 4 | 5 | 4 | 0.5 | 40
| Situ | CFT | 2 | 10 | 2.5 | 0.5 | 25
| Situ | CFT | 2 | 12 | 2.5 | 0.5 | 30
| B/Wall F1 | CFT | 90 | 4 | 4 | 0.5 | 720
| B/Wall Situ | CFT | 1 | 900 | 2.5 | 0.5 | 1125
| Under Floor External Door | CFT | 1 | 100 | 30 | 0.5 | 1500
| Out Side of Class Room | CFT | 1 | 30 | 30 | 0.5 | 450
| Out Side of Class Room | CFT | 1 | 35 | 30 | 0.5 | 525
| Back Corridor | CFT | 1 | 150 | 40 | 0.5 | 3000
| TOTAL | [5 empty] | 7415
5 | TERMITE PROOFING
| Providing anti-termite treatment by spraying / sprinkling / spreading Neptachler 0.5% Emulsion as an overall pre-construction treatment in slab type construction under the slab and attached preches or entrances etc. Complete in all respect as per directions of the Engineer-in-Charge (Page No. 108, Item No. 92) (QTY add Stone Soling) | [5 empty] | 7415 | 7593.75
| Toilet | SFT | 1 | 13 | 13.75 |  | 178.75
| TOTAL | [5 empty] | 7593.75
6 | C C 1:4:8 IN FOUNDATION
Cement concrete plain Ratio 1:4:8 6" thick including placing compacting, finishing and curing complete (including screining ang washing at stone aggregate without shuttering (Page No. 15, Item No. 5-i)
Toilet (A)
| FOOTING F1,F2 | CFT | 4 | 5 | 4 | 0.5 | 40
| F3 Situ Hor | CFT | 2 | 10 | 2 | 0.5 | 20
| FOOTING F4 Ver | CFT | 2 | 12 | 2.5 | 0.5 | 30
| B/W F1 | CFT | 90 | 4 | 4 | 0.5 | 720
| Vertical Situ | CFT | 1 | 440 | 2.5 | 0.5 | 550
| Rehab M.Building | CFT | 1 | 11.75 | 32 | 0.42 | 157.92
| Stone | CFT | 1 | 20 | 17 | 0.5 | 170
| TOTAL | [5 empty] | 1687.92
7 | SUB FLOORING
Cement concrete ratio (1:3:6) including placing compacting, finishing and curing complete (including screening ang washing at stone aggregate without shuttering (Page No. 15, Item No. 5-h)
| Toilet | CFT | 1 | 11.75 | 12.25 | 0.33 | 47.4994
| Toilet Situ | CFT | 2 | 11.75 | 0.75 | 3 | 52.875
| BACK CORRIDOR Situ | CFT | 2 | 12.25 | 0.75 | 3 | 55.125
| B/W Situ | CFT | 1 | 900 | 0.75 | 3 | 2025
|  | CFT | 1 | 100 | 30 | 0.33 | 990
|  | CFT | 1 | 30 | 30 | 0.33 | 297
|  | CFT | 1 | 35 | 30 | 0.33 | 346.5
|  | CFT | 1 | 150 | 40 | 0.33 | 1980
| TOTAL | [5 empty] | 5793.9994
8 | ERECTION OF CENTERING
Erection and removal of centering for R.C.C or plain cement concrete works (2nd-Class) (b) (ii) Vertical. (S.I.No: 19(b) (ii) P/17).
TOILET
|  | SFT | 2x2 | 11.75 |  | 3 | 141
|  | SFT | 2x2 | 12.25 |  | 3 | 147
| B/W Situ | SFT | 2 | 900 |  | 3 | 5400
| TOTAL | [5 empty] | 5688
9 | R.C.C WORKS 1:2:4
Reinforced cement concrete work including all labour and material except the cost of steel reinforcement and its labour for bending and binding which will be paid separately. This rate also includes all kinds of forms moulds lifting shuttering curing rendering and finishing the exposed surface (including screening and washing of shingle) Page No. 15. Item No. 6.
Toilet
| FOOTING F1,F2 | CFT | 4 | 4 | 3 | 1.5 | 72
| FOOTING F3 Boundary Wall | CFT | 90 | 3.5 | 3.5 | 1.5 | 1653.75
FOOTING F4 P/Beam
| FOOTING F5 Toilet | CFT | 2 | 13.75 | 0.75 | 2 | 41.25
| FOOTING F5 Toilet |  | 2 | 11.75 | 0.75 | 2 | 35.25
| B/Wall |  | 1 | 900 | 0.75 | 2 | 1350
HM ROOM+TOILET BLOCK+ENT+STAIRCASE (B)
| FOOTING F1 | CFT
| F. 2 R.C.C Beam | CFT | 2 | 13.75 | 0.75 | 2 | 41.25
| F.3 Toilet | CFT | 2 | 11.75 | 0.75 | 2 | 35.25
| F.4 Rehab C/Room | CFT | 1 | 15.5 | 0.75 | 1.25 | 14.5312
| F.5 R.C.C Slab Toilet | CFT | 1 | 12.25 | 18.75 | 0.5 | 114.8438
| F.7 Class Rooom Rehab | CFT | 1 | 22.5 | 18.5 | 0.42 | 174.825
| F.8 OHT Wall | CFT | 2 | 7.5 | 2.5 | 4.5 | 168.75
| F.9 OHT Wall | CFT | 2 | 13.75 | 0.5 | 4.5 | 61.875
| F.12 RCC Slab T/Bell | CFT | 2 | 13.75 | 8.5 | 0.5 | 116.875
| TOTAL | [5 empty] | 3880.45
R.C.C 1:1 1/2:3
CLASS ROOM ( A)
| COLUMN UPTO PLINTH | CFT | 4 | 1.25 | 0.75 | 10 | 37.5
| COLUMN UPTO PLINTH | CFT | 90 | 1 | 1 | 12 | 1080
| TOTAL | [5 empty] | 1117.5
10 | DAMP PROOF COURSE
Damp proof course 2" thick with (cement sand and shingle concrete 1:2:4) including 2 coats of asphaltic mixture. (Page No. 18, Item No. 28-b.)
TOILET ROOM(A)
| HORIZONTAL | SFT | 2 | 13.75 | 0.75 |  | 20.625
| VERTICAL | SFT | 2 | 11.75 | 0.75 |  | 17.625
| B/Wall | SFT | 1 | 900 | 0.75 |  | 675
| TOTAL | [5 empty] | 713.25
11 | BITUMEN FELT PAPER
Providing and fixing bitumen felt paper of 60 Lbs over roof I/C cleaning or roof with wire brush an removing dust, applying bitumen coat at the rate of 34 Lbs per % Sft as permix inter coats and then applying and spreading hill sand at the rate of 1 Cft for 100 Sft. The cost also I/C necessary fire material, kerosene oil, wood etc.
| HORIZONTAL | SFT | 2 | 13.75 | 0.75 |  | 20.625
| VERTICAL | SFT | 2 | 11.75 | 0.75 |  | 17.625
| B/Wall | SFT | 1 | 900 | 0.75 |  | 675
| TOTAL | [5 empty] | 713.25
12 | BRICK MASONRY
Pacca Brick Work in ground floor in cement sand mortar (1:4) Page No. 20, Item No. 5-I ©
CLASS ROOM (A)
| HORIZONTAL | CFT | 4 | 4 | 0.75 | 7 | 84
| VERTICAL | CFT | 2 | 1.75 | 0.5 | 7 | 12.25
| PARAPIT | CFT | 1 | 900 | 0.5 | 6 | 2700
| TOTAL | [5 empty] | 2796.25
13 | SURFACE RENDERING
Cement Plaster 1:5 upto 12' height
| CEILING PLASTER CLASS ROOM 1/2" | SFT | 1 | 11.75 | 12.25 |  | 143.9375
| Rehab PLASTER TOILET 1/2" | SFT | 1 | 11 | 11.5 |  | 126.5
| BOUNDARY WALL PLASTER 1/2" | SFT | 1 | 92.5 | 8.375 |  | 774.6875
| BOUNDARY WALL PLASTER 1/2" | SFT | 1 | 12.25 | 7.5 |  | 91.875
| BOUNDARY WALL PLASTER 1/2" | SFT | 6 | 2 | 1.5 |  | 18
| TOTAL | [5 empty] | 1155
PLASTER 3/8"
| CORRIDOR 3/8" | SFT | 2 | 11.75 |  | 9 | 211.5
| BOUNDARY WALL PLASTER 3/8" | SFT | 2 | 12.25 |  | 9 | 220.5
| BOUNDARY WALL PLASTER 3/8" | SFT | 8 | 4 |  | 7 | 224
| BOUNDARY WALL PLASTER 3/8" | SFT | 2 | 800 |  | 8 | 12800
| TOTAL | [5 empty] | 13456
INTERNAL WALL PLASTER (3/4")
CLASS ROOM
| HORIZONTAL Rehab | SFT | 1 | 92.5 | 8.375 |  | 774.6875
| VERTICAL Rehab | SFT | 1 | 11.5 | 11.5 |  | 132.25
| BEAM CORIDOR Rehab | SFT | 1 | 12.25 | 7.5 |  | 91.875
| COLUMN Rehab | SFT | 2 | 1.5 | 6 |  | 18
| HORIZONTAL | SFT | 2 | 11.75 |  | 9 | 211.5
| VERTICAL | SFT | 2 | 12.25 |  | 9 | 220.5
| TOTAL | [5 empty] | 1448.8125
EXTERNAL PLASTER
| HORIZONTAL + VERTICAL | SFT | 2 | 11.75 |  | 9 | 211.5
| PARAPET WALL HORIZONTAL | SFT | 2 | 12.25 |  | 9 | 220.5
| PARAPET WALL VERTICAL | SFT | 8 | 4 |  | 7 | 224
| COLUMN Compound Wall | SFT | 2 | 800 |  | 8 | 12800
| TOTAL | SFT |  |  |  |  | 13456
14 | DRIP COURSE Eave brick moulded Weather coat and threated with back cricks or deill cornice in 1:3 mortar | RFT | 4 | 9 |  |  | 36
15 | EXTRA LABOUR FOR GROVES Extra labour rate for making groves of 1" x 1/4" or 3/4" x1/2" plastered surface with true edges both vertically and horizontly with uniform depth and with groove base smoothly finished etc. complete as per instruction of Engineer Incharge. Page No 55 item # 34 | RFT | 3 | 350 |  |  | 1050
15 | EXTRA LABOUR FOR CEMENT
| Ectra labour rate for making cement plaster pattas/band around straight or carved openings and around the edges of roof slabs, the width not less than 6" with fine finishing as derected by Engineer Incharge Page # 55 Item # 35 | LUMP SUMP | 4 | 900 |  |  | 3600
16 | DOORS
Providing and fixing in position door and windows and ventilator for first class deodar wood frames 1 ½" thick and teak wood ply shutters of first class deodar wood skelton (Solid) Stiled and ply wood stiled and rail core of Partal wood and teak ply wood (3 Ply) on both sides including hold fasts hinges al-drops Iron Tower Bolts handles Cleats with Cord etc.Complete (Page No. 64, Item No. 51) Rate of Door: Rs. 1245.96 -Wooden Frame Rs. 370.83 = Door & Window (Rs. 875.13)
| Toilet Door | SFT | 4 | 2.5 |  | 7 | 70
| Toilet Door | SFT | 1 | 3.5 |  | 7 | 24.5
| Rehab C/Room | SFT | 1 | 4 |  | 7 | 28
| TOTAL | [5 empty] | 122.5
17 | WINDOWS AND VENTILATOR
First class deodar wood wrought, joinery in doors and windows etc, fixed in position including chowkats hold fasts hinges, iron tower bolts, chocks cleats, handles and cords with hooks, etc. Deodar panelled or panelled and glazed, or fully glazed. Rate of Door: Rs. 1273.76 - Wooden Frame Rs. 370.83 = Door & Window (Rs. 902.93)
| Toilet Ventilator | SFT | 6 | 2 |  | 1.5 | 18
| CLASS ROOM Rehab | SFT | 3 | 4 |  | 4 | 48
| TOTAL | [5 empty] | 66
18 | WOODEN ARCHITRAVE
Supplying and fixing with sunk iron screws wooden Architrave approved design / shape having width not less than 2½ inches as drected by Engineer-in-Charge. (S.I.No: 60 P-66).
| DOORS TOILET | RFT | 4x2 | 2.5 |  | 7 | 140
| DOORS TOILET | RFT | 1x2 | 3.5 |  | 7 | 49
| WINDOWS Toilet | RFT | 6x2 | 2 |  | 1.5 | 36
| WINDOWS CLASS ROOM | RFT | 3x2 | 4 |  | 4 | 96
| TOTAL | [5 empty] | 321
19 | MORTICE LOCK
Providing and fixing approved quality Mortice Lock.
| TOILET AND CLASS ROOM | EACH | 15 |  |  |  | 15 NOS
20 | G.I FRAMES FOR DOORS
Providing and fixing G.I. Frames / Choukhats of size 7" X 2" or 4½ X 3" for door using 20 gauge G.I. sheet including welded hinges and fixing at site with necessary hold fasts, filing with cement sand slurry of ratio 1:6 and repairing the jambs. The cost also includes all carriage tools and plants used in making and fixing. (Page No. 92, Item No. 29)
| TOILET | RFT | 4 | 16.5 |  |  | 66
| TOILET | RFT | 1 | 17.5 |  |  | 17.5
| TOTAL | RFT |  |  |  |  | 83.5
21 | G.I FRAMES FOR WINDOWS
Providing and fixing G.I. Frames / Choukhats of size 7" X 2" or 4½ X 3" for door using 20 gauge G.I. sheet including welded hinges and fixing at site with necessary hold fasts, filing with cement sand slurry of ratio 1:6 and repairing the jambs. The cost also including all carriage tools and plants used in making and fixing. (Page No. 93, Item No. 28)
CLASS ROOM (A)
| CLASS ROOM | RFT | 6 | 7 |  |  | 42
| TOILET ROOM | RFT | 3 | 16 |  |  | 48
| TOTAL | RFT |  |  |  |  | 90
22 | G.I EXPENDED METAL
P/F Gi expended metal 1/8-20 guage fixed to ckowkats and bitumen brick massonry and RCC joints. Page # 66 Item # 66(B)
| CLASS ROOM | SFT | 3 | 4 |  | 4 | 48
| TOILET | SFT | 6 | 2 | 1.5 |  | 18
| TOTAL | SFT |  |  |  |  | 66
23 | IRON STEEL GRILL
Providing and fixing iron grill using solid square bars of size 1/2" x 1/2" placed at 4" I/c and frame of flat iron patti of 3/4" x 3/4" I/c circle shape at 1-0 apart equivalent fixed with screw or pins I/c painting 3 coats with 1st cost of red oxide paint etc. Page # 94 Item No.30
| TOILET ROOM | SFT | 6 | 2 | 1.5 |  | 18
| TOTAL | SFT |  |  |  |  | 18
24 | PRIMING COAT
| Priming coat of chalk distemper (Page No. 53, Item No. 22) | Qty same as Int+Ext Plaster |  |  |  |  | 14616
| INTERNAL PLASTER Rehab C/Wall | SFT | 1 | 800 |  | 5 | 4000
| EXTERNAL PLASTER Pillar | SFT | 2 | 133 |  | 5 | 1330
| Class | SFT | 2 | 26.5 |  | 12 | 636
| Office | SFT | 2x2 | 8.25 |  | 12 | 396
| Verenda | SFT | 2 | 26.75 |  | 12 | 642
|  | SFT | 2 | 18 |  | 12 | 432
|  | SFT | 2 | 42.5 |  | 12 | 1020
| TOTAL | SFT |  |  |  |  | 23072
25 | DISTEMPERING
Preparing surface and painting with Distemper- 1st coat over priming coat (Page No. 53, Item No. 24-c) 3 Coats
| INTERNAL PLASTER Rehab C/Wall | SFT | 1 | 800 |  | 5 | 4000
| EXTERNAL PLASTER Pillar | SFT | 2 | 133 |  | 5 | 1330
| Class | SFT | 2 | 26.5 |  | 12 | 636
| Office | SFT | 2x2 | 8.25 |  | 12 | 396
| Verenda | SFT | 2 | 26.75 |  | 12 | 642
|  | SFT | 2 | 18 |  | 12 | 432
|  | SFT | 2 | 42.5 |  | 12 | 1020
| TOTAL | SFT |  |  |  |  | 8456
26 | INTERNAL WALL PAINTAING
Preparing the surface and painting with matt finish including rubbing the surface with bathy (silicon carbide rubbing brick) filling the voids with zink / chalk / plaster of paris mixture, applying first coat premix, making the surface smooth and then painting 3 coats with matt finish of approved make etc. complete (new surface). Page No. 54, Item No. 36-b. (3 Coats)
| QTY SAME AS INTERNAL WALL PLASTER | [5 empty] | 1448.8
| TOTAL | SFT |  |  |  |  | 1448.8
27 | EXTERNAL WALL PAINTAING
Painting guard bars, gates iron bars gratings, railing including standard braces etc. and similar open work (3 coats). Page No. 68, Item No. 4-d-II
|  | Sft | 2 | 800 |  | 8 | 12800
| QTY SAME AS INTERNAL WALL PLASTER | Sft |  |  |  |  | 1448.8
| Rehab ver F.3 | Sft | 3 | 22 |  | 12 | 792
| TOTAL | SFT |  |  |  |  | 15040.8
28 | ENAMEL PAINT ON WOOD WORKS
Painting guard bars, gates iron bars gratings, railing including standard braces etc. and similar open work (3 coats). Page No. 68, Item No. 4-d-II
| Rehab |  | 4 | 4 |  | 7 | 112
|  |  | 2 | 3.5 |  | 7 | 49
|  |  | 12 | 4 |  | 4 | 192
|  |  | 6 | 3 |  | 4 | 72
|  |  | 12 | 2 |  | 1.5 | 36
|  |  | 76 | 2 |  | 1 | 152
| TOTAL | SFT |  |  |  |  | 613
29 | FRENCH POLISH
French Polishing complete in new work (Page No. 70, Item No. 7-a)
|  |  | 8 | 2.5 |  | 7 | 140
|  |  | 2 | 3.5 |  | 7 | 49
| TOTAL | SFT |  |  |  |  | 189
30 | POLYTHENE SHEET
Providing and laying single per layer of polythene sheet 0.13 mm thick for water proffing as per specification andd instruction of engineer incharge. (S.I.No: 38 P/37).
|  | SFT | 1 | 11.75 |  | 12.25 | 143.9375
31 | BITUMAN COATING
Two coats of bituman laid hot using 34 Lbs for %Sft. Ober roof and blinded with sand at one Cft Per % Sft. (S.I.No: 30 P/34).
FIRST COAT
| UNDER FLOOR SITU AND PLINTH BEAM | SFT | 4 | 11.75 |  | 4 | 188
|  | SFT | 4 | 12.25 |  | 4 | 196
|  | SFT | 1 | 11.75 |  | 12.25 | 143.9375
| B/Wall |  | 2 | 800 |  | 4 | 6400
REHABILITATION(B)
| FIRST COAT |  | 2 |  | 24.87 | 28.25 | 1405.155
| TOTAL | SFT |  |  |  |  | 8333.0925
32 | ORNAMENTAL CEMENT JALI
Providing and fixing ornamental cement jalli 2" thick (1:2:4) without steel. (S.I.No: 11 P/18).
| EXTERNAL SIDE | SFT | 2 | 6 | 2 |  | 24
| TOTAL | SFT |  |  |  |  | 24
33 | TOPPING CEMENT CONCRETE PLAIN
Providing and laying 1" thick topping cement concrete (1:2:4) including surface finishing and dividing into panels. (d) 3" Thick. (S.I.No: 16 (d) P/42).
| Toilet | SFT | 1 | 11.75 | 12.25 |  | 143.9375
CLASS ROOM+HMROOM+TOILET BLOCK (A)
| WINDOW | SFT | 3 | 20 | 16 |  | 960
REHABILITATION(B)
| 3" TOPING | SFT | 1 | 22.5 | 18.5 |  | 416.25
| TOTAL | SFT |  |  |  |  | 1520.1875
34 | REINFORCED CEMENT CONCRETE SPOUT
| Reinforced cement concrete spout including fixing in position 2-½" X 6" X 5" (S.I.No: 14 P/18). | EACH | 2 |  |  |  | 2 NOS
35 | DIFFRENCE OF SR CEMENT
| C.C 1:4:8 | PER BAG
| C.C PLAIN 1:3:6 | PER BAG
| CEMENT PLASTER 1:6 | PER BAG
| CEMENT PLASTER 1:4 | PER BAG
| C.C PLAIN 1:2:4 | PER BAG
| TOTAL P.BAG | [5 empty] | 1226
36 | CEMENT POINTING STRUCKING JOINTS
| Cement pointing strucking joints on walls (a) Ratio 1:2. (S.I.No.19 (a) P/52). | RFT | 4 | 900 |  |  | 3600
37 | GROOVES( S1 NO.34 P-54) | RFT | 3 | 900 |  |  | 2700
Including complete internal plaster and external edges of building
38 | STEEL DOOR
| S/F special heavy type steel doors ( S.I.No.27 P-92 | SFT | 2 | 12 |  | 6 | 144
39 | KERB STONE
Providing & fixing precast Edge Block 3750 PSI Industrial made Reincluding the cost of cartage excavation, form work for haunching, 1450 PSI lean concrete, 2250 PSI concrete for 6 inches thick x 12 inches long x 12 inches high hauncheing , 1:4 cement sand mortor. ( S.I.No.14 P-16)
|  | RFT | 4 | 50 |  |  | 200
40 | EXTERNAL DEVELOPMENT PAVING BLOCK
Providing & fixing cement paving blocks flooring having size of 197 x 97 x 60 (mm) of city / quddra / cobble shape with natural colour, having strength b/w 5000 psi to 8500 psi I/c filling the joints with hill sand and layihng in specified manner /pattern and design etc: complete (S.I.No.71 P-49)
|  | CFT | 1 | 30 | 30 |  | 900
|  | CFT | 1 | 35 | 30 |  | 1050
| TOTAL | [5 empty] | 1950
41 | LAWNS
| Leveling, dressing and making lawns(S.I.NO. 42 P-103) | SFT | 1 | 30 | 30 |  | 900
|  |  | 1 | 35 | 30 |  | 1050
| TOTAL | [5 empty] | 1950
42 | MANURE
| Supply Manure | SFT | 1 | 30 | 30 | 1 | 900
|  |  | 1 | 35 | 30 | 1 | 1050
| TOTAL | [5 empty] | 1950
43 | GLAZED CERAMIC TILE FLOOR
Laying floors of approved coloured glazed tiles ¼" thick laid in white cement and pigment on a bed of ¾" thick cement mortar 1:2. (Page No. 42, Item No 25)
| HM ROOM TOILETS+TOILET BLOCKS | SFT | 1 | 11.75 | 12.25 |  | 143.9375
| HM ROOM Rehab Class | SFT | 2 | 20 | 7 |  | 280
| PASSAGE STAIR Rehab Class | SFT | 2 | 20 | 6 |  | 240
| TOTAL | [5 empty] | 663.9375
44 | GLAZED CERAMIC TILE DADO
Glazed tile dado ¼" thick laid in pigment over 1:2 cement sand mortar ¾" thick including finishing. (Page No. 44, Item No 38)
| HM ROOM TOILETS+TOILET BLOCKS New | SFT | 2 | 11.75 |  | 7 | 164.5
| HM ROOM TOILETS+TOILET BLOCKS New | SFT | 2 | 12.25 |  | 7 | 171.5
| HM ROOM TOILETS+TOILET BLOCKS New | SFT | 8 | 4 |  | 7 | 224
| Rehab C/R / Ver | SFT | 6 | 20 |  | 0.5 | 60
| TOTAL | [5 empty] | 620
45 | MANHOLE COVER
| Providing CI Manhole cover & Frame i/c cost of material (ch:p health page#35.item#j1 | KG | 13 |  |  |  | 13 KG
46 | SCRRAPPING ORDINARY DISTEMPER
| Scrapping ordinary distemper oil bond distemper or paint on walls (S-1 no.54(b) Page no.13 | SFT
| HM Off | 1 | 2 | 22 |  | 12 | 528
| C/R | 1 | 6 | 40 |  | 12 | 2880
| Ent | 1 | 2 | 20.25 |  | 12 | 486
| Off | 1 | 2 | 31 |  | 12 | 744
| Ver | 1 | 2 | 75.62 |  | 12 | 1815
| C/R | 1 | 2 | 36 |  | 12 | 864
| Ver | 1 | 21.5 | 2 |  | 12 | 516
| Hell In | 1 | 2 | 55.75 |  | 12 | 1338
| = | 1 | 2 | 43 |  | 12 | 1032
| C/R | 1 | 10 | 33 |  | 12 | 3960
| Ver | 1 | 2 | 24 |  | 12 | 576
|  | 1 | 2 | 97.75 |  | 9 | 1760
| C/R Window | sft | 6 | 36 |  | 11.5 | 2484
| Ver : | sft | 2 | 2 | 27 | 11.5 | 1242
| See detail Rehab M.Sheet | sft | 2 | 26 | 11.75 |  | 611
| DEDUCTION | sft | 3 | 21.5 | 11.5 |  | 741.75
| C/R Door | sft | 2 | 32 | 11 |  | 704
| TOTAL | [5 empty] | 22281.75
47 | FILLING ,WATERING AND RAMMING EARTH UNDER FLOOR
Filling watering and ramming earth under floor with new earth excavated from outside lead upto one chain and lift upto 5 feet (S-1 NO.54 (b) Page No.13
| External Dev | Cft | 1 | 100 | 40 | 2 | 8000
| NEW CONSTRUCTION | Cft | 1 | 30 | 30 | 2 | 1800
| Class | Cft | 1 | 35 | 30 | 2 | 2100
| Room | Cft | 1 | 150 | 40 | 2 | 12000
| REHABILITATION | Cft | 1 | 120 | 70 | 2 | 16800
| TOTAL | [5 empty] | 40700
48 | WOODEN PAINTING
Preparing the surface painting with old surface doors & windows any type including edge (3 coats) (S-I No.4 Page No.68)
| WINDOW | SFT | 16 | 3.5 | 7 |  | 392
| TOTAL | [5 empty] | 392
49 | IRON PAINTING
Preparing the the surface painting with old surface guard bars gates any type including edge (S-I No.4 Page No.68)
WINDOW GRILLS NEW
| Rehab New | SFT | 12 | 2 |  | 1.5 | 36
| Rehab |  | 9 | 1.125 |  | 3.5 | 35.4375
| Rehab |  | 2 | 18.75 |  | 1.5 | 56.25
| TOTAL | [5 empty] | 127.6875
50 | WHITE WASH
White wash two coats (S-iI No.38 Page No.54) Rehab
| (a) 3 CoatC/R Roof | SFT | 3 | 20 |  | 16 | 960
| .= Beam | SFT | 2 | 20 |  | 7 | 280
| Ver : | SFT | 1 | 20 |  | 6 | 120
| TOTAL | [5 empty] | 1360
51 | Dismantling cement concrete plain 1:2:4 (S.I No. 19c Page no. 10)
| C/R Floor H.M Office | cft | 1 | 10 | 12 | 0.25 | 30
| Ver : Rehab Sheet | cft | 1 | 10 | 10 | 0.25 | 25
|  |  | 1 | 20.25 | 8 | 0.25 | 40.5
|  |  | 1 | 8 | 4 | 0.12 | 3.84
|  |  | 1 | 6 | 6 | 0.25 | 9
|  |  | 3 | 3 | 4 | 0.12 | 4.32
|  |  | 1 | 31 | 22 | 0.12 | 81.84
|  |  | 3 | 8.25 | 8.25 | 0.12 | 24.5025
|  |  | 1 | 40.5 | 7 | 0.12 | 34.02
|  |  | 1 | 20 | 16 | 0.12 | 38.4
|  |  | 1 | 40.8 | 6 | 0.12 | 29.376
|  |  | 1 | 20 | 16 | 0.25 | 80
|  |  | 1 | 21.5 | 6 | 0.25 | 32.25
|  |  | 1 | 9 | 8 | 0.25 | 18
|  |  | 1 | 91.75 | 5.5 | 0.25 | 126.1562
|  |  | 5 | 15 | 8.4 | 0.25 | 157.5
| TOTAL | [5 empty] | 734.7047
52 | Dismantling Cement Concrete Re Inforcement Separating Inforcement From Concrete Cleaning & Straightening the same (S-I No.20 Page No.10)
| 2 C/R Roof See details Rehab | cft | 1 | 46.375 | 28.375 | 0.42 | 552.6741
| Gate Pillar M.Sheet | cft | 3 | 43.375 | 1.125 | 0.75 | 109.793
|  | cft | 1 | 12.25 | 7.25 | 0.33 | 29.3081
| TOTAL | [5 empty] | 691.7752
53 | Dismantling Tiles | Cft | 1 | 1 | 19.5 | 15.5 | 302.25
54 | Dismantling Rolled Steel Beam Old Rails |  | 1 | 3 | 16 | 0.080357 | 3.8571
|  |  | 1 | 13 | 19 | 0.013393 | 3.308
| TOTAL | [5 empty] | 7.1652
55 | Removing Cement or Lime Plaster (S-I No.53 Page No: 13)
a | C/R roof C/Class Room | sft | 4 | 36 | 3 |  | 432
| Ver : See details Rehab | sft | 4 | 20 | 3 |  | 240
| .= Off: = M.Sheet | sft | 2 | 32 | 3 |  | 192
| TOTAL | [5 empty] | 864
56 | Removing Door With Chowkats (S-I No.33(a) Page No.12)
| Gen:Lav:Door |  | 1 | 2 |  |  | 2 Nos
57 | Removing Door With Windows (S-I No.33(a) Page No.12)
| Gen:Lav:Door |  | 1 | 2 |  |  | 2 Nos
NON SCHEDULE ITEM
1 | DEFOREMED STEEL BARS
| Providing and laying deformed (Grade-60) Reindorcement bars including the cost of strainghtenting, cutting, bending, binding, wastages, and such overlaps as are not shown in the drawings, placing in position on cement concrete 1:2:4 preCost spacer or M.s chairs and tying with binding wire etc. complete in all respects as per drawings and in accordance with the specifications, (Horixontal and Vertical mambers.) | [7 empty] | jkollllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllllll
| CLASS ROOM,BOUNDARY WALL,TOILET,HM ROOM | TON |  |  |  |  | 14.50 Ton
3 | ROOM NAME PLATE
Room name plate see attached drawings
| CLASS ROOM AND TOILET | EACH |  |  |  |  | 15 Nos
4 | WRITING BOARD
Provide and install writing board in frame for class rooms and also for use as notice board having acrylic cleanable surface in the soft cloth made of Acrylic/PVC (Petroleum Product) material with glazed sueface capable of writing with marker, frame, writing board and the based to be produred from the manufacture approved by the engineer incharge. see attached drawings
| CLASS ROOM | EACH | 1 | 15 |  |  | 15
5 | TERRAZO TILE FLOOR
Terrazo tiles flooring and Skirting with white cement 1-0 x 1-0 x 1" of approved shade laid flat in 1:2 white cement mortar over a bed of 3/4 thick cement mortar.
| CLASS ROOM | SFT | 10 | 16 | 22 |  | 3520
6 | BOTICINA MARBLE TO ENTRANCE STEPS TREDS
laying boticena marble to entrance steps trades dressed on the surface without winding set in cement mortar 1:2 inlucding rubbing and polishing of the joints 3/4" thick.
| TOTAL | SFT | 5 | 10 | 1 |  | 50
7 | BOTICINA MARBLE TO ENTRANCE STEPS RISER
| laying boticena marble to entrance steps riser fine dressed on the surface without winding set in cement mortar 1:2 inlucding rubbing and polishing of the joints 3/4" thick. | SFT
|  |  | 5 | 10 |  | 0.67 | 33.5
8 | PLASTER WORK (PUDLO)
providing and applying cement plaster 1/2" thick in 1:4 cement sand mortar with Pudlo 5lbs of pudlo per bag cement for Over Head Water Tank & Under Ground Water Tank include all corners, recesses, jams and racking mortar to walls, and base etc and marketing of chamber on all corner of UGWT, OHWT and water curing as per engineering Specification
| OVERHEAD TANK BOTTOM AND TOP | SFT | 1 | 12 | 8.5 |  | 102
| OVERHEAD TANK WALL HORIZONTAL | SFT | 2 | 12 | 5.5 |  | 132
| OVERHEAD TANK WALL VERTICAL | SFT | 2 | 8 | 5.5 |  | 88
| TOTAL | [5 empty] | 322
9 | WATER STOPPER
Supply and fixing of PVC 4" wide water stopper
| OVERHEAD TANK | RFT | 2 | 12 |  |  | 24
| OVERHEAD TANK | RFT | 2 | 8.5 |  |  | 17
| TOTAL | [5 empty] | 41
10 | GARDEN SOIL
|  |  | 1 | 100 | 40 | 1.5 | 6000
|  |  | 1 | 30 | 30 | 1.5 | 1350
|  |  | 1 | 35 | 30 | 1.5 | 1575
|  |  | 1 | 150 | 40 | 1.5 | 9000
|  |  | 1 | 120 | 70 | 1.5 | 12600
| TOTAL | [5 empty] | 30525
11 | LIVE DHAKA GRASS |  | 1 | 100 | 40 |  | 4000
|  |  | 1 | 35 | 30 |  | 1050
| TOTAL | [5 empty] | 5050