## B.D.F
BIDDING DATA
( This Section Shoulde be filled in by the Engineer / Procuring Agency before issuance of the Bidding Documents)
(a) | Name of Procuring Agency : | Chief Municipal Officer ,Municipal Committee Nawabshah
(b) | Brief Description of works | Providing C.C Topping in various Streets of ward No.17 to 24 M.C Nawabshah
(c) | Procuring Agency,s Address | Chief Municipal Officer ,Municipal Committee Nawabshah
(d) | Estimated Cost | 0.850(M)
(e ) | Amount of Bid Security | 5% Rs._________________________
(f) | Period of Bid Validity | 90 Days
(g) | Security Deposit i/c ( Bid Security). | 5% of Bill Amount
(h) | Percentage , if any, to be deducted from bills. | Income Tax
(i) | Deadline for submission of Bids alongwith time | 04.10.2017 ( 01.00 PM)
(j) | Venue, Time and Date of Bid Opening | Office of the Chief Municipal Officer Municipal Committee Nawabshah @(01:45:00PM) Date.04.10.2017
(k) | Time for completion from written order of commence : | 06 Months
(l) | Liquidity Damages :- | (0.05% of Estimated cost of Bid cost per day of delay, but total not exceeding 10%)
(m) | Name of Contractor / Agency
(n) | Deposit Receipt No./Agency
DR.No. _______________ Rs.________________ Date._________________
o) | Call Deposit No_____________________________ | Amounting to Rs.________________Dated___________________
p) | Amount of Schedule item | Rs:______________________
q) | Rateuoted by Contractor Below__________ /Above__________ | Rs:______________________
r) | Amount of Non Schedule item | Rs:______________________
| Total Bid Cost | Rs:______________________
| Contractor | Chief Municipal Officer
Municipal Committee
Nawabshah