## Schd B
S C H E D U L E -B
Name of work: |  |  | Renovation & Uplifting of Tando Allahyar Gym Khana (Musjid)
S. No. | Description |  |  |  | QTY | Rate | Unit | AMOUNT
PART (A) Ground Floor
1 |  | Dismantling cement concratereinforced separating reinforcement from concrete cleaning and straightening the same.(s,I no 20 p-no 10)
[5 empty] | 286.19 | 5445 | %cft | 1558.3046
(Rupees Five Thousands Four Hundred Forty Five Only)
2 |  | Dismentling brick work in lime or cement motar (s,I no13,p- no 1o)
[5 empty] | 945.38 | 1285.63 | %cft | 12154.0889
(Rupees One Thousands Two Hundred Eigty Five Point Six Three Only)
3 |  | Excavation in foundation of building bridge & other structure i/c dagbelling dressing refilling around the structure with excavated earth watering & ramming lead upto 5' fts. In ordinary soil. (S.I. No.: 18/b/p-4 Vol-3,Part-3 Schdl Rates of (General) Edition 2012)
[5 empty] | 1541 | 3176.25 | %cft | 48946.0125
(Rupees Three Thousands One Hundred Seventy Six Point Two Five Only)
4 |  | Cement conrate brick or stone ballast 1-1/2"To2" gauge ratio 1:4:8.(s,I no4(b) p-no 15)
[5 empty] | 708.73 | 9416.28 | %cft | 66736.0012
(Rupees Nine Thousands Four Hundred Sixteen Point Two Eight Only)
5 |  | Pacca brick work in foundation and plinth in cement mortar 1:6.(s,I no4(E),p-no 20)
[5 empty] | 332.44 | 11948.36 | %cft | 39721.128
(Rupees Eleven Thousands Nine Hundred Forty Eight Point Three Six Only)
6 |  | RCC work I/c all labor and material except the cost of steel reinforcement and its labor for bending and binding which will be paid separately this rate also include all kinds of forms moulds lifting shuttering curing rendering and finishing the exposed surface (i/c screening and washing of shingle R.C work in roof slab, beams columns rafts, lintels and other structural members laid in situ or precast laid in position complete in all respects ratio 1:2:4 ) 90 lbs. cement 2cft Sand 4 cft shingle 1/8" to 1/4" gauge. (S.I.No.6 (a) (i) P-16)
[5 empty] | 1659.84 | 337 | pcft | 559367
(Rupees Three Hundred Thirty Seven Only)
7 |  | Fabrication of mild steel reinforcement for cement concrete I/c cutting bending laying in position making joints and fastenings I/c cost of binding wire (also includes removal of rust from bars) using Tor bars (S.I. No: 8 (a) (b)/P-16 /17)
[5 empty] | 99.59 | 5001.7 | pcwt | 498119.303
(Rupees Five Thousand One Point Seven Zero Only)
8 |  | Filling watering and ramming earth in floors with surplus earth from foundation lead upto one chain and lift up to 5 feet (S.I.No 21 P-5)
[5 empty] | 243 | 1512.5 | %0cft | 367.5375
(Rupees Three Thousand Six Hundred Thirty Only)
9 |  | Filling watering and ramming earth in floors with New earth from excavated from out side lead upto one chain and lift up to 5 feet (S.I.No 22 P-5)
[5 empty] | 2741.94 | 3630 | %0cft | 9953.2422
(Rupees One Thousands One Hundred Forty One Point Two Five Only)
10 |  | Pacca brick work in ground floor in cement mortar 1:6.(s,I no5(d),p-no 21)
[5 empty] | 693.66 | 12674.36 | %cft | 87916.9656
(Rupees Twelve Thousands Six Hundred Seventy Four Point Three Six Only)
11 |  | P/F G.I frames /Chowkets of size 7"x2" or 4-1/2"x3" foor door using 20 gauge G.I sheet i/c welded hinges & fixing at site with necessary hold asts filling with cement sand slurry of ratio 1:6(S.Ino.29/P-98)
[5 empty] | 86 | 228.9 | prft | 19685.4
(Rupees Two Hundred Twenty Eight Point Nine Zero Only)
12 |  | P/F G.I frames /Chowkets of size 7"x2" or 4-1/2"x3" for windows using 20 gauge G.I sheet i/c welded hinges & fixing at site with necessary hold asts filling with cement sand slurry of ratio 1:6(S.Ino.29/P-98)
[5 empty] | 152 | 240.5 | prft | 36556
(Rupees Two Hundred Forty Point Five Zero Only)
13 |  | First class deodar wood with wrought joinery in doors & wind: etc fixed in position i/c chowkhats hold fasts hinges iron tower bolts, chocks cleats handle and cords with hocks etc. (b) 1. 3/4" thick (S.I.No.7(b)/P-57)
[5 empty] | 126.32 | 902.93 | psft | 114056
(Rupees Nine Hundred Two Point Nine Three Only)
14 |  | Cement plaster 1:6 upto 12' height 1/2" thick (S.I. No. 13/b/p-51).
[5 empty] | 3594.94 | 2206.6 | %sft | 79325.946
(Rupees Two Thousand Two Hundred Six Point Six Zero Only)
15 |  | Cement plaster 1:4 upto 12' height 3/8" thick (S.I. No. 11/a/p-51).
|  | Same Qty item No.10 |  |  | 3594.94 | 2197.52 | %sft | 78999
(Rupees Two Thousand One Hundred Ninety Seven Point Five Two Only)
16 |  | Cement concrete plain i/c placing compacting finishing and curring complete (i/c Screening and Washing at stone aggregate without shuttering 1:2:4 (S.I.No-5 f/P-16)
[5 empty] | 164.26 | 14429.25 | %cft | 23701.486
(Rupees Fourteen Thousand Four Hundred Twenty Nine Point Two Five Only)
17 |  | Laying with marble flooring fine dressed on the surface without winding set' in lime mortar 1:2 including rubbing and polishing of the joints. 3/4" thick flooring (S.I.No.28.P.No.54)
[5 empty] | 1131 | 567.48 | psft | 641819.88
(Rupees Five Hundred Sixty Seven Point Four Eight Only)
18 |  | P/F 3/8" thick marble tiles of approved quailty and color shade size 8"x4/6"x4" in dado skriting and facing removal /tucking of existing plaster surafce 1/2" thick base of cement mortor 1:3 (S.I.No68/P-55)
[5 empty] | 215 | 186.04 | psft | 39998.6
(Rupees One Hundred Eighty Six Point Four Zero Only)
19 |  | Laying floor of approved with glazed tile 1/4" thick in white cement 1:2 over 3/4" thick cement mortor 1:2 complete (S.I.No24/P-42)
[5 empty] | 40 | 27678.86 | %sft | 11071.544
(Rupees Twenty Seven Thousands Six Hundred Seventy Eight Point Eight Six Only)
20 |  | Wite glazed tile 1/4" thick dado jointed wite cement and laid over 1:2 cement sand mortar 3/4" thick I/c finishing.(S.I.No.37 P-45, Vol-3,Part-3 Schdl Rates of (General) Edition 2012).
[5 empty] | 165 | 28253.61 | %sft | 46618.4565
(Rupees Twenty Eight Thousands Two Hundred Fifty Three Point Six One Only)
21 |  | S/F in position iron steel girrl of approved design of 3/4 x1/4 size flate from i/c painting htree coats etc complete weight not less than 3.7 ibs/sft foot finishing (s,I, no,30p- 93)
[5 empty] | 14.72 | 194.16 | psft | 2858.0352
(Rupees One Hundred Ninety Four Point One Six Only)
22 |  | P/F de0dar Almirah 9"x 12" depth i/c boxing wiyh back shelves,shutters brass fitting complet.
[5 empty] | 20 | 1778.5 | psft | 35570
(Rupees One Thousand Seven Hundred Seventy Eight Point Five Zero Only)
23 |  | Preparing the surface and painting with mattfinish i/c rubbing the surafce with bathy(Silicon carbide rubbing brick) filling the voids with zink /chalk/plaster of paris mixture applying first coat premix making the surafce smooth and then painting 3 coats with matt finish of approved make etc complete (new surface) SI.No-36a+b(P-55)
[5 empty] | 2194.5 | 2717 | %sft | 59624.565
(Rupees Two Thousands Seven Hundred Seventeen Only)
24 |  | preparing the surface and applying rock wall / shield (Natural wall texture) coating to provide crust to wall thickness b/w 2mm to32mm (1/8) with acrylic co-polymer emulsion selected marble chips adhsive and bactericdes, water resistance and fire and termite resistance (upto20-0ft height). (s,i no43,p-no 56).
[5 empty] | 1974 | 4504.5 | %sft | 88918.83
(Rupees Four Thousands Five Hundred Four Point Five Zero Only)
25 |  | Painting new surface (c ) Preparing surface and painting of door and windows any type (i/c edge) (iii) 3 coas (S.I. No. 5(c-ii) p-69 Vol-3,Part-3 Schdl Rates of (General) Edition 2012).
[5 empty] | 1147.13 | 2116.41 | %Sft | 24278
(Rupees Two Thousands One Hundred Sixteen Point Four One Only)
26 |  | Providing and laying 1" thick topping cement concrate (1:2:4) including surface finishing and dividing into pannells (xs,I no 16 (B0 p-no42).
[5 empty] | 1379.63 | 2548.29 | %sft | 35156.9733
(Rupees Two Thousands Five Hundred Forty Eight Point Two Nine Only)
[5 empty] | Total Part-A |  | 2663078.2996
PART (B) Entrance Gate
Renovation Main Entrance Gate at Gym Khana Tando Allahyar
1 |  | Dismentling brick work in lime or cement motar (s,I no13,p- no 1o)
[5 empty] | 248.63 | 1285.63 | %cft | 3196.4619
(Rupees One Thousands Two Hundred Eigty Five Point Six Three Only)
2 |  | Dismentling cement concrate plain 1:2:4.(s,I no19© p-no10).
[5 empty] | 129.75 | 3327.5 | %cft | 4317.4312
(Rupees Three Thousands Three Hundred Twenty Seven Point Five Zero Only)
3 |  | Excavation in foundation of building bridge & other structure i/c dagbelling dressing refilling around the structure with excavated earth watering & ramming lead upto 5' fts. In ordinary soil. (S.I. No.: 18/b/p-4 Vol-3,Part-3 Schdl Rates of (General) Edition 2012)
[5 empty] | 225 | 3176.25 | %cft | 7146.5625
(Rupees Three Thousands One Hundred Seventy Six Point Two Five Only)
4 |  | Cement conrate brick or stone ballast 1-1/2"To2" gauge ratio 1:4:8.(s,I no4(b) p-no 15)
[5 empty] | 332.7 | 9416.28 | %cft | 31327.9636
(Rupees Nine Thousands Four Hundred Sixteen Point Two Eight Only)
5 |  | Pacca brick work in foundation and plinth in cement mortar 1:6.(s,I no4(E),p-no 20)
[5 empty] | 101.7 | 11948.36 | %cft | 12151.4821
(Rupees Eleven Thousands Nine Hundred Forty Eight Point Three Six Only)
6 |  | RCC work I/c all labor and material except the cost of steel reinforcement and its labor for bending and binding which will be paid separately this rate also include all kinds of forms moulds lifting shuttering curing rendering and finishing the exposed surface (i/c screening and washing of shingle R.C work in roof slab, beams columns rafts, lintels and other structural members laid in situ or precast laid in position complete in all respects ratio 1:2:4 ) 90 lbs. cement 2cft Sand 4 cft shingle 1/8" to 1/4" gauge. (S.I.No.6 (a) (i) P-16)
|  | Total |  |  | 459.5 | 337 | pcft | 154851.5
(Rupees Three Hundred Thirty Seven Only)
7 |  | Fabrication of mild steel reinforcement for cement concrete I/c cutting bending laying in position making joints and fastenings I/c cost of binding wire (also includes removal of rust from bars) using Tor bars (S.I. No: 8 (a) (b)/P-16 /17)
[5 empty] | 99.59 | 5001.7 | pcwt | 498119.303
(Rupees Five Thousand One Point Seven Zero Only)
8 |  | Pacca brick work in other than building striking of joints upto 20ft height in cement mortar 1:6.(s,I no7 (d),p-no 22)
[5 empty] | 157.5 | 12346.65 | %cft | 19445.9738
(Rupees Twelve Thousands Three Hundred Forty Six Point Six FIve Only)
9 |  | Cement plaster 1:6 upto 12' height 1/2" thick (S.I. No. 13/b/p-51).
[5 empty] | 540 | 2206.6 | %sft | 11915.64
(Rupees Two Thousand Two Hundred Six Point Six Zero Only)
10 |  | Cement plaster 1:4 upto 12' height 3/8" thick (S.I. No. 11/a/p-51).
[5 empty] | 540 | 2197.52 | %sft | 11866.608
(Rupees Two Thousand One Hundred Ninety Seven Point Five Two Only)
11 |  | Cement concrete plain i/c placing compacting finishing and curring complete (i/c Screening and Washing at stone aggregate without shuttering 1:2:4 (S.I.No-5 f/P-16)
[5 empty] | 2074.75 | 14429.25 | %cft | 299370.8644
(Rupees Fourteen Thousand Four Hundred Twenty Nine Point Two Five Only)
12 |  | Laying with marble flooring fine dressed on the surface without winding set' in lime mortar 1:2 including rubbing and polishing of the joints. 3/4" thick flooring (S.I.No.28.P.No.54)
[5 empty] | 590.4 | 567.48 | psft | 335040.192
(Rupees Five Hundred Sixty Seven Point Four Eight Only)
13 |  | P/F 3/8" thick marble tiles of approved quailty and color shade size 8"x4/6"x4" in dado skriting and facing removal /tucking of existing plaster surafce 1/2" thick base of cement mortor 1:3 (S.I.No68/P-55)
[5 empty] | 70 | 186.04 | psft | 13022.8
(Rupees One Hundred Eighty Six Point Four Zero Only)
14 |  | Laying floor of approved with glazed tile 1/4" thick in white cement 1:2 over 3/4" thick cement mortor 1:2 complete (S.I.No24/P-42)
[5 empty] | 40 | 27678.86 | %sft | 11071.544
(Rupees Twenty Seven Thousands Six Hundred Seventy Eight Point Eight Six Only)
15 |  | P/L HALLA or pattwen tiles glazed 6" x6"x 1/4" on floor or wall facing in required colour and pattern of STILLE spercifucation joint in white cement and pigment over a base of 1:2 grey cement mortar 3/4" thick including washing and filling of joint with slurry of white cement and pigment in desired shap with finishing ,cleaning and cost of wax polish etc , complete including cuting tiles to proper profile.(s,i no61,p-no 48)
[5 empty] | 530 | 47651.56 | %sft | 252553.268
(Rupees Forty Seven Thousands Six Hundred Fifty One Point Five Six Only)
16 |  | S/F in position iron steel girrl of approved design of 3/4 x1/4 size flate from i/c painting htree coats etc complete weight not less than 3.7 ibs/sft foot finishing (s,I, no,30p- 93)
[5 empty] | 21 | 194.16 | psft | 4077.36
(Rupees One Hundred Ninety Four Point One Six Only)
17 |  | Preparing surface and painting gourd bars gates of iron bars, grattimg railings including standards braces etc) and similar open work.( s,i no 5 (d) p-no70). of door and windows any type (i/c edge) (iii) 3 coas (S.I. No. 5(c-ii) p-69 Vol-3,Part-3 Schdl Rates of (General) Edition 2012).
[5 empty] | 369 | 1270.83 | %Sft | 4689
(Rupees One Thousands Two Hundred Seventy Point Eight Three Only)
[5 empty] | Total Part-B |  | 1674163.9544
TERMS & CONDITIONS:
1 | No Premium Shall be allowed on items based on market rates or sanctined by competent
authority the Schedule of rates.
2 | Nothing shall be paid for cartage of any material what so ever brought at the site of work
material cartage form Government stores
3 | The material for use in the work or his finished product can be got tested an approved lab, at the
direction of incharge Engineer or his representative and all expencess in connection with such
testing shall be borne by the Government on his account.
| Contractor |  |  | Executive Engineer
B u i l d i n g s D i v i s i o n
Tando Allahyar