## M. Khan Shoro-I
Annexure A-1
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Provincial ADP 2015-2016
1 | Supplying Installing & Testing Pumping Machinery 20 BHP (2 Sets) i/c Inter Connection @ Water Works, Providing, Laying Jointing and Testing PVC Pipe 4” dia for Distribution System for Rural Water Supply Scheme Muhammad Khan Shoro (Dabhoo) Taluka Kotri District Jamshoro Rs:- 5.000 | 5 | 0 | 5 | Rs: - 5.000 01. Tube Well i/c Trial Bore (01 No) 02. Pump House (01 No) 03. P/Machinery 15 BHP 01 Set 04. Distribution System i. PVC Pipe 3" (2770 Rft:) ii. PVC Pipe 3" (1700 Rft:) 05. L.S.R / Storage Tank (01 No) | 5 | Execution of construction work | Single Stage Envelope | 11/2015 | After issue of Work Order | 06/2016
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## M. Khan Shoro-II
ANNEXURE A-II
ANNEXURE-II
PROCUREMENT PLAN (Non-Development)
S. No | Found Head & Sub head | Name of work and break up | Allocated Found and break up for different locations/sites | ltems to be executed | Method of Procurement | Anticipated/Actual of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
--------------NIL--------------
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## Yameen Palari-I
Annexure A-1
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Provincial ADP 2015-2016
1 | Construction of Water Supply Scheme Yameen Palari, Taluka Thana Bula Khan District Jamshoro Rs:- 5.500 | 6.685 | 0 | 6.685 | Rs: - 5.500 01. Tube Well i/c Trial Bore (01 No) 02. Pump House (01 No) 03. P/Machinery 15 BHP 01 Set 04. Distribution System i. PVC Pipe 3" (2770 Rft:) ii. PVC Pipe 3" (1700 Rft:) 05. L.S.R / Storage Tank (01 No) | 6.685 | Execution of construction work | Single Stage Envelope | 11/2015 | After issue of Work Order | 06/2016
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## Yameen Palari-II
ANNEXURE A-II
ANNEXURE-II
PROCUREMENT PLAN (Non-Development)
S. No | Found Head & Sub head | Name of work and break up | Allocated Found and break up for different locations/sites | ltems to be executed | Method of Procurement | Anticipated/Actual of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
--------------NIL--------------
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## P-Mach Subhanallah Colony-I
Annexure A-1
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Provincial ADP 2015-2016
1 | Supplying / Installing & Testing Pumping Machinery 30 BHP (4 Sets) i/c Diesel Engine 48 BHP @ Disposal work i/c P/L/J Testing A.C. Pipe 20" dia for Drainage Scheme Subhanallah Colony Taluka Kotri District Jamshoro Rs:- 6.570 | 6.57 | 0 | 6.57 | Rs: - 6.570 01. Tube Well i/c Trial Bore (01 No) 02. Pump House (01 No) 03. P/Machinery 15 BHP 01 Set 04. Distribution System i. PVC Pipe 3" (2770 Rft:) ii. PVC Pipe 3" (1700 Rft:) 05. L.S.R / Storage Tank (01 No) | 6.57 | Execution of construction work | Single Stage Envelope | 12/2015 | After issue of Work Order | 06/2016
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## Annexure-I
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Provincial ADP 2017-18
1 | Supplying and Fixing of Diesel Generator (150 KVA) for Renovation of Existing scheme for Removal of hazardous dirty water accumulated behind village Bakhar Jamali Taluka Saeedabad, District Matiari. (5.942) | 30.352 | 29.616 | 5.583 | Rs.5.942 1. Supplying & Fixing of diesel Genrator (150 KVA) 1 No. | 24.769 | S/F of Diesel Generator (150 KVA) | Single Stage Envelope | 2017-02-11 | After issue of Work Order | 2018-02-01
2 | Providing, Laying, Jointing F.C Pipr Rising Main 16" dia for Removal of hazardous dirty water accumulated behind village Bakhar Jamali Taluka Saeedabad District Matiari. (8.300) |  |  |  | Rs. 8.300 1. Providing Laying Jointing F.C Pipe Rising Main 16" dia (5500.00 Rft) |  | Execution of construction work | Single Stage Envelope | 2017-02-11 | After issue of Work Order | 2018-02-01
3 | Construction of Oxidation Ponds for Rural Drainage Scheme Sanghar Soomro Taluka & District Matiari.(0.850) | 16.964 | 10.224 | 3.72 | Rs. 0.850 1 .Construction of Oxidation ponds (3 No) 2. Sump Wells Nos. | 3.02 | Execution of construction work | Single Stage Envelope | 2017-02-11 | After issue of Work Order | 2018-02-01
(ABDUL RASHEED BHUTTO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG:DIVISION
MATIARI

## Annexure-II
ANNEXURE A-II
ANNEXURE-II
PROCUREMENT PLAN (Non-Development)
S. No | Found Head & Sub head | Name of work and break up | Allocated Found and break up for different locations/sites | ltems to be executed | Method of Procurement | Anticipated/Actual of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
--------------NIL--------------
ABDUL RASHEED BHUTTO
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
MATIARI