## Annexure A
PROCUREMENT PLAN (Development/Capital)
Serial No. | Name of Scheme & Estimated Cost | Allocated Fund (Million) | Cost of ongoing works | Fund earmarked for ongoing works | Cost of New works (Million) | Funds for New works (c+e) (Million) | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
a | b | c | d | e | f | g | h | i | j | k | l
1 | Internal Development works (Road, Water Supply & Sewerage) at Benazir Town, Badin (Contract Package No. SMBBT/BDN/INF-001) | 65.030 (ADP No. 072, FY 2017-18) | Nil | Nil | 65.03 | 65.03 | Development Works | Open Competitive Bidding method Single Stage-One Envelope Procedure through Press and SPPRA website | 2017-11-01 | 2017-12-01 | Oct 2018
2 | Internal Development works (Road, Water Supply & Sewerage) at Benazir Town, Mehar (Contract Package No. SMBBT/MHR/INF-001) | 44.776 (ADP No. 072, FY 2017-18) | Nil | Nil | 44.776 | 44.776 | Development Works | Open Competitive Bidding method Single Stage-One Envelope Procedure through Press and SPPRA website | 2017-11-01 | 2017-12-01 | Oct 2018
3 | Internal Development works (Road, Water Supply & Sewerage) at Benazir Town, Dadu (Contract Package No. SMBBT/DDU/INF-001) | 57.552 (ADP No. 072, FY 2017-18) | Nil | Nil | 57.552 | 57.552 | Development Works | Open Competitive Bidding method Single Stage-One Envelope Procedure through Press and SPPRA website | 2017-11-01 | 2017-12-01 | Oct 2018
4 | Internal Development works (Road, Water Supply & Sewerage) at Benazir Town, Sehwan (Contract Package No. SMBBT/SWN/INF-002) | 63.263 (ADP No. 072, FY 2017-18) | Nil | Nil | 63.263 | 63.263 | Development Works | Open Competitive Bidding method Single Stage-One Envelope Procedure through Press and SPPRA website | 2017-11-01 | 2017-12-01 | Oct 2018