## M. Khan Shoro-I
Annexure A-1
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Provincial ADP 2015-2016
1 | Supplying Installing & Testing Pumping Machinery 20 BHP (2 Sets) i/c Inter Connection @ Water Works, Providing, Laying Jointing and Testing PVC Pipe 4” dia for Distribution System for Rural Water Supply Scheme Muhammad Khan Shoro (Dabhoo) Taluka Kotri District Jamshoro Rs:- 5.000 | 5 | 0 | 5 | Rs: - 5.000 01. Tube Well i/c Trial Bore (01 No) 02. Pump House (01 No) 03. P/Machinery 15 BHP 01 Set 04. Distribution System i. PVC Pipe 3" (2770 Rft:) ii. PVC Pipe 3" (1700 Rft:) 05. L.S.R / Storage Tank (01 No) | 5 | Execution of construction work | Single Stage Envelope | 11/2015 | After issue of Work Order | 06/2016
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## M. Khan Shoro-II
ANNEXURE A-II
ANNEXURE-II
PROCUREMENT PLAN (Non-Development)
S. No | Found Head & Sub head | Name of work and break up | Allocated Found and break up for different locations/sites | ltems to be executed | Method of Procurement | Anticipated/Actual of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
--------------NIL--------------
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## Yameen Palari-I
Annexure A-1
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Provincial ADP 2015-2016
1 | Construction of Water Supply Scheme Yameen Palari, Taluka Thana Bula Khan District Jamshoro Rs:- 5.500 | 6.685 | 0 | 6.685 | Rs: - 5.500 01. Tube Well i/c Trial Bore (01 No) 02. Pump House (01 No) 03. P/Machinery 15 BHP 01 Set 04. Distribution System i. PVC Pipe 3" (2770 Rft:) ii. PVC Pipe 3" (1700 Rft:) 05. L.S.R / Storage Tank (01 No) | 6.685 | Execution of construction work | Single Stage Envelope | 11/2015 | After issue of Work Order | 06/2016
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## Yameen Palari-II
ANNEXURE A-II
ANNEXURE-II
PROCUREMENT PLAN (Non-Development)
S. No | Found Head & Sub head | Name of work and break up | Allocated Found and break up for different locations/sites | ltems to be executed | Method of Procurement | Anticipated/Actual of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
--------------NIL--------------
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## P-Mach Subhanallah Colony-I
Annexure A-1
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Provincial ADP 2015-2016
1 | Supplying / Installing & Testing Pumping Machinery 30 BHP (4 Sets) i/c Diesel Engine 48 BHP @ Disposal work i/c P/L/J Testing A.C. Pipe 20" dia for Drainage Scheme Subhanallah Colony Taluka Kotri District Jamshoro Rs:- 6.570 | 6.57 | 0 | 6.57 | Rs: - 6.570 01. Tube Well i/c Trial Bore (01 No) 02. Pump House (01 No) 03. P/Machinery 15 BHP 01 Set 04. Distribution System i. PVC Pipe 3" (2770 Rft:) ii. PVC Pipe 3" (1700 Rft:) 05. L.S.R / Storage Tank (01 No) | 6.57 | Execution of construction work | Single Stage Envelope | 12/2015 | After issue of Work Order | 06/2016
(RASHEED AHMED SOOMRO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
JAMSHORO

## Annexure-I
(Annexure-A)
PROCUREMENT PLAN (Development)
Serial No/ ADP No: | Name of Scheme & Estimated Cost | Allocated Funds | Cost of ongoing works (Expenditure already incurred | Funds ongoing works | Cost of new works (components) | Funds for New works | Nature of Procurement | Method of Procurement | Anticipated / Actual Date of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
District ADP 2017-18
1 | Construction of Collecting Tank, Inter Connection, Screening Chamber, Pump House, Rising main 4" dia i/c C.C Block for Rural Drainage Scheme Sacho Abro Taluka & District Matiari ( Work No.01)(2.000) | 1.5 | 0 | 0 | Rs.2.000 1.Collecting tank 10' dia (1 No.) 2.Screening Chamber (5'x8') 1 No. 3. Inter Connection RCC ASTM pipe 12" dia 16.00 Rft 4. Pump House (10'12') 1 No. 5. PVC Rising Main 4" dia 9900.00 Rft 6. C.C Block 6500.00 Sft | 1.5 | Execution of construction work | Single Stage Envelope | 21-12-2017 | After issue of Work Order | 2018-06-01
2 | Construction of Surface Drains and C.C Block Makhdoom Talib-ul-Mola Colony and Sakhi Murad Shah Colony Taluka Hala District Matiari (WorkNo.02) (1.500) | 2.5 | 0 | 0 | Rs.1.500 M 1. S/Drain T-A= 1000 Rft 2. T-B= 500 Rft 3. C.C Block 5600.0 Sft | 2.5 | Execution of construction work | Single Stage Envelope | 21-12-2017 | After issue of Work Order | 2018-06-01
3 | P/L/J & Testing PVC 4" dia Rising main for Rural Drainage Scheme Makdoom Talib-ul-Mola colony & Sakhi Muard Shah Colony New Hala Taluka Hala District Matiari. (Work No.07) (Rs.1.140) |  |  |  | Rs.1.140 M 1. PVC Rising Main 4" dia 6000.00 Rft. |  | Execution of construction work | Single Stage Envelope | 21-12-2017 | After issue of Work Order | 2018-06-01
4 | Providing & Installing Pumping Machinery 10 BHP for Rural Drainage Scheme Makhdoom Talib-ul-Mola Colony & Sakhi Muarad Shah Colony New Hala District Matiari (Work No.11) (1.560 ) |  |  |  | Rs.1.560 M 1. S/F of Electric Pumping Machinery 10 BHP 2 sets with all assercriess |  | Execution of work of Pumping Machinery | Single Stage Envelope | 21-12-2017 | After issue of Work Order | 2018-06-01
5 | Construction of Surface Drains and C.C Block for Rural Drainage Scheme Sukhio Mirjat Taluka Hala District Matiari (Work No.03) (0.950) | 1.5 | 0 | 0 | Rs.0.950 1. S/Drain T-A= 500 Rft T-B = 300 Rft 3.C.C Block 4000.0 Sft | 1.5 | Execution of construction work | Single Stage Envelope | 21-12-2017 | After issue of Work Order | 2018-06-01
6 | Construction of Collecting Tank,. Screening Chamber, Inter connection, Pump House & Compound Wall for Rural Drainage Scheme Sukhio Mirjat Taluka Hala District Matiari (Work No.04) (2.150) |  |  |  | Rs.2.150 M 1. C/Tank 15' dia 1 No. 2. S/Chamber (5' 8' ) 1 No. 3.Inter Connection 12" dia 64.00 Rft 4. Pump House 10x12' 1 No. 5. C/Wall 250.00 Rft |  | Execution of construction work | Single Stage Envelope | 21-12-2017 | After issue of Work Order | 2018-06-01
7 | Construction of Pump House ,Compound Wall & C.C Block for Warwary Colony for Rural Drainage Scheme Old Hala Taluka Hala District Matiari ( Work No.05) (0.900) | 4.5 | 0 | 0 | Rs.0.900 M 1.Pump Houe 314.0 Sft 2.C/Wall 200.00 Rft 3. C.C Block = 1000 Rft | 3.915 | Execution of construction work | Single Stage Envelope | 21-12-2017 | After issue of Work Order | 2018-06-01
8 | Construction of Surface Drains & C.C Block for Sarwary Colony for Rural Drainage Scheme Old Hala Taluka Hala District Matiari (Work No.06) (Rs.0.950) |  |  |  | Rs.0.950 M 1. S/Drain T-A-500 Rft Type-B = 300 Rft 2. C.C Block = 4000 Sft |  | Execution of construction work | Single Stage Envelope | 21-12-2017 | After issue of Work Order | 2018-06-01
9 | P/L/J & Testing PVC 6" dia Rising Main for Sarwary Colony Rural Drainage Scheme Hala Old Taluka Hala District Matiari ( Work No.09) (Rs.0.515) |  |  |  | Rs.0.515 M 1. PVC Rising Main 6" dia 1500.00 Rft |  | Execution of Piping Work | Single Stage Envelope | 21-12-2017 | After issue of Work Order | 2018-06-01
10 | Providing & Installing Pumping Machinery 10BHP for Sarwary Colony Rural Drainage Scheme Hala Old Taluka Hala District Matiari. (Work No.10) (Rs.1.550) |  |  |  | Rs.1.550 M 1.Electric Pumping Machinery 10 BHP 2 Sets with accesserces |  | Execution of Pumping Machinery work. | Single Stage Envelope | 21-12-2017 | After issue of Work Order | 2018-06-01
11 | P/L/J and Testing PVC 6" dia Rising Main for Improvement & Extension for Rural Drainage Scheme (Disposal Works Bhutta Muhalla ) Hala Old Taluka Hala District Matiri. (Work No.08) (2.475) | 3.785 | 0 | 0 | Rs.2.475M 1.PVC Rising Main 6" dia 7480.00 Rft | 2.5 | Execution of Piping Work | Single Stage Envelope | 21-12-2017 | After issue of Work Order | 2018-06-01 | 2018-06-01
12 | Construction of Surface Drains and C.C Block for Village Haji Hameed Rahooja Taluka Saeedabad, District Matiari | 0.815 | 0 | 0 | Rs.0.800 M 1. S/Drain T-A = 250.0 Rft 2. C.C Block =6000. Sft | 0.815 | Execution of construction work | Single Stage Envelope | 21-12-2017 | After issue of Work Order | 2018-06-01
(ABDUL RASHEED BHUTTO)
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG:DIVISION
MATIARI

## Annexure-II
ANNEXURE A-II
ANNEXURE-II
PROCUREMENT PLAN (Non-Development)
S. No | Found Head & Sub head | Name of work and break up | Allocated Found and break up for different locations/sites | ltems to be executed | Method of Procurement | Anticipated/Actual of Advertisement | Anticipated/Actual Date of Start | Anticipated/Actual Date of Completion | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
--------------NIL--------------
ABDUL RASHEED BHUTTO
EXECUTIVE ENGINEER
PUBLIC HEALTH ENGG: DIVISION
MATIARI