## Procurement Plan
OFFICE OF THE EXECUTIVE ENGINEER BUILDINGS WORKS & SERVICES DEPARTMENT KHAIRPUR
PROCUREMENT PLAN FOR THE YEAR 2017-18
SR. NO. | ADP | NAME OF WORK | ESTIMATE/ TENDER COST | ALLOCATION 2017-18 | RELEASE 2017-18 | UTILIZATION / PROCUREMENT PROGRESS PLAN |  |  |  | REMARKS
[6 empty] | DECEMBER TO JANUARY 2017-18 | JANUARY TO FEBRUARY 2017-18 | MARCH TO JUNE 2018 | JULY TO JUNE 2018-19
1 | 709 | Up-Gradation of R.H.C Pir-Jo-Goth to the level of Taluka Head Quarter Hospital at Kingri Taluka Kingri District Khairpur.
| a) | Non-Residential Building Construction of Hospital (OPD, ICU, IPD Block) Ground Floor & First Floor | 56000000 | 40000000 | 10000000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
| b) | Internal & External Electrification | 4500000
2 | 710 | Up-Gradation of R.H.C Center to the level of Taluka Head Quarter Hospital at Thari Mirwah Taluka Thari Mirwah District Khairpur.
| a) | Non-Residential Building Construction of Hospital (OPD, ICU, IPD Block) Ground Floor & First Floor | 60000000 | 40000000 | 10000000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
| b) | Internal & External Electrification | 4800000
3 | 1576 | Construction of Municipal Committee Hall at Kingri & Gambat District Khairpur.
| a) | Municipal Committee Hall at Kingri. | 42100000 | 40000000 | 10000000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
| a-ii) | Internal & External Electrification | 3500000
| b) | Municipal Committee Hall at Gambat. | 41500000
| b-ii) | Internal & External Electrification | 3500000
4 | 45 | Extension /Rehabilitation of Dargah Sachal Sarmast Taluka Gambat District Khairpur.
| a) | Extension of Dargah Sachal Sarmast (Sheds) | 11000000 | 39000000 | 19500000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
| b) | External Development | 3000000
| c) | Electrification | 500000
5 | 692 | Construction of Government Dispensary at Village Phulpota & Pahore, Taluka Khairpur. (Civil work i/c Water Supply & S/Fittings, Compound wall). | 4000000 | 1125000 | 280000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
6 | 693 | Construction of Compound wall of Graveyard Syed Papu Shah, TC Baberloi Taluka Khairpur. | 2300000 | 593000 | 148000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
7 | 694 | Construction of Compound wall for Graveyard Mohalla Soomra, TC Baberloi Taluka Khairpur. | 3800000 | 951000 | 238000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
8 | 695 | Construction of Entrance Gate at Atta Muhammad Hami, U/C Atta Muhammad Hami Taluka Kotdiji. | 1500000 | 375000 | 94000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
9 | 696 | Construction of Musafir Khana at Dargah Village Khair Shah, U/C Luqman Taluka Khairpur. | 2400000 | 646000 | 162000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
10 | 697 | Rehabilitation of Dargah Naseer Fakir Jalalani, U/C Naseer Fakir Jalalani Taluka Kotdiji. | 3150000 | 849000 | 212000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
11 | 698 | Construction of Internal work for Dargah Pir Gudo, U/C Raheem Bux Wassan Taluka Kotdiji. | 1900000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
12 | 699 | Construction of Shiv Mandar (F-Floor) at Panjhatti Mohalla Taluka Khairpur. | 2750000 | 750000 | 187000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
13 | 700 | Construction of Public Park at City Karoondi TC Karoondi Taluka Faiz Ganj. | 2700000 | 750000 | 187000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
14 | 701 | Construction of Compound wall for Graveyard Shaheed Dildar Chang and Ali Muhammad Chang Taluka Faiz Ganj. | 3000000 | 750000 | 187000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
15 | 702 | Construction of Government Dispensary at Village Zafar Ali Hisbani Taluka Faiz Ganj. | 4000000 | 1125000 | 280000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
16 | 704 | Construction Compound wall for Graveyard Main Fateh Muhammad Faqir Ward No.06 M/C Pir-Jo-Goth Taluka Kingri | 1000000 | 250000 | 63000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
17 | 705 | Additional work of Revenue Complex old Mukhtiarkar Office Khairpur. | 890000 | 1250000 | 313000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
18 | 706 | Construction Additional work of Embriodary Center at Therhi Taluka Khairpur.
| a) | Civil work | 3200000 | 2500000 | 625000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
| b) | External Electrification | 1200000
19 | 707 | Establishment of Modern Fire Station City Khairpur.
| a) | Civil work (Modern Fire Station) | 14800000 | 5000000 | 1250000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
| b) | Residential Flats 02 Nos. | 3900000
| c) | Electrification | 1200000
20 | 708 | Establishment of Public Park at Dakhan Mohalla Near Sim Nala Luqman Taluka Khairpur. | 4500000 | 1250000 | 313000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
21 | 709 | Construction of Compound wall at Graveyard near Police Station Baberloi/Shafi Muhammad TC Baberloi Taluka Khairpur. | 3000000 | 750000 | 187000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
22 | 710 | Remaining work Dargah Khush Khair Muhammad Hisbani Taluka Faiz Ganj. | 1950000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
23 | 711 | Construction of Dargah Mithan Shah at Village Rahooja Taluka Kingri. | 2500000 | 625000 | 156000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
24 | 712 | Construction of Jamia Masjid at Shia Eidgah Taluka Khairpur. | 4700000 | 1250000 | 313000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
25 | 713 | Construction of Dargah Pir Gaffar Shah Taluka Khairpur. | 1850000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
26 | 714 | Construction of Musafir Khana & Compound wall at Dargah Yateem Shah Taluka Khairpur. | 1900000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
27 | 715 | Construction of Dargah Pir Shah at Village Khokhar Taluka Khairpur. | 1400000 | 375000 | 94000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
28 | 716 | Construction of Musafir Khana at Dargah Syed Bachal Shah Mohalla Taluka Khairpur. | 2350000 | 625000 | 156000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
29 | 717 | Construction of Compound wall, Musafir Khana Pir Shah Panjo Dahot Mohalla Taluka Khairpur. | 1900000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
30 | 718 | Remaining work of Masjid at Village Raina/ Manganhar Taluka Khairpur. | 1350000 | 375000 | 94000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
31 | 719 | Construction of Dargah Wadhal Shah near Mir Bahar Mohalla Taluka Khairpur. | 950000 | 250000 | 63000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
32 | 720 | Construction of Dargah Pir Bachal Shah at Village Lal Bux Mangi U/c Shah Bhangio Taluka Khairpur. | 1900000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
33 | 721 | Construction of Compound wall Path & Musafir Khana at Dargah Rattal Shaheed U/c Naseer Fakir Jalalani Taluka Kotdiji. | 1950000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
34 | 722 | Construction Additional work of Dargah Syed Gul Shah Ghazi U/c Fatehpur Taluka Kotdiji. | 1900000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
35 | 723 | Construction of Compound wall of Graveyard Syed Jo Qabarustan Mitho Mari Taluka Khairpur. | 1500000 | 375000 | 94000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
36 | 724 | Rehabilitation of Masjid Sharief Ali Raza at Wado Alam Kolab Jial Taluka Kingri. | 1500000 | 375000 | 94000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
37 | 725 | Construction of Masjid at Village Lal Bux Targar Taluka Khairpur. | 1850000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
38 | 726 | Remaining work of Masjid Jamkarn Wandh Mohalla near Water Supply Taluka Khairpur. | 1400000 | 375000 | 94000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
39 | 727 | Construction of Dargah Aachar Shah Shadi Shaheed near Khalid Petrol Pump Taluka Khairpur. | 1350000 | 375000 | 94000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
40 | 728 | Rehabilitation of Dargah Pir Shah Bhangio U/c Shah Bhangio Taluka Khairpur. | 2000000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
41 | 729 | Construction of Musafir Khana at Markazi Imam Bargah Hyderi Taluka Khairpur. | 950000 | 250000 | 63000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
42 | 730 | Construction of Eidgah Imamia at Bhurgari Mohalla Unit No.14 Taluka Khairpur. | 2800000 | 750000 | 187000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
43 | 731 | Construction of Compound wall and C.C. Block at Eidgah at Village Rind Hajana Taluka Kotdiji. | 2000000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
44 | 732 | Construction of Compound wall & Musafir Khana / Hall at Jagir Ali Akbar Kot Mir Muhammad Taluka Kingri. | 2350000 | 625000 | 156000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
45 | 733 | Construction of Musafir Khana/ Waiting Shed Ali Raza Chowdary at Village Mumtaz Hundal U/c Tando Mastti Taluka Khairpur. | 1400000 | 375000 | 94000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
46 | 734 | Construction of Compound wall of Waiting Shed Hazrat Abutalib (A.S) City Bungalow Kotdiji Taluka Kotdiji. | 1950000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
47 | 735 | Construction of Musafir Khana / Waiting Shed Punjtani Muhalla Dabbar Mohalla Taluka Khairpur. | 1900000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
48 | 736 | Construction of Compound wall of Earth Filling near Imam Bargah Syed Sachal Shah Mitho Mari Taluka Khairpur. | 1950000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
49 | 737 | Construction of Security Barriers / C.C Blocks near Imam Bargah Qasar-e-Hussaini Muhalla Ali Murad Shah Taluka Khairpur. | 1000000 | 250000 | 63000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
50 | 738 | Remaining work of Musafir Khana near Imam Bargah at Village Muhammad Hayat Shaikh near Karamabad Taluka Khairpur. | 900000 | 250000 | 63000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
51 | 739 | Construction of Compound wall of Imam Bargah Qasar-e-Batool near Chandia More Taluka Khairpur. | 1850000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
52 | 740 | Constructionof Compound wall & C.C Block at Imam Bargah Muhban-e-Ahlebet Osta Gahi Taluka Khairpur. | 1000000 | 250000 | 63000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
53 | 741 | Construction of New Union Council Office Building U/c Jiskani Taluka Kotdiji. | 3750000 | 1000000 | 250000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
54 | 742 | Construction of Compound wall for Graveyard at Village Muhammad Bux Dahar U/C Naseer Fakir Jalalani Taluka Kotdiji | 1180000 | 296000 | 74000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
55 | 743 | Construction of Compound wall for Graveyard at Village Ghulam Qasim Bugti Taluka Kotdiji. | 1900000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
56 | 744 | Construction of Compound wall of Mandar & Darbar @ Baseer Fakir U/c Raheem Bux Wassan Taluka Kotdiji. | 2440000 | 625000 | 156000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
57 | 745 | Construction of Dispensary in Ward 04 U/c Raheem Bux Wassan Taluka Kotdiji. | 4000000 | 1125000 | 281000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
58 | 746 | Construction of Eidgah at Village Muhammad Bux Wassan U/c Jiskani Taluka Kotdiji. | 1450000 | 375000 | 94000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
59 | 747 | Renovation of Eidgah at Village Jiskani U/c Jiskani Taluka Kotdiji. | 1500000 | 375000 | 94000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
60 | 748 | Construction of Government Dispensary at Village Jhando Mashaikh near Main Road U/c Raheem Bux Wassan Taluka Kotdiji. | 4000000 | 1125000 | 281000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
61 | 749 | Construction of Compound wall for Graveyard Village Bagho Daro U/c Naseer Fakir Jalalani Taluka Kotdiji. | 3000000 | 750000 | 187000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
62 | 750 | Construction of Eidgah at Village Malangabad U/c Mohbat Wah Taluka Kotdiji. | 1950000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
63 | 751 | Construction of Government Dispensary at Village Gul Bahar Kandhro Mohalla Malhar Kandhro U/c Deh Sohoo Taluka Kotdiji | 4000000 | 1125000 | 281000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
64 | 752 | Construction of Library at Bozdar Wada Taluka Kotdiji. | 2350000 | 625000 | 156000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
65 | 753 | Remaining work of Musafir Khana Shaheed Iqbal Hussain Hisbani Taluka Faiz Ganj. | 2800000 | 750000 | 187000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
66 | 754 | Rehabilitation of Basic Health Unit (BHU) Gadeji Taluka Sobhodero. | 2000000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
67 | 755 | Rehabilitation of Basic Health Unit (BHU) Setharja Taluka Thari Mirwah. | 1750000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
68 | 756 | Construction of Girls Library at Hingorja Taluka Sobhodero. | 2350000 | 625000 | 156000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
69 | 759 | Installation/ Extension of 50 CCTV Cameras in the Luqman Area Taluka Khairpur. | 20000000 | 5000000 | 1250000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
70 | 760 | Rehabilitation of Mumtaz Ground Khairpur Taluka Khairpur. | 1950000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
71 | 761 | Construction of Rescue Center at Main Road Gambat Taluka Gambat. | 2800000 | 750000 | 187000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
72 | 762 | Providing for the Computer Lab for Sweet Home Taluka Khairpur. | 500000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
73 | 763 | Providing Solar System at SOS House Taluka Khairpur. | 1000000 | 250000 | 63000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
74 | 765 | Construction of Library at Chondiko City Taluka Nara. | 2350000 | 625000 | 156000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
75 | 766 | Construction of Public Library at Therhi Town Taluka Khairpur. | 2350000 | 625000 | 156000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
76 | 767 | Construction of Government Dispensary at Village Ghulam Jaffar Khaki Taluka Sobhodero. | 4000000 | 1125000 | 281000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
77 | 768 | Rehabilitation of Old Meat Market Shahi Bazar Taluka Kotdiji. | 1400000 | 375000 | 94000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
78 | 769 | Construction of Blood Bank Scouts Taluka Kotdiji. | 940000 | 250000 | 63000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
79 | 770 | Construction of Compound wall of Graveyard for Pir Misri Shah near Petrol Pump Taluka Kotdiji. | 2000000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
80 | 771 | Rehabilitation of Meghwar Mandar at Mohalla Pir Dilbar Taluka Kotdiji. | 1400000 | 375000 | 94000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
81 | 772 | Construction of Compound wall of Eidgah Shaikh Mohalla Taluka Kotdiji. | 1000000 | 250000 | 63000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
82 | 773 | Construction of Government Dispensary at Village Miani U/c Naseem Kharal Taluka Gambat. | 4000000 | 1125000 | 281000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
83 | 774 | Construction of Musafir Khana near Imam Bargah Sayeda Zainab (A.S) Ali Murad Mohalla Ranipur Taluka Sobhodero. | 2300000 | 625000 | 156000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
84 | 775 | Construction of Public Park Rais Sikandar Ali Khan Chandio at Shahbaz Colony, Khairpur. | 2000000 | 500000 | 125000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
85 | 776 | Construction of Government Dispensary at Village Pipri Taluka Khairpur. | 4000000 | 1125000 | 281000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
86 | 777 | Establishment of Rescue Center at Khairpur (Revenue Components). | 15000000 | 3750000 | 938000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
87 | 778 | Up-Gradation of Dispensary to the B.H.U at Village Rafique Mahesar Taluka Kingri. | 3750000 | 1000000 | 250000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
88 | 779 | Construction of Compound wall for Graveyard for Pir Phul Wado Taluka Kotdiji. | 3000000 | 750000 | 188000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
89 | 780 | Earth Filling of Graveyard at Village Agra Taluka Gambat | 1500000 | 375000 | 94000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
90 | 418 | Construction of Compound wall for Graveyard at Village Sadoro Janwari Taluka Khairpur. | 1500000 | 375000 | 187000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
91 | 457 | Construction of Basic Health Uunit (BHU) at Khadim Hussain Katohar U/C Shadi Shaheed Taluka Khairpur. (Remaining work) | 1300000 | 1300000 | 1300000 |  | Tendering process | 30% | 70% | The utilization is subject to receipt of budget
EXECUTIVE ENGINEER (BUILDINGS) WORKS & SERVICES DEPARTMENT KHAIRPUR