## HBS
SCHEDULE-B
Name of Work:- Rehabilitation/Addition of Class Room/Provision of Missing Facilities for Primary/Elementry Schools of Taluka Sakrand and Qazi Ahmed District Shaheed Benazir Abad 2017-18 Programme @ G.B.P.S Hazoor Bux Shah Taluka Qazi Ahmed (Add:01 Class Room)
S.# | Description | Measurement | Quantity |  |  | Rate | Unit | Amount
1 | Excavation in foundation of building bridges and other structure i/c degbelling dressing refilling arround the structure with excavated earth watering ramming lead upto 5 feet. (S.I.No.18-b,P-4)
|  | Total | = | 1102 | Cft | 3176.25 | %oCft | 3500
2 | Cement concrete brick or stone ballast 1-1/2 to 2 guage(Ratio 1:5:10)(S.I.No.4c,P-15)
|  | Total:- | = | 572 | Cft | 8694.95 | %Cft | 49735
3 | Pacca brick work in foundation & plinth cement sand mortar ratio1:6(S.I.No.4(i)e,P-21)
|  | Total:- | = | 925 | Cft | 11948.36 | %Cft | 110522
4 | R.C.C work i/c all labour and material except the cost of steel reinforcement its labour for bending and binding which will be paid separately this rate also includes all kinds of forms molds lifting shuttering curring rendering and finishing the expose surface i/c screening and washing of shingle RCC work in roof slabe beam coloum raft lintel and other structure member laid in situ are precast laid in position complete in all respects (S.I No.6(i) P-17)
|  | Total:- | = | 494 | Cft | 337 | P.Cft | 166478
5 | Fabrication of mild steel reinforcement including cutting bending laying making joints in fastering including the cost of binding wire also removal of the rust from bars. (S.I No.8 (b) P-17)
|  | Total:- | = | 24.26 | cwt | 5001.7 | P.cwt | 121341.242
6 | Filling watering ramming earth in flooring earth surplus from foundation lead upto one chain and lift upto 5' (S.I No.21 P-4)
|  | Total:- | = | 555 | Cft | 1512.5 | %oCft | 839
7 | Filling watering ramming new earth excavated outside lead upto 1 chain and lift upto 5' (S.I No. 22 / P-4)
|  | Total:- | = | 998 | Cft | 3630 | %oCft | 3623
8 | S/F sand under floor & plugging in walls (S.I.No.29,P-No.25)
|  | Total:- | = | 218 | Cft | 1141.25 | %Cft | 2488
9 | Pacca brick work in ground floor cement sand mortar 1:6. (S.I.No.5-(i)e,P-21)
|  | Total:- | = | 1149 | Cft | 12674.36 | %Cft | 145628
10 | Providing and fixing G.I frames / chowkhats of size 7"x2" or 4 1/2"x3" for Door using 20 guage G.I sheet I/c welded hinges and fixing at site with necessary hold fasts. Filling with cement sand slurry of ratio 1:6 and repairing the jambs. The cost also i/c all carriage tools and plants used in making and fixing (S.I No.29 P-93)
|  | Total:- | = | 18 | Rft | 228.9 | P.Rft | 4120
11 | Providing and fixing G.I frames / chowkhats of size 7"x2" or 4 1/2"x3" for Windows using 20 guage G.I sheet I/c welded hinges and fixing at site with necessary hold fasts. Filling with cement sand slurry of ratio 1:6 and repairing the jambs. The cost also i/c all carriage tools and plants used in making and fixing (S.I No.28 P-93)
|  | Total:- | = | 71 | Rft | 240.5 | P.Rft | 17076
12 | S/F in position iron/steel grill of 3/4" x 1/4" size flat iron of approved design i/c painting 3 coats etc, complete (Weight not to be less than 3.7Lbs/Sq.Foot of finished grill.) (S.I No.26, P-92)
|  | Total:- | = | 37 | Sft | 180.5 | P.Sft | 6679
13 | First class deoder wood wrought joinery in doors in windows wtc fixed in position i/c chowkats hold fasts hinges iron tower bolts chocks cleats handles and cards with hooks etc. 1-3/4" thick (S.I.No.7-b,P-57)
Only Shutters
|  | Total:- | = | 67 | Sft | 902.93 | P.Sft | 60496
14 | Cement concrete plain i/c placing compacting finishing and curing complete i/c screening & washing of stone aggregate w/o suttering a ratio 1:3:6. (S.I:No.5(h)P-16)
|  | Total:- | = | 55 | Cft | 12595 | %Cft | 6927
15 | P/L floor of verona marble size 12x12x3/4" fine dressed on the surface without winding set in white cement laid over 3/4" thick bed of 1:2 grey cement mortar setting the tile with grey cement with slurry jointing & washing the tile with slurry of white cement pigment to match the colour of tiles i/c curing grinding rubbing & chemical polishing etc complete i/c cutting of proper profile. (R/A)
|  | Total:- | = | 570 | Sft | 307 | P.Sft | 174990
16 | P/L 1" thick topping C.C (1:2:4) i/c surface finishing & dividing into pannels. (S.I.No.16,P-42).
2" thick
|  | Total:- | = | 1074 | Sft | 3275.5 | %Sft | 35179
17 | Cement plaster 1:6 upto 12' height 1/2" thick (S.I.No.13-b,P-52)
|  | Total:- | = | 1928 | Sft | 2206.6 | %Sft | 42543
18 | Cement plaster 1:4 upto 20 feet height 3/8" thick (S.I.No.11-a,P-52)
|  | Total:- | = | 1928 | Sft | 2197.52 | %Sft | 42368
19 | Cement plaster 1:4 upto 12' height 3/4" thick. (S.I.No.11-c,P-52)
|  | Total:- | = | 92 | Sft | 3015.76 | %Sft | 2774
20 | Notice board made with cement (S.I.No.1,P-95)
|  | Total:- | = | 32 | Sft | 58.11 | P.Sft | 1860
21 | Cement pointing struck joints on wall 1:2. (S.I.No.19-a,P-53)
|  | Total:- | = | 658 | Sft | 1287.44 | %Sft | 8471
22 | Two coats of bitumen laid hot using 34 lbs per %sft over roof & blinded with sand one Cft per %Sft. (S.I No.13 P-35)
|  | Total:- | = | 742 | Sft | 1887.4 | %Sft | 14005
23 | Extra labour for making grooves of 1"x1/4" or 3/4"x1/4" plastered surface with true edges both vertically & horizontally with uniform depth & with groove base smoothly finished etc. complete as per instruction of Engineer incharge. (S.I.No.34,P-55)
|  | Total:- | = | 747 | Rft | 7.71 | P.Rft | 5759
24 | White Washing 3- | Coats. (S.I.No.26 P-54)
|  | Total:- | = | 685 | Sft | 829.95 | %Sft | 5685
25 | Colour washing 2-coats.(S.I.No.25-b,P-53)
|  | Total:- | = | 750 | Sft | 859.9 | %Sft | 6449
26 | Primary coat of chalk under distempering. (S.I.No.23,P-53)
|  | Total:- | = | 1928 | Sft | 442.75 | %Sft | 8536
27 | Distempering 3-Coats. (S.I.No.24-c,P.No.54)
|  | Total:- | = | 1928 | Sft | 1079.65 | %Sft | 20816
28 | Preparing surface and painting of doors and windows any type new surface 3-coats (S.I.No.5-c,(i+ii) P-70)
|  | Total:- | = | 164 | Sft | 2116.41 | %Sft | 3471
29 | Extra labour for making cement plaster pattas/band around straight or carved openings and around the edges of roof slabs,the width not less than 6" with fine finishing as directed by Engineer incharge. (S.I.No.35,P-55)
|  | Total:- | = | 184 | Rft | 19.36 | P.Rft | 3562
[6 empty] | G.Total Rs:- |  | 1075920.242