## M.SHEET-2
II--Memorandum of Payment
[8 empty] | Rs: | Ps:
1. Total value of workdone as per Account-I, Coloumn 5 Entry (A)
2. Deduct Amount with held :-
Figure of works |  | a) Form Previous Bill as per Running Account |  |  | Rs: | Ps:
Abstracts
Rs: | Ps: | b) From this bill
|  | 3. Balance i.e, "Up-to-date" payment (Item 1---2) |  |  |  | (K)
4. Total amount of payments already made as per entry (K) of
last Running Account B ill No: of forwarded
with account for
|  | Payment now to be made as detailed below |  |  | Rs: | Ps:
|  | (a) | By rexcovery of amount creditable to
this work:-
Value of stock supplied as detailed
in the ledger in
Total 2 (b) + 5(a) G
|  | (b) | by recovery of amount creditabble to
other work or heads of accounts
DEDUCTION
6% I.TAX Rs.
3% S.Deposit Rs.
|  | (`c) | By Cheques
Total 5 (b) + (`c) H
PAY RS: ( )(Rupees
By Cheque
(Dated Intials of Disburshing Officer )
RECEIVED RS: ( ) |  |  |  | as per above memorandum
on account of this work
Dated:- / /200
Stamp
Witness |  |  |  | (Full Signature of the Contractors)
Paid by me Vide Cheque No: |  |  |  | Dated |  | Cashier
(Dated Initials of persons actually making payments
IV R E M A R K S
This space is reserved to any remarks the disburshing Officer or the Executive Engineer may with to
record in respect to the execution work cheque of measurement or the State or Contractore Accounts
`Here specify the net amount payable vide item 5(e)

## M. ALI LEGHARI
NAME OF WORK:- |  | (ADP-154/158) ADDITIONAL OF CLASS ROOMS IN EXISTING MIDDLE SCHOOLS IN DISTRICT HYDERABAD (15-CLASS ROOMS) UNDER BLOCK ALLOCATION (2011-12) PROGRAMME @ GBLSS MOHAMMAD ALI LEGHARI, TALUKA HYDERABAD (BALANCE WORK).
S.NO. | DESCRIPTION |  | QUANTITY |  | RATE |  | UNIT | AMOUNT
1 | Excavation in forundation of building, bridges and other structures i/c degbelling, dressing refilling around structure with excavated earth watering and ramming lead upto five feet (b) in ordinary soil (S.I. # 18/P-4)
|  |  |  | 141 | @ | 3176 | %0Cft | Rs. | 447.816
2 | Cement concrete brick or stone ballast 1 1/2" to 2" guage ratio 1:4:8 (S.I. # 04/P-17).
|  |  |  | 349 | @ | 9416.28 | %Cft | Rs. | 32862.8172
3 | Pacca brick work in foundation and plinth in cement sand and mortor ratio 1:6. (S.I. # 04/P-24).
|  |  |  | 246 | @ | 11984.36 | %Cft | Rs. | 29481.5256
3 | Filling sand under floor pluging in well (S.I.No:29/P-25).
|  |  |  | 344 | @ | 1141.25 | %Cft | Rs. | 3925.9
4 | R.C.C work i/c all labour and material except the cost of steel reinforrcement and its labour forr bending and binding which will be paid seperately. This rate also includes all kinds of forrms moulds lifting shuttering curring rendering and finishing the exposed surface (i/c screeening and washing of shingle (a) R.C work in roof slab beams, columns, rafts lintels and other structural members laid in situ or precast in position complete in all respect ratio 1:2:4 (S.I. # 06-a/P-18).
|  |  |  | 559 | @ | 337 | P.Cft | Rs. | 188383
5 | Fabrication of mild steel reinforcement for cement concrete i/c cutting bending laying in position, making joints and fastenings i/c cost of binding wire (also removal of rust from bars)(S.I.# 7(ii)/P-20).
| Tor Bars |  |  | 29.94 | @ | 5001.7 | P.cwt | Rs. | 149750.898
6 | Pacca brick work in Ground Floor in i/c stricking of joints cement sand mortar 1:6 (S.I. # 05(i)e/P-25).
|  |  |  | 362 | @ | 12674.36 | %Cft | Rs. | 45881.1832
7 | Providing and fixing G.I. frames / chowkhats of a size 7" x 2" or 4 1/2" x 3" for a door using 20 guage G.I. sheet including welded hanges and fixing at site with necessary hold fasts. Filling with cement sand slurry of ratio 1:6 and repairing the jambs. The cost also includes all carriage tools and plants used in making and fixing. (S.I. # 29/P-98).
(A) | DOOR FRAMES.
|  |  |  | 18 | @ | 228.9 | P.Rft | Rs. | 4120.2
(B) | WINDOW FRAMES.
|  |  |  | 51 | @ | 240.5 | P.Rft | Rs. | 12265.5
8 | Cement plaster 1:6 upto 20' height (b) 1/2" thick. (S.I. # 13(b)/P-58).
|  |  |  | 3152 | @ | 2206.6 | %Sft | Rs. | 69552.032
9 | Cement plaster 1:4 upto 20' height (b) 3/8"" thick. (S.I. # 13(b)/P-58).
|  |  |  | 3152 | @ | 2197.52 | %Sft | Rs. | 69265.8304
10 | Supplying and fixing in position Iron steel grill of 3/4" x 3/4" size flat iron of approved design i/c painting three coats etc. Complete (Wt not to be less than 3 - 7 lbs sq; ft of finishing grill. (S.I. # 26/P-97).
|  |  |  | 204 | @ | 180.5 | P.Sft | Rs. | 36822
11 | First class deodar wood wrought joinery in doors and windows etc: fixed in position i/c chowkhats hold fasts hinges iron tower bolts, chocks cleats handles and cords with hooks etc. Deodar panelled or panelled and glazed or fully glazed (b) 1 3/4" thick. (S.I.# 07(b)/P-65).
|  |  |  | 56 | @ | 902.93 | P.Sft | Rs. | 50564.08
12 | Making notice board made with cement and sand (S.I.No: /P- ).
|  |  |  | 32 | @ | 58.11 | P.Sft | Rs. | 1859.52
13 | Providing and laying topping cement concrete (1:2:4) i/c surface finishing and divided into panelles. (S.I. # 6/P-47).
3" Thick.
|  |  |  | 510 | @ | 4411.82 | %Sft | Rs. | 22500.282
2" Thick.
|  |  |  | 1077 | @ | 3275.5 | %Sft | Rs. | 35277.135
14 | Two coat of bitumen laid hot using 34 lbs forr %sft over roof and blinded with sand at one Cft per% Sft. (S.I.# 13/P- ).
| C/R+Ver: O/R | 1x24.58x30.25 |  | 744 | @ | 1887.4 | %Sft | Rs. | 14042.256
15 | Primary coat of chalk under distempering. (S.I.# 23/P-55).
|  |  |  | 3868 | @ | 442.75 | %Sft | Rs. | 17125.57
16 | Distempering three coats. (S.I.# 24/P-59).
|  |  |  | 3868 | @ | 1079.65 | %Sft | Rs. | 41760.862
17 | Painting new surface, preparing surface and painting of doors and windows any type i/c edges three coats. (S.I.# 66/P-97).
|  |  |  | 128 | @ | 2116.41 | %Sft | Rs. | 2709.0048
[6 empty] | TOTAL |  | Rs. | 828597.4122
SCHEDULE-B

## P.B
PART-B
S# | DESCRIPTION | QUANTITY |  | RATE |  | UNIT | AMOUNT
1 | P/F squatting type white glazed earthenware W.C pan with front flush inlet & complete with i/c the cost of flushing internal fitting & flush pipe with bend & making requisite no: ofcistern with holes inwall plinth & floor for pipe connection &making good in C.C.1:2:4 a)W.C pan 23" & low level earthenware flush tank 3-gallons (i) with 4" dia C.I Trape.(S/I/NO:2/P-1)
|  | 2 | Nos: | @ | 5728.8 | Each | Rs: | 11457.6
2 | Proviuding G.I.Pipes specials & clamps etc i/c fixing cutting & fitting complete with & i/c the cost of breaking through wall & roof making good etc painting 2-coats after cleaning the pipe ^ with white zink paint with pigment to match the colour of the building & testing water to a pressure head of 200 ft: & handling.(S.I.NO:1/P-12).
a) | 1/2" DIA | 40 | Rft | @ | 73.21 | P.Rft | Rs: | 2928.4
b) | 3/4" DIA | 40 | Rft | @ | 95.79 | P.Rft | Rs: | 3831.6
3 | Providing R.C.C Pipe with collars class "B" & Digging the trences to required depth & fixing in position i/c cutting fitting & jointing with maxphalt composition & cement mortor 1:1 & testing with watrer pressure to a head of 4 feet above the top of the heighest pipe & re-filling with excavated stuff.(S.I.NO:2/P-21)
| 4" dia. | 30 | Rft | @ | 199.25 | P.Rft | Rs: | 5977.5
4 | S/Fixing Long-Bib-Cock of supperior quality with C.P head 1/2" dia. (S.I.NO15/P-15)
|  | 2 |  | @ | 1109.46 | Each | Rs: | 2218.92
5 | S/Fixing Cancealle Tee-Cock of supperior quality with C.P. head 1/2" dia. (S.I.No:12/P-18).).
|  | 2 |  | @ | 843.92 | Each | Rs: | 1687.84
6 | P/Fixing Water Pumping Set 1 H.P Mono-Block Single-Phase 220 Volts with 1-1/2"x1-1/2" suction & delivery 120 ft: head i/c making C.C.1:3:6 plate form of required size & fixing with nuts & boklts etc complete in all respect.(Sc: of Elect:) (R.A).
|  | 1 | Nos: | @ | 14417.7 | Each | Rs: | 14417.7
7 | P/Fixing Handle Valves (China) (S.I.No:5/P-17).
| 1/2" dia. | 1 | Nos: | @ | 200.42 | Each | Rs: | 200.42
| 3/4" dia. | 1 | Nos: | @ | 271.92 | Each | Rs: | 271.92
8 | P/Fixing 4"x4" dia C.I Branch of the required degree with access doors rubber washers 3/8" thick & built & nuts & extra painting to match the colour of the building.(S.I.NO:5/P-8)
|  | 2 | Nos: | @ | 702 | Each | Rs: | 1404
9 | Providing and installing hand pump with all accessories 1.1/4" dia coir strainer with wooden shoe i/c boring fitting and fixing etc. complete. (R.A approved).
(A) | Coir Strainer | 10 | Rft | @ | 76.05 | Each | Rs: | 760.5
(B) | Boring | 100 | Rft | @ | 38.95 | Each | Rs: | 3895
10 | S/F FIBER-GLASS-TANK of approved quaity & design & wall thickness as specified i/c the cost of nuts, bolts & fixing in plate form of cement concrete 1:3:6 & making connections for in-let & out-let & over-flow pipe etc etc complete.(S.I.NO:3/P-8)
| (250 GALLONS) | 1 | Nos: | @ | 21989.61 | Each | Rs: | 21989.61
[6 empty] | TOTAL | Rs: | 71041.01
s