## Sheet4
FACE SHEET
FUND HEAD | : - |  | SC-12058(58)-09, Education Affairs & Services
MAJOR HEAD | : -
MINOR HEAD | : -
SERVICE HEAD | : -
DEPARTMEN HEAD | : - |  | Package No: 1 Rehabilitation & Expansion of High Priority '4560' Schools (Non-ADP) Primary / Elementary Sector @ 1-GBPS Sahafi Colony, 2-GBPS Sayed Qutub Shah, 3-GBLSS Raees Khan Mohammad Chandio, 4-GBPS American Quarter, 5-GBLSS Nawab Muzaffer, 6-GBPS Hadi Mill Taluka Latifabad
This Estimate has been prepared in the office of the Assistant Engineer, Electrical Education Works Sub-Division Hyderabad,The probable expenditure incurred on the above said work, will be chargeable against the head of Account _____________
|  |  | Estimated Cost Rs: | #REF!
GENERAL DESCRIPTION
1 | HISTORY: - | The Government of Sindh has approved the New A.D.P./ M&R / REPAIR RENOVATION Schemes during The year 2008-2009 for whole of Sindh which are to executed the Works & Services Department in this current financial year. The above said scheme is one of the approved schemes. Hence this estimate has been prepared.
2 | SCOPE: - | All necessary item has been included in the estimate for smooth Functioning
3 | METHOD: - | The Work will be carried out after calling tenders / quotations and Observing all coddle formalities.
4 | DESIGN: - | Provision of light and fan points is made in accordance with illumination Design & balance distribution of light in the Educational Institutions.
5 | RATE: - | Estimate is based on Pak P.W.D. Schedule of Rates 2012 and R.A.Approved by the competent authority.
6 | Time: - | __________ Months are sufficient for completion of work.
ASSISTANT ENGINEER
ELECTRICAL EDUCATION WORKS
HYDERABAD.

## SCH-B
SCHEDULE-B
Package No: 1 Rehabilitation & Expansion of High Priority '4560' Schools (Non-ADP) Primary / Elementary Sector @ 1-GBPS Sahafi Colony, 2-GBPS Sayed Qutub Shah, 3-GBLSS Raees Khan Mohammad Chandio, 4-GBPS American Quarter, 5-GBLSS Nawab Muzaffer, 6-GBPS Hadi Mill Taluka Latifabad
S.No. | DESCRIPTION OF ITEMS | Qty. |  |  | Rate | Unit |  | Amount
PART "A" SCHEDULE ITEMS
1 | Wiring for light or fan point with 3/.029 PVC insulated wire in 20mm (3/4") channal patti on surface as required. (S.I.No. 129/P-15). | 215 | Points | @ | 910 | P/P | Rs. | 195650
2 | Wiring for Plug Point with 3/.029 PVC insulated wire in 20mm (3/4")channal patti on surface as required. (S.I.No. 130/P-15). | 39 | Points | @ | 742 | P/P | Rs. | 28938
3 | Providing & Laying (Main or sub-mains) PVC insulated with size 2-7/0.29 copper conductor in 3/4" dia PVC condiut on surface. (S.I.No. 03/P-01). | 399 | Meter. | @ | 171 | P.Met | Rs. | 68229 | 3.25 | 1296.75
4 | Providing & Laying (Main or sub-mains) PVC insulated with size 2-7/0.44 (6mm2) copper conductor in 1" dia PVC condiut on surface. (S.I.No. 05/P-01). | 150 | Meter. | @ | 305 | P.Met | Rs. | 45750 | 3.25 | 487.5
5 | P/F AC one way S.P. 5 Amps switch flush type.(S.I.No. 219/P-33). | 215 | Nos. | @ | 54 | P.No. | Rs. | 11610
6 | P/F flush type 2 pin 5 Amps S.P. plug socket.(S.I.No. 222/P-33). | 39 | Nos. | @ | 80 | P.No. | Rs. | 3120
7 | P/F type 3-Pin 10/15 Amps S.P. Plug Socket. (S.I.No. 227/P-33). | 11 | Nos. | @ | 162 | P.No. | Rs. | 1782
8 | P/F brass batten holder (S.I.No. 232/P-33). | 84 | Nos. | @ | 70 | P.No. | Rs. | 5880
9 | P/F backlight ceiling rose with two terminals.(S.I.No. 228/P-33). | 113 | Nos. | @ | 72 | P.No. | Rs. | 8136
10 | P/F Circuit Breaker 6,10,15,20,30,40,50 & 63 Amp SP (TB-5S) on prepared board as required. (S.I.No. 203/P-31). | 35 | Nos. | @ | 916 | P.No. | Rs. | 32060
11 | P/F Circuit Breaker 6, 10, 15, 20, 30, 40, 50 & 63 Amp DP (TB-5S) on prepared board as required. (S.I.No. 204/P-31). | 8 | Nos. | @ | 2456 | P.No. | Rs. | 19648
12 | Providing Circuit Breaker 15,20,30,40,50,60,75 & 100 Amp T.P (XS-100NS)on a prepared board as required.(S.I.No.207/P-31). | 2 | Nos. | @ | 9261 | P.No. | Rs. | 18522
13 | Providing & Fixing voltmeter size 96/96mm 500 volts as required & as per instruction of EI.(S.I.No.285/P-41). | 12 | Nos. | @ | 999 | P.No. | Rs. | 11988
14 | Providing & Laying (Main or sub-mains) PVC insulated with single core copper conductor 250/440 volts size (2-7/0.52) 10mm2. (S.I.No. 48/P-06). | 240 | Meter. | @ | 335 | P.Met | Rs. | 80400 | 3.25 | 780
|  | #VALUE! | Total Part "A" |  |  |  | Rs. | 531713
| PART "B" NON SCHEDULE ITEMS. (R/A APPROVED). | #VALUE!
1 | P/F 1-40 watts tube light complete with 40-watts with rod, chowk, starter etc complete Philips made. | 58 | Nos. | @ | 802.63 | P.No. | Rs. | 46552.54
2 | P/F capsole light superior quality with plastic reflector i/c connection as required. | 20 | Nos. | @ | 609.84 | P.No. | Rs. | 12196.8
3 | P/F Enegy sever superior quality i/c fixing on existing holder. | 104 | Nos. | @ | 407 | P.No. | Rs. | 42328
4 | P/F ceilling fan 56" complete in all respect as required (GFC Karachi made/Pak orignal good Quility). | 46 | Nos. | @ | 5262 | P.No. | Rs. | 242052
5 | P/F flush type ceiling fan dimmer imported quality as required. | 62 | Nos. | @ | 354.64 | P.No. | Rs. | 21987.68
6 | P/F Mild Steel Bar Fan Clamp 15.8mm 5/8" dia suitable for RCC Roof. | 46 | Nos. | @ | 236.94 | P.No. | Rs. | 10899.24
7 | P/F Panel Distribution Board Double Shutter to Accommodate circuit Breker i/c Painting. | 9.5 | Sft. | @ | 1950 | P.Sft. | Rs. | 18525
8 | P/F Main Panel Board of 1/2" thick sheeting Double Shutter to Accommodate heavy duty circuit Breker i/c Painting with enammelled paint. | 5 | Sft. | @ | 2324 | P.Sft | Rs. | 11620
8 | S/F of pilot lamp (Neon sign) 200/240 volts fixing on a prepared i/c necessary connection as required. | 36 | Nos. | @ | 204 | P.No. | Rs. | 7344
|  |  | Total Part "B" |  |  |  | Rs. | 413505.26 |  | 845218.26
| GENARAL ABSTRACT | [8 empty] | 2523.0396
| Cost of Schedule Items Part "A" | Rs. | 531713
| Cost of Non-Schedule Items Part "B" | Rs. | 413505.26
| Grand Total | Rs. | 945218.26
CONTRACTOR
EXECUTIVE ENGINEER ELECTRICAL C EDUCATION WORKS
DIVISION HYDERABAD.