## SCHEDULE-B
NAME OF WORK:- UP-GRADATION OF BHU TO RHC AT KUNDA KHAHI DISTRICT NAUSHAHRO FEROZE
SCHEDULE-B
PART (A) FOUNDATION
S# | Item Of Work | Quantity | Rate | Unit | Amount
1 | Excavation in foundation of building bridges i/c dag belling dressing and refilling around the structure with excavated earth watering and ramming earth lead upto one chain and Lift upto 5"ft. S.I.No. 18 (b) P-04. | 41108.34 | 3176.25 | P%0Cft | 130570.3649
2 | Cement concrete brick or stone ballast 1 1/2"to 2" guage ratio 1:4:8. S.I.No. 4 (b) P-14. | 7707.8137 | 9416.28 | P%Cft | 725789.3246
3 | R.C.C work inroof slab beams coloums raft lintels and other structural member laid in situ or precast laid in position complete in all respects ratio (1:2:4) 90 Lbs cement 2 Cft sand 4 Cft shingle concrete 1/8" to 1/4:" guage S.I.No., 6(a) P. 16 | 7238.5 | 337 | P.Cft | 2439374.5
4 | Fabarication of mild steel reinforcement for cement concrete building cutting bending and laying in position making of joints and fastesting i/c cost of binding wire also i/c removal of rust from bars. S.I.No 8 (a) P 16. | 323.1473 | 5001.7 | P.Cwt | 1616285.9576
5 | Filling watering and ramming earth in floor with foundation lead upto one chain and lift upto 5"ft S.I.No. 21 P.04 | 27159 | 1512.5 | P%0Cft | 41077.9875
6 | Cement concrete plain 1/c placing compacting finishing and curring etc complete i/c screening and wahing of stone aggregate w/o shutteiring 1:3:6 S.I.No. 5(e) P-16 | 5658.91 | 12595 | P%Cft | 712739.7145
7 | Errection and removal of cenetering for RCC or pain CC work of partial wood (i) vertical S.I.No. 18(b) (ii) P- 18. | 12213.82 | 3127.41 | P%Sft | 381976.2281
8 | Filling watering and ramming earth in floor with foundation lead upto one chain and lift upto 5"ft Extra Lead S.I.No 22 P.No 04). | 16581.9119 | 11349 | P%0Cft | 188188.1182
9 | Supplying and fixing sand under floor and ploughing into walls S.I.No. 29. P.25 | 3323.7775 | 1141.25 | P%Cft | 37932.6107
10 | Cement concrete brick or stone ballast 1 1/2"to 2" guage ratio 1:5:10 S.I.No. 4 (b) P-15. | 2193.6932 | 8694.95 | P%Cft | 190740.5225
11 | Providing Anti- Termite by spraying / sprinkling / spreading nepture o.5% emulsion as an over all pre construction treatment in slab type constreuction under the slab and along attached perches or enternaces etc complete as per direction of Engineer Incharge S.I.No 92 P.71 | 6647.555 | 9.74 | P.Sft | 64747.1857
12 | pacca brick work in Foundation and plinth in cement sand mortor (1:6) S.I.No 4(e) P.No.25 ). | 1029 | 11948.36 | P%Cft | 122948.6244
|  |  |  | TOTAL | 6652371.1387
PART (B) GROUND FLOOR.
S# | Item Of Work | Quantity | Rate | Unit | Amount
1 | R.C.C work inroof slab beams coloums raft lintels and other structural member laid in situ or precast laid in position complete in all respects ratio (1:2:4) 90 Lbs cement 2 Cft sand 4 Cft shingle concrete 1/8" to 1/4:" guage S.I.No., 6(a) P. 16 | 7637.2812 | 337 | P.Cft | 2573763.7812
2 | Fabarication of mild steel reinforcement for cement concrete building cutting bending and laying in position making of joints and fastesting i/c cost of binding wire also i/c removal of rust from bars. S.I.No 8 (a) P 16. | 340.9501 | 5001.7 | P.Cwt | 1705329.8941
3 | pacca brick work in Ground floor in cement sdand mortor 1:6 S.I.No 5 (e) P.No. 21 ). | 6480.4688 | 12674.36 | P%Cft | 821357.9391
4 | Cement plaster 1:6 upto 12" Height 1/2" thick S.I.No. 13 (b) P-51 | 28559.53 | 2206.6 | P%Sft | 630194.589
5 | Cement plaster 1:6 upto 12" Height 3/8" thick S.I.No. 11 (a) P-51 | 28210.2 | 2197.52 | P%Sft | 619924.787
6 | Cement concrete plain 1/c placing compacting finishing and curring etc complete i/c screening and wahing of stone aggregate w/o shutteiring 1:2:4 S.I.No. 5(C) P-16 | 1259.9278 | 14429.25 | P%Cft | 181798.1321
7 | Laying floor of approved with glazed tiles 1/4" thick laid in white cement and pigment on a bend of 3/4" thick cement mortor 1:2 ( S.I.No 25 P.No 42 | 6249.51 | 27747.06 | P%Sft | 1734055.2894
8 | glazed tiles dado 1/4" thick laid in pigment over 1:2 cement sand mortor 3/4" thick i/.c finishing S.I. No 38 P.No 44 | 1807.5 | 28299.3 | P%Sft | 511509.8475
9 | Laying white marble floor fine dressed on the surface with out winding set in lime mortor 1:2 i/c rubbling and polishing iof the joints 3/4" thick i/c finishing S.I.No 28 P.No 42 | 1161.83 | 567.48 | P.Sft | 659315.2884
10 | P/F 3/8" thick marbel tiles of approved quality & Colour shade size 8x4" 6x4" in dado skirting & facing removsal/ tucking of existin gplaster surface etc over 1/2" thick base of white cement over mortor base i/c filling of the joints ans washing the tiles with cement sand slury current finishing and cleaning and polishing etc complete for new works S.IO.No. 68 P.48. | 111.455 | 186.04 | P.Sft | 20735.0882
11 | P/F G.I frames / chowkts of size 7x2" 4x1/2x3" for doors uusing 20 gauge G.i sheet i/cwelded hinges and fixing at site with necessary holds fats filling with cement sands slury of ratio 1:6 and reparing the jambs the cost of also i/c all carriage of tools and plants are used in making and fixing S.I.No. 28 P.92 | 610 | 228.9 | P.Rft | 139629
12 | P/F G.I frames / chowkts of size 7x2" 4x1/2x3" for windows uusing 20 gauge G.i sheet i/cwelded hinges and fixing at site with necessary holds fats filling with cement sands slury of ratio 1:6 and reparing the jambs the cost of also i/c all carriage of tools and plants are used in making and fixing S.I.No. 29 P.92 | 931 | 240.5 | P.Rft | 223905.5
13 | First class deodar wood wrought joinary in doors and windows etc fixed in position i/c chowkts holds fasts hinges iron tower bolts chocks cleats handles & cords with hook etc complete deodar panneled glazed or fully glazed.S.I.No. 7 (b) P-57 | 1309.5 | 902.93 | P.Sft | 1182386.835
14 | Providing and fixing ironsteel grill using solid square bars of size 1/2"x1/2" placed at4" i/c and frame of flat iron patti 3/4"x3/4" i/c circle shape at 1-0 apart equivalent fited with screws are pins i/c apinting 3 coats with Isrt coat of red oxide paint etc S.I.No. 30 . P. 93. | 567 | 194.16 | P.Sft | 110088.72
15 | First class deodar wood worught joinary work in wire gauzed door and windows with 22 S.W.G Glavinized wire gauzed 144 mesh per sq inch iron fitting complete (d) Glavinized wire gauzed fixed to chowkts with 3/4" striops and screws S.I.No 14 (d) P.58 ). | 567 | 190.72 | P.Sft | 108138.24
16 | Primary coat of chalk under distemper S.I.No. 23 P.No. 60 | 7411.34 | 442.75 | P%Sft | 32813.7078
17 | Distempering of walls any type three coats S.I.No. 24 © P.53 | 7411.34 | 1079.65 | P%Sft | 80016.5323
18 | Preparing the surface and painting with Matt finishing/c rubbling the surface with rubbing brick / sand paper filling the coids with chalk/ plaster of paris and then painting with matt finishing of approved make S.I.No 38 P.No 56 | 22607.76 | 3444.38 | P%Sft | 778697.1639
18 | Preparing the surface and painting with weather coat i/c rubbling the surface with rubbing brick / sand paper filling the coids with chalk/ plaster of paris and then painting with weather coat of approved make S.I.No 38 P.No 56 | 5602.44 | 2567.95 | P%Sft | 143867.858
19 | Preparing durface and painting of doors and windows any type i/c edges three coats S.I.No. 5 (c) P.69. | 2619 | 2116.41 | P%Sft | 55428.7779
20 | S/F in position Aluminium channles framing for hinged doors or Alcop made with 5 mm thick tinted glass glazed ( Belgium) and Alpha ( japan) locks i/c handles stoppers etc (b) Deluxe Model ) ( Brozone) S.I.No 84 (b) P. 107 | 136 | 1507.66 | P.Sft | 205041.76
21 | S/F in position Aluminium channles framing for hinged windows or Alcop made with 5 mm thick tinted glass glazed ( Belgium) and Alpha ( japan) locks i/c handles stoppers etc (b) Deluxe Model ) ( Brozone) S.I.No 84 (b) P. 107 | 50 | 1647.69 | P.Sft | 82384.5
24 | hard wood Railing of amny shape & design i/c bends & corners fixed in position i/c polishing complete as directed (a) teak wood S.I.No 30 (a) P.No 62 | 260 | 375.78 | P.Rft | 97702.8
|  |  | TOTAL |  | 12698086.031
PART (C) FIRST FLOOR.
S# | Item Of Work | Quantity | Rate | Unit | Amount
1 | R.C.C work inroof slab beams coloums raft lintels and other structural member laid in situ or precast laid in position complete in all respects ratio (1:2:4) 90 Lbs cement 2 Cft sand 4 Cft shingle concrete 1/8" to 1/4:" guage S.I.No., 6(a) P. 16 | 7591.7188 | 337 | P.Cft | 2558409.2188
2 | Fabarication of mild steel reinforcement for cement concrete building cutting bending and laying in position making of joints and fastesting i/c cost of binding wire also i/c removal of rust from bars. S.I.No 8 (a) P 16. | 338.916 | 5001.7 | P.Cwt | 1695156.2354
3 | pacca brick work in First floor in cement sdand mortor 1:6 S.I.No 5 (e) P.No. 21 ). | 6351.375 | 12674.36 | P%Cft | 804996.1325
4 | Cement plaster 1:6 upto 12" Height 1/2" thick S.I.No. 13 (b) P-51 | 27026.19 | 2206.6 | P%Sft | 596359.9085
5 | Cement plaster 1:6 upto 12" Height 3/8" thick S.I.No. 11 (a) P-51 | 24868.19 | 2197.52 | P%Sft | 546483.4489
6 | Cement concrete plain 1/c placing compacting finishing and curring etc complete i/c screening and wahing of stone aggregate w/o shutteiring 1:2:4 S.I.No. 5(C) P-16 | 1524.395 | 14429.25 | P%Cft | 219958.7655
7 | Laying floor of approved with glazed tiles 1/4" thick laid in white cement and pigment on a bend of 3/4" thick cement mortor 1:2 ( S.I.No 25 P.No 42 | 4772.5 | 27747.06 | P%Sft | 1324228.4385
8 | glazed tiles dado 1/4" thick laid in pigment over 1:2 cement sand mortor 3/4" thick i/.c finishing S.I. No 38 P.No 44 | 1678 | 28299.3 | P%Sft | 474862.254
9 | Laying white marble floor fine dressed on the surface with out winding set in lime mortor 1:2 i/c rubbling and polishing iof the joints 3/4" thick i/c finishing S.I.No 28 P.No 42 | 1851 | 567.48 | P.Sft | 1050405.48
10 | P/F 3/8" thick marbel tiles of approved quality & Colour shade size 8x4" 6x4" in dado skirting & facing removsal/ tucking of existin gplaster surface etc over 1/2" thick base of white cement over mortor base i/c filling of the joints ans washing the tiles with cement sand slury current finishing and cleaning and polishing etc complete for new works S.IO.No. 68 P.48. | 191.125 | 186.04 | P.Sft | 35556.895
11 | P/F G.I frames / chowkts of size 7x2" 4x1/2x3" for doors uusing 20 gauge G.i sheet i/cwelded hinges and fixing at site with necessary holds fats filling with cement sands slury of ratio 1:6 and reparing the jambs the cost of also i/c all carriage of tools and plants are used in making and fixing S.I.No. 28 P.92 | 610 | 228.9 | P.Rft | 139629
12 | P/F G.I frames / chowkts of size 7x2" 4x1/2x3" for windows uusing 20 gauge G.i sheet i/cwelded hinges and fixing at site with necessary holds fats filling with cement sands slury of ratio 1:6 and reparing the jambs the cost of also i/c all carriage of tools and plants are used in making and fixing S.I.No. 29 P.92 | 931 | 240.5 | P.Rft | 223905.5
13 | First class deodar wood wrought joinary in doors and windows etc fixed in position i/c chowkts holds fasts hinges iron tower bolts chocks cleats handles & cords with hook etc complete deodar panneled glazed or fully glazed.S.I.No. 7 (b) P-57 | 1309.5 | 902.93 | P.Sft | 1182386.835
14 | Providing and fixing ironsteel grill using solid square bars of size 1/2"x1/2" placed at4" i/c and frame of flat iron patti 3/4"x3/4" i/c circle shape at 1-0 apart equivalent fited with screws are pins i/c apinting 3 coats with Isrt coat of red oxide paint etc S.I.No. 30 . P. 93. | 567 | 194.16 | P.Sft | 110088.72
15 | First class deodar wood worught joinary work in wire gauzed door and windows with 22 S.W.G Glavinized wire gauzed 144 mesh per sq inch iron fitting complete (d) Glavinized wire gauzed fixed to chowkts with 3/4" striops and screws S.I.No 14 (d) P.58 ). | 567 | 190.72 | P.Sft | 108138.24
16 | Primary coat of chalk under distemper S.I.No. 23 P.No. 60 | 6623.5 | 442.75 | P%Sft | 29325.5462
17 | Distempering of walls any type three coats S.I.No. 24 © P.53 | 6623.5 | 1079.65 | P%Sft | 71510.6178
18 | Preparing the surface and painting with Matt finishing/c rubbling the surface with rubbing brick / sand paper filling the coids with chalk/ plaster of paris and then painting with matt finishing of approved make S.I.No 38 P.No 56 | 20988.25 | 3444.38 | P%Sft | 722915.0853
18 | Preparing the surface and painting with weather coat i/c rubbling the surface with rubbing brick / sand paper filling the coids with chalk/ plaster of paris and then painting with weather coat of approved make S.I.No 38 P.No 56 | 5602.44 | 2567.95 | P%Sft | 143867.858
19 | Preparing durface and painting of doors and windows any type i/c edges three coats S.I.No. 5 (c) P.69. | 2619 | 2116.41 | P%Sft | 55428.7779
20 | S/F in position Aluminium channles framing for hinged doors or Alcop made with 5 mm thick tinted glass glazed ( Belgium) and Alpha ( japan) locks i/c handles stoppers etc (b) Deluxe Model ) ( Brozone) S.I.No 84 (b) P. 107 | 136 | 1507.66 | P.Sft | 205041.76
21 | S/F in position Aluminium channles framing for hinged windows or Alcop made with 5 mm thick tinted glass glazed ( Belgium) and Alpha ( japan) locks i/c handles stoppers etc (b) Deluxe Model ) ( Brozone) S.I.No 84 (b) P. 107 | 49.5 | 1647.69 | P.Sft | 81560.655
24 | hard wood Railing of amny shape & design i/c bends & corners fixed in position i/c polishing complete as directed (a) teak wood S.I.No 30 (a) P.No 62 | 260 | 375.78 | P.Rft | 97702.8
25 | CCToping 1-1/2" thick i/c surface finishing and dividing in to panals | 7796.6875 | 2548.29 | P%sft | 198682.2079
26 | Two coats of bitumin | 7796.6875 | 1887.4 |  | 147154.6799
|  |  | TOTAL |  | 12823755.06
| CONTRACTOR | Executive Engineer
Provincial Buildings Division
Shaheed Benazir Abad

## Foundation Measrment (hidden)
NAME OF WORK:- UP-GRADATION OF BHU TO RHC AT KUNDA KHAHI DISTRICT NAUSHAHRO FEROZE
PART (A) FOUNDATION ( Measurement Shet ).
S# | Item Of Work | No | length | Bredth | Height | Quantity
Part (A) Foundation
1 | Excavation in foundation of building bridges i/c dag belling dressing and refilling around the structure with excavated earth watering and ramming earth lead upto one chain and Lift upto 5"ft. S.I.No. 18 (b) P-04.
|  | 1 | 132.5 | 54.25 | 4 | 28752.5
|  | 1 | 20 | 17 | 4 | 1360
|  | 1 | 51.75 | 53.12 | 4 | 10995.84
[5 empty] | TOTAL | 41108.34
2 | Cement concrete brick or stone ballast 1 1/2"to 2" guage ratio 1:4:8 S.I.No P.No.
|  | 1 | 132.5 | 54.25 | 0.75 | 5391.0938
|  | 1 | 20 | 17 | 0.75 | 255
|  | 1 | 51.75 | 53.12 | 0.75 | 2061.72
[5 empty] | TOTAL | 7707.8137
3 | R.C.C work inroof slab beams coloums raft lintels and other structural member laid in situ or precast laid in position complete in all respects ratio (1:2:4) 90 Lbs cement 2 Cft sand 4 Cft shingle concrete 1/8" to 1/4:" guage S.I.No., 6(a) P. 16
FOOTING
| F1. | 1 | 4 | 4 | 1.5 | 24
| F2. | 5 | 6 | 6 | 1.5 | 270
| F3. | 13 | 6.5 | 6.5 | 1.5 | 823.875
| F4. | 23 | 7 | 7 | 1.5 | 1690.5
| F5. | 16 | 7.5 | 7.5 | 1.5 | 1350
| F6. | 2 | 8 | 8 | 1.5 | 192
| CF1 | 3 | 12 | 6 | 1.5 | 324
| CF2 | 1 | 14 | 5.5 | 1.5 | 115.5
[5 empty] | TOTAL | 4789.875
C Coloum Upto Plinth Beam'
| PC1 | 50 | 1 | 1.75 | 3.5 | 306.25
| PC2 | 18 | 1 | 2.25 | 3.5 | 141.75
[5 empty] | TOTAL | 448
Plinth Beam
(A) Horizental Walls
| F/S Surgeon to Dental & Const to Const (PB-2) | 2 | 36.25 | 1 | 1.5 | 108.75
| Waiting Hall (PB-9) | 2 | 39.25 | 1 | 1.5 | 117.75
| Male& Female Ent: i/I (PB-9) | 2 | 13.75 | 1 | 1.5 | 41.25
| Stair case I/I (PB-9) | 1 | 11.75 | 1 | 1.5 | 17.625
| V/Side. Bath to Bath (PB-4) | 1 | 126.5 | 1 | 1.5 | 189.75
| Bath to Ver: B/Side (PB-3) I/O | 1 | 43.13 | 1 | 1.5 | 64.695
| Pharmacy Hall O/O (PB-8) | 1 | 13.75 | 1 | 1.5 | 20.625
| WMO to Bath O/O (PB-2) | 1 | 35.25 | 1 | 1.5 | 52.875
| Emargency i/I (PB-10) | 1 | 15.75 | 1 | 1.5 | 23.625
| Store O/O (PB-8) | 1 | 13.75 | 1 | 1.5 | 20.625
| Lav: O/O (PB-10) | 1 | 17.75 | 1 | 1.5 | 26.625
| Store TO Lav: O/O (PB-1) | 1 | 66 | 1 | 1.5 | 99
| X-Ray & Lab: O/O (PB-9) | 2 | 15.75 | 1 | 1.5 | 47.25
| Dark Room.I/I (PB-8) | 1 | 11.75 | 1 | 1.5 | 17.625
| Dark room 1/1 (PB-8) | 1 | 5.62 | 1 | 1.5 | 8.43
| X-Ray & Lab: O/O (PB-2) | 1 | 43.25 | 1 | 1.5 | 64.875
| Store B/Side (PB-5) | 1 | 20.5 | 1 | 1.5 | 30.75
Vertical Walls.
| Surgeon MO Dental (PB-10) | 8 | 15.75 | 1 | 1.5 | 189
| Stair case I/I (PB-5) | 2 | 25 | 1 | 1.5 | 75
| Ver: i/I (PB-5) | 2 | 11.75 | 1 | 1.5 | 35.25
| Bath to Bath i/I (PB-10) | 8 | 15.75 | 1 | 1.5 | 189
| Bath Partician i/I (PB-8) | 2 | 9.75 | 1 | 1.5 | 29.25
| Bath Partician i/I (PB-8) | 2 | 10 | 1 | 1.5 | 30
| Bath Partician i/I (PB-8) | 2 | 5.25 | 1 | 1.5 | 15.75
| Emergency to Store i/I (PB-6) | 1 | 33.25 | 1 | 1.5 | 49.875
| Emergency to Store i/I (PB-2) | 1 | 33.25 | 1 | 1.5 | 49.875
| Store & Pharmacy i/I (PB-7) | 1 | 33.25 | 1 | 1.5 | 49.875
| Store & Pharmacy i/I (PB-2) | 1 | 33.25 | 1 | 1.5 | 49.875
| lav: i/I (PB-8) | 1 | 5.75 | 1 | 1.5 | 8.625
| Lav: (PB-8) | 2 | 10.25 | 1 | 1.5 | 30.75
| Lav: (PB-8) | 1 | 15.75 | 1 | 1.5 | 23.625
| Lav: (PB-8) | 2 | 5.75 | 1 | 1.5 | 17.25
| Waiting to X-Ray i/I (PB-6) | 1 | 28.5 | 1 | 1.5 | 42.75
| Waiting to X-Ray i/I (PB-3) | 1 | 28.5 | 1 | 1.5 | 42.75
| Waiting to X-Ray i/I (PB-7) | 1 | 28.5 | 1 | 1.5 | 42.75
| Waiting to X-Ray i/I (PB-5) | 1 | 28.5 | 1 | 1.5 | 42.75
| Store B/Side (PB-3,7,8) | 4 | 5.75 | 1 | 1.5 | 34.5
[5 empty] | TOTAL | 2000.625
| Net: Total : (A+B+C) |  |  |  |  | 7238.5
4 | Fabarication of mild steel reinforcement for cement concrete building cutting bending and laying in position making of joints and fastesting i/c cost of binding wire also i/c removal of rust from bars. S.I.No 8 (a) P 16.
| Same Qty of item Mno (3) as above |  | 7239x5/112 |  |  | 323.1473
[5 empty] | TOTAL | 323.1473
5 | Filling watering and ramming earth under floor weith new earth excavbatyed from out side l;ead upto one chain and lift upto 5" ft S.I.No P.No.
|  |  | 41108.34 | X2/3 |  | 27405.56
[5 empty] | TOTAL | 27159
6 | C.C Plain (1:2:4) i/c placing compacting and finishing and curring complete i/c screening and washing of stone aggregate w/o shuttering S . I.No P.No.
1ST STEP
(A) Horizental Walls
| F/S Surgeon to Dental & Const to Const (PB-2) | 4 | 4.75 | 1.5 | 1.5 | 42.75
| F/S Surgeon to Dental & Const to Const (PB-2) | 2 | 5.25 | 1.5 | 1.5 | 23.625
| Waiting Hall (PB-9) | 2 | 4.5 | 1.5 | 1.5 | 20.25
| Waiting Hall (PB-9) | 2 | 4.25 | 1.5 | 1.5 | 19.125
| Waiting Hall (PB-9) | 2 | 7.25 | 1.5 | 1.5 | 32.625
| Male& Female Ent: i/I (PB-9) | 2 | 10.75 | 1.5 | 1.5 | 48.375
| Stair case I/I (PB-9) | 1 | 4.25 | 1.5 | 1.5 | 9.5625
| V/Side. Bath to Bath (PB-4) | 2 | 3.5 | 1.5 | 1.5 | 15.75
| V/Side. Bath to Bath (PB-4) | 2 | 4.25 | 1.5 | 1.5 | 19.125
| V/Side. Bath to Bath (PB-4) | 2 | 4.75 | 1.5 | 1.5 | 21.375
| V/Side. Bath to Bath (PB-4) | 1 | 0.25 | 1.5 | 1.5 | 0.5625
| V/Side. Bath to Bath (PB-4) | 1 | 4.25 | 1.5 | 1.5 | 9.5625
| V/Side. Bath to Bath (PB-4) | 1 | 4 | 1.5 | 1.5 | 9
| V/Side. Bath to Bath (PB-4) | 1 | 9.75 | 1.5 | 1.5 | 21.9375
| V/Side. Bath to Bath (PB-4) | 1 | 2.25 | 1.5 | 1.5 | 5.0625
| V/Side. Bath to Bath (PB-4) | 2 | 4 | 1.5 | 1.5 | 18
| Bath to Ver: B/Side (PB-3) I/O | 2 | 4.75 | 1.5 | 1.5 | 21.375
| Bath to Ver: B/Side (PB-3) I/O | 1 | 5 | 1.5 | 1.5 | 11.25
| Bath to Ver: B/Side (PB-3) I/O | 1 | 3.5 | 1.5 | 1.5 | 7.875
| Bath to Ver: B/Side (PB-3) I/O | 1 | 5.25 | 1.5 | 1.5 | 11.8125
| Pharmacy Hall O/O (PB-8) | 1 | 5 | 1.5 | 1.5 | 11.25
| Emargency i/I (PB-10) | 1 | 10.25 | 1.5 | 1.5 | 23.0625
| Lav: O/O (PB-10) | 1 | 10.75 | 1.5 | 1.5 | 24.1875
| Lav: O/O (PB-10) | 1 | 9.75 | 1.5 | 1.5 | 21.9375
| Store TO Lav: O/O (PB-1) | 1 | 6.75 | 1.5 | 1.5 | 15.1875
| X-Ray & Lab: O/O (PB-9) | 1 | 9.25 | 1.5 | 1.5 | 20.8125
| X-Ray & Lab: O/O (PB-9) | 1 | 9.75 | 1.5 | 1.5 | 21.9375
| Dark room 1/1 (PB-8) | 1 | 5.62 | 1.5 | 1.5 | 12.645
| X-Ray & Lab: O/O (PB-2) | 1 | 12 | 1.5 | 1.5 | 27
| Store B/Side (PB-5) | 2 | 7.5 | 1.5 | 1.5 | 33.75
| Store B/Side (PB-5) | 1 | 7.25 | 1.5 | 1.5 | 16.3125
| Store B/Side (PB-5) | 2 | 8.25 | 1.5 | 1.5 | 37.125
| Store B/Side (PB-5) | 1 | 6.75 | 1.5 | 1.5 | 15.1875
| Store B/Side (PB-5) | 1 | 0.75 | 1.5 | 1.5 | 1.6875
Vertical Walls.
| Surgeon MO Dental (PB-10) | 8 | 10 | 1.5 | 1.5 | 180
| Stair case I/I (PB-5) | 2 | 5.42 | 1.5 | 1.5 | 24.39
| Ver: i/I (PB-5) | 4 | 5.5 | 1.5 | 1.5 | 49.5
| Bath to Bath i/I (PB-10) | 8 | 9.5 | 1.5 | 1.5 | 171
| Bath Partician i/I (PB-8) | 2 | 7.75 | 1.5 | 1.5 | 34.875
| Bath Partician i/I (PB-8) | 2 | 7.75 | 1.5 | 1.5 | 34.875
| Bath Partician i/I (PB-8) | 2 | 2.75 | 1.5 | 1.5 | 12.375
| Emergency to Store i/I (PB-6) | 1 | 4.25 | 1.5 | 1.5 | 9.5625
| Emergency to Store i/I (PB-2) | 1 | 3.25 | 1.5 | 1.5 | 7.3125
| Emergency to Store i/I (PB-6) | 1 | 4.75 | 1.5 | 1.5 | 10.6875
| Emergency to Store i/I (PB-6) | 2 | 4.25 | 1.5 | 1.5 | 19.125
| Store & Pharmacy i/I (PB-7) | 1 | 7.25 | 1.5 | 1.5 | 16.3125
| Store & Pharmacy i/I (PB-2) | 2 | 7.75 | 1.5 | 1.5 | 34.875
| Store & Pharmacy i/I (PB-2) | 1 | 4.25 | 1.5 | 1.5 | 9.5625
| Store & Pharmacy i/I (PB-2) | 1 | 4.75 | 1.5 | 1.5 | 10.6875
| Lav: (PB-8) | 1 | 5.25 | 1.5 | 1.5 | 11.8125
| Lav: (PB-8) | 1 | 4.75 | 1.5 | 1.5 | 10.6875
| Waiting to X-Ray i/I (PB-6) | 1 | 3.75 | 1.5 | 1.5 | 8.4375
| Waiting to X-Ray i/I (PB-3) | 1 | 4.25 | 1.5 | 1.5 | 9.5625
| Waiting to X-Ray i/I (PB-7) | 1 | 3.75 | 1.5 | 1.5 | 8.4375
| Waiting to X-Ray i/I (PB-5) | 1 | 3.5 | 1.5 | 1.5 | 7.875
| Waiting to X-Ray i/I (PB-5) | 1 | 5 | 1.5 | 1.5 | 11.25
| Waiting to X-Ray i/I (PB-5) | 1 | 5.5 | 1.5 | 1.5 | 12.375
| Waiting to X-Ray i/I (PB-5) | 2 | 11.5 | 1.5 | 1.5 | 51.75
| Waiting to X-Ray i/I (PB-5) | 2 | 4.5 | 1.5 | 1.5 | 20.25
| Store B/Side (PB-5) | 2 | 2.25 | 1.5 | 1.5 | 10.125
2ND STEP
(A) Horizental Walls
| F/S Surgeon to Dental & Const to Const (PB-2) | 2 | 36.25 | 1 | 3.5 | 253.75
| Waiting Hall (PB-9) | 2 | 39.25 | 1 | 3.5 | 274.75
| Male& Female Ent: i/I (PB-9) | 2 | 13.75 | 1 | 3.5 | 96.25
| Stair case I/I (PB-9) | 1 | 11.75 | 1 | 3.5 | 41.125
| V/Side. Bath to Bath (PB-4) | 1 | 126.5 | 1 | 3.5 | 442.75
| Bath to Ver: B/Side (PB-3) I/O | 1 | 43.13 | 1 | 3.5 | 150.955
| Pharmacy Hall O/O (PB-8) | 1 | 13.75 | 1 | 3.5 | 48.125
| WMO to Bath O/O (PB-2) | 1 | 35.25 | 1 | 3.5 | 123.375
| Emargency i/I (PB-10) | 1 | 15.75 | 1 | 3.5 | 55.125
| Store O/O (PB-8) | 1 | 13.75 | 1 | 3.5 | 48.125
| Lav: O/O (PB-10) | 1 | 17.75 | 1 | 3.5 | 62.125
| Store TO Lav: O/O (PB-1) | 1 | 66 | 1 | 3.5 | 231
| X-Ray & Lab: O/O (PB-9) | 2 | 15.75 | 1 | 3.5 | 110.25
| Dark Room.I/I (PB-8) | 1 | 11.75 | 1 | 3.5 | 41.125
| Dark room 1/1 (PB-8) | 1 | 5.62 | 1 | 3.5 | 19.67
| X-Ray & Lab: O/O (PB-2) | 1 | 43.25 | 1 | 3.5 | 151.375
| Store B/Side (PB-5) | 1 | 20.5 | 1 | 3.5 | 71.75
| Vertical Walls. |  |  |  | 3.5
| Surgeon MO Dental (PB-10) | 8 | 15.75 | 1 | 3.5 | 441
| Stair case I/I (PB-5) | 2 | 25 | 1 | 3.5 | 175
| Ver: i/I (PB-5) | 2 | 11.75 | 1 | 3.5 | 82.25
| Bath to Bath i/I (PB-10) | 8 | 15.75 | 1 | 3.5 | 441
| Bath Partician i/I (PB-8) | 2 | 9.75 | 1 | 3.5 | 68.25
| Bath Partician i/I (PB-8) | 2 | 10 | 1 | 3.5 | 70
| Bath Partician i/I (PB-8) | 2 | 5.25 | 1 | 3.5 | 36.75
| Emergency to Store i/I (PB-6) | 1 | 33.25 | 1 | 3.5 | 116.375
| Emergency to Store i/I (PB-2) | 1 | 33.25 | 1 | 3.5 | 116.375
| Store & Pharmacy i/I (PB-7) | 1 | 33.25 | 1 | 3.5 | 116.375
| Store & Pharmacy i/I (PB-2) | 1 | 33.25 | 1 | 3.5 | 116.375
| lav: i/I (PB-8) | 1 | 5.75 | 1 | 3.5 | 20.125
| Lav: (PB-8) | 2 | 10.25 | 1 | 3.5 | 71.75
| Lav: (PB-8) | 1 | 15.75 | 1 | 3.5 | 55.125
| Lav: (PB-8) | 2 | 5.75 | 1 | 3.5 | 40.25
| Waiting to X-Ray i/I (PB-6) | 1 | 28.5 | 1 | 3.5 | 99.75
| Waiting to X-Ray i/I (PB-3) | 1 | 28.5 | 1 | 3.5 | 99.75
| Waiting to X-Ray i/I (PB-7) | 1 | 28.5 | 1 | 3.5 | 99.75
| Waiting to X-Ray i/I (PB-5) | 1 | 28.5 | 1 | 3.5 | 99.75
| Store B/Side (PB-3,7,8) | 4 | 5.75 | 1 | 3.5 | 80.5
[5 empty] | TOTAL. | 6106.91
Deduction
| PC1 | 50 | 1 | 1.75 | 3.5 | 306.25
| PC2 | 18 | 1 | 2.25 | 3.5 | 141.75
[5 empty] | TOTAL | 448
|  |  |  | Net Qty A-B= |  | 5658.91
7 | Errection and removal of cenetering of RCC S.I.No P.No.,
|  |  | 5658.91 | X2= |  | 11317.82
[5 empty] | TOTAL. | 12213.82
8 | Filling watering and ramming earth under floor weith new earth excavbatyed from out side l;ead upto one chain and lift upto 5" ft S.I.No P.No.
| surgeon mo Dental | 6 | 10.75 | 15.75 | 6.58 | 6684.4575
| Consulting., WMO | 4 | 10.75 | 15.75 | 6.58 | 4456.305
| Emergency | 1 | 15.75 | 21.5 | 6.58 | 2228.1525
| Store | 1 | 5 | 10.75 | 6.58 | 353.675
| MOT | 1 | 9.75 | 10.75 | 6.58 | 689.6662
| Store | 1 | 11.75 | 9.75 | 6.58 | 753.8212
| Pharmacy Hall O/O (PB-8) | 1 | 11.75 | 13.75 | 6.58 | 1063.0812
| Waiting | 1 | 13.75 | 9.75 | 6.58 | 882.1313
| X-Ray | 1 | 13.75 | 17.75 | 6.58 | 1605.9313
| Dark Room | 1 | 5.75 | 9.75 | 6.58 | 368.8913
| Store | 1 | 5.75 | 9.75 | 6.58 | 368.8913
| " | 1 | 12 | 5.75 | 6.58 | 454.02
| Lab. | 1 | 13.75 | 17.75 | 6.58 | 1605.9313
| Rec/Tech: | 1 | 9.75 | 13.75 | 6.58 | 882.1312
| M& Female Ent: | 2 | 13.75 | 22.75 | 6.58 | 4116.6125
| Bath | 4 | 5.25 | 4.75 | 6.58 | 656.355
| " | 2 | 9.75 | 4.75 | 6.58 | 609.4725
| Lav: | 2 | 3.75 | 9.75 | 6.58 | 481.1625
| Lav: | 1 | 15.75 | 9.75 | 6.58 | 1010.4412
| Stair Case | 1 | 11.75 | 22.75 | 6.58 | 1758.9162
| Ver: | 2 | 38 | 11.75 | 6.58 | 5875.94
| Ver | 1 | 15.75 | 7.75 | 6.58 | 803.1712
| Ver: | 1 | 33.25 | 9.75 | 6.58 | 2133.1537
| " | 1 | 24.5 | 6 | 6.58 | 967.26
| " | 1 | 18 | 7.75 | 6.58 | 917.91
| Ent: | 1 | 11.75 | 18.25 | 6.58 | 1410.9988
| Passage | 1 | 5 | 9.25 | 6.58 | 304.325
| Lav.` | 2 | 5.33 | 4.25 | 6.58 | 298.1069
[5 empty] | TOTAL,. | 43740.9119
| Same Qty of item No (5) as above |  |  |  | TOTAL | 27159
|  |  |  | Net: Qty: (A) (-) (B) |  | 16581.9119
9 | Supplying and fixing sand undere floor and ploughing into walls S.I.No P.No.,
| surgeon mo Dental | 6 | 10.75 | 15.75 | 0.5 | 507.9375
| Consulting., WMO | 4 | 10.75 | 15.75 | 0.5 | 338.625
| Emergency | 1 | 15.75 | 21.5 | 0.5 | 169.3125
| Store | 1 | 5 | 10.75 | 0.5 | 26.875
| MOT | 1 | 9.75 | 10.75 | 0.5 | 52.4062
| Store | 1 | 11.75 | 9.75 | 0.5 | 57.2812
| Pharmacy Hall O/O (PB-8) | 1 | 11.75 | 13.75 | 0.5 | 80.7812
| Waiting | 1 | 13.75 | 9.75 | 0.5 | 67.0312
| X-Ray | 1 | 13.75 | 17.75 | 0.5 | 122.0312
| Dark Room | 1 | 5.75 | 9.75 | 0.5 | 28.0312
| Store | 1 | 5.75 | 9.75 | 0.5 | 28.0312
| " | 1 | 12 | 5.75 | 0.5 | 34.5
| Lab. | 1 | 13.75 | 17.75 | 0.5 | 122.0312
| Rec/Tech: | 1 | 9.75 | 13.75 | 0.5 | 67.0312
| M& Female Ent: | 2 | 13.75 | 22.75 | 0.5 | 312.8125
| Bath | 4 | 5.25 | 4.75 | 0.5 | 49.875
| " | 2 | 9.75 | 4.75 | 0.5 | 46.3125
| Lav: | 2 | 3.75 | 9.75 | 0.5 | 36.5625
| Lav: | 1 | 15.75 | 9.75 | 0.5 | 76.7812
| Stair Case | 1 | 11.75 | 22.75 | 0.5 | 133.6562
| Ver: | 2 | 38 | 11.75 | 0.5 | 446.5
| Ver | 1 | 15.75 | 7.75 | 0.5 | 61.0312
| Ver: | 1 | 33.25 | 9.75 | 0.5 | 162.0938
| " | 1 | 24.5 | 6 | 0.5 | 73.5
| " | 1 | 18 | 7.75 | 0.5 | 69.75
| Ent: | 1 | 11.75 | 18.25 | 0.5 | 107.2188
| Passage | 1 | 5 | 9.25 | 0.5 | 23.125
| Lav.` | 2 | 5.33 | 4.25 | 0.5 | 22.6525
[5 empty] | TOTAL> | 3323.7775
10 | Cement concrete brick or stone ballast 1 1/2"to 2" guage ratio 1:5:10 S.I.No P.No.
| surgeon mo Dental | 6 | 10.75 | 15.75 | 0.33 | 335.2388
| Consulting., WMO | 4 | 10.75 | 15.75 | 0.33 | 223.4925
| Emergency | 1 | 15.75 | 21.5 | 0.33 | 111.7463
| Store | 1 | 5 | 10.75 | 0.33 | 17.7375
| MOT | 1 | 9.75 | 10.75 | 0.33 | 34.5881
| Store | 1 | 11.75 | 9.75 | 0.33 | 37.8056
| Pharmacy Hall O/O (PB-8) | 1 | 11.75 | 13.75 | 0.33 | 53.3156
| Waiting | 1 | 13.75 | 9.75 | 0.33 | 44.2406
| X-Ray | 1 | 13.75 | 17.75 | 0.33 | 80.5406
| Dark Room | 1 | 5.75 | 9.75 | 0.33 | 18.5006
| Store | 1 | 5.75 | 9.75 | 0.33 | 18.5006
| " | 1 | 12 | 5.75 | 0.33 | 22.77
| Lab. | 1 | 13.75 | 17.75 | 0.33 | 80.5406
| Rec/Tech: | 1 | 9.75 | 13.75 | 0.33 | 44.2406
| M& Female Ent: | 2 | 13.75 | 22.75 | 0.33 | 206.4563
| Bath | 4 | 5.25 | 4.75 | 0.33 | 32.9175
| " | 2 | 9.75 | 4.75 | 0.33 | 30.5663
| Lav: | 2 | 3.75 | 9.75 | 0.33 | 24.1313
| Lav: | 1 | 15.75 | 9.75 | 0.33 | 50.6756
| Stair Case | 1 | 11.75 | 22.75 | 0.33 | 88.2131
| Ver: | 2 | 38 | 11.75 | 0.33 | 294.69
| Ver | 1 | 15.75 | 7.75 | 0.33 | 40.2806
| Ver: | 1 | 33.25 | 9.75 | 0.33 | 106.9819
| " | 1 | 24.5 | 6 | 0.33 | 48.51
| " | 1 | 18 | 7.75 | 0.33 | 46.035
| Ent: | 1 | 11.75 | 18.25 | 0.33 | 70.7644
| Passage | 1 | 5 | 9.25 | 0.33 | 15.2625
| Lav.` | 2 | 5.33 | 4.25 | 0.33 | 14.9507
[5 empty] | TOTAL. | 2193.6932
11 | Providing Anti- termite Treatment by spraying / sprinkling
| surgeon mo Dental | 6 | 10.75 | 15.75 |  | 1015.875
| Consulting., WMO | 4 | 10.75 | 15.75 |  | 677.25
| Emergency | 1 | 15.75 | 21.5 |  | 338.625
| Store | 1 | 5 | 10.75 |  | 53.75
| MOT | 1 | 9.75 | 10.75 |  | 104.8125
| Store | 1 | 11.75 | 9.75 |  | 114.5625
| Pharmacy Hall O/O (PB-8) | 1 | 11.75 | 13.75 |  | 161.5625
| Waiting | 1 | 13.75 | 9.75 |  | 134.0625
| X-Ray | 1 | 13.75 | 17.75 |  | 244.0625
| Dark Room | 1 | 5.75 | 9.75 |  | 56.0625
| Store | 1 | 5.75 | 9.75 |  | 56.0625
| " | 1 | 12 | 5.75 |  | 69
| Lab. | 1 | 13.75 | 17.75 |  | 244.0625
| Rec/Tech: | 1 | 9.75 | 13.75 |  | 134.0625
| M& Female Ent: | 2 | 13.75 | 22.75 |  | 625.625
| Bath | 4 | 5.25 | 4.75 |  | 99.75
| " | 2 | 9.75 | 4.75 |  | 92.625
| Lav: | 2 | 3.75 | 9.75 |  | 73.125
| Lav: | 1 | 15.75 | 9.75 |  | 153.5625
| Stair Case | 1 | 11.75 | 22.75 |  | 267.3125
| Ver: | 2 | 38 | 11.75 |  | 893
| Ver | 1 | 15.75 | 7.75 |  | 122.0625
| Ver: | 1 | 33.25 | 9.75 |  | 324.1875
| " | 1 | 24.5 | 6 |  | 147
| " | 1 | 18 | 7.75 |  | 139.5
| Ent: | 1 | 11.75 | 18.25 |  | 214.4375
| Passage | 1 | 5 | 9.25 |  | 46.25
| Lav.` | 2 | 5.33 | 4.25 |  | 45.305
[5 empty] | TOTAL. | 6647.555
12 | Pacca Brick work in Foundation and plinth in cement sdanf mortor (1:6) S.I.No P.Mno.
| F/Side Ent: Steps | 2 | 14 | 10.75 | 2 | 602
| " | 2 | 14 | 9.5 | 0.5 | 133
| " | 2 | 14 | 8.25 | 0.5 | 115.5
| " | 2 | 14 | 7 | 0.5 | 98
| " | 2 | 14 | 5.75 | 0.5 | 80.5
[5 empty] | TOTAL | 1029

## GF Measurment (hidden)
( Measurement Shet ).
S# | Item Of Work | No |  | length | Bredth | Height | Quantity
PART (B) GROUND FLOOR
1 | R.C.C work inroof slab beams coloums raft lintels and other structural member laid in situ or precast laid in position complete in all respects ratio (1:2:4) 90 Lbs cement 2 Cft sand 4 Cft shingle concrete 1/8" to 1/4:" guage S.I.No., 6(a) P. 16
(A) Super Coloum
| C1 | 50 |  | 1.5 | 0.75 | 8.5 | 478.125
| C2 | 18 |  | 2 | 0.75 | 8.5 | 229.5
[6 empty] | TOTAL | 707.625
(B) Lintals
(A) Horizental Walls
| F/S Surgeon to Dental & Const to Const (PB-2) | 2 |  | 36 | 0.75 | 1 | 54
| Waiting Hall (PB-9) | 2 |  | 39 | 0.75 | 1 | 58.5
| Male& Female Ent: i/I (PB-9) | 2 |  | 14 | 0.75 | 1 | 21
| Stair case I/I (PB-9) | 1 |  | 12 | 0.75 | 1 | 9
| V/Side. Bath to Bath (PB-4) | 1 |  | 126.75 | 0.75 | 1 | 95.0625
| Bath to Ver: B/Side (PB-3) I/O | 1 |  | 43.25 | 0.75 | 1 | 32.4375
| Pharmacy Hall O/O (PB-8) | 1 |  | 12 | 0.75 | 1 | 9
| WMO to Bath O/O (PB-2) | 1 |  | 35 | 0.75 | 1 | 26.25
| Emargency i/I (PB-10) | 2 |  | 16 | 0.75 | 1 | 24
| Store O/O (PB-8) | 1 |  | 12 | 0.75 | 1 | 9
| Lav: O/O (PB-10) | 1 |  | 17.5 | 0.75 | 1 | 13.125
| Store TO Lav: O/O (PB-1) | 1 |  | 66.25 | 0.75 | 1 | 49.6875
| X-Ray & Lab: O/O (PB-9) | 2 |  | 15.5 | 0.75 | 1 | 23.25
| Dark Room.I/I (PB-8) | 1 |  | 11.5 | 0.75 | 1 | 8.625
| Dark room 1/1 (PB-8) | 1 |  | 6 | 0.75 | 1 | 4.5
| X-Ray & Lab: O/O (PB-2) | 1 |  | 43 | 0.75 | 1 | 32.25
| Store B/Side (PB-5) | 1 |  | 20.75 | 0.75 | 1 | 15.5625
Vertical Walls.
| Surgeon MO Dental (PB-10) | 8 |  | 16 | 0.75 | 1 | 96
| Stair case I/I (PB-5) | 2 |  | 25.25 | 0.75 | 1 | 37.875
| Ver: i/I (PB-5) | 2 |  | 12 | 0.75 | 1 | 18
| Bath to Bath i/I (PB-10) | 8 |  | 16 | 0.75 | 1 | 96
| Bath Partician i/I (PB-8) | 2 |  | 10 | 0.75 | 1 | 15
| Bath Partician i/I (PB-8) | 2 |  | 10.25 | 0.75 | 1 | 15.375
| Bath Partician i/I (PB-8) | 2 |  | 5.5 | 0.75 | 1 | 8.25
| Emergency to Store i/I (PB-6) | 1 |  | 33.5 | 0.75 | 1 | 25.125
| Emergency to Store i/I (PB-2) | 1 |  | 33.5 | 0.75 | 1 | 25.125
| Store & Pharmacy i/I (PB-7) | 1 |  | 33.5 | 0.75 | 1 | 25.125
| Store & Pharmacy i/I (PB-2) | 1 |  | 24.75 | 0.75 | 1 | 18.5625
| lav: i/I (PB-8) | 1 |  | 6 | 0.75 | 1 | 4.5
| Lav: (PB-8) | 2 |  | 10 | 0.75 | 1 | 15
| Lav: (PB-8) | 1 |  | 16 | 0.75 | 1 | 12
| Lav: (PB-8) | 2 |  | 6 | 0.75 | 1 | 9
| Waiting to X-Ray i/I (PB-6) | 1 |  | 28.75 | 0.75 | 1 | 21.5625
| Waiting to X-Ray i/I (PB-3) | 1 |  | 28.75 | 0.75 | 1 | 21.5625
| Waiting to X-Ray i/I (PB-7) | 1 |  | 28.75 | 0.75 | 1 | 21.5625
| Waiting to X-Ray i/I (PB-5) | 1 |  | 28.75 | 0.75 | 1 | 21.5625
| Store B/Side (PB-3,7,8) | 4 |  | 6 | 0.75 | 1 | 18
[6 empty] | TOTAL | 1010.4375
( C ) Roof Beams
(A) Horizental Walls
| F/S Surgeon to Dental & Const to Const (PB-2) | 2 |  | 36 | 0.75 | 2 | 108
| Waiting Hall (PB-9) | 2 |  | 39 | 0.75 | 2 | 117
| Male& Female Ent: i/I (PB-9) | 2 |  | 14 | 0.75 | 2 | 42
| Stair case I/I (PB-9) | 1 |  | 12 | 0.75 | 2 | 18
| V/Side. Bath to Bath (PB-4) | 1 |  | 126.75 | 0.75 | 2 | 190.125
| Bath to Ver: B/Side (PB-3) I/O | 1 |  | 43.25 | 0.75 | 2 | 64.875
| Pharmacy Hall O/O (PB-8) | 1 |  | 12 | 0.75 | 2 | 18
| WMO to Bath O/O (PB-2) | 1 |  | 35 | 0.75 | 2 | 52.5
| Emargency i/I (PB-10) | 2 |  | 16 | 0.75 | 2 | 48
| Store O/O (PB-8) | 1 |  | 12 | 0.75 | 2 | 18
| Lav: O/O (PB-10) | 1 |  | 17.5 | 0.75 | 2 | 26.25
| Store TO Lav: O/O (PB-1) | 1 |  | 66.25 | 0.75 | 2 | 99.375
| X-Ray & Lab: O/O (PB-9) | 2 |  | 15.5 | 0.75 | 2 | 46.5
| Dark Room.I/I (PB-8) | 1 |  | 11.5 | 0.75 | 2 | 17.25
| Dark room 1/1 (PB-8) | 1 |  | 6 | 0.75 | 2 | 9
| X-Ray & Lab: O/O (PB-2) | 1 |  | 43 | 0.75 | 2 | 64.5
| Store B/Side (PB-5) | 1 |  | 20.75 | 0.75 | 2 | 31.125
Vertical Walls.
| Surgeon MO Dental (PB-10) | 8 |  | 16 | 0.75 | 2 | 192
| Stair case I/I (PB-5) | 2 |  | 25.25 | 0.75 | 2 | 75.75
| Ver: i/I (PB-5) | 2 |  | 12 | 0.75 | 2 | 36
| Bath to Bath i/I (PB-10) | 8 |  | 16 | 0.75 | 2 | 192
| Bath Partician i/I (PB-8) | 2 |  | 10 | 0.75 | 2 | 30
| Bath Partician i/I (PB-8) | 2 |  | 10.25 | 0.75 | 2 | 30.75
| Bath Partician i/I (PB-8) | 2 |  | 5.5 | 0.75 | 2 | 16.5
| Emergency to Store i/I (PB-6) | 1 |  | 33.5 | 0.75 | 2 | 50.25
| Emergency to Store i/I (PB-2) | 1 |  | 33.5 | 0.75 | 2 | 50.25
| Store & Pharmacy i/I (PB-7) | 1 |  | 33.5 | 0.75 | 2 | 50.25
| Store & Pharmacy i/I (PB-2) | 1 |  | 24.75 | 0.75 | 2 | 37.125
| lav: i/I (PB-8) | 1 |  | 6 | 0.75 | 2 | 9
| Lav: (PB-8) | 2 |  | 10 | 0.75 | 2 | 30
| Lav: (PB-8) | 1 |  | 16 | 0.75 | 2 | 24
| Lav: (PB-8) | 2 |  | 6 | 0.75 | 2 | 18
| Waiting to X-Ray i/I (PB-6) | 1 |  | 28.75 | 0.75 | 2 | 43.125
| Waiting to X-Ray i/I (PB-3) | 1 |  | 28.75 | 0.75 | 2 | 43.125
| Waiting to X-Ray i/I (PB-7) | 1 |  | 28.75 | 0.75 | 2 | 43.125
| Waiting to X-Ray i/I (PB-5) | 1 |  | 28.75 | 0.75 | 2 | 43.125
| Store B/Side (PB-3,7,8) | 4 |  | 6 | 0.75 | 2 | 36
[6 empty] | TOTAL | 2020.875
(D) ROOF SLABS
| F/Side Surgen to Consultant | 2 |  | 36 | 16.75 | 0.5 | 603
| Male & Female Entr: | 2 |  | 14 | 10.25 | 0.5 | 143.5
| Stair Case | 1 |  | 12 | 11.75 | 0.5 | 70.5
| Ver: | 1 |  | 119.5 | 12.75 | 0.5 | 761.8125
| Bath to Bath | 1 |  | 125.25 | 17.5 | 0.5 | 1095.9375
| Partition to Lav: | 1 |  | 53 | 5 | 0.5 | 132.5
| Store to Lav: | 1 |  | 64.75 | 12 | 0.5 | 388.5
| Wait to Lab: | 1 |  | 29.5 | 43 | 0.5 | 634.25
| Store | 1 |  | 20.25 | 6.75 | 0.5 | 68.3438
[6 empty] | TOTAL | 3898.3438
[5 empty] | TOTAL (A+B+C+D) = |  | 7637.2812
2 | Fabarication of mild steel reinforcement for cement concrete building cutting bending and laying in position making of joints and fastesting i/c cost of binding wire also i/c removal of rust from bars. S.I.No 8 (a) P 16.
| Same Qty of item No (1) as above. |  |  | 7637.2812 | X5/112 |  | 340.9501
[6 empty] | TOTAl | 340.9501
3 | Pacca brick work in Grounds floor i/c stricking of joints ( 1:6) S.I.No P.No.
(A) Horizental Walls
| F/S Surgeon to Dental & Const to Const (PB-2) | 2 |  | 36 | 0.75 | 11.5 | 621
| Waiting Hall (PB-9) | 2 |  | 39 | 0.75 | 11.5 | 672.75
| Male& Female Ent: i/I (PB-9) | 2 |  | 14 | 0.75 | 11.5 | 241.5
| Stair case I/I (PB-9) | 1 |  | 12 | 0.75 | 11.5 | 103.5
| V/Side. Bath to Bath (PB-4) | 1 |  | 126.75 | 0.75 | 11.5 | 1093.2188
| Bath to Ver: B/Side (PB-3) I/O | 1 |  | 43.25 | 0.75 | 11.5 | 373.0312
| Pharmacy Hall O/O (PB-8) | 1 |  | 12 | 0.75 | 11.5 | 103.5
| WMO to Bath O/O (PB-2) | 1 |  | 35 | 0.75 | 11.5 | 301.875
| Emargency i/I (PB-10) | 2 |  | 16 | 0.75 | 11.5 | 276
| Store O/O (PB-8) | 1 |  | 12 | 0.75 | 11.5 | 103.5
| Lav: O/O (PB-10) | 1 |  | 17.5 | 0.75 | 11.5 | 150.9375
| Store TO Lav: O/O (PB-1) | 1 |  | 66.25 | 0.75 | 11.5 | 571.4062
| X-Ray & Lab: O/O (PB-9) | 2 |  | 15.5 | 0.75 | 11.5 | 267.375
| Dark Room.I/I (PB-8) | 1 |  | 11.5 | 0.75 | 11.5 | 99.1875
| Dark room 1/1 (PB-8) | 1 |  | 6 | 0.75 | 11.5 | 51.75
| X-Ray & Lab: O/O (PB-2) | 1 |  | 43 | 0.75 | 11.5 | 370.875
| Store B/Side (PB-5) | 1 |  | 20.75 | 0.75 | 11.5 | 178.9688
Vertical Walls.
| Surgeon MO Dental (PB-10) | 8 |  | 16 | 0.75 | 11.5 | 1104
| Stair case I/I (PB-5) | 2 |  | 25.25 | 0.75 | 11.5 | 435.5625
| Ver: i/I (PB-5) | 2 |  | 12 | 0.75 | 11.5 | 207
| Bath to Bath i/I (PB-10) | 8 |  | 16 | 0.75 | 11.5 | 1104
| Bath Partician i/I (PB-8) | 2 |  | 10 | 0.75 | 11.5 | 172.5
| Bath Partician i/I (PB-8) | 2 |  | 10.25 | 0.75 | 11.5 | 176.8125
| Bath Partician i/I (PB-8) | 2 |  | 5.5 | 0.75 | 11.5 | 94.875
| Emergency to Store i/I (PB-6) | 1 |  | 33.5 | 0.75 | 11.5 | 288.9375
| Emergency to Store i/I (PB-2) | 1 |  | 33.5 | 0.75 | 11.5 | 288.9375
| Store & Pharmacy i/I (PB-7) | 1 |  | 33.5 | 0.75 | 11.5 | 288.9375
| Store & Pharmacy i/I (PB-2) | 1 |  | 24.75 | 0.75 | 11.5 | 213.4688
| lav: i/I (PB-8) | 1 |  | 6 | 0.75 | 11.5 | 51.75
| Lav: (PB-8) | 2 |  | 10 | 0.75 | 11.5 | 172.5
| Lav: (PB-8) | 1 |  | 16 | 0.75 | 11.5 | 138
| Lav: (PB-8) | 2 |  | 6 | 0.75 | 11.5 | 103.5
| Waiting to X-Ray i/I (PB-6) | 1 |  | 28.75 | 0.75 | 11.5 | 247.9688
| Waiting to X-Ray i/I (PB-3) | 1 |  | 28.75 | 0.75 | 11.5 | 247.9688
| Waiting to X-Ray i/I (PB-7) | 1 |  | 28.75 | 0.75 | 11.5 | 247.9688
| Waiting to X-Ray i/I (PB-5) | 1 |  | 28.75 | 0.75 | 11.5 | 247.9688
| Store B/Side (PB-3,7,8) | 4 |  | 6 | 0.75 | 11.5 | 207
[6 empty] | TOTAL | 11620.0312
Deduction
| Columns | [5 empty] | 707.625
| Lintals | [5 empty] | 1010.4375
| Roof Beams | [5 empty] | 2020.875
| MD | 2 |  | 8 | 0.75 | 8.5 | 102
| D1 | 15 |  | 3.5 | 0.75 | 8.5 | 334.6875
| D2 | 2 |  | 3 | 0.75 | 8.5 | 38.25
| D3 | 13 |  | 2.5 | 0.75 | 7 | 170.625
| W. | 29 |  | 4.5 | 0.75 | 4 | 391.5
| Oppenings | 4 |  | 6 | 0.75 | 6 | 108
| HW | 10 |  | 3 | 0.75 | 1.5 | 33.75
| Oppenings | 1 |  | 14 | 0.75 | 7 | 73.5
| Oppenings | 1 |  | 10.25 | 0.75 | 7 | 53.8125
| Oppenings | 1 |  | 8 | 0.75 | 7 | 42
| Oppenings | 1 |  | 10 | 0.75 | 7 | 52.5
[6 empty] | TOTAL | 5139.5625
[5 empty] | TOTAL (A-B) |  | 6480.4688
4 | Cement Plaster 1/2" thick (1:^) upto 12" ft Height S.I.,No P.No..
| Surgeon,MO,D/Surgeon | 3 | 2 | (11+16) |  | 11.5 | 1863 | 27
| Consultant,LHV,EPI | 3 | 2 | (11+16) |  | 11.5 | 1863 | 27
| Consultant &WMO | 2 | 2 | (12+16) |  | 11.5 | 1288 | 28
| Consultant | 2 | 2 | (11+16) |  | 11.5 | 1242 | 27
| Pantry | 2 | 2 | (7+5) |  | 11.5 | 552 | 12
| Pharmacy | 1 | 2 | (12+14) |  | 11.5 | 598 | 26
| Store | 1 | 2 | (12+10) |  | 11.5 | 506 | 22
| Emergency | 1 | 2 | (16+22) |  | 11.5 | 874 | 38
| M.O.T | 1 | 2 | (10+11) |  | 11.5 | 483 | 21
| Store | 1 | 2 | (5.25+11) |  | 11.5 | 373.75 | 16.25
| Ultra Sound | 1 | 2 | (14+10) |  | 11.5 | 552 | 24
| X-Ray | 1 | 2 | (14+18) |  | 11.5 | 736 | 32
| Dark room | 1 | 2 | (6+6) |  | 11.5 | 276 | 12
| Changing | 1 | 2 | (6+10) |  | 11.5 | 368 | 16
| Store | 1 | 2 | (12.25+6) |  | 11.5 | 419.75 | 18.25
| Laboratory | 1 | 2 | (14+18) |  | 11.5 | 736 | 32
| Rec: /Tech: | 1 | 2 | (14+10) |  | 11.5 | 552 | 24
| Male & Female Entr: | 2 | 2 | (14+23) |  | 11.5 | 1702 | 37
| Waiting hall | 1 | 2 | (35.25+12) |  | 11.5 | 1086.75 | 47.25
| Waiting hall | 1 | 2 | (39.25+12) |  | 11.5 | 1178.75 | 51.25
| ver; | 1 | 2 | (17.50+8) |  | 11.5 | 586.5 | 25.5
| Ver: | 1 | 2 | (35.25+10) |  | 11.5 | 1040.75 | 45.25
| Ver: | 1 | 2 | (18.75+12) |  | 11.5 | 707.25 | 30.75
| Ver: | 1 | 2 | (10+6) |  | 11.5 | 368 | 16
| waiting | 1 | 2 | (13.50+7.58) |  | 11.5 | 484.84 | 21.08
| ver | 1 | 2 | (35.25+8) |  | 11.5 | 994.75 | 43.25
| stair case | 2 | 2 | (14+16) |  | 11.5 | 1380 | 30
| Bath | 7 | 2 | (5.5+5) |  | 11.5 | 1690.5 | 10.5
| Gen: Lav: | 1 | 2 | (10+4) |  | 11.5 | 322 | 14
[6 empty] | TOTAL | 24824.59
© | Out side Building
| O/Side of Building | (115.0+48.0+25.50+9.0+11.0+12.0+21.87+29.50+8.0+6.75+20.25+6.75+14.75+47.25+40.0+30.0+4.50+16.75) | [5 empty] | 466.87
[6 empty] | 12 | 5602.44
[6 empty] | TOTAL | 5602.44
| DEDUCTION |  |  |  |  | Net total | 30427.03
| MD | 2 |  | 8 |  | 8.5 | 136
| D1 | 15 |  | 3.5 |  | 8.5 | 446.25
| D2 | 2 |  | 3 |  | 8.5 | 51
| D3 | 13 |  | 2.5 |  | 7 | 227.5
| W. | 29 |  | 4.5 |  | 4 | 522
| Oppenings | 4 |  | 6 |  | 6 | 144
| HW | 10 |  | 3 |  | 1.5 | 45
| Oppenings | 1 |  | 14 |  | 7 | 98
| Oppenings | 1 |  | 10.25 |  | 7 | 71.75
| Oppenings | 1 |  | 8 |  | 7 | 56
| Oppenings | 1 |  | 10 |  | 7 | 70
[6 empty] | TOTAL | 1867.5
[5 empty] | Net: Qty: (A) (_) (B) |  | 28559.53
5 | Cement plaster 3/8" thick (1:4) upto 12" ft Height S.I.No P.No…
| Surgeon,MO,D/Surgeon | 3 | 2 | (11+16) |  | 11 | 1782 | 27
| Consultant,LHV,EPI | 3 | 2 | (11+16) |  | 11 | 1782 | 27
| Consultant &WMO | 2 | 2 | (12+16) |  | 11 | 1232 | 28
| Consultant | 2 | 2 | (11+16) |  | 11 | 1188 | 27
| Pantry | 2 | 2 | (7+5) |  | 11 | 528 | 12
| Pharmacy | 1 | 2 | (12+14) |  | 11 | 572 | 26
| Store | 1 | 2 | (12+10) |  | 11 | 484 | 22
| Emergency | 1 | 2 | (16+22) |  | 11 | 836 | 38
| M.O.T | 1 | 2 | (10+11) |  | 11 | 462 | 21
| Store | 1 | 2 | (5.25+11) |  | 11 | 357.5 | 16.25
| Ultra Sound | 1 | 2 | (14+10) |  | 11 | 528 | 24
| X-Ray | 1 | 2 | (14+18) |  | 11 | 704 | 32
| Dark room | 1 | 2 | (6+6) |  | 11 | 264 | 12
| Changing | 1 | 2 | (6+10) |  | 11 | 352 | 16
| Store | 1 | 2 | (12.25+6) |  | 11 | 401.5 | 18.25
| Laboratory | 1 | 2 | (14+18) |  | 11 | 704 | 32
| Rec: /Tech: | 1 | 2 | (14+10) |  | 11 | 528 | 24
| Male & Female Entr: | 2 | 2 | (14+23) |  | 11 | 1628 | 37
| Waiting hall | 1 | 2 | (35.25+12) |  | 11 | 1039.5 | 47.25
| Waiting hall | 1 | 2 | (39.25+12) |  | 11 | 1127.5 | 51.25
| ver; | 1 | 2 | (17.50+8) |  | 11 | 561 | 25.5
| Ver: | 1 | 2 | (35.25+10) |  | 11 | 995.5 | 45.25
| Ver: | 1 | 2 | (18.75+12) |  | 11 | 676.5 | 30.75
| Ver: | 1 | 2 | (10+6) |  | 11 | 352 | 16
| waiting | 1 | 2 | (13.50+7.58) |  | 11 | 463.76 | 21.08
| ver | 1 | 2 | (35.25+8) |  | 11 | 951.5 | 43.25
| stair case | 2 | 2 | (14+16) |  | 11 | 1320 | 30
| Bath | 7 | 2 | (5.5+5) |  | 4.5 | 661.5 | 10.5
| Gen: Lav: | 1 | 2 | (10+4) |  | 4.5 | 126 | 14
[6 empty] | TOTAL | 22607.76
(B) | Out side Building
| O/Side of Building | (115.0+48.0+25.50+9.0+11.0+12.0+21.87+29.50+8.0+6.75+20.25+6.75+14.75+47.25+40.0+30.0+4.50+16.75) | [5 empty] | 466.87
[6 empty] | 12 | 5602.44
[6 empty] | TOTAL | 5602.44
[6 empty] | Net total | 28210.2
DEDUCTION
| MD | 2 |  | 8 |  | 8.5 | 136
| D1 | 15 |  | 3.5 |  | 8.5 | 446.25
| D2 | 2 |  | 3 |  | 7 | 42
| D3 | 13 |  | 2.5 |  | 7 | 227.5
| W. | 29 |  | 4.5 |  | 4 | 522
| Oppenings | 4 |  | 6 |  | 6 | 144
| HW | 10 |  | 3 |  | 1.5 | 45
| Oppenings | 1 |  | 14 |  | 7 | 98
| Oppenings | 1 |  | 10.25 |  | 7 | 71.75
| Oppenings | 1 |  | 8 |  | 7 | 56
| Oppenings | 1 |  | 10 |  | 7 | 70
[6 empty] | TOTAL | 1858.5
[5 empty] | Net: Qty: (A) (_) (B) |  | 26351.7
6 | C.C.Plain I/c compacting finishing and curring complete io/c screening and washing of stone aggregate w/o shuttering S.I.No P.No.
| Surgeon,MO,D/Surgeon | 3 |  | 11 | 16 | 0.17 | 89.76
| Consultant,LHV,EPI | 3 |  | 11 | 16 | 0.17 | 89.76
| Consultant &WMO | 2 |  | 12 | 16 | 0.17 | 65.28
| Consultant | 2 |  | 11 | 16 | 0.17 | 59.84
| Pantry | 2 |  | 7 | 5 | 0.17 | 11.9
| Pharmacy | 1 |  | 12 | 14 | 0.17 | 28.56
| Store | 1 |  | 12 | 10 | 0.17 | 20.4
| Emergency | 1 |  | 16 | 22 | 0.17 | 59.84
| M.O.T | 1 |  | 10 | 11 | 0.17 | 18.7
| Store | 1 |  | 5.25 | 11 | 0.17 | 9.8175
| Ultra Sound | 1 |  | 14 | 10 | 0.17 | 23.8
| X-Ray | 1 |  | 14 | 18 | 0.17 | 42.84
| Dark room | 1 |  | 6 | 6 | 0.17 | 6.12
| Changing | 1 |  | 6 | 10 | 0.17 | 10.2
| Store | 1 |  | 12.25 | 6 | 0.17 | 12.495
| Laboratory | 1 |  | 14 | 18 | 0.17 | 42.84
| Rec: /Tech: | 1 |  | 14 | 10 | 0.17 | 23.8
| Male & Female Entr: | 2 |  | 14 | 23 | 0.17 | 109.48
| Entr: | 2 |  | 14 | 5.42 | 0.17 | 25.7992
| Entr: Steps | 2 |  | 14 | 4 | 0.17 | 19.04
| Waiting hall | 1 |  | 35.25 | 12 | 0.17 | 71.91
| Waiting hall | 1 |  | 39.25 | 12 | 0.17 | 80.07
| ver; | 1 |  | 17.5 | 8 | 0.17 | 23.8
| Ver: | 1 |  | 35.25 | 10 | 0.17 | 59.925
| Ver: | 1 |  | 18.75 | 12 | 0.17 | 38.25
| Ver: | 1 |  | 10 | 6 | 0.17 | 10.2
| waiting | 1 |  | 13.5 | 7.58 | 0.17 | 17.3961
| ver | 1 |  | 35.25 | 8 | 0.17 | 47.94
| stair case F/side | 2 | 12 | 4 | 1 | 0.17 | 1.36
| Stair Case Landing | 1 | 1 | 14 | 4 | 0.17 | 9.52
| stair case | 2 |  | 14 | 16 | 0.17 | 76.16
| Bath | 7 |  | 5.5 | 5 | 0.17 | 32.725
| Gen: Lav: | 3 |  | 10 | 4 | 0.17 | 20.4
[6 empty] | TOTAL | 1259.9278
7 | Laying floor of approved with glazed tiles 1/4" thick laid in white cement and pigment on a bend of 3/4" thick cement mortor 1:2 ( S.I.No 25 P.No 42
| Surgeon,MO,D/Surgeon | 3 |  | 11 | 16 |  | 528
| Consultant,LHV,EPI | 3 |  | 11 | 16 |  | 528
| Consultant &WMO | 2 |  | 12 | 16 |  | 384
| Consultant | 2 |  | 11 | 16 |  | 352
| Pantry | 2 |  | 7 | 5 |  | 70
| Pharmacy | 1 |  | 12 | 14 |  | 168
| Store | 1 |  | 12 | 10 |  | 120
| Emergency | 1 |  | 16 | 22 |  | 352
| M.O.T | 1 |  | 10 | 11 |  | 110
| Store | 1 |  | 5.25 | 11 |  | 57.75
| Ultra Sound | 1 |  | 14 | 10 |  | 140
| X-Ray | 1 |  | 14 | 18 |  | 252
| Dark room | 1 |  | 6 | 6 |  | 36
| Changing | 1 |  | 6 | 10 |  | 60
| Store | 1 |  | 12.25 | 6 |  | 73.5
| Laboratory | 1 |  | 14 | 18 |  | 252
| Rec: /Tech: | 1 |  | 14 | 10 |  | 140
| Male & Female Entr: | 2 |  | 14 | 23 |  | 644
| Entr: | 2 |  | 14 | 5.42 |  | 151.76
| Entr: Steps | 2 |  | 14 | 4 |  | 112
| Waiting hall | 1 |  | 35.25 | 12 |  | 423
| Waiting hall | 1 |  | 39.25 | 12 |  | 471
| stair case F/side | 2 | 12 | 4 | 1 |  | 8
| Stair Case Landing | 1 | 1 | 14 | 4 |  | 56
| stair case | 2 |  | 14 | 16 |  | 448
| Bath | 7 |  | 5.5 | 5 |  | 192.5
| Gen: Lav: | 3 |  | 10 | 4 |  | 120
[6 empty] | TOTAL | 6249.51
8 | glazed tiles dado 1/4" thick laid in pigment over 1:2 cement sand mortor 3/4" thick i/.c finishing S.I. No 38 P.No 44
| Surgeon,MO,D/Surgeon | 3 | 2 | (11+16) |  | 0.5 | 81 | 27
| Consultant,LHV,EPI | 3 | 2 | (11+16) |  | 0.5 | 81 | 27
| Consultant &WMO | 2 | 2 | (12+16) |  | 0.5 | 56 | 28
| Consultant | 2 | 2 | (11+16) |  | 0.5 | 54 | 27
| Pantry | 2 | 2 | (7+5) |  | 0.5 | 24 | 12
| Pharmacy | 1 | 2 | (12+14) |  | 0.5 | 26 | 26
| Store | 1 | 2 | (12+10) |  | 0.5 | 22 | 22
| Emergency | 1 | 2 | (16+22) |  | 0.5 | 38 | 38
| M.O.T | 1 | 2 | (10+11) |  | 0.5 | 21 | 21
| Store | 1 | 2 | (5.25+11) |  | 0.5 | 16.25 | 16.25
| Ultra Sound | 1 | 2 | (14+10) |  | 0.5 | 24 | 24
| X-Ray | 1 | 2 | (14+18) |  | 0.5 | 32 | 32
| Dark room | 1 | 2 | (6+6) |  | 0.5 | 12 | 12
| Changing | 1 | 2 | (6+10) |  | 0.5 | 16 | 16
| Store | 1 | 2 | (12.25+6) |  | 0.5 | 18.25 | 18.25
| Laboratory | 1 | 2 | (14+18) |  | 0.5 | 32 | 32
| Rec: /Tech: | 1 | 2 | (14+10) |  | 0.5 | 24 | 24
| Male & Female Entr: | 2 | 2 | (14+23) |  | 0.5 | 74 | 37
| Waiting hall | 1 | 2 | (35.25+12) |  | 0.5 | 47.25 | 47.25
| Waiting hall | 1 | 2 | (39.25+12) |  | 0.5 | 51.25 | 51.25
| stair case | 2 | 2 | (14+16) |  | 0.5 | 60 | 30
| Bath | 7 | 2 | (5.5+5) |  | 7 | 1029 | 10.5
| Gen: Lav: | 1 | 2 | (10+4) |  | 7 | 196 | 14
[6 empty] | TOTAL | 2035
DEDUCTION
| D3 | 13 |  | 2.5 |  | 7 | 227.5
[6 empty] | TOTAL | 227.5
[5 empty] | Net: Qty: (A) (_) (B) |  | 1807.5
9 | Laying white marble floor fine dressed on the surface with out winding set in lime mortor 1:2 i/c rubbling and polishing iof the joints 3/4" thick i/c finishing S.I.No 28 P.No 42
| ver; | 1 |  | 17.5 | 8 |  | 140
| Ver: | 1 |  | 35.25 | 10 |  | 352.5
| Ver: | 1 |  | 18.75 | 12 |  | 225
| Ver: | 1 |  | 10 | 6 |  | 60
| waiting | 1 |  | 13.5 | 7.58 |  | 102.33
| ver | 1 |  | 35.25 | 8 |  | 282
[6 empty] | TOTAL | 1161.83
10 | P/F 3/8" thick marbel tiles of approved quality & Colour shade size 8x4" 6x4" in dado skirting & facing removsal/ tucking of existin gplaster surface etc over 1/2" thick base of white cement over mortor base i/c filling of the joints ans washing the tiles with cement sand slury current finishing and cleaning and polishing etc complete for new works S.IO.No. 68 P.48.
| ver; | 1 | 2 | (17.50+8) |  | 0.5 | 25.5 | 25.5
| Ver: | 1 | 2 | (35.25+10) |  | 0.5 | 45.25 | 45.25
| Ver: | 1 | 2 | (18.75+12) |  | 0.5 | 30.75 | 30.75
| Ver: | 1 | 2 | (10+6) |  | 0.5 | 16 | 16
| waiting | 1 | 2 | (13.50+7.58) |  | 0.5 | 21.08 | 21.08
| ver | 1 | 2 | (35.25+8) |  | 0.5 | 43.25 | 43.25
[6 empty] | TOTAL | 181.83
DEDUCTION
| MD | 2 |  | 8 |  | 0.5 | 8
| D1 | 15 |  | 3.5 |  | 0.5 | 26.25
| D2 | 2 |  | 3 |  | 0.5 | 3
| Oppenings | 4 |  | 6 |  | 0.5 | 12
| Oppenings | 1 |  | 14 |  | 0.5 | 7
| Oppenings | 1 |  | 10.25 |  | 0.5 | 5.125
| Oppenings | 1 |  | 8 |  | 0.5 | 4
| Oppenings | 1 |  | 10 |  | 0.5 | 5
[6 empty] | TOTAL | 70.375
[5 empty] | Net: Qty: (A) (_) (B) |  | 111.455
11 | P/Fixing G.I frame sfor chowkts of size 7x2" 4-1/2x3" for doors using 20 guage G.I sheet i/c welded hinges and fixing at site withnecessary holds fasts and filling with cement sand slury of ratio 1:6 and reparing rhe jambs <the cost of also i/c all carriage of tools and plants are used in making and fixing.S.I.No. 28.P.92.
| W. | 29 | (2X4.50+5X4.0) |  |  |  | 841
| HW | 10 | (2X3.0+2X1.50) |  |  |  | 90
[6 empty] | TOTAL | 931
12 | P/Fixing G.I frame sfor chowkts of size 7x2" 4-1/2x3" for doors using 20 guage G.I sheet i/c welded hinges and fixing at site withnecessary holds fasts and filling with cement sand slury of ratio 1:6 and reparing rhe jambs <the cost of also i/c all carriage of tools and plants are used in making and fixing.S.I.No. 29.P.92.
| D1. | 15 | (2X3.50+2X8.50) |  |  |  | 360
| D2. | 2 | (3.50+2X7.0) |  |  |  | 35
| D3. | 13 | (2.5+2X7.0) |  |  |  | 215
[6 empty] | TOTAL | 610
13 | 1st class deodar wood wraught joinery in D/W etc fixed in position i/c chowkats hold fast iron tower bolts chocks cleats handles and chords with hooks etc Deodar pannalled and glazed or fully glazed 1-3/4"thick (SIN0:7 P-57)
| D1. | 15 |  |  | 3.5 | (7.50+1.5) | 473
| D2. | 2 |  |  | 3 | 7 | 42
| D3. | 13 |  |  | 2.5 | 7 | 227.5
| W1. | 29 |  |  | 4.5 | 4 | 522
| HW | 10 |  |  | 3 | 1.5 | 45
[6 empty] | TOTAL | 1309.5
14 | P/Fixing iron steel grill SINO:26 P-92
| W1. | 29 |  |  | 4.5 | 4 | 522
| HW | 10 |  |  | 3 | 1.5 | 45
[6 empty] | TOTAL | 567
15 | 1st class deodar wood wraught joinery in D/W etc fixed in position i/c chowkats hold fast iron tower bolts chocks cleats handles and chords with hooks etc Deodar pannalled and glazed or fully glazed 1-3/4"thick (SIN0:7 P-57)
| W1. | 29 |  |  | 4.5 | 4 | 522
| HW | 10 |  |  | 3 | 1.5 | 45
[6 empty] | TOTAL | 567
16 | Primary coat of chalk under distrm,per or oil bund distemper or paint on walls S.I.No P.No.
| Same Qty of item No (7) as above. | [5 empty] | 6249.51
| Same Qty of item No (9) as above. | [5 empty] | 1161.83
[6 empty] | TOTAL | 7411.34
17 | Distempering of walls any type three coats S.I.No P.No.
| Same Qty of item No (16) as above. | [5 empty] | 7411.34
[6 empty] | TOTAL | 7411.34
18 | S/Fixing matt Finish 3 Coats
| Same Qty of item No 5 (a) as above. | [5 empty] | 22607.76
[6 empty] | TOTAL | 22607.76
19 | Weather coat 3 coats
| Same Qty of item No (5) (b) as above. | [5 empty] | 5602.44
[6 empty] | TOTAL | 5602.44
20 | Preparring new surface and painting of doors and windows any type i/c edges three coats S.I.No P.No.
| Double Qty of item No (13) as above. |  |  | 1309.5 | x2= |  | 2619
[6 empty] | TOTAL | 2619
21 | Supplying and fixing Aluminium channels framing for hinged doors and alcope made
| MD | 1 |  | 2 | 8 | 8.5 | 136
[6 empty] | TOTAl | 136
22 | Supplying and fixing Aluminium channels framing for hinged Windows and alcope made
| W. | 1 |  | 2 | 4.5 | 5.5 | 49.5
[6 empty] | TOTAL | 49.5
25 | Hard wood railing of any shape & design i/c bends S.I.No30 P.No.61
| " " | 1 | 2 |  | 26 |  | 52
| " " | 1 | 52 |  | 4 |  | 208
[6 empty] | TOTAL. | 260

## FF Measurment (hidden)
( Measurement Shet ).
S# | Item Of Work | No |  | length | Bredth | Height | Quantity
PART (B) FIRST FLOOR
1 | R.C.C work inroof slab beams coloums raft lintels and other structural member laid in situ or precast laid in position complete in all respects ratio (1:2:4) 90 Lbs cement 2 Cft sand 4 Cft shingle concrete 1/8" to 1/4:" guage S.I.No., 6(a) P. 16
(A) Super Coloum
| C1 | 50 |  | 1.5 | 0.75 | 8.5 | 478.125
| C2 | 18 |  | 2 | 0.75 | 8.5 | 229.5
[6 empty] | TOTAL | 707.625
(B) Lintals
(A) Horizental Walls
| WARDS | 2 |  | 36 | 0.75 | 1 | 54
| Waiting Hall (PB-9) | 2 |  | 39 | 0.75 | 1 | 58.5
| Beside Stair case | 2 |  | 14 | 0.75 | 1 | 21
| Stair case I/I (PB-9) | 1 |  | 12 | 0.75 | 1 | 9
| V/Side. Bath to Bath (PB-4) | 1 |  | 126.75 | 0.75 | 1 | 95.0625
| Bath to Ver: B/Side (PB-3) I/O | 1 |  | 43.25 | 0.75 | 1 | 32.4375
| N/Station | 1 |  | 12 | 0.75 | 1 | 9
| Ward & store | 1 |  | 35 | 0.75 | 1 | 26.25
| n/Station & waiting | 2 |  | 16 | 0.75 | 1 | 24
| Store O/O (PB-8) | 1 |  | 12 | 0.75 | 1 | 9
| Lav: O/O (PB-10) | 1 |  | 17.5 | 0.75 | 1 | 13.125
| Technical staff to Lav: | 1 |  | 66.25 | 0.75 | 1 | 49.6875
| Ansthetic & surgeon | 2 |  | 15.5 | 0.75 | 1 | 23.25
| Scurb | 1 |  | 12 | 0.75 | 1 | 9
| Sterilization & Bath | 1 |  | 20.75 | 0.75 | 1 | 15.5625
| X-Ray & Lab: O/O (PB-2) | 1 |  | 43 | 0.75 | 1 | 32.25
Vertical Walls.
| ward | 8 |  | 16 | 0.75 | 1 | 96
| Stair case I/I (PB-5) | 2 |  | 25.25 | 0.75 | 1 | 37.875
| Ver: i/I (PB-5) | 2 |  | 12 | 0.75 | 1 | 18
| Bath to Bath i/I (PB-10) | 8 |  | 16 | 0.75 | 1 | 96
| Bath Partician i/I (PB-8) | 2 |  | 10 | 0.75 | 1 | 15
| Bath Partician i/I (PB-8) | 2 |  | 10.25 | 0.75 | 1 | 15.375
| Bath Partician i/I (PB-8) | 2 |  | 5.5 | 0.75 | 1 | 8.25
| N/Station to Tech | 1 |  | 33.5 | 0.75 | 1 | 25.125
| N/Station to Tech | 1 |  | 33.5 | 0.75 | 1 | 25.125
| N/Station to Store | 2 |  | 24.75 | 0.75 | 1 | 37.125
| lav: i/I (PB-8) | 1 |  | 6 | 0.75 | 1 | 4.5
| Lav: (PB-8) | 2 |  | 10 | 0.75 | 1 | 15
| Lav: (PB-8) | 1 |  | 16 | 0.75 | 1 | 12
| Lav: (PB-8) | 2 |  | 6 | 0.75 | 1 | 9
| Anesthetic to OT | 4 |  | 28.75 | 0.75 | 1 | 86.25
| Sterilization & Bath | 3 |  | 6 | 0.75 | 1 | 13.5
[6 empty] | TOTAL | 995.25
( C ) Roof Beams
(A) Horizental Walls
| WARDS | 2 |  | 36 | 0.75 | 2 | 108
| Waiting Hall (PB-9) | 2 |  | 39 | 0.75 | 2 | 117
| Beside Stair case | 2 |  | 14 | 0.75 | 2 | 42
| Stair case I/I (PB-9) | 1 |  | 12 | 0.75 | 2 | 18
| V/Side. Bath to Bath (PB-4) | 1 |  | 126.75 | 0.75 | 2 | 190.125
| Bath to Ver: B/Side (PB-3) I/O | 1 |  | 43.25 | 0.75 | 2 | 64.875
| N/Station | 1 |  | 12 | 0.75 | 2 | 18
| Ward & store | 1 |  | 35 | 0.75 | 2 | 52.5
| n/Station & waiting | 2 |  | 16 | 0.75 | 2 | 48
| Store O/O (PB-8) | 1 |  | 12 | 0.75 | 2 | 18
| Lav: O/O (PB-10) | 1 |  | 17.5 | 0.75 | 2 | 26.25
| Technical staff to Lav: | 1 |  | 66.25 | 0.75 | 2 | 99.375
| Ansthetic & surgeon | 2 |  | 15.5 | 0.75 | 2 | 46.5
| Scurb | 1 |  | 12 | 0.75 | 2 | 18
| Sterilization & Bath | 1 |  | 20.75 | 0.75 | 2 | 31.125
| X-Ray & Lab: O/O (PB-2) | 1 |  | 43 | 0.75 | 2 | 64.5
Vertical Walls.
| ward | 8 |  | 16 | 0.75 | 2 | 192
| Stair case I/I (PB-5) | 2 |  | 25.25 | 0.75 | 2 | 75.75
| Ver: i/I (PB-5) | 2 |  | 12 | 0.75 | 2 | 36
| Bath to Bath i/I (PB-10) | 8 |  | 16 | 0.75 | 2 | 192
| Bath Partician i/I (PB-8) | 2 |  | 10 | 0.75 | 2 | 30
| Bath Partician i/I (PB-8) | 2 |  | 10.25 | 0.75 | 2 | 30.75
| Bath Partician i/I (PB-8) | 2 |  | 5.5 | 0.75 | 2 | 16.5
| N/Station to Tech | 1 |  | 33.5 | 0.75 | 2 | 50.25
| N/Station to Tech | 1 |  | 33.5 | 0.75 | 2 | 50.25
| N/Station to Store | 2 |  | 24.75 | 0.75 | 2 | 74.25
| lav: i/I (PB-8) | 1 |  | 6 | 0.75 | 2 | 9
| Lav: (PB-8) | 2 |  | 10 | 0.75 | 2 | 30
| Lav: (PB-8) | 1 |  | 16 | 0.75 | 2 | 24
| Lav: (PB-8) | 2 |  | 6 | 0.75 | 2 | 18
| Anesthetic to OT | 4 |  | 28.75 | 0.75 | 2 | 172.5
| Sterilization & Bath | 3 |  | 6 | 0.75 | 2 | 27
[6 empty] | TOTAL | 1990.5
(D) ROOF SLABS
| Ward to D/Doctor | 2 |  | 36 | 16.75 | 0.5 | 603
| Male & Female Entr: | 2 |  | 14 | 10.25 | 0.5 | 143.5
| Stair Case | 1 |  | 12 | 11.75 | 0.5 | 70.5
| Ver: | 1 |  | 119.5 | 12.75 | 0.5 | 761.8125
| Bath to Bath | 1 |  | 125.25 | 17.5 | 0.5 | 1095.9375
| Partition to Lav: | 1 |  | 53 | 5 | 0.5 | 132.5
| Store to Lav: | 1 |  | 64.75 | 12 | 0.5 | 388.5
| Wait to Lab: | 1 |  | 29.5 | 43 | 0.5 | 634.25
| Store | 1 |  | 20.25 | 6.75 | 0.5 | 68.3438
[6 empty] | TOTAL | 3898.3438
[5 empty] | TOTAL (A+B+C+D) = |  | 7591.7188
2 | Fabarication of mild steel reinforcement for cement concrete building cutting bending and laying in position making of joints and fastesting i/c cost of binding wire also i/c removal of rust from bars. S.I.No 8 (a) P 16.
| Same Qty of item No (1) as above. |  |  | 7591.7188 | X5/112 |  | 338.916
[6 empty] | TOTAl | 338.916
3 | Pacca brick work in Grounds floor i/c stricking of joints ( 1:6) S.I.No P.No.
(A) Horizental Walls
| WARDS | 2 |  | 36 | 0.75 | 11.5 | 621
| Waiting Hall (PB-9) | 2 |  | 39 | 0.75 | 11.5 | 672.75
| Beside Stair case | 2 |  | 14 | 0.75 | 11.5 | 241.5
| Stair case I/I (PB-9) | 1 |  | 12 | 0.75 | 11.5 | 103.5
| V/Side. Bath to Bath (PB-4) | 1 |  | 126.75 | 0.75 | 11.5 | 1093.2188
| Bath to Ver: B/Side (PB-3) I/O | 1 |  | 43.25 | 0.75 | 11.5 | 373.0312
| N/Station | 1 |  | 12 | 0.75 | 11.5 | 103.5
| Ward & store | 1 |  | 35 | 0.75 | 11.5 | 301.875
| n/Station & waiting | 2 |  | 16 | 0.75 | 11.5 | 276
| Store O/O (PB-8) | 1 |  | 12 | 0.75 | 11.5 | 103.5
| Lav: O/O (PB-10) | 1 |  | 17.5 | 0.75 | 11.5 | 150.9375
| Technical staff to Lav: | 1 |  | 66.25 | 0.75 | 11.5 | 571.4062
| Ansthetic & surgeon | 2 |  | 15.5 | 0.75 | 11.5 | 267.375
| Scurb | 1 |  | 12 | 0.75 | 11.5 | 103.5
| Sterilization & Bath | 1 |  | 20.75 | 0.75 | 11.5 | 178.9688
| X-Ray & Lab: O/O (PB-2) | 1 |  | 43 | 0.75 | 11.5 | 370.875
Vertical Walls.
| ward | 8 |  | 16 | 0.75 | 11.5 | 1104
| Stair case I/I (PB-5) | 2 |  | 25.25 | 0.75 | 11.5 | 435.5625
| Ver: i/I (PB-5) | 2 |  | 12 | 0.75 | 11.5 | 207
| Bath to Bath i/I (PB-10) | 8 |  | 16 | 0.75 | 11.5 | 1104
| Bath Partician i/I (PB-8) | 2 |  | 10 | 0.75 | 11.5 | 172.5
| Bath Partician i/I (PB-8) | 2 |  | 10.25 | 0.75 | 11.5 | 176.8125
| Bath Partician i/I (PB-8) | 2 |  | 5.5 | 0.75 | 11.5 | 94.875
| N/Station to Tech | 1 |  | 33.5 | 0.75 | 11.5 | 288.9375
| N/Station to Tech | 1 |  | 33.5 | 0.75 | 11.5 | 288.9375
| N/Station to Store | 2 |  | 24.75 | 0.75 | 11.5 | 426.9375
| lav: i/I (PB-8) | 1 |  | 6 | 0.75 | 11.5 | 51.75
| Lav: (PB-8) | 2 |  | 10 | 0.75 | 11.5 | 172.5
| Lav: (PB-8) | 1 |  | 16 | 0.75 | 11.5 | 138
| Lav: (PB-8) | 2 |  | 6 | 0.75 | 11.5 | 103.5
| Anesthetic to OT | 4 |  | 28.75 | 0.75 | 11.5 | 991.875
| Sterilization & Bath | 3 |  | 6 | 0.75 | 11.5 | 155.25
[6 empty] | TOTAL | 11445.375
Deduction
| Columns | [5 empty] | 707.625
| Lintals | [5 empty] | 995.25
| Roof Beams | [5 empty] | 1990.5
| MD | 2 |  | 8 | 0.75 | 8.5 | 102
| D1 | 15 |  | 3.5 | 0.75 | 8.5 | 334.6875
| D2 | 2 |  | 3 | 0.75 | 8.5 | 38.25
| D3 | 13 |  | 2.5 | 0.75 | 7 | 170.625
| W. | 29 |  | 4.5 | 0.75 | 4 | 391.5
| Oppenings | 4 |  | 6 | 0.75 | 6 | 108
| HW | 10 |  | 3 | 0.75 | 1.5 | 33.75
| Oppenings | 1 |  | 14 | 0.75 | 7 | 73.5
| Oppenings | 1 |  | 10.25 | 0.75 | 7 | 53.8125
| Oppenings | 1 |  | 8 | 0.75 | 7 | 42
| Oppenings | 1 |  | 10 | 0.75 | 7 | 52.5
[6 empty] | TOTAL | 5094
[5 empty] | TOTAL (A-B) |  | 6351.375
4 | Cement Plaster 1/2" thick (1:^) upto 12" ft Height S.I.,No P.No..
| 5Beded ward | 4 | 2 | (22.75+16) |  | 11.5 | 3565 | 38.75
| D/Doctor | 2 | 2 | (11+10) |  | 11.5 | 966 | 21
| Male & Female Waiting | 2 | 2 | (14+14) |  | 11.5 | 1288 | 28
| N/Station | 1 | 2 | (12+14) |  | 11.5 | 598 | 26
| N/Station | 1 | 2 | (16+14 |  | 11.5 | 690 | 30
| Waiting | 1 | 2 | (16+7.25) |  | 11.5 | 534.75 | 23.25
| Waiting | 1 | 2 | (12+7.25) |  | 11.5 | 442.75 | 19.25
| Pantry | 2 | 2 | (7.75+5) |  | 11.5 | 586.5 | 12.75
| Technical Staff | 1 | 2 | (16+11) |  | 11.5 | 621 | 27
| Anesthetic | 1 | 2 | (12+11) |  | 11.5 | 529 | 23
| Recovery | 1 | 2 | (14+11) |  | 11.5 | 575 | 25
| surgeon | 1 | 2 | (14+11) |  | 11.5 | 575 | 25
| O-T | 1 | 2 | (14+18) |  | 11.5 | 736 | 32
| Scrub & Sterilization | 2 | 2 | (12+7) |  | 11.5 | 874 | 19
| Labour Room | 1 | 2 | (14+18) |  | 11.5 | 736 | 32
| Stair Case steps | 2 | 12 | 4 |  | 11.5 | 1104
| Stair Case Landing | 1 | 1 | 14 |  | 11.5 | 161
| stair case F/side | 1 | 2 | (14+8) |  | 11.5 | 506 | 22
| ver; | 1 | 2 | (39.25+12) |  | 11.5 | 1178.75 | 51.25
| Ver: | 1 | 2 | (35.25+12) |  | 11.5 | 1086.75 | 47.25
| Ver: | 2 | 2 | (17.5+8) |  | 11.5 | 1173 | 25.5
| Ver: | 1 | 2 | (35.25+10) |  | 11.5 | 1040.75 | 45.25
| Ver: | 1 | 2 | (21+12) |  | 11.5 | 759 | 33
| ver | 1 | 2 | (11.75+8) |  | 11.5 | 454.25 | 19.75
| Ver: | 1 | 2 | (7+7) |  | 11.5 | 322 | 14
| Lav: | 2 | 2 | (11+5.5) |  | 11.5 | 759 | 16.5
| Lav: | 1 | 2 | (7.75+10) |  | 11.5 | 408.25 | 17.75
| WC | 1 | 2 | (6+6) |  | 11.5 | 276 | 12
| Lav: | 1 | 2 | (16+10.50) |  | 11.5 | 609.5 | 26.5
[6 empty] | TOTAL | 23155.25
© | Out side Building
| O/Side of Building | (115.0+48.0+25.50+9.0+11.0+12.0+21.87+29.50+8.0+6.75+20.25+6.75+14.75+47.25+40.0+30.0+4.50+16.75) | [5 empty] | 466.87
[6 empty] | 12 | 5602.44
[6 empty] | TOTAL | 5602.44
| DEDUCTION |  |  |  |  | Net total | 28757.69
| D1 | 15 |  | 3.5 |  | 8.5 | 446.25
| D2 | 2 |  | 3 |  | 8.5 | 51
| D3 | 13 |  | 2.5 |  | 7 | 227.5
| W. | 29 |  | 4.5 |  | 4 | 522
| Oppenings | 4 |  | 6 |  | 6 | 144
| HW | 10 |  | 3 |  | 1.5 | 45
| Oppenings | 1 |  | 14 |  | 7 | 98
| Oppenings | 1 |  | 10.25 |  | 7 | 71.75
| Oppenings | 1 |  | 8 |  | 7 | 56
| Oppenings | 1 |  | 10 |  | 7 | 70
[6 empty] | TOTAL | 1731.5
[5 empty] | Net: Qty: (A) (_) (B) |  | 27026.19
5 | Cement plaster 3/8" thick (1:4) upto 12" ft Height S.I.No P.No…
| 5Beded ward | 4 | 2 | (22.75+16) |  | 11 | 3410 | 38.75
| D/Doctor | 2 | 2 | (11+10) |  | 11 | 924 | 21
| Male & Female Waiting | 2 | 2 | (14+14) |  | 11 | 1232 | 28
| N/Station | 1 | 2 | (12+14) |  | 11 | 572 | 26
| N/Station | 1 | 2 | (16+14 |  | 11 | 660 | 30
| Waiting | 1 | 2 | (16+7.25) |  | 11 | 511.5 | 23.25
| Waiting | 1 | 2 | (12+7.25) |  | 11 | 423.5 | 19.25
| Pantry | 2 | 2 | (7.75+5) |  | 11 | 561 | 12.75
| Technical Staff | 1 | 2 | (16+11) |  | 11 | 594 | 27
| Anesthetic | 1 | 2 | (12+11) |  | 11 | 506 | 23
| Recovery | 1 | 2 | (14+11) |  | 11 | 550 | 25
| surgeon | 1 | 2 | (14+11) |  | 11 | 550 | 25
| O-T | 1 | 2 | (14+18) |  | 11 | 704 | 32
| Scrub & Sterilization | 2 | 2 | (12+7) |  | 11 | 836 | 19
| Labour Room | 1 | 2 | (14+18) |  | 11 | 704 | 32
| Stair Case steps | 2 | 12 | 4 |  | 11 | 1056
| Stair Case Landing | 1 | 1 | 14 |  | 11 | 154
| stair case F/side | 1 | 2 | (14+8) |  | 11 | 484 | 22
| ver; | 1 | 2 | (39.25+12) |  | 11 | 1127.5 | 51.25
| Ver: | 1 | 2 | (35.25+12) |  | 11 | 1039.5 | 47.25
| Ver: | 2 | 2 | (17.5+8) |  | 11 | 1122 | 25.5
| Ver: | 1 | 2 | (35.25+10) |  | 11 | 995.5 | 45.25
| Ver: | 1 | 2 | (21+12) |  | 11 | 726 | 33
| ver | 1 | 2 | (11.75+8) |  | 11 | 434.5 | 19.75
| Ver: | 1 | 2 | (7+7) |  | 11 | 308 | 14
| Lav: | 2 | 2 | (11+5.5) |  | 4.5 | 297 | 16.5
| Lav: | 1 | 2 | (7.75+10) |  | 4.5 | 159.75 | 17.75
| WC | 1 | 2 | (6+6) |  | 4.5 | 108 | 12
| Lav: | 1 | 2 | (16+10.50) |  | 4.5 | 238.5 | 26.5
[6 empty] | TOTAL | 20988.25
(B) | Out side Building
| O/Side of Building | (115.0+48.0+25.50+9.0+11.0+12.0+21.87+29.50+8.0+6.75+20.25+6.75+14.75+47.25+40.0+30.0+4.50+16.75) | [5 empty] | 466.87
[6 empty] | 12 | 5602.44
[6 empty] | TOTAL | 5602.44
[6 empty] | Net total | 26590.69
DEDUCTION
| D1 | 15 |  | 3.5 |  | 8.5 | 446.25
| D2 | 2 |  | 3 |  | 7 | 42
| D3 | 13 |  | 2.5 |  | 7 | 227.5
| W. | 29 |  | 4.5 |  | 4 | 522
| Oppenings | 4 |  | 6 |  | 6 | 144
| HW | 10 |  | 3 |  | 1.5 | 45
| Oppenings | 1 |  | 14 |  | 7 | 98
| Oppenings | 1 |  | 10.25 |  | 7 | 71.75
| Oppenings | 1 |  | 8 |  | 7 | 56
| Oppenings | 1 |  | 10 |  | 7 | 70
[6 empty] | TOTAL | 1722.5
[5 empty] | Net: Qty: (A) (_) (B) |  | 24868.19
6 | C.C.Plain I/c compacting finishing and curring complete io/c screening and washing of stone aggregate w/o shuttering S.I.No P.No.
| 5Beded ward | 4 |  | 22.75 | 16 | 0.17 | 247.52
| D/Doctor | 2 |  | 11 | 10 | 0.17 | 37.4
| Male & Female Waiting | 2 |  | 14 | 14 | 0.17 | 66.64
| N/Station | 1 |  | 12 | 14 | 0.17 | 28.56
| N/Station | 1 |  | 16 | 14 | 0.17 | 38.08
| Waiting | 1 |  | 16 | 7.25 | 0.17 | 19.72
| Waiting | 1 |  | 12 | 7.25 | 0.17 | 14.79
| Pantry | 2 |  | 7.75 | 5 | 0.17 | 13.175
| Technical Staff | 1 |  | 16 | 11 | 0.17 | 29.92
| Anesthetic | 1 |  | 12 | 11 | 0.17 | 22.44
| Recovery | 1 |  | 14 | 11 | 0.17 | 26.18
| surgeon | 1 |  | 14 | 11 | 0.17 | 26.18
| O-T | 1 |  | 14 | 18 | 0.17 | 42.84
| Scrub & Sterilization | 2 |  | 12 | 7 | 0.17 | 28.56
| Labour Room | 1 |  | 14 | 18 | 0.17 | 42.84
| Stair Case steps | 2 | 12 | 4 | 1 | 0.17 | 16.32
| Stair Case Landing | 1 | 1 | 14 | 4 | 0.17 | 9.52
| stair case F/side | 1 |  | 14 | 8 | 0.17 | 19.04
| ver; | 1 |  | 39.25 | 12 | 0.17 | 80.07
| Ver: | 1 |  | 35.25 | 10 | 0.17 | 59.925
| Ver: | 2 |  | 17.5 | 8 | 0.17 | 47.6
| Ver: | 1 |  | 35.25 | 10 | 0.17 | 59.925
| Ver: | 1 |  | 21 | 12 | 0.17 | 42.84
| ver | 1 |  | 11.75 | 8 | 0.17 | 15.98
| Ver: | 1 |  | 7 | 7 | 0.17 | 8.33
| Lav: | 2 |  | 11 | 5.5 | 0.17 | 121
| Lav: | 2 |  | 7.75 | 10 | 0.17 | 155
| WC | 1 |  | 6 | 6 | 0.17 | 36
| Lav: | 1 |  | 16 | 10.5 | 0.17 | 168
[6 empty] | TOTAL | 1524.395
7 | Laying floor of approved with glazed tiles 1/4" thick laid in white cement and pigment on a bend of 3/4" thick cement mortor 1:2 ( S.I.No 25 P.No 42
| 5Beded ward | 4 |  | 22.75 | 16 |  | 1456
| D/Doctor | 2 |  | 11 | 10 |  | 220
| Male & Female Waiting | 2 |  | 14 | 14 |  | 392
| N/Station | 1 |  | 12 | 14 |  | 168
| N/Station | 1 |  | 16 | 14 |  | 224
| Waiting | 1 |  | 16 | 7.25 |  | 116
| Waiting | 1 |  | 12 | 7.25 |  | 87
| Pantry | 2 |  | 7.75 | 5 |  | 77.5
| Technical Staff | 1 |  | 16 | 11 |  | 176
| Anesthetic | 1 |  | 12 | 11 |  | 132
| Recovery | 1 |  | 14 | 11 |  | 154
| surgeon | 1 |  | 14 | 11 |  | 154
| O-T | 1 |  | 14 | 18 |  | 252
| Scrub & Sterilization | 2 |  | 12 | 7 |  | 168
| Labour Room | 1 |  | 14 | 18 |  | 252
| Stair Case steps | 2 | 12 | 4 | 1 |  | 96
| Stair Case Landing | 1 | 1 | 14 | 4 |  | 56
| stair case F/side | 1 |  | 14 | 8 |  | 112
| Lav: | 2 |  | 11 | 5.5 |  | 121
| Lav: | 2 |  | 7.75 | 10 |  | 155
| WC | 1 |  | 6 | 6 |  | 36
| Lav: | 1 |  | 16 | 10.5 |  | 168
[6 empty] | TOTAL | 4772.5
8 | glazed tiles dado 1/4" thick laid in pigment over 1:2 cement sand mortor 3/4" thick i/.c finishing S.I. No 38 P.No 44
| 5Beded ward | 4 | 2 | (22.75+16) |  | 0.5 | 155 | 38.75
| D/Doctor | 2 | 2 | (11+10) |  | 0.5 | 42 | 21
| Male & Female Waiting | 2 | 2 | (14+14) |  | 0.5 | 56 | 28
| N/Station | 1 | 2 | (12+14) |  | 0.5 | 26 | 26
| N/Station | 1 | 2 | (16+14 |  | 0.5 | 30 | 30
| Waiting | 1 | 2 | (16+7.25) |  | 0.5 | 23.25 | 23.25
| Waiting | 1 | 2 | (12+7.25) |  | 0.5 | 19.25 | 19.25
| Pantry | 2 | 2 | (7.75+5) |  | 0.5 | 25.5 | 12.75
| Technical Staff | 1 | 2 | (16+11) |  | 0.5 | 27 | 27
| Anesthetic | 1 | 2 | (12+11) |  | 0.5 | 23 | 23
| Recovery | 1 | 2 | (14+11) |  | 0.5 | 25 | 25
| surgeon | 1 | 2 | (14+11) |  | 0.5 | 25 | 25
| O-T | 1 | 2 | (14+18) |  | 0.5 | 32 | 32
| Scrub & Sterilization | 2 | 2 | (12+7) |  | 0.5 | 38 | 19
| Labour Room | 1 | 2 | (14+18) |  | 0.5 | 32 | 32
| Stair Case steps | 2 | 12 | 4 |  | 0.5 | 48
| Stair Case Landing | 1 | 1 | 14 |  | 0.5 | 7
| stair case F/side | 1 | 2 | (14+8) |  | 0.5 | 22 | 22
| Lav: | 2 | 2 | (11+5.5) |  | 7 | 462 | 16.5
| Lav: | 1 | 2 | (7.75+10) |  | 7 | 248.5 | 17.75
| WC | 1 | 2 | (6+6) |  | 7 | 168 | 12
| Lav: | 1 | 2 | (16+10.50) |  | 7 | 371 | 26.5
[6 empty] | TOTAL | 1905.5
DEDUCTION
| D3 | 13 |  | 2.5 |  | 7 | 227.5
[6 empty] | TOTAL | 227.5
[5 empty] | Net: Qty: (A) (_) (B) |  | 1678
9 | Laying white marble floor fine dressed on the surface with out winding set in lime mortor 1:2 i/c rubbling and polishing iof the joints 3/4" thick i/c finishing S.I.No 28 P.No 42
| ver; | 1 |  | 39.25 | 12 |  | 471
| Ver: | 1 |  | 35.25 | 10 |  | 352.5
| Ver: | 2 |  | 17.5 | 8 |  | 280
| Ver: | 1 |  | 35.25 | 10 |  | 352.5
| Ver: | 1 |  | 21 | 12 |  | 252
| ver | 1 |  | 11.75 | 8 |  | 94
| Ver: | 1 |  | 7 | 7 |  | 49
[6 empty] | TOTAL | 1851
10 | P/F 3/8" thick marbel tiles of approved quality & Colour shade size 8x4" 6x4" in dado skirting & facing removsal/ tucking of existin gplaster surface etc over 1/2" thick base of white cement over mortor base i/c filling of the joints ans washing the tiles with cement sand slury current finishing and cleaning and polishing etc complete for new works S.IO.No. 68 P.48.
| ver; | 1 | 2 | (39.25+12) |  | 0.5 | 51.25 | 51.25
| Ver: | 1 | 2 | (35.25+12) |  | 0.5 | 47.25 | 47.25
| Ver: | 2 | 2 | (17.5+8) |  | 0.5 | 51 | 25.5
| Ver: | 1 | 2 | (35.25+10) |  | 0.5 | 45.25 | 45.25
| Ver: | 1 | 2 | (21+12) |  | 0.5 | 33 | 33
| ver | 1 | 2 | (11.75+8) |  | 0.5 | 19.75 | 19.75
| Ver: | 1 | 2 | (7+7) |  | 0.5 | 14 | 14
[6 empty] | TOTAL | 261.5
DEDUCTION
| MD | 2 |  | 8 |  | 0.5 | 8
| D1 | 15 |  | 3.5 |  | 0.5 | 26.25
| D2 | 2 |  | 3 |  | 0.5 | 3
| Oppenings | 4 |  | 6 |  | 0.5 | 12
| Oppenings | 1 |  | 14 |  | 0.5 | 7
| Oppenings | 1 |  | 10.25 |  | 0.5 | 5.125
| Oppenings | 1 |  | 8 |  | 0.5 | 4
| Oppenings | 1 |  | 10 |  | 0.5 | 5
[6 empty] | TOTAL | 70.375
[5 empty] | Net: Qty: (A) (_) (B) |  | 191.125
11 | P/Fixing G.I frame sfor chowkts of size 7x2" 4-1/2x3" for doors using 20 guage G.I sheet i/c welded hinges and fixing at site withnecessary holds fasts and filling with cement sand slury of ratio 1:6 and reparing rhe jambs <the cost of also i/c all carriage of tools and plants are used in making and fixing.S.I.No. 28.P.92.
| W. | 29 | (2X4.50+5X4.0) |  |  |  | 841
| HW | 10 | (2X3.0+2X1.50) |  |  |  | 90
[6 empty] | TOTAL | 931
12 | P/Fixing G.I frame sfor chowkts of size 7x2" 4-1/2x3" for doors using 20 guage G.I sheet i/c welded hinges and fixing at site withnecessary holds fasts and filling with cement sand slury of ratio 1:6 and reparing rhe jambs <the cost of also i/c all carriage of tools and plants are used in making and fixing.S.I.No. 29.P.92.
| D1. | 15 | (2X3.50+2X8.50) |  |  |  | 360
| D2. | 2 | (3.50+2X7.0) |  |  |  | 35
| D3. | 13 | (2.5+2X7.0) |  |  |  | 215
[6 empty] | TOTAL | 610
13 | 1st class deodar wood wraught joinery in D/W etc fixed in position i/c chowkats hold fast iron tower bolts chocks cleats handles and chords with hooks etc Deodar pannalled and glazed or fully glazed 1-3/4"thick (SIN0:7 P-57)
| D1. | 15 |  |  | 3.5 | (7.50+1.5) | 473
| D2. | 2 |  |  | 3 | 7 | 42
| D3. | 13 |  |  | 2.5 | 7 | 227.5
| W1. | 29 |  |  | 4.5 | 4 | 522
| HW | 10 |  |  | 3 | 1.5 | 45
[6 empty] | TOTAL | 1309.5
14 | P/Fixing iron steel grill SINO:26 P-92
| W1. | 29 |  |  | 4.5 | 4 | 522
| HW | 10 |  |  | 3 | 1.5 | 45
[6 empty] | TOTAL | 567
15 | 1st class deodar wood wraught joinery in D/W etc fixed in position i/c chowkats hold fast iron tower bolts chocks cleats handles and chords with hooks etc Deodar pannalled and glazed or fully glazed 1-3/4"thick (SIN0:7 P-57)
| W1. | 29 |  |  | 4.5 | 4 | 522
| HW | 10 |  |  | 3 | 1.5 | 45
[6 empty] | TOTAL | 567
16 | Primary coat of chalk under distrm,per or oil bund distemper or paint on walls S.I.No P.No.
| Same Qty of item No (7) as above. | [5 empty] | 4772.5
| Same Qty of item No (9) as above. | [5 empty] | 1851
[6 empty] | TOTAL | 6623.5
17 | Distempering of walls any type three coats S.I.No P.No.
| Same Qty of item No (16) as above. | [5 empty] | 6623.5
[6 empty] | TOTAL | 6623.5
18 | S/Fixing matt Finish 3 Coats
| Same Qty of item No 5 (a) as above. | [5 empty] | 20988.25
[6 empty] | TOTAL | 20988.25
19 | Weather coat 3 coats
| Same Qty of item No (5) (b) as above. | [5 empty] | 5602.44
[6 empty] | TOTAL | 5602.44
20 | Preparring new surface and painting of doors and windows any type i/c edges three coats S.I.No P.No.
| Double Qty of item No (13) as above. |  |  | 1309.5 | x2= |  | 2619
[6 empty] | TOTAL | 2619
21 | Supplying and fixing Aluminium channels framing for hinged doors and alcope made
| MD | 1 |  | 2 | 8 | 8.5 | 136
[6 empty] | TOTAl | 136
22 | Supplying and fixing Aluminium channels framing for hinged Windows and alcope made
| W. | 1 |  | 2 | 4.5 | 5.5 | 49.5
[6 empty] | TOTAL | 49.5
23 | Hard wood railing of any shape & design i/c bends S.I.No30 P.No.61
| " " | 1 | 2 |  | 26 |  | 52
| " " | 1 | 52 |  | 4 |  | 208
[6 empty] | TOTAL. | 260
24 | CCToping 1-1/2" thick i/c surface finishing and dividing in to panals
| Ward to D/Doctor | 2 |  | 36 | 16.75 |  | 1206
| Male & Female Entr: | 2 |  | 14 | 10.25 |  | 287
| Stair Case | 1 |  | 12 | 11.75 |  | 141
| Ver: | 1 |  | 119.5 | 12.75 |  | 1523.625
| Bath to Bath | 1 |  | 125.25 | 17.5 |  | 2191.875
| Partition to Lav: | 1 |  | 53 | 5 |  | 265
| Store to Lav: | 1 |  | 64.75 | 12 |  | 777
| Wait to Lab: | 1 |  | 29.5 | 43 |  | 1268.5
| Store | 1 |  | 20.25 | 6.75 |  | 136.6875
[6 empty] | TOTAL. | 7796.6875
25 | Two coats of bitumin
| Ward to D/Doctor | 2 |  | 36 | 16.75 |  | 1206
| Male & Female Entr: | 2 |  | 14 | 10.25 |  | 287
| Stair Case | 1 |  | 12 | 11.75 |  | 141
| Ver: | 1 |  | 119.5 | 12.75 |  | 1523.625
| Bath to Bath | 1 |  | 125.25 | 17.5 |  | 2191.875
| Partition to Lav: | 1 |  | 53 | 5 |  | 265
| Store to Lav: | 1 |  | 64.75 | 12 |  | 777
| Wait to Lab: | 1 |  | 29.5 | 43 |  | 1268.5
| Store | 1 |  | 20.25 | 6.75 |  | 136.6875
[6 empty] | TOTAL. | 7796.6875