## Measurment (hidden)
NAME OF WORK:- M&R To Rest House at Moro
Measurment Sheet
S# | Item of Work | NO: |  | Length | Bredth | Height | Quantity
1 | Dismentling of Glazed or encaustic tile (sino:55 P-13)
| Tiolet VIP NO: 3 | 2 | 2 | (7+9) | 5 |  | 320 | 16
[5 empty] | Total |  | 320
2 | Applying floating coat of cement 1/32" thick SINO:14 P-52
| Same Qty of item no: 1 as above | [5 empty] | 320
[5 empty] | TOTAL |  | 320
3 | Cement plaster 3/4" thick upto 12" ft height S.I.No. 13 (b) P-51
| Same Qty of item no: 1 as above | [5 empty] | 320
[5 empty] | TOTAL |  | 320
4 | Cement Concrete Plain i/c Plasing Compacting ,curing complete SINo: 5(f) P-15
| Tiolet VIP NO: 3 wc | 1 |  | 7 | 9 | 0.25 | 15.75
| Tiolet VIP NO: 3 | 1 |  | 14 | 12 | 0.25 | 42
[5 empty] | Total |  | 57.75
5 | Laying Flooring with approved glazed tile 1/4" th laid in white SINO: 24 P-42
| Tiolet VIP NO: 3 wc | 1 |  | 7 | 9 |  | 63
| Tiolet VIP NO: 3 | 1 |  | 14 | 12 |  | 168
[5 empty] | Total |  | 231
6 | White Glazed tile 1/4" thick in dado jointed SINO: 37 P-44
| Tiolet VIP NO: 3 wc | 1 | 2 | (7+9) | 7 |  | 224 | 16
| Tiolet VIP NO: 3 | 1 | 2 | (14+12) | 7 |  | 364 | 26
[5 empty] | Total |  | 588
7 | S/Fixing in Position Aluminium Chanals framming for hinged doors or alcop (SINO: 83(b)P-107
| Tiolet VIP NO: 3 D | 1 |  | 3.5 | 6.75 |  | 23.625
[5 empty] | Total |  | 23.625
8 | P/Fixing Fiber sheet wall panals of superior quality fixing with screws on vertical walls complete in all respect as desired at site. ( R A Attached)
| Tiolet VIP NO: 3 | 1 | 2 | (16.0+12.0) |  | 9 | 504 | 28
| Tiolet VIP NO: 4 | 1 | 2 | (16.0+12.0) |  | 9 | 504 | 28
[5 empty] | Total |  | 1008

## Abstract sheet
NAME OF WORK:- M&R To Rest House at Moro
Abstract Sheet.
S.,NO | ITEM OF WORK | QUANTITY | RATE | UNIT | AMOUNT
1 | Dismentling of Glazed or encaustic tile (sino:55 P-13) | 320 | 786.5 | P%Sft | 2516.8
2 | Applying floating coat of cement 1/32" thick SINO:14 P-52 | 320 | 660 | P%Sft | 2112
3 | Cement plaster 3/4" thick upto 12" ft height S.I.No. 13 (b) P-51 | 320 | 3015.76 | P%Sft | 9650.432
4 | Cement Concrete Plain i/c Plasing Compacting ,curing complete SINo: 5(f) P-15 | 57.75 | 14429.25 | P%Cft | 8332.8919
5 | Laying Flooring with approved glazed tile 1/4" th laid in white SINO: 24 P-42 | 231 | 27678.86 | P%Sft | 63938.1666
6 | White Glazed tile 1/4" thick in dado jointed SINO: 37 P-44 | 588 | 28253.61 | P%Sft | 166131.2268
7 | S/Fixing in Position Aluminium Chanals framming for hinged doors or alcop (SINO: 83(b)P-107 | 23.625 | 1507.66 | PSft | 35618.4675
8 | P/Fixing Fiber sheet wall panals of superior quality fixing with screws on vertical walls complete in all respect as desired at site. ( R A Attached) | 1008 | 250 | PSft | 252000
|  |  | TOTAL |  | 540299.9848
Internal W/S&S/F
S.NO. | ITEM OF WORK. | QTY | RATE | UNIT | AMOUNT.
(a) Shedule Items
2 | Providing and fixing orisa type white colour glazed earthern were W.C pan low level flush tank of 3 gallons capacity of approved quality i/c making requisite number of holes in wall plinth & floor and making good in c.c1:2:4 (A) W.C pan with orisa type 23" wit plastic of low down 3 gallons C.I trap & C.I thumble Superior quality (S.I.NO. (3) (a) (i) p.No. 02 ). | 1 | 5836.6 | Each. | 5836.6
3 | P/F 24x18" lavaratory basin in white glazed earthern were complete i/c the cost of W.I or C.I entilever brackets 6inch built into walls and painted white or or two coats after a primary coat of red lead paint a piar of 1/2" dia rubber plug and chrome pated brass chain 1-1/4" dia malloable iron or brass unions and making requisite number of holes in walls pipe connections and making good in c.c 1:2:4 ( S.I.No P.No. ). | 1 | 4928 | Each. | 4928
4 | Add: extra for labour for providing & fixing of earthern were pedestal white or coloured glazed foreign or equivalent S.I.No 9 P.No. 03 | 1 | 2533.47 | Each. | 2533.47
| P/F in position nyloon connections complete with 1/2" dia brass stop cock with pair of brass nuts and lining joints to nyloon connection (S.I.No.23.P.6 ). | 6 | 447.15 | Each. | 2682.9
5 | S/F bath room accessories set (07) piece i/c towel rod, brush holder, shelf tray of approved design I/C cost of screws and nuts etc complete master brand.( S.I.No. 23.P.No. 19 ).. | 1 | 10322.4 | Each. | 10322.4
8 | Wash basin mixture of superior quality with with c,p head 1/2" dia SINO:14P-19 | 1 | 3179 |  | 3179
9 | S/Fixing CP Muslim shower with double bib cock and ring pipe etc complete SINO: 19 P-19 | 1 | 3432 | Each | 3432
10 | S/Fixing conceiles stop cock of superor quality with c.p head 1/2" dia SINO: 11(b) p-18 | 6 | 509.74 | Each | 3058.44
11 | Supplying and Fixing in position C.P bib cock (b) 3/4" cp Bib cock standard pattern SINO:2(b) P-16 | 1 | 348.92 | Each | 348.92
12 | P/F chamber 15x9" inside daimension 24" deep for house meters with 6" thick c.c1:3:6 Block set 1:6 cement mortor 6"thick c.c 1:4:8 in foundation 1/.2" thick SINO: 1 P-20 | 1 | 4905.67 | Each | 4905.67
13 | P/Fixing 6"x4" cc gully trape with 4" outlet complete with 4" thick 1:2:4 cc for bed and 1/2" thick cement Plaster 1:3 to kerb C.I grating 6"x6" and with RCC Cover (S:1 (ii) P-23) | 1 | 1259.5 | Each | 1259.5
14 | P/Fixing 6"x2 or 6"x3" C.I Floor Trape of the approved selt cleaning design with a C.I screwd down grating with or with out vent aram complete SINO:20 P-6 | 1 | 2024.34 | Each | 2024.34
|  | TOTAL |  |  | 44511.24
S.NO. | ITEM OF WORK. | QTY | RATE | UNIT | AMOUNT.
1 | S/F UPVC soil & vent pipe AGM make of approverd qulaity on walls & in C.C flooring working upto 90 Ft height jointing with UPVC fitting by using approved paste/ solution making good etc in complete as per instruction of Engineer Incharge rate i/.c all cost of labour material cartage scaffolding jhoola etc complete. RA Attached
| b) 3/4" dia Pipe 1x70 =70 | 70 | 126 | Prft | 8820
| c) 1-1/2" dia pipe 1x90=90 | 90 | 169 | Prft | 15210
| d) 4" dia 1x40 | 40 | 356 | Prft | 14240
2 | P/F UPVC Fitting of schedule 40 (E) AGM or pak arab make in/c jointing with PVC solvent / JTC solution and fixing at any height / floor using jhoola or long laddar in horizental or vertical pipe as
directed by the Engineer Incharge,
| plain Elbow 4'dia. | 12 | 835 | Each. | 10020
3 | P/F UPVC Fitting of schedule 40 (E) AGM or pak arab make in/c jointing with PVC solvent / JTC solution and fixing at any height / floor using jhoola or long laddar in horizental or vertical pipe as
directed by the Engineer Incharge,
| plug Elbow. | 1 | 922 | Each. | 922
4 | P/F UPVC Fitting of schedule 40 (E) AGM or pak arab make in/c jointing with PVC solvent / JTC solution and fixing at any height / floor using jhoola or long laddar in horizental or vertical pipe as
| Plain -Tee 4"dia. 1x1=1 | 1 | 1290 | Each. | 1290
5 | P/F UPVC Fitting of schedule 40 (E) AGM or pak arab make in/c jointing with PVC solvent / JTC solution and fixing at any height / floor using jhoola or long laddar in horizental or vertical pipe as
| Jubilee Clip. 1 x4=4 | 4 | 83 | Each. | 332
6 | P/F UPVC Fitting of schedule 40 (E) AGM or pak arab make in/c jointing with PVC solvent / JTC solution and fixing at any height / floor using jhoola or long laddar in horizental or vertical pipe as
directed by the Engineer Incharge,
| 4" dia Cowel. 1x1 | 1 | 348.41 | Each. | 348.41
|  | TOTAL |  |  | 51182.41
CONTRACTOR
EXECUTIVE ENGINEER
PROVINCIAL BUILDINGS DIVISION
SHAHEED BENAZIR ABAD

## ws & sf
GENERAL ABSTRACT
(1) Schedule Items RS: | 44511.24
(2) Non-Schedule Items RS: | 51182.41
Total RS: | 95693.65
SUB-ENGINEER
ASSISTANT ENGINEER
PROVINCIAL BUILDINGS SUB-DIVISION
NAUSHAHRO FEROZE
EXECUTIVE ENGINEER
PROVINCIAL BUILDINGS DIVISION
SHAHEED BENAZIR ABAD